## A31 - QPR - Executive Summary
Page by:
Program: DR CDBG
Appropriation: 2017 HIM:2017 Hurricanes Harvey, Irma and Maria
Grant | Grantee State | Grantee | QPR Actual Begin Date |  | QPR Executive Summary
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2018-07-01 | 2018 Q4 | - 2 activities were added during Q3. - Obligations changes for quarter were $5,500,000. - Budget changes for quarter were $38,889,619.60.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2018-10-01 | 2019 Q1 | Overall Narrative: - 20 activities were added during Q4. - Obligations changes for quarter were $15,500,000. - Budget changes for quarter were $157,987,228.26.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2019-01-01 | 2019 Q2 | - 14 activities were added during this quarter. - Obligations changes for quarter were $184,000,000.00. - Budget changes for quarter were $362,987,228.26. Activities with MID Expenditures: PREPS_HI_UN
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2019-04-01 | 2019 Q3 | - 36 activities were added during this quarter. - Obligations changes for quarter were $1,450,329,525.42. - Budget changes for quarter were $1,438,225,468.66.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2019-07-01 | 2019 Q4 | -All activities were renamed and projects reorganized during this quarter. -Total budget amounts were adjusted to include the additional allocation of $652 million. -The budget amount changes for the quarter total $5,391,465,260.04 and the obligation amount changes total $5,375,135,410.04. Affordable Rental Program: -New Construction - 22 projects and 1346 total units. -Reconstruction &ndash; 7 projects and 201 total units. -Rehabilitation &ndash; 32 projects and 2123 total units. 30 of the projects are already under construction and for the remaining projects construction should be commencing by the first quarter of 2020. The majority of the properties will be funded solely by CDBG-DR funds and the properties&apos; numbers of units above will be those units that will target LMI residents. Beneficiaries will not be determined until construction is complete and lease-up has taken place which will be in 2020. City of Houston: HOUSING ACTIVITIES: The City of Houston submitted a draw request for $55,000 for 3 homeowner reimbursements on 7/1/19. The General Land Office (GLO) determined the support documentation to be insufficient and sent a request for information (RFI) on 7/17/2019 and follow-up RFIs on 9/23/19, 10/18/19. To date a response has not been received. The City submitted a draw request for $1,097,200.13 on 10/3/19 for planning costs incurred. The GLO determined the support documentation to be insufficient and sent an RFI on 10/18/19. To date a response has not be received. The City has not submitted any additional draw requests. GLO has provided Technical Assistance on the draw and invoice submittal process on multiple dates. Houston HoAP Program ($427,900,063) Applications Received - 5514 Houston Reviewing Applicant Eligibility/Property Assessment - 5398 Applications in GLO/Enviro Review or awaiting RFI response - 19 GLO Approved for Construction/ Reimbursement - 75 Approved Low-to-Moderate (LMI) Projects - 70 Construction Completed - 5 Reimbursed - 17 The HoAP Guidelines have been conditionally approved by the GLO. During Q3 2019, the GLO conducted technical assistance with the City to help ensure the applications documented compliance with local, State, and federal requirements. The City of Houston Homeowner Assistance Program includes the following benefits: rehabilitation, reconstruction, reimbursement, interim mortgage assistance, and acquisition. Below is the number of GLO approved Applications by activity as of the end of Q3 2019. Note that Applicants to the HoAP program can participate in more than one activity and the numbers below count Applicants in all activities they were approved to receive a benefit in. -Rehabilitation-27 Applications Approved (27 LMI Applicants) -Reconstruction-32 Applications Approved (32 LMI Applicants) -Reimbursement-43 Applications Approved (38 LMI Applicants) Houston Multifamily Rental Program ($350,050,472) Houston Applications Received - 54 Houston In Review/ Pending Additional Information - 15 Applications in GLO/Enviro Review or awaiting RFI response - 0 GLO Approved - 0 In Construction - 0 The Multifamily Rental Program Guidelines ,e been conditionally approved by the GLO. The City released a Notice of Funding Available (NOFA) in Q2 2019 and selected 15 projects for funding in Q3 2019. The City will submit project applications for the 15 development to the GLO for review and the City is expected to award eligible projects during the next quarter. Houston Homebuyer Assistance Program (HBAP) ($23,688,328) Houston Applications Received - 104 Houston In Review/ Pending Additional Information - 100 Applications in GLO/Enviro Review or awaiting RFI response - 4 GLO Approved - 0 Approved Low-to-Moderate (LMI) Projects - 0 Homebuyers Assisted - 0 The Homebuyer Assistance Program Guidelines have been approved by the GLO. The City of Houston Homebuyer Assistance program provides down payment assistance. During Q3 2019 The GLO conducted technical assistance with the City to help ensure the applications documented compliance with local, State, and federal requirements. Houston Public Services Program ($350,050,472) The City posted an RFP June 17, 2019. Project Activities Not Yet Begun Houston Buyout Program ($40,800,000) Houston Economic Revitalization Program ($30,264,834) Houston Planning Program ($23,100,000) Houston Single Family Development Program ($222,269,086) Houston Small Rental Program ($66,686,282) Harris County: During the Reporting Quarter the following accomplishments occurred: Housing Assistance Program (HAP) ($270,359,499) The GLO conditionally approved the Housing Assistance Program Guidelines. Projects must meet the GLO&apos;s unit size requirements. For projects not in compliance with the requirements, the county must submit a waiver request to the GLO or use other funds to supplement the CDBG-DR funds. Harris Co. Applications Received - 15 Harris County Reviewing Applicant Eligibility/Property Assessment - 6 Projects Received by GLO - 2 GLO Approved for Construction - 1 Low-to-Moderate (LMI) Projects - 1 Construction Completed - 0 Buyout Program ($270,359,499) The GLO and HUD had a URA Technical Assistance conference call on September 6 to discuss the possibility of converting the County&apos;s Residential Buyout Program to an involuntary program. The County plans to submit a formal request and data to support the change in program design. The table includes accomplishments from the County&apos;s two Harvey Buyout Programs. Harris Co. Applications Received - 35 Harris County Reviewing Applicant Eligibility/ Property Assessment - 13 Projects Received by GLO - 6 GLO Approved for Buyout - 3 Low-to-Moderate (LMI) Projects - 1 Buyout Completed - 0 Reimbursement Program ($15,000,000) Harris Co. Applications Received - 70 Harris County Reviewing Applicant Eligibility/Property Assessment - 39 Projects Received by GLO - 0 GLO Approved for Reimbursement - 0 Low-to-Moderate (LMI) Projects - 0 Reimbursement Completed - 0 Method of Distribution Infrastructure Program ($120,000,000) The GLO received 21 applications for the Method of Distribution Infrastructure Program. During Quarter 3 2019, three drainage projects were amended into the contract totaling $16,329,850. The GLO awarded an additional 11 draina,ge, sewer, and community center projects totaling $70,910,838 and is in the process of amending the projects into the contract. Projects Received by GLO - 21 In Review/ Pending Additional Information - 7 GLO Approved - 14 In Construction - 0 Competitive Application Infrastructure Program ($76,668,492) The County submitted six project applications to the GLO for eligibility review. In Quarter 3, three drainage and transportation services projects were approved and awarded funding in the amount of $25,349,973. The projects are being amended into the contract. Projects Received by GLO - 6 In Review/ Pending Additional Information - 3 GLO Approved - 3 In Construction - 0 Commercial Buyout Program ($12,500,000) In Quarter 3 2019, the GLO requested a program status update as the County has not submitted the program guidelines. No projects have been submitted to the GLO for review. Projects Received by GLO - 0 In Review/ Pending Additional Information - 0 GLO Approved - 0 In Construction - 0 Affordable Rental Program ($224,500,000) In the past month, the County submitted four affordable rental projects to the GLO for review and Affirmatively Furthering Fair Housing reviews are under way. State Senator Miles&apos; office reached out to the GLO regarding the denial of the Sunrise Orchard Apartments. The GLO has responded to his request for additional information. Harris Co. Applications Received - 23 In Review/ Pending Additional Information - 8 GLO Approved - 0 In Construction - 0 Homeowners Assistance Program: Reconstruction 150 HUD Most Impacted 141 Low/Mod 113 Urgent Need 28 State Most Impacted 9 Low/Mod 7 Urgent Need 2 Rehabilitaion 10 HUD Most Impacted 10 Low/Mod 6 Urgent Need 4 Grand Total 160 Homeowners Reimbursement Program: Draft Applications 6,245 Verifying Eligibility 2,862 Reimbursement Approved 603 Total Outlays of Reimbursements $19,454,620.00 Ineligible 2,027 Total 11,865 Planning: Planning operations are ongoing.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2019-10-01 | 2020 Q1 | There were 63 activities added for the Local Buyout/Acquisition and 47 activities added for the Local Infrastructure programs. The budget amount changes for the quarter total $2,268,917,390.04 and the obligation amount changes total $1,647,063,322.77. There were also activity number changes for this quarter that affected the budget and obligation amount adjustments. HOMEOWNER ASSISTANCE PROGRAM: At the end of the Fourth Quarter of 2019, the Homeowner Assistance Program accomplished the following activities that will primarily meet the LMI National Objective. Approved 882 households for assistance Had 758 homes under construction Completed construction on 455 homes Approved $36,613,641.93 in payments for construction services. Staff are completing the close-out process and will begin reporting closed activities in the next QPR. BUYOUT PROGRAM: 17 Buyout/Acquisition contracts were executed REIMBURSEMENT PROGRAM: At the end of the Fourth Quarter of 2019, the Homeowner Reimbursement Program has served ~400 Homeowners with ~$13M in Reimbursement Grants. An additional ~$23M has been approved and pending release of payment or execution of the homeowner signing event. At the end of Q4, the Homeowner Reimbursement Program was approximately 43% obligated Draft Applications 8187 Verifying Eligibility 2378 Reimbursement Approved 739 Total Outlays of Reimbursements $11,728,897.53 Ineligible 1375 AFFORDABLE RENTAL PROGRAM: At the end of the Fourth Quarter of 2019, the Affordable Rental Program accomplished the following activities that will meet the LMI National Objective. 68 applications were awarded funding totaling $439,574,367 to rehab, reconstruct or build 4,858 new units construct 52 contracts have been executed 37 Projects are currently under construction $42,264,244.66 has been approved in draw requests by the Multifamily team ARP is in the process of awarding an additional $135,231,628 from other CDBG DR activities in accordance with the action plan. Conditional Award letters have been sent out. PREPS No new update and no activity in Q4 2019. The program is complete and the draws have been made. INFRASTRUCTURE PROGRAM 39 Infrastructure contracts were executed Grantee Draws Approved - 1 for $11,292 ECONOMIC REVITALIZATION PROGRAM The GLO Economic Revitalization Program was designed to create jobs and help small businesses that were negatively affected by Hurricane Harvey. An official announcement and application availability took place on December 2, 2019. Aggressive marketing and outreach campaigns are currently being executed by NASI/GLO IGR. The average grant request is for $136,500, and over 1,00 applications have already been submitted. Applications will be accepted until March 2, 2020 at which point applications will be randomly selected to begin an underwriting process prior to award recommendations. $90,000,000 will be awarded to small businesses in grants ranging from $50,000 to $250,000 in exchange for job creation or job retention. PLANNING Planning operations are ongoing. HOUSTON - HOMEOWNERS ASSISTANCE PROGRAM During Quarter 4 2019, the GLO continued to review and approve eligible applications. As of end of Q4, the GLO had received 144 applications and approved 130 applications for the program. Additionally, 8 rehabilitations and 5 reconstructions were completed, and 24 reimbursement checks were cut. The City has not yet provided documentation to complete a draw on any of the completed activites by the end of Q4. Throughout the quarter, the GLO provided technical assistance to the City through daily calls and weekly visits during the months of October and November, including technical assistance and guidance for the submission and processing of eligible draws to the GLO. Applications Received 144 Houston Reviewing Applicant Eligibility/Property Assessment 130 Projects Received by GLO 130 GLO Approved 130 HOUTON - SINGLE FAMILY DEVELOPMENT PROGRAM Projects have not begun and are in the planning stage. HOUSTON - MULTIFAMILY RENTAL PROGRAM During Quarter 4 2019, the GLO continued to review and approve eligible applications. As of end of Q4, the GLO had received 12 applications and approved 2 applications (highlighted below) for the program. Additionally, the GLO provided technical assistance to the City through weekly visits during the months of October and November. Applications Received 55 Houston Reviewing Applicant Eligibility/Property Assessment 43 Projects Received by GLO 12 GLO Approved 2 HOUSTON - SMALL RENTAL PROGRAM Projects have not begun and are in the planning stage. HOUSTON - HOMEBUYER ASSISTANCE PROGRAM During Quarter 4 2019, the GLO continued to review and approve eligible applications. As of end of Q4, the GLO had received 76 applications and approved 71 applications for the program. Additionally, 56 applicants received downpayment assistance checks. The City has not yet provided documentation to complete a draw on any of the completed activites by the end of Q4. Throughout the quarter, the GLO provided technical assistance to the City through daily calls and weekly visits during the months of October and November, including technical assistance and guidance for the submission and processing of eligible draws to the GLO. Applications Received 99 Reviewing Applicant Eligibility/Property Assessment 8 Projects Received by GLO 76 GLO Approved for Reimbursement 71 <br /,HOUSTON - BUYOUT PROGRAM Projects have not begun and are in the planning stage. HOUSTON - PUBIC SERVICES During Q4 2019, the City of Houston continues to review applications received through their Notice of Funding Available (NOFA). The GLO provided technical assistance in how to submit applications to GLO for eligibility review. HOUSTON - ECONOMIC REVITALIZATION Projects have not begun and are in the planning stage. HOUSTON - PLANNING As of the end of Q4 2019, the City has completed a needs assessment and necessary planning for program design. Additional projects have not begun and are in the planning stage. HARRIS COUNTY - HOMEOWNER ASSISTANCE PROGRAM To date, County received a total of 45 Homeowner Assistance Program applications including 30 that were received in Quarter 4 2019. The County continues to review the applications for eligibility and submitted two to the GLO in Quarter 4. The County anticipates submitting 100-200 projects to the GLO in Quarter 1 2020. Applications Received 30 Projects Received by GLO 2 HARRIS COUNTY - BUYOUT AND ACQUISITION PROGRAM To date, the County received 28 applications and is currently reviewing five for eligibility. In total, two projects have been approved by the Buyout Program. The County plans to submit a formal request to change its Voluntary Buyout Program to an Involuntary Program in Quarter 1 2020. County is in the planning stage and did not submit any additional projects to the GLO in Quarter 4 2019. HARRIS COUNTY - SF AFFORDABLE HOUSING PRESERVATION County is in the planning stage and has not submitted projects in Quarter 4 2019. HARRIS COUNTY - REIMBURSEMENT PROGRAM Since the program started, the County received 191 applications of which 121 applications were received in Quarter 4 2019. County began submitting projects to the GLO in Quarter 4 2019 and the GLO approved 35 projects totaling over $1M during the reporting period. Applications Received 121 Projects Received by GLO 87 GLO Approved for Reimbursement 35 Low-to-Moderate (LMI) Projects 15 HARRIS COUNTY - AFFORDABLE RENTAL PROGRAM In a prior reporting period, the County received a total of 23 project applications and they are in the process of selecting and submitting the projects to the GLO for review. No new applications were received by the County in Quarter 4 2019. To date, the County submitted a total of 10 Multifamily projects to the GLO that are under review. While no projects have been approved, several projects are anticipated to be approved in Quarter 1 2020. A Request for Application was released for the multifamily program and applications are being accepted until January 22, 2020. The County anticipates obligating the remainder of its funding with this funding round. In Review/Pending Additional Information 10 HARRIS COUNTY - SINGL,E FAMIILY NEW CONSTRUCTION In Quarter 4 2019, the County submitted four Single Family New Construction projects to the GLO for eligibility and Affirmatively Furthering Fair Housing reviews. The County is in the process of responding to requests for additional information in order for the GLO to complete the reviews. Applications Received 4 In Review/Pending Additional Information 4 HARRIS COUNTY - COMMERCIAL BUYOUT PROGRAM During Quarter 4 2019, the County submitted an extension request for the program guidelines. In December 2019, the GLO requested additional information to support the request to submit the guidelines in March 2020. No projects have been submitted to the GLO since the program is in the planning stage. HARRIS COUNTY - METHOD OF DISTRIBUTION INFRASTRUCTURE PROGRAM By the end of Quarter 4 2019, the GLO received 24 projects of which three were submitted in Quarter 4. During the reporting period, seven projects were under review by the GLO and in total, 17 projects were approved by the end of 2019, including three that were approved in the quarter. Amendment 2 was executed in Quarter 4 2019, which added nine infrastructure projects into the contract. The GLO is in the process of amending into the contract three drainage and sewer improvements projects in the amount of $14,555,377. Projects Received by GLO 3 In Review/ Pending Additional Information 7 GLO Approved 3 HARRIS COUNTY - COMPETITIVE APPLICATION INFRASTRUCTURE PROGRAM To date, the County submitted six projects to the GLO, all of which were submitted during previous quarters. At the end of Quarter 4 2019, three projects were approved and three were in review by the GLO. During the quarter, the contract amendment was executed to add one Competitive Application Infrastructure project into the contract. The GLO is in the process of amending two drainage improvements projects into the contract in the amount of $21,252,540. The County plans to submit an additional 10 projects starting in late Quarter 1 2020 which will obligate the remainder of the program budget. In Review/ Pending Additional Information 3 HARRIS COUNTY - PLANNING Current Quarter Narrative To date, the County completed the Community Needs Assessment planning study. In Quarter 4 2019, the County began two flood control district planning projects and one LIDAR planning project along with starting the procurement for two projects including a tunnel feasibility study and LIDAR planning study. Projects Received by GLO 5 GLO Approved 5 In Construction/ In Progress 3
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2020-01-01 | 2020 Q2 | There were 61 activities added for the Local Buyout/Acquisition and 45 activities added for the Local Infrastructure programs. The budget amount changes for the quarter total ($262,694,896.02) and the obligation amount changes total $357,789,926.25. AFFORDABLE RENTAL PROGRAM: New Construction Projects - 34 New Construction Units - 3233 Reconstruction Projects - 9 Reconstruction units - 279 Rehabilitation projects - 34 Rehabilitation units - 2459 Houston - Homeowners Assistance Program: During the reporting period, Houston received 0 applications and verified 15 projects for eligibility. 8 total projects have completed by Houston and 3 projects are underway. During the reporting period, the GLO has approved 53 Houston applications. One payment request was completed during this reporting period. Throughout the quarter, the GLO provided technical assistance to the City through daily calls and weekly visits, including technical assistance and guidance for the submission and processing of eligible draws to the GLO. Reviewing Applicant Eligibility/Property Assessment - 15 Projects Received by GLO - 82 GLO Approved for Construction - 53 Low-to-Moderate (LMI) Projects - 36 Reconstrution HMID Low/Mod - 21 Rehabilitation HMID Low/Mod - 7 Reimbursement HMID Low/Mod - 8 Reimbursement HMID UN - 3 Houston - Single Family Development Program: Projects have not begun and are in the planning stage. Houston - Multifamily Rental Program: During the reporting period, Houston received 0 applications and verified 9 projects for eligibility. 0 total projects have completed by Houston and 2 projects are underway. During the reporting period, the GLO has approved 5 Houston applications. 2 payment request was completed during this reporting period. Throughout the quarter, the GLO provided technical assistance to the City through daily calls and weekly visits, including technical assistance and guidance for the submission and processing of eligible draws to the GLO. Reviewing Applicant Eligibility/Property Assessment - 9 Projects Received by GLO - 1 GLO Approved for Buyout - 13 Low-to-Moderate (LMI) Projects - 1195 Houston - Small Rental Program: Projects have not begun and are in the planning stage. Houston - Homebuyer Assistance Program: During the reporting period, Houston received 42 applications and verified 38 projects for eligibility. 19 total projects have completed by Houston and 9 projects are underway. During the reporting period, the GLO has approved 49 Houston applications. 1 payment request was completed during this reporting period. Throughout the quarter, the GLO provided technical assistance to the City through daily calls and weekly visits, including technical assistance and guidance for the submission and processing of eligible draws to the GLO. Applications Received - 42 Reviewing Applicant Eligibility/Property Assessment - 38 Projects Received by GLO - 55 GLO Approved for Reimbursement - 49 Low-to-Moderate (LMI) Projects - 46 Houston - Buyout Program: Projects have not begun and are in the planning stage. ,ouston - Public Services: During the reporting period, Houston continues to review applications received through their Notice of Funding Available (NOFA). The GLO provided technical assistance in how to submit applications to GLO for eligibility review. Houston was provided the monthly report template to begin reporting for next quarters activities. Houston - Economic Revitalization: Projects have not begun and are in the planning stage. Houston - Planning: During this reporting period, Houston has completed a needs assessment and necessary planning for program design. Additional projects have not begun and are in the planning stage. Harris County - Homeowner Assistance Program: To date, County received a total of 2,404 Homeowner Assistance Program applications including 62 that were received by the County in Quarter 1 2020. The County continues to review the applications for eligibility and submitted 20 to the GLO in Quarter 1 2020. Applications Received - 62 Reviewing Applicant Eligibility/Property Assessment - 839 Projects Received by GLO - 20 GLO Approved for Construction - 4 Low-to-Moderate (LMI) Projects - 4 Reconstruction HMID Low/Mod - 3 Rehabilitation HMID Low/Mod - 1 Harris County - Buyout and Acquisition Program: To date, the County received 28 applications. In the reporting period, the County received 0 new applications and is currently reviewing 5 for eligibility. In total, 4 projects have been approved, 2 of which occurred this reporting period. The County submitted a formal request to add Involuntary Program activities to its Buyout Program and the GLO provided Technical Assistance to the County regarding the program design change process. Reviewing Applicant Eligibility/Property Assessment - 5 Projects Received by GLO - 2 GLO Approved for Buyout - 2 Harris County - SF Affordable Housing Preservation: County is in the planning stage and has not submitted projects in Quarter 1 2020. A Request for Application for a non-profit to run a turnkey program was published during the quarter with responses due March 13th. Harris County - Reimbursement Program: Since the program started, the County received 679 applications. For this reporting period, 0 new applications were received. The County began submitting projects to the GLO in Quarter 4 2019 and the GLO approved 140 projects totaling over $5M during the reporting period. Reviewing Applicant Eligibility/Property Assessment - 452 Projects Received by GLO - 210 GLO Approved for Reimbursement - 140 Low-to-Moderate (LMI) Projects - 72 Harris County - Affordable Rental Program: In the reporting period, the County received 20 new applications as part of their second notice of funding and they&apos;re currently reviewing the submittals. The County anticipates obligating the remainder of its funding under this notice. To date, the County has submitted a total of 10 Multifamily projects to the GLO. In Quarter 1 2020, no new projects were submitted to the GLO and seven projects were approved with a total of 1,150 units. Applications Received - 20 In Review/Pending Additional Information - 24 Projects Received by GL, - 10 GLO approved - 7 Harris County - Single Family New Construction: In Quarter 1 2020, the County submitted four Single Family New Construction projects to the GLO for eligibility and Affirmatively Furthering Fair Housing reviews. The County is in the process of responding to requests for additional information in order for the GLO to complete the reviews. One project with 49 lots was approved during the reporting period. Applications Received - 5 In Review/Pending Additional Information - 7 GLO approved - 1 Harris County - Commercial Buyout Program: During Quarter 1 2020, the County submitted a request to add involuntary activities to its buyout program and is working on its guidelines in preparation for these programattic changes. No projects have been submitted to the GLO since the program is in the planning stage. Harris County - Method of Distribution Infrastructure Program: By the end of Quarter 1 2020, the GLO received 24 projects. No new projects were submitted to the GLO as the submitted projects will fully obligate the program budget. During the reporting period, six projects were under review by the GLO and County. In total, 18 projects were approved by the end of Quarter 1 2020. Amendment 3 was executed in this reporting period, which added three drainage and sewer improvements projects into the contract. Amendment 4 is in progress and will add six drainage and neighborhood facility projects totalling $32,719,020 into the contract. Projects Received by GLO - 24 In Review/ Pending Additional Information - 6 GLO Approved - 18 Harris County - Competitive Application Infrastructure Program: To date, the County submitted nine projects to the GLO, including three that were submitted in Quarter 1 2020. At the end of Quarter 1 2020, four projects were approved and five were in review by the GLO or pending additional information from the County. During the quarter, a contract amendment was executed to add two drainage project into the contract. The GLO is in the process of amending one sewer improvements projects into the contract in the amount of $2,637,400. The County plans to submit an additional seven projects, which will obligate the remainder of the program budget. Projects Received by GLO - 3 In Review/ Pending Additional Information - 5 GLO Approved - 4 Harris County - Planning: To date, the County completed the Community Needs Assessment planning study. In Quarter 1 2020, two studies were under way including a flood control district watershed planning project and a LIDAR planning project. Thirteen planning projects were in the procurement phase during the reporting period and another three were in development. ECONOMIC REVITALIZATION PROGRAM: The GLO $100 million Economic Revitalization Program was announced on December 2, 2019, and applications were accepted until March 2, 2020. Aggressive marketing and outreach campaigns were executed by the NASI/GLO IGR teams. The average grant request is $144,036 and 2,714 applications were received. The list of applicants has been randomly "shuffled," and applicants are now being interviewed for underwriting in priority order. Approved applications should be received b,y the GLO by April 3, 2020. HOMEOWNER ASSISTANCE PROGRAM: During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q1, GLO was in the process of reviewing 2963 projects for eligibility, had approved 2680 Homeowner Assistance Program applications for assistance, completed construction on 963 households, had construction underway on 869 houses, and had approved 425 payment requests. HOMEOWNER REIMBURSEMENT PROGRAM: At the end of the First Quarter of 2020, the Homeowner Reimbursement Program has served 1320 homeowners with ~$40.1M in reimbursement grants. An additional $25.3M has been approved and pending release of payment or execution of the closing documentation. At the end of Q1 2020, the Homeowner Reimbursement Program was approximately 79% obligated. Starting in Q2, HRP will be conducting long-term compliance monitoring of applicants. Draft Applications - 8046 Verifying Eligibility - 774 Reimbursement Approved - 1100 Total Outlays of Reimbursements - $27,091,694.55 Ineligible - 669 LOCAL BUYOUT PROGRAM: 23 Buyout/Acquisition contracts were executed. LOCAL INFRASTRUCTURE PROGRAM: 65 Infrastructure contracts were executed. 10 subrecipient draws approved for a total of $94,130.30. Contract Executed - 65 Environmental Underway - 40 AUGF issued (Authority to use grant funds) - 1 PLANNING: Planning operations are ongoing. PREPS: No new update and no activity in Q1 2020. The program is complete and the draws have been made.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2020-04-01 | 2020 Q3 | Budget amount changes for Q2 2020 total: $455,194,201.05. Obligation amount changes for Q2 2020 total: $456,459,530.05. 103 activities added in Q2 2020. AFFORDABLE RENTAL PROGRAM: Project count currently at 78 in total, with 57 projects under construction, 5 complete and a further 16 in the due diligence process. New Construction Projects - 33 New Construction Units - 3077 Reconstruction Projects - 9 Reconstruction units - 231 Rehabilitation projects - 34 Rehabilitation units - 2411 CITY OF HOUSTON: During the reporting period, the City of Houston accepted applications for 185 new projects, reviewed eligibility of 397 new projects, issued notice to proceed to construction on 28 projects, reimbursed 35 homeowners, and completed construction on 31. Applications Received - 185 Reviewing Applicant Eligibility/Property Assessment - 397 Projects Received by GLO - 102 GLO Approved for Construction - 72 Low-to-Moderate (LMI) Projects - 70 Reconstrution HMID Low/Mod - 45 Reconstrution HMID UN - 1 Rehabilitation HMID Low/Mod - 12 Rehabilitation HMID UN - 1 Reimbursement HMID Low/Mod - 24 Reimbursement HMID UN - 11 Houston - Single Family Development Program: During the reporting period, the City of Houston continued to develop the guidelines for the program. Houston - Multifamily Rental Program: During the reporting period, the City of Houston received 46 project applications through its 2nd notice of funding availability The City currently has 5 new projects under construction this quarter. Applications Received - 46 Projects Received by GLO - 2 GLO Approved for Buyout - 5 Low-to-Moderate (LMI) Projects - 25 Houston - Small Rental Program: During the reporting period, the City of Houston began implementation of the program, including releasing a notice of funding availability. Houston - Homebuyer Assistance Program: During the reporting period, the City of Houston accepted applications from 234 downpayment assistance applicants, reviewed eligibility of 132, worked towards finalizing approvals for 65 applicants, and provided downpayment assistance for 46 applicants. Applications Received - 234 Reviewing Applicant Eligibility/Property Assessment - 132 Projects Received by GLO - 66 GLO Approved for Reimbursement - 65 Low-to-Moderate (LMI) Projects - 46 Houston - Buyout Program: During the reporting period, the City , Houston initially identified 4 properties and continues to identify sites for participation in the buyout program and submitted 1 project for approval which is pending additional information. Reviewing Applicant Eligibility/Property Assessment - 4 Projects Received by GLO - 1 Houston - Public Services: During the reporting period, the City of Houston continued to review eligibility for 19 projects and nonprofit partners began or continued to implement 7 public service programs which served 257 clients. # of applications received - 19 # of applications approved by GLO - 7 # of client cases closed - 13 # of client cases opened - 257 # of persons - 257 Houston - Economic Revitalization: During the reporting period, the City of Houston continued to carry out administrative services for its Economic Revitalization Program. Houston - Planning: During the reporting period, the City of Houston continued development of RFPs for planning studies and is reviewing solicitation responses to 1 RFP published in May. Projects Received by GLO - 2 GLO Approved - 2 HARRIS COUNTY: Harris County - Homeowner Assistance Program: During the reporting period, Harris County had applications under review and two underway for the Homeowner Assistance Program. The County continues to review the applications for eligibility and submitted 115 projects to the GLO in Quarter 2 2020. Projects Received by GLO - 115 GLO Approved for Construction - 60 Low-to-Moderate (LMI) Projects - 46 Reconstruction HMID Low/Mod - 22 Reconstruction HMID UN - 4 Rehabilitation HMID Low/Mod - 24 Rehabilitation HMID UN - 10 Harris County - Buyout and Acquisition Program: During the reporting period, Harris County had applications under review and none underway for the Buyout Program. The County submitted a formal request to add Involuntary Program activities to its Buyout Program, the GLO provided Technical Assistance to the County regarding the program design change process, and an action plan amendment has been drafted to add Involuntary Buyout activities to the County&apos;s Programs. Harris County - SF Affordable Housing Preservation: During the reporting period, the GLO informed the County that this Program is being cancelled. Harris County - Reimbursement Program: During the reporting period, Harris County had applications under review and 104 underway for the Reimbursement Program. Since the program started, 278 projects were approved by the GLO. Reviewing Applicant Eligibility/Property Assessment - 165 Projects Received by GLO - 109 GLO Approved for Reimbursement - 104 Low-to-Moderate (LMI) Projects - 58 Harris County - Affordable Rental Program: During the reporting period, Harris County had applications under review and none underway. The County anticipates submitting the remainder of projects to the GLO by the end of Quarter 3 2020. In Quarter 2 2020, one (1) new project was submitted to the GLO and to date, ten projects were approved with a total of 1,774 units. Projects Received by GLO - 1 GLO approved - 3 Harris County - Single Family New Constructo,: During the reporting period, Harris County had applications under review and none underway. In Quarter 2 2020, one project was submitted to the GLO. Applications Received - 1 In Review/Pending Additional Information - 1 Harris County - Commercial Buyout Program: During the reporting period, Harris County had program guideline development underway for its Involuntary Buyout Program, which includes commercial sites. Harris County - Method of Distribution Infrastructure Program: During the reporting period, Harris had engineering design underway for three flood and drainage facilities project and environmental reviews underway for twelve flood and drainage facilities and sewer projects. During the reporting period, Harris County had construction underway for one public facilities project. GLO Approved - 3 In Construction - 1 Harris County - Competitive Application Infrastructure Program: During the reporting period, Harris County completed environmental review for one of its flood and drainage facilities projects. During the reporting period, Harris County completed construction procurement for two flood and drainage facilities projects. Projects Received by GLO - 1 In Review/ Pending Additional Information - 1 GLO Approved - 1 Harris County - Planning: During the reporting period, Harris County had two planning studies underway. ECONOMIC REVITALIZATION PROGRAM Approved applications have been submitted to the GLO by the vendor, but none have been approved by the GLO yet. Multiple technical assistance meetings have been held with the vendor to help them understand the federal requirements of an approved economic development award. Expectations are that the vendor will change their operation to satisfy the GLO&apos;s requirement of a complete determination as to applicant eligibility and award amount by the end of July 2020. HOMEOWNER ASSISTANCE PROGRAM: During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q2, GLO was in the process of reviewing 2703 projects for eligibility, had approved 3315 Homeowner Assistance Program applications for assistance, completed construction on 1564 households, had construction underway on 670 houses and approved 1680 payment requests. Measure Description Reviewing Applicant Eligibility/Property Assessment - 2703 GLO Approved for Construction - 3315 Reconstruction HMID Low/Mod - 1167 Reconstruction HMID UN - 247 Reconstruction SMID Low/Mod - 95 Reconstruction SMID UN - 20 Rehabilitation HMID Low/Mod - 14 Rehabilitation HMID UN - 21 Rehabilitation SMID Low/Mod - 0 Rehabilitation SMID UN - 0 Total LMI Projects - 1276 Total UN Projects - 288 HOMEOWNER REIMBURSEMENT PROGRAM: At the end of the Second Quarter of 2020, the Homeowner Reimbursement Program has served ~2020 homeowners with ~$59.9M in reimbursement grants. An additional ~$20.95M has been approved and pending release of payment or execution of the closing documentation. At the end of Q2 2020, the Homeowner Reimbursement Program ,was approximately 97% obligated. The program is expected to exhaust all grant funding in Q3 and will continue the monitoring process and start the close-out of the program. Draft Applications - 8046 Verifying Eligibility - 218 Reimbursement Approved - 524 Total Outlays of Reimbursements - $19,757,295.88 Ineligible - 38 LOCAL BUYOUT PROGRAM: 23 Buyout/Acquisition contracts were executed. Program Guidelines Approved - 8 LOCAL INFRASTRUCTURE PROGRAM 84 Infrastructure contracts were executed. 42 Subrecipient Draws were approved for a total of $2,065,331.46 Environmental Underway - 48 AUGF issued (Authority to use grant funds) 2 PLANNING Planning operations are ongoing. PREPS No new update and no activity in Q2 2020. The program is complete and the draws have been made.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2020-07-01 | 2020 Q4 | Budget amount changes for the quarter total: $17,954,379.80 Obligation amount changes for the quarter total: $18,048,295.04 49 activities added for the quarter. AFFORDABLE RENTAL PROGRAM - Project count currently at 78 in total, with 57 projects under construction, 8 complete and a further 13 in the due diligence process. Measure Description Low-to-Moderate (LMI) Projects - 0 New Construction Projects - 0 New Construction Units - 0 Reconstruction Projects - 0 Reconstruction units - 0 Rehabilitation projects - 0 Rehabilitation units - 0 ECONOMIC REVITALIZATION PROGRAM - Approved applications have been submitted to the GLO by the vendor, but none have been approved by the GLO yet. Multiple technical assistance meetings have been held with the vendor to help them understand the federal requirements of an approved economic development award. Expectations are that the vendor will change their operation to satisfy the GLO&apos;s requirement of a complete determination as to applicant eligibility and award amount by the end of October 2020. HOMEOWNER ASSISTANCE PROGRAM - During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q3, GLO was in the process of reviewing 2069 projects for eligibility, had approved 3956 Homeowner Assistance Program applications for assistance, completed construction on 2054 households, had construction underway on 517 houses and approved 2336 payment requests. Measure Description Applications Received - 0 Reviewing Applicant Eligibility/Property Assessment - 2069 GLO Approved for Construction - 3956 Reconstruction HMID Low/Mod - 1523 Reconstruction HMID UN - 327 Reconstruction SMID Low/Mod - 116 Reconstruction SMID UN - 23 Rehabilitation HMID Low/Mod - 30 Rehabilitation HMID UN - 34 Rehabilitation SMID Low/Mod - 1 Rehabilitation SMID UN - 0 Total LMI Projects - 1670 Total UN Projects - 384 HOMEOWNER REIMBURSEMENT PROGRAM - At the end of the Third Quarter of 2020, the Homeowner Reimbursement Program has served ~2850 homeowners with ~$82.8M in reimbursement grants, and the Homeowner Reimbursement Program was approximately 99% obligated. The decision to extend the program to cover all Eligible applicants has pushed the program&apos;s completion date into Q4 2020 where the monitoring process will continue and close-out of the program will begin. Measure Description Draft Applications - 8046 Verifying Eligibility - 92 Reimbursement Approved - 87 Total Outlays of Reimbursements - $22,900,480.79 Ineligible - 42 LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM - 104 Subrecipient Draws were approved for a total of $4,912,404.92. 8 Infrastructure contracts were executed. 1 Buyout/Acquisition contract was executed. Measure Description - Local Buyout/Acquistion Program Guidelines Approved - 12 Measure Description - Local Infrastructure Contract Executed - 8 Environmental Underway - 42 AUGF issued (Authority to use grant funds) - 17 Construction Procurement Underway - 2 PLANNING - Planning operations are ongoing. PREPS - The program is complete and final budget reconciliat,on in process. Houston - Homeowners Assistance Program - During the reporting period, the City of Houston accepted applications for 38 new projects, reviewed eligibility of 267 new projects, issued notice to proceed to construction on 52 projects, reimbursements paid to 33 homeowners, and completed construction on 27. Measure Description Applications Received by City of Houston - 38 Reviewing Applicant Eligibility/Property Assessment - 267 Projects Received by GLO - 151 GLO Application Approvals - 167 Low-to-Moderate (LMI) Applications Approved - 139 Reconstruction HMID Low/Mod Applications Approved - 98 Reconstruction HMID UN Applications Approved - 1 Rehabilitation HMID Low/Mod Applications Approved - 32 Rehabilitation HMID UN Applications Approved - 2 Reimbursement HMID Low/Mod Applications Approved - 25 Reimbursement HMID UN Applications Approved - 26 Houston - Single Family Development Program - During the reporting period, the City of Houston began implementation of the program. Houston - Multifamily Rental Program - During the reporting period, the City of Houston continued to implement its Multifamily Program. The City issued notice to proceed on 1 development and currently has 7 projects under construction this quarter. Measure Description Applications Received by City of Houston - 0 Reviewing Applicant Eligibility/Property Assessment - 42 Projects Received by GLO - 3 GLO Approved - 1 Household Units Approved - 70 Houston - Small Rental Program - The City of Houston has begun implementation of the program. The City of Houston reported to GLO during Q3 of 21 new applications received by the City at the very end of Q2. Measure Description Applications Received by City of Houston - 21 Houston - Homebuyer Assistance Program - During the reporting period, the City of Houston accepted applications from 32 down payment assistance applicants, reviewed eligibility of 93 and provided down payment assistance for 23 applicants. Measure Description Applications Received by City of Houston - 32 Reviewing Applicant Eligibility/Property Assessment - 93 Projects Received by GLO - 85 GLO Approved for Reimbursement - 72 Households Assisted - 23 Houston - Buyout Program - During the reporting period, the City of Houston continued to implement the Buyout Program and the GLO approved one project. Measure Description GLO Approved - 1 Houston - Public Services - During the reporting period, the City of Houston continued to implement 18 public service programs, with 26 additional beneficiaries who have been served and completed public service programs. Measure Description # of applications received - 0 # of applications approved by GLO - 9 # of client cases closed - 26 # of client cases opened - 552 # of persons - 552 Houston - Economic Revitalization - During the reporting period, the City of Houston continued to carry out administrative services for its Economic Revitalization Program. Houston - Plnning - During the reporting period, the City of Houston continued development of RFPs for planning studies. ,p>Measure Description Projects Received by GLO - 2 In Review/ Pending Additional Information - 2 GLO Approved - 2 Harris County - Homeowner Assistance Program - During the reporting period, Harris County had applications under review and one underway for the Homeowner Assistance Program. The County continued to review the applications for eligibility and submitted 77 projects to the GLO in Quarter 3 2020. Measure Description Projects Received by GLO - 77 GLO Approved for Construction - 119 Low-to-Moderate (LMI) Projects - 94 Reconstruction HMID Low/Mod - 33 Reconstruction HMID UN - 10 Rehabilitation HMID Low/Mod - 22 Rehabilitation HMID UN - 12 Harris County - Buyout and Acquisition Program - During the reporting period, Harris County had outreach underway and applications under review for its buyout program. An action plan amendment was submitted to HUD to add involuntary buyout activities to the County&apos;s programs and GLO is providing Technical Assistance to the County regarding the program design and policies and procedures. Measure Description Applications Received - 1 Reviewing Applicant Eligibility/Property Assessment - 1 Harris County - Reimbursement Program - During the reporting period, Harris County had applications under review and 175 underway for the Reimbursement Program. Since the program started, 454 projects were approved by the GLO. Measure Description Reviewing Applicant Eligibility/Property Assessment - 117 Projects Received by GLO - 158 GLO Approved for Reimbursement - 175 Low-to-Moderate (LMI) Projects - 78 Harris County - Affordable Rental Program - During the reporting period, Harris County had applications under review and five underway. In Quarter 3 2020, six new projects were submitted to the GLO and to date, ten projects were approved with a total of 1,774 units. During the reporting period, Harris County had construction underway for five ARP projects. Measure Description Projects Received by GLO - 6 In Construction - 5 Harris County - Single Family New Construction - During the reporting period, Harris County had applications under review and five underway. Harris County completed acquisition for one Single Family New Construction project. During the reporting period, Harris County had planning and design underway for three projects. Measure Description Applications Received - 2 In Review/Pending Additional Information - 2 GLO approved - 5 Harris County - Commercial Buyout Program - During the reporting period, Harris County had program guidelines under review for its Involuntary Buyout Program, which includes commercial sites. An action plan amendment was submitted to HUD to add involuntary buyout activities, including commercial sites, to the County&apos;s programs and GLO is providing Technical Assistance to the County regarding the program design and policies and procedures. Harris County - Method of Distribution Infrastructure Program - During the reporting period, Harris had engineering design underway for eight sewer facilities and flood and drainage projects and environmental reviews underway for twelve flood and drainage facilities an,d sewer projects. During the reporting period, Harris County had construction underway for one public facilities project. Measure Description Projects Received by GLO - 1 In Review/ Pending Additional Information - 1 Harris County - Competitive Application Infrastructure Program - During the reporting period, Harris County had construction underway for two flood and drainage facilities projects. Measure Description Projects Received by GLO - 5 In Review/ Pending Additional Information - 5 GLO Approved - 1 In Construction - 2 Harris County - Planning - During the reporting period, Harris County had five planning studies underway. During the reporting period, Harris County had procurement underway for eleven planning projects. Measure Description New In Progress - 3
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2020-10-01 | 2021 Q1 | Budget amount changes for the quarter total: $197,625,279.87 Obligation amount changes for the quarter total: $197,625,280.63 9 activities added for the quarter. AFFORDABLE RENTAL PROGRAM: Project count currently at 77 in total, with 55 projects under construction, 14 substantially completed construction and a further 8 in the due diligence process. COVID has caused both material and labor shortages and slowdown. Nevertheless, construction has continued across the board with a large number of construction completions and closeouts scheduled for 2021. Measure Description - Q4 Low-to-Moderate (LMI) Projects - 77 New Construction Projects - 33 New Construction Units - 3066 Reconstruction Projects - 9 Reconstruction units - 280 Rehabilitation projects - 35 Rehabilitation units - 2539 ECONOMIC REVITALIZATION PROGRAM Approved applications have been submitted to the GLO by the vendor, but none have been approved by the GLO yet. Multiple technical assistance meetings have been held with the vendor to help them understand the federal requirements of an approved economic development award. Vendor has replaced personnel to satisfy the GLO&apos;s requirement of a complete determination as to applicant eligibility and award amount by the end of January 2021. HOMEOWNER ASSISTANCE PROGRAM During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q4, GLO was in the process of reviewing 1473 projects for eligibility, had approved 4687 Homeowner Assistance Program applications for assistance, completed construction on 2441 households, had construction underway on 512 houses and approved 2094 payment requests. Measure Description - Q4 Applications Received - 0 Reviewing Applicant Eligibility/Property Assessment - 1473 GLO Approved for Construction - 4687 Reconstruction HMID Low/Mod - 1811 Reconstruction HMID UN - 384 Reconstruction SMID Low/Mod - 133 Reconstruction SMID UN - 25 Rehabilitation HMID Low/Mod - 50 Rehabilitation HMID UN - 37 Rehabilitation SMID Low/Mod - 1 Rehabilitation SMID UN - 0 Total LMI Projects - 1995 Total UN Projects - 446 HOMEOWNER REIMBURSEMENT PROGRAM At the end of the Fourth Quarter of 2020, the Homeowner Reimbursement Program has served ~2882 homeowners with ~$83.9M in reimbursement grants, and the Homeowner Reimbursement Program was approximately 99% obligated. The decsion to extend the program to cover all Eligible appllcants has pushed the program&apos;s completion date into Q1 2021 where the monitoring process will continue and close-out of the program will begin. Measure Description - Q4 Draft Applications - 8046 Verifying Eligibility - 8 Reimbursement Approved - 91 Total Outlays of Reimbursements - $1,075,155.65 Ineligible - (-4) LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM 123 Grantee Draws were approved for a total of $9,641,639.55 1 Buyout contract was executed. Measure Description - Local Buyout/Acquistion - Q4 Program Guidelines Approved - 5 Reviewing Applicant Eligibility/Property Assessment - 8 Measure Des,iption - Local Infrastructure - Q4 Environmental Underway - 11 AUGF issued (Authority to use grant funds) - 14 Construction Procurement Underway - 1 Construction Underway - 3 PLANNING Planning operations are ongoing. PREPS The program and budget reconciliation are complete. Houston - Homeowners Assistance Program Current Quarter Narrative During the reporting period, the City of Houston accepted applications for 23 new projects, reviewed eligibility of 103 new projects, issued notice to proceed to construction on 55 projects, reimbursed 22 homeowners, and completed construction on 62. Data Measure Description - Q4 Applications Received by City of Houston - 23 Reviewing Applicant Eligibility/Property Assessment - 103 Projects Received by GLO - 67 GLO Application Approvals - 33 Low-to-Moderate (LMI) Applications Approved - 25 Reconstruction HMID Low/Mod Applications Approved - 17 Reconstruction HMID UN Applications Approved - 0 Rehabilitation HMID Low/Mod Applications Approved - 5 Rehabilitation HMID UN Applications Approved - 0 Reimbursement HMID Low/Mod Applications Approved - 5 Reimbursement HMID UN Applications Approved - 9 Houston - Single Family Development Program Current Quarter Narrative "During the reporting period, the City of Houston began implementation of the program. Houston - Multifamily Rental Program Current Quarter Narrative During the reporting period, the City of Houston continued to implement its Multifamily Program. The City issued notice to proceed on 4 developments and currently has 10 projects under construction this quarter. Data Measure Description - Q4 Applications Received by City of Houston - 0 Reviewing Applicant Eligibility/Property Assessment - 0 Projects Received by GLO - 8 GLO Approved - 2 Household Units Approved - 270 Houston - Small Rental Program Current Quarter Narrative The City of Houston has begun implementation of the program. Data Measure Description - Q4 Reviewing Applicant Eligibility/Property Assessment - 21 Houston - Homebuyer Assistance Program Current Quarter Narrative During the reporting period, the City of Houston accepted applications from 66 down payment assistance applicants, reviewed eligibility of 74 and provided down payment assistance for 44 applicants. Data Measure Description - Q4 Applications Received by City of Houston - 66 Reviewing Applicant Eligibility/Property Assessment - 74 Projects Received by GLO - 60 GLO Approved - 55 Households Assisted - 44 Houston - Buyout Program Current Quarter Narrative During the reporting period, the City of Houston continued to implement the Buyout Program. b,> Houston - Public Services Current Quarter Narrative "During the reporting period, the City of Houston continued to implement 18 public service programs, with 176 additional beneficiaries who have been served and completed public service programs. " Data Measure Description - Q4 # of applications received by GLO - 0 # of applications approved by GLO - 0 # of client cases closed - 176 # of client cases opened - 307 Houston - Economic Revitalization Current Quarter Narrative During the reporting period, the City of Houston continued to carry out administrative services for its Economic Revitalization Program. Houston - Planning Current Quarter Narrative During the reporting period, the City of Houston continued development of RFPs for planning studies. Harris County - Homeowner Assistance Program Current Quarter Narrative During the reporting period, Harris County had eight new projects underway for the Homeowner Assistance Program. To date, the County submitted a total of 215 applications of which 185 were approved. Seven are in construction. Due to the reallocation of funds, no new projects will be submitted for the program. Data Measure Description - Q4 Projects Received by GLO - 0 GLO Approved for Construction - 8 Low-to-Moderate (LMI) Projects - 6 Reconstruction HMID Low/Mod - 4 Reconstruction HMID UN - 0 Rehabilitation HMID Low/Mod - 2 Rehabilitation HMID UN - 2 Harris County - Buyout and Acquisition Program Current Quarter Narrative During the reporting period, Harris County had outreach underway and applications under review for its involuntary buyout program. An Action Plan Amendment was submitted to HUD to change the voluntary program to an involuntary program and it was approved October 6, 2020. GLO is providing Technical Assistance to the County regarding the program design, relocation options, and policies and procedures. County anticipates submitting applications for eligibility review to the GLO starting in Quarter 1 2021. Data Measure Description - Q4 Applications Received - 22 Reviewing Applicant Eligibility/Property Assessment - 326 Harris County - Reimbursement Program Current Quarter Narrative During the reporting period, Harris County had applications under review and 113 new projects underway for the Reimbursement Program. Since the program started, 567 projects were approved by the GLO. 181 checks have been disbursed to homeowners totaling $6.8 million. Data Measure Description - Q4 Reviewing Applicant Eligibility/Property Assessment - 653 Projects Received by GLO - 92 GLO Approved for Reimbursement - 113 Low-to-Moderate (LMI) Projects - 69 Harris County - Affordable Rental Program Current Quarter Narrative During the reporting period, Harris County had six applications under review of which three projects were approved. To date, thirteen projects were approved with a total of 2,212 units. In Quarter 4 2020, Harris County had construction underway for eight affordable rental projects. Data Measure Description - Q4 GLO Approved - 3 In Construction - 3 <b,r>Harris County - Single Family New Construction Current Quarter Narrative In Quarter 4 2020, Harris County completed acquisition for one Single Family New Construction project. In total, six approved projects were approved and underway. Harris County - Commercial Buyout Program Current Quarter Narrative During the reporting period, Harris County had program guidelines under review for its Involuntary Buyout Program, which includes commercial sites. An action plan amendment was submitted and approved by HUD on October 6, 2020 to add involuntary buyout activities, including commercial sites, to the County&apos;s programs. The Commercial Buyout Program was merged with the Residential Buyout Program. County has identified 49 sites for program eligibility. Harris County - Method of Distribution Infrastructure Program Current Quarter Narrative To date, 25 infrastructure projects have been submitted of which 21 have been approved and one is in construction. During the reporting period, Harris County had engineering design and environmental reviews underway for thirteen flood and drainage facilities and sewer projects. Harris County - Competitive Application Infrastructure Program Current Quarter Narrative To date, 15 applications have been submitted, seven have been approved, and two are in construction. During the reporting period, Harris County had engineering design and environmental review underway for one sewer project. Data Measure Description - Q4 GLO Approved - 1 Harris County - Planning Current Quarter Narrative To date, Harris County had eight planning studies underway and procurement underway for 10 additional planning projects. Data Measure Description - Q4 New In Progress - 3
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2021-01-01 | 2021 Q2 | 33 new activities have been added this quarter. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 464 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q1 2021, GLO completed 108 such reviews, primarily covering new Mitigation applications. For more information please see the individual programs&apos; narrtives below. AFFORDABLE RENTAL PROGRAM: Project count currently at 77 in total, with 59 projects under construction, 17 substantially completed construction and only one project remaining in the due diligence process. COVID has caused both material and labor shortages and slowdown. Nevertheless, construction has continued across the board with a large number of construction completions and closeouts scheduled for Q2 2021 onwards as the Affordable Rental Team work to develop the closeout process to officially close projects out and begin to report demographic information from Q2 2021 onwards. All projects have submitted AFHMP (Fair Housing Marketing Plans) to the ARP team, which will be reviewed during their first compliance monitoring period. Measure Description - Q1 Low-to-Moderate (LMI) Projects - 0 New Construction Projects - 0 New Construction Units - 0 Reconstruction Projects - 0 Reconstruction units - 0 Rehabilitation projects - 0 Rehabilitation units - 0 CITY OF HOUSTON See Attachment A HARRIS COUNTY See Attachment B ECONOMIC REVITALIZATION PROGRAM Approved applications have been submitted to the GLO by the vendor, but none have been approved by the GLO yet. Multiple technical assistance meetings have been held with the vendor to help them understand the federal requirements of an approved economic development award. Vendor has replaced personnel to satisfy the GLO&apos;s requirement of a complete determination as to applicant eligibility and award amount by the end of April 2021. HOMEOWNER ASSISTANCE PROGRAM During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q1, GLO was in the process of reviewing 1279 projects for eligibility, had approved 340 Homeowner Assistance Program applications for assistance, completed construction on 369 households, had construction underway on 527 houses and approved 1192 payment requests. Measure Description - Q1 Applications Received - 0 Reviewing Applicant Eligibility/Property Assessment - 1279 GLO Approved for Construction - 340 Reconstruction HMID Low/Mod - 254 Reconstruction HMID UN - 56 Reconstruction SMID Low/Mod - 27 Reconstruction SMID UN - 7 Rehabilitation HMID Low/Mod - 17 Rehabilitation HMID UN - 8 Rehabilitation SMID Low/Mod - 0 Rehabilitation SMID UN - 0 Total LMI Projects - 298 Total UN Projects - 71 HOMEOWNER REIMBURSEMENT PROGRAM At the end of the First Quarter of 2021, the Homeowner Reimbursement Program has served ~2963 homeowners with ~$85.99M in reimbursement grants, and the Homeowner Reimbursement Program was approximately ,% obligated. The decision to extend the program to cover all Eligible applicants has pushed the program&apos;s completion date into Q1 2021 where the monitoring process will continue and close-out of the program will begin. The -5 Ineligibles indicate 5 appeals resulted in overturned ineligibility and reentered application processing with no additional ineligibles added. Measure Description - Q1 Draft Applications - 8046 Verifying Eligibility - 4 Reimbursement Approved - 7 Total Outlays of Reimbursements - $2,097,734.88 Ineligible - (-5) LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM "101 Grantee Draws were approved for a total of 5,529,824.68 0 Buyout contracts executed" Measure Description - Local Buyout/Acquistion - Q1 Program Guidelines Approved - 2 AUGF issued (Authority to use grant funds) - 3 Measure Description - Local Infrastructure - Q1 Contract Executed - 10 Environmental Assesment Began - 4 AUGF issued (Authority to use grant funds) - 7 Construction Procurement Began - 2 Construction Began - 3 Construction Complete - 1 PLANNING Planning operations are ongoing. PREPS The program and budget reconciliation are complete. GLO Homeowners Assistance Program - City of Houston During the reporting period, the GLO approved applications for 404 new projects, issued notice to proceed to construction on 106 projects, issued final retainage payment to builders on 6 projects, and completed the construction phase on 49 homes. County developed an Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. The goal is to ensure that outreach and communication efforts reach eligible homeowners from all groups including, but not limited to, racial, ethnic, national origin, religious, familial status, the disabled, special needs, and gender groups. This plan is further supported by the Homeowner Assistance Program Guidelines and Standard Operating Procedures to ensure access to program benefits. Measure Description - Q1 Applications Received - 492 GLO Application Approvals - 404 Reconstrution HMID Low/Mod Applications Approved - 330 Reconstrution HMID UN Applications Approved - 49 Rehabilitation HMID Low/Mod Applications Approved - 20 Rehabilitation HMID UN Applications Approved - 5 Projects Under Construction - 106 Projects with Construction Completed - 49 GLO Homeowners Assistance Program - Harris County During the reporting period, the GLO approved applications for 214 new projects, issued notice to proceed to construction on 51 projects, issued final retainage payment to builders on 1 project, and completed the construction phase on 14 homes. GLO developed an Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. The goal is to ensure that outreach and communicato, efforts reach eligible homeowners from all groups including, but not limited to, racial, ethnic, national origin, religious, familial status, the disabled, special needs, and gender groups. This plan is further supported by the Program Guidelines and Standard Operating Procedures to ensure access to program benefits. Measure Description - Q1 Applications Received - 238 GLO Application Approvals - 214 Reconstrution HMID Low/Mod Applications Approved - 145 Reconstrution HMID UN Applications Approved - 36 Rehabilitation HMID Low/Mod Applications Approved - 21 Rehabilitation HMID UN Applications Approved - 12 Projects Under Construction - 51 Projects with Construction Completed - 14 Harvey 5b Houston Programs - Attachment A Houston - Homeowners Assistance Program During the reporting period, the City of Houston reviewed eligibility of 1,307 new applications, issued notice to proceed to construction on 41 projects, completed the reimbursment phase for 9 homeowners and completed the construction phase on 57 homes. The City of Houston developed an Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. The plan ensures that outreach and communication efforts reach eligible homeowners and renters from all racial, ethnic, national origin, religious, familial status, disabled, and gender groups. The plan puts particular emphasis on successful outreach to LMI areas and those communities with minority concentrations that were affected by Hurricane Harvey. This plan is further supported by the Homeowner Assistance Program Guidelines and Standard Operating Procedures to ensure access to program benefits. Measure Description - Q1 Applications Received by City of Houston - 0 City of Houston Reviewing Applicant Eligibility/Property Assessment - 1307 Applications Submitted to the GLO - 14 Applications Approved by GLO - 11 Reconstruction HMID Low/Mod Applications Approved - 2 Reconstruction HMID UN Applications Approved - 0 Rehabilitation HMID Low/Mod Applications Approved - 0 Rehabilitation HMID UN Applications Approved - 0 Reimbursement HMID Low/Mod Applications Approved - 4 Reimbursement HMID UN Applications Approved - 5 Projects Under Construction - 41 Projects with Construction Completed - 57 Projects with Reimbursement Checks Issued - 9 Houston - Single Family Development Program During the reporting period, the City of Houston revised the program guidelines and began developing the Notice of Funding Availability to select developers. The City of Houston developed an Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. The plan ensures that outreach and communication efforts reach eligible homeowners and renters from all racial, ethnic, national origin, religious, familial status, disabled, and gender groups. The plan puts particular emphasis on successful outreach to LMI areas and thse,communities with minority concentrations that were affected by Hurricane Harvey. This plan is further supported by the Single Family Development Program Guidelines and Standard Operating Procedures to ensure access to program benefits. The guidelines and Standard Operating Procedures require that each awarded application be evaluated by the City of Houston and the GLO to confirm compliance with AFFH requirements. Projects must also have an Affirmative Fair Housing Marketing Plan in place. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Construction began on four multifamily projects. Including the new projects under construction, the City of Houston currently has 14 total projects under construction. The City of Houston developed an Affirmative Fair Housing (AFFH) Marketing and Outreach Plan for its housing programs. The plan ensures that outreach and communication efforts reach eligible homeowners and renters from all racial, ethnic, national origin, religious, familial status, disabled, and gender groups. The plan puts particular emphasis on successful outreach to LMI areas and those communities with minority concentrations that were affected by Hurricane Harvey. This plan is further supported by the Multifamily Rental Program Guidelines and Standard Operating Procedures to ensure access to program benefits. The guidelines and Standard Operating Procedures require that each awarded application be evaluated by the City of Houston and the GLO to confirm compliance with AFFH requirements. Projects must also have a correctly completed Affirmative Fair Housing Marketing Plan in place. During the reporting period, the City of Houston submitted an AFFH evaluation for one project and the GLO issued AFFH evaluation conditional approval letters for 4 projects. Measure Description - Q1 Applications Received by City of Houston - 0 City of Houston Reviewing Application Eligibility - 0 Applications Submitted to GLO - 1 Applications Approved by GLO - 4 Household Units Approved - 508 Projects Under Construction - 4 Projects with Construction Completed - 0 Houston - Small Rental Program During the reporting period, the City of Houston continued to review the eligibility of applications received under the Notice of Funding Availability and prepared application documentation for submission to GLO. The City of Houston developed an Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. The plan ensures that outreach and communication efforts reach eligible homeowners and renters from all racial, ethnic, national origin, religious, familial status, disabled, and gender groups. The plan puts particular emphasis on successful outreach to LMI areas and those communities with minority concentrations that were affected by Hurricane Harvey. This plan is further supported by the Small Rental Program Guidelines and Standard Operating Procedures to ensure access to program benefits. The guidelines and Standard Operating Procedures require that each awarded application be evaluated by the City of Houston and the GLO to confirm compliance with AFFH requirements. Projects must also have an Affirmative Fair Housing Marketing Plan in place. Houston - Homebuyer Assistance Program Current Quarter Narrative During the reporting perod,,the City of Houston accepted applications from 141 down payment assistance applicants, reviewed eligibility of 30 and provided down payment assistance for 38 applicants, who are in the closeout phase. The City of Houston developed an Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. The plan ensures that outreach and communication efforts reach eligible homeowners and renters from all racial, ethnic, national origin, religious, familial status, disabled, and gender groups. The plan puts particular emphasis on successful outreach to LMI areas and those communities with minority concentrations that were affected by Hurricane Harvey. This plan is further supported by the Homebuyer Assistance Program Guidelines and Standard Operating Procedures to ensure access to program benefits. Measure Description - Q1 Applications Received by City of Houston - 141 City of Houston Reviewing Applicant Eligibility - 30 Applications Submitted to GLO - 45 Applications Approved by GLO - 55 LMI Applications Approved by GLO - 32 UN Applications Approved by GLO - 23 Homebuyer Households - Received Down payment Assistance - 38 Houston - Buyout Program During the reporting period, the City of Houston and the GLO initiated the environmental review process for one property and the City of Houston submitted one application to the GLO. The City of Houston developed an Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. The plan ensures that outreach and communication efforts reach eligible homeowners and renters from all racial, ethnic, national origin, religious, familial status, disabled, and gender groups. The plan puts particular emphasis on successful outreach to LMI areas and those communities with minority concentrations that were affected by Hurricane Harvey. This plan is further supported by the Buyout Program Guidelines and Standard Operating Procedures to ensure access to program benefits. Measure Description - Q1 Applications Submitted to GLO - 1 Houston - Public Services During the reporting period, the City of Houston continued to implement 18 public service programs. Additionally, 249 beneficiaries were provided public service programs and are in the closeout phase. Two public service programs: Montrose Center and the Women&apos;s Home Homeless Services completed contracts during the reporting period. The City of Houston developed an Affirmative Fair Housing Marketing and Outreach Plan for its programs. The plan ensures that outreach and communication efforts reach eligible homeowners and renters from all racial, ethnic, national origin, religious, familial status, disabled, and gender groups. The plan puts particular emphasis on successful outreach to LMI areas and those communities with minority concentrations that were affected by Hurricane Harvey. This plan is further supported by the Homeowner Assistance Program Guidelines and Standard Operating Procedures to ensure access to program benefits. Measure Description - Q1 Applications Received by City of Houston - 0 City of Houston Reviewing Application Eligibility - 0 Number of Beneficiaries who began Services - 852 Number of Beneficiaries who Completed Services - 249 Number of Beneficiaries who Exited/Did not Complete - 47 Number of Projects Completed - 2 Houston - Economic Developmet Pr,gram During the reporting period, the City of Houston continued to carry out administrative services for its Economic Revitalization Program. Through the HEDP Guidelines ensure that the program affirmatively furthers fair housing through its commitment to creating jobs and economic opportunity for LMI persons and communities. Houston - Planning During the reporting period, the City of Houston continued development of RFPs for planning studies. Measure Description - Q1 Projects Approved by GLO - 1 Harvey 5b Harris County Programs - Attachment B Harris County - Homeowner Assistance Program No expenditures this period. To date, Harris County has had 11 projects in construction for the Homeowner Assistance Program of which three (3) are construction complete. The County submitted a total of 215 applications of which 185 were approved. Due to the reallocation of funds, no new projects will be submitted for the program. Harris County - Buyout and Acquisition Program No expenditures this period. During the reporting period, the GLO approved the Harris County program guidelines for its Involuntary Buyout Program. In Quarter 1 2021, the County began submitting projects to the GLO and 39 were submitted totaling over $8 million in projects. The County has until June 30, 2021 to submit sites to the GLO. The County developed an Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. County has conducted outreach, held various town hall meetings, including town hall meetings in other languages, and performed door to door canvassing. In Quarter 1 2021, a buyout town hall session was held in English and Spanish and buyout information is posted on Harris County&apos;s Recovery website in both languages. Measure Description - Q1 Reviewing Applicant Eligibility/Property Assessment - 33 Projects Received by GLO - 39 Harris County - Reimbursement Program No expenditures this period. During the reporting period, Harris County had applications under review and 121 new projects underway for the Reimbursement Program. Since the program started, 688 projects were approved by the GLO. 234 checks have been disbursed to homeowners totaling $9.1 million. County developed an Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. During this period, County held events in three communities over two weekends to assist applicants with completing eligibility documentation; the events included interpreters and County reported that over 200 applicants attended the events. Measure Description - Q1 Reviewing Applicant Eligibility/Property Assessment - 516 Projects Received by GLO - 113 GLO Approved for Reimbursement - 121 Low-to-Moderate (LMI) Projects - 66 Harris County - Affordable Rental Program During the reporting period, Harris County had three (3) applications under review of which two (2) of them were approved. To date, fifteen (15) projects have been approved with a total of 2,411 units. In Quarter 1 2021, Harris County had construction underway for nine (9) affordable rental projects. The GLO has completed an Affirmatively Furthering Fair Housing (AFFH) review for each project as part of the eligibility review phase and prior to project approval. Mesure ,escription - Q1 GLO Approved - 2 In Construction - 1 Harris County - Single Family New Construction No expenditures this period. In total, eight (8) projects have been approved including one (1) that has since been withdrawn by the County. Five (5) projects are in the design/ engineering and environmental review phases. Two (2) built inventory projects are in construction. One (1) project was submitted this quarter; County has until June 30, 2021 to submit remainder of projects to the GLO. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. In the quarter, two AFFH reviews were completed. Measure Description - Q1 Applications Received - 1 In Review/Pending Additional Information - 1 GLO approved - 2 Harris County - Commercial Buyout Program No expenditures this period. During the reporting period, Harris County had program guidelines approved for its Involuntary Buyout Program, which includes commercial sites. In Quarter 1 2021, County began submitting projects to the GLO and four (4) were submitted totaling nearly $2 million in projects. County has until June 30, 2021 to submit sites to the GLO. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan; for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County&apos;s Community Services Department using Harris County Flood Control District data as most affected and hopelessly deep in the flood plain. Measure Description - Q1 Projects Received by GLO - 4 In Review/ Pending Additional Information - 4 Harris County - Method of Distribution Infrastructure Program No expenditures this period. To date, 25 infrastructure projects have been submitted of which 21 have been approved and one is in construction (93% complete). During the reporting period, Harris County had engineering design underway on 16 projects and environmental review underway for seven (7) projects. For the 21 approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Harris County - Competitive Application Infrastructure Program To date, 15 applications have been submitted, 11 have been approved, including one (1) public services project. Two (2) drainage projects are under construction. During the reporting period, GLO approved four (4) neighborhood facility/ community center projects and Harris County had an environmental review underway for four (4) projects. For the ten (10) approved infrastructure projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. In Quarter 1, three AFFH reviews were completed. Measure Description - Q1 GLO Approve - 4 Harris County - Planning No expenditures this period. In Quarter 1 2021, Harris County had one (1) planning project begin; plan is regarding mitigation efforts to reduce the impact of new development. In total, seven (7) planning studies are currently in progress and procurement is underway for nine (9) additional planning projects. Three (3) planning stud,ies are complete. Measure Description - Q1 New In Progress - 1
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2021-04-01 | 2021 Q3 | OVERALL NARRATIVE 3 new activities added this quarter. 850 Households reported as completed this quarter. Due to reporting issues in previous quarters, all of Q2 completed households cannot be reported this quarter and additional data corrections will be resolved with HUD. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 499 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q2 2021, GLO completed 35 such reviews. AFFORDABLE RENTAL PROGRAM: Project count currently at 77 in total, with 42 projects under construction, 34 substantially completed construction and only one project remaining in the due diligence process. COVID has caused both material and labor shortages and slowdown. Nevertheless, construction has continued across the board with a large number of construction completions and closeouts scheduled for Q2 2021 onwards. The Affordable Rental Team work has developed the closeout process to officially close projects out. All projects have submitted AFHMP (Fair Housing Marketing Plans) to the ARP team, which will be reviewed during their first compliance monitoring period. CITY OF HOUSTON See Attachment A HARRIS COUNTY See Attachment B ECONOMIC REVITALIZATION PROGRAM Over 800 applicants have been assigned to the eligibility team to begin the initial eligibility review. From this population over 100 have requested to be withdrawn from the program. Another 230 have been nonresponsive and the program has begun the process of alerting these applicants that they may loss their eligibility if they do not respond in a timely manner. The program has approved $9,400,000.00 in Grant Awards to 58 applicants. Measure Description - Q2 Applications Received - 0 GLO Approved - 58 HOMEOWNER ASSISTANCE PROGRAM During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q2, GLO was in the process of reviewing 164 projects for eligibility, had approved 193 Homeowner Assistance Program applications for assistance, completed construction on 335 households, had construction underway on 623 houses and approved 1391 payment requests. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Measure Description - Q2 Applications Received - 0 Reviewing Applicant Eligibility/Property Assessment - 164 GLO Approved for Construction - 193 Reconstruction HMID Low/Mod - 233 Reconstruction HMID UN - 65 Reconstruction SMID Low/Mod - 22 Reconstruction SMID UN - 2 Rehabilitation HMID Low/Mod - 8 Rehabilitation HMID UN - 5 Rehabilitation SMID Low/Mod - 0 Rehabilitation SMID UN - 0 Total LMI Projects - 263 Total UN Projects - 72 HOMEOWNER REIMBURSEMENT PROGRAM At the end of the Second Quarter of 2021, the Homeowner Reimbursement Program has served ~2967 homeowners with ~$86.1M in reimbursement grants, and the Homeowner Reimbursement Prog,m was approximately 99% obligated. The decsion to extend the program to cover all Eligible appllcants has pushed the program&apos;s completion date into Q3 2021 where the monitoring process will continue and close-out of the program will begin. There is one remaining application that has reentered the program through the appeals process that will be processed in Q3 2021. The -1 Ineligibles indicate 1 appeal resulted in overturned ineligibiliity and reentered application processing with no additional ineligibles added. Measure Description - Q2 Draft Applications - 8046 Verifying Eligibility - 1 Reimbursement Approved - 4 Total Outlays of Reimbursements - $100,699.83 Ineligible - (-1) LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM 104 Subrecipient Draws were approved for $7,293,300.24. 0 Buyout Contracts executed. Measure Description - Local Buyout/Acquistion - Q2 Program Guidelines Approved - 0 AUGF broad review complete (Authority to use grant funds) - 7 Buyout Completed LMI - 0 Buyout Completed UN - 0 Measure Description - Local Infrastructure - Q2 Contracts Executed - 1 "Kick-off" - 7 Environmental Review Initiated - 1 AUGF Issued - 20 Construction Initiated/Bid Advertised - 5 Construction Complete - 1 COCC Complete - 1 PLANNING Planning operations are ongoing. GLO Homeowners Assistance Program - City of Houston During the reporting period, GLO approved applications for 259 new projects, construction started on 69 homes, and completed construction (final inspection) on 63 homes. The GLO updated their methodology for reporting completed rehabilitation and reconstruction projects in DRGR. Previously, GLO reported completed projects once the CDBG-DR funds were fully expensed. The methodology has been updated to report on completed rehabilitation and reconstruction projects once the final inspection is complete. The performance measures and associated demographic information have been updated to reflect all rehabilitation and reconstruction projects that have received final inspection as of the end of the reporting period. To date, 117 rehabilitation or reconstruction projects have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q2 Applications Received - 262 GLO Application Approvals - 259 Reconstruction HMID Low/Mod Applications Approved - 227 Reconstruction HMID UN Applications Approved - 21 Rehabilitation HMID Low/Mod Applications Approved - 11 Rehabilitation HMID UN Applications Approved - 0 Projects Under Construction - 69 Projects with Construction Completed (Final Inspection) - 63 GLO Homeowners Assistance Program - Harris County During the reporting period, GLO approved applications for 87 new projects, construction started on 41 homes, and completed construction (final inspection) on 27 homes. The GLO updated their methodology for reporting completed rehabilitation and reconstruction projects in DRGR. Previously, GLO reported completed projects once the CDBG-DR funds were fully expensed. The methodology has been updated to report on completed rehabilitation and reconstruction projects once te,final inspection is complete. The performance measures and associated demographic information have been updated to reflect all rehabilitation and reconstruction projects that have received final inspection as of the end of the reporting period. To date, 43 rehabilitation or reconstruction projects have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q2 Applications Received - 89 GLO Application Approvals - 87 Reconstruction HMID Low/Mod Applications Approved - 59 Reconstruction HMID UN Applications Approved - 26 Rehabilitation HMID Low/Mod Applications Approved - 1 Rehabilitation HMID UN Applications Approved - 1 Projects Under Construction - 41 Projects with Construction Completed (Final Inspection) - 27 Harvey 5b Houston Programs - Attachment A Houston - Homeowners Assistance Program During the reporting period, the City of Houston issued notice to proceed to construction on 18 projects, reimbursed 10 homeowners (not yet reportable in DRGR) and completed final inspection on 31 rehabilitation or reconstruction projects (27 for low-to-moderate income households and 4 for non-low-to-moderate income households). The GLO updated their methodology for reporting completed rehabilitation and reconstruction projects in DRGR. Previously, GLO reported completed projects once the CDBG-DR funds were fully expensed. The methodology has been updated to report on completed rehabilitation and reconstruction projects once the final inspection is completed as reported by the City of Houston to GLO. The performance measures and associated demographic information have been updated to reflect all rehabilitation and reconstruction projects that have received final inspection as of the end of the reporting period. To date, 242 rehabilitation or reconstruction projects have received final inspection as reported by the City of Houston to GLO (226 for low-to-moderate income households and 16 for non-low-to-moderate income households). As projects proceed, the City works to include AFFH measures in the approved projects as reported. Measure Description - Q2 Applications Received by City of Houston - 0 City of Houston Reviewing Applicant Eligibility/Property Assessment - 54 Applications Submitted to the GLO - 18 Applications Approved by GLO - 15 Reconstruction HMID Low/Mod Applications Approved - 1 Reconstruction HMID UN Applications Approved - 0 Rehabilitation HMID Low/Mod Applications Approved - 1 Rehabilitation HMID UN Applications Approved - 0 Reimbursement HMID Low/Mod Applications Approved - 5 Reimbursement HMID UN Applications Approved - 9 Projects Under Construction - 12 Rehabilitation or Reconstruction Projects with Final Inspection - 31 Projects with Reimbursement Checks Issued - 10 Houston - Single Family Development Program During the reporting period, the City of Houston revised the program guidelines (approved by the GLO) and began dve,oping the Notice of Funding Availability to select developers. The City of Houston submitted one application to the GLO for eligibility review. As projects proceed, the City works to include AFFH measures in the approved projects as reported. All awarded Developers will be required to conduct an AFFH review. The City will conduct its own AFFH review and identify High Opportunity Areas including Census Tracts with lower levels of minority concentration and low poverty rates to focus land acquisition efforts. The GLO will also conduct its own AFFH review. Measure Description - Q2 Applications Submitted to the GLO - 1 Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Construction began on two multifamily projects. Including the new projects under construction, the City of Houston currently has 16 total projects under construction. The City of Houston developed an Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. The plan ensures that outreach and communication efforts reach eligible homeowners and renters from all racial, ethnic, national origin, religious, familial status, disabled, and gender groups. The plan puts particular emphasis on successful outreach to LMI areas and those communities with minority concentrations that were affected by Hurricane Harvey. This plan is further supported by the Multifamily Rental Program Guidelines and Standard Operating Procedures to ensure access to program benefits. The guidelines and Standard Operating Procedures require that each awarded application be evaluated by the City of Houston and the GLO to confirm compliance with Affirmatively Furthering Fair Housing (AFFH) requirements. Projects must also have a correctly completed Affirmative Fair Housing Marketing Plan in place. During the reporting period, the City of Houston submitted an AFFH evaluation for three projects and the GLO issued AFFH evaluation conditional approval letters for two projects. Measure Description - Q2 Applications Received by City of Houston - 0 City of Houston Reviewing Application Eligibility - 0 Applications Submitted to GLO - 3 Applications Approved by GLO - 2 Household Units Approved - 322 Projects Under Construction - 2 Projects with Construction Completed - 0 Houston - Small Rental Program During the reporting period, the City of Houston continued to review the eligibility of applications received under the Notice of Funding Availability and prepared application documentation for submission to GLO. As projects proceed, the City will work to include AFFH measures in any approved projects. Houston - Homebuyer Assistance Program During the reporting period, the City of Houston accepted applications from 192 down payment assistance applicants, and reviewed eligibility of 58 applicants. Additionally, the City of Houston provided down payment assistance for 27 applicants, who are in the closeout phase and not yet reportable in DRGR. As projects proceed, the City works to include AFFH measures in the approved projects as reported. Measure Description - Q2 Applications Received by City of Houston - 192 City of Houston Reviewing Applicant Eligibility - 58 Applications Submitted to GLO - 57 Applications Approved by GLO - 61 LMI Applications Approved by GLO - 32br>,N Applications Approved by GLO - 29 Homebuyer Households - Received Down payment Assistance - 27 Houston - Buyout Program During the reporting period, the City of Houston submitted one application to the GLO. Additionally, the City of Houston acquired one property and has initiated the relocation of tenant households residing at the property. As projects proceed, the City works to include AFFH measures in the approved projects as reported. Measure Description - Q1 Applications Submitted to GLO - 1 Houston - Public Services During the reporting period, the City of Houston continued to implement 18 public service programs with 1,142 participants who began services. Additionally, 423 beneficiaries completed public service programs, and are in the closeout phase and are not yet reportable in DRGR. Two public service programs, Montrose Center and Women&apos;s Home Homeless Services which were reported in the last QPR as complete received contract extensions from the City of Houston and will continue to provide services through March, 2021. As projects proceed, the City works to include AFFH measures in the approved projects as reported. Measure Description - Q2 Applications Received by City of Houston - 0 City of Houston Reviewing Application Eligibility - 0 Number of Participants who began Services - 1142 Number of Beneficiaries who Completed Services - 423 Number of Participants who Exited/Did not Complete - 85 Number of Projects Completed - 0 Houston - Economic Development Program During the reporting period, the City of Houston received 64 applicants to the HEDP program, began or completed eligibility review on 64 applications, and submitted 12 to the GLO for eligibility review. The HEDP Guidelines ensure that the program affirmatively furthers fair housing through its commitment to creating jobs and economic opportunity for LMI persons and communities. Measure Description - Q2 Applications Received by City of Houston - 64 City of Houston Reviewing Applicant Eligibility - 64 Applications Submitted to GLO - 12 Houston - Planning During the reporting period, the City of Houston continued development of RFPs for planning studies. The City of Houston released six RFP/Qs for planning work and completed one planning project, which is in the closeout phase and not yet reportable in DRGR. Measure Description - Q2 Projects Approved by GLO - 2 RFP/Qs Published - 6 Planning Activities Initiated - 0 Planning Activities Completed - 1 Harvey 5b Harris County Programs - Attachment B Harris County - Homeowner Assistance Program No expenditures this period. County has held Tri-Party events to promote homeowner completion of document signing. During the reporting period, Harris County issued notices to proceed on construction for 11 projects and completed final inspection on 7 rehabilitation or reconstruction projects. The GLO updated their methodology for reporting completed rehabilitation and reconstruction projects in DRGR. Previously, GLO reported completed projects once the CDBG-DR funds were fully expensed. The methodology has been updated to report on completed rehabilitation and reconstruction projects once the final inspection is completed as reported by Harris County to GLO. The performance measures and associated demographicinfo,mation have been updated to reflect all rehabilitation and reconstruction projects that have received final inspection as of the end of the reporting period. Due to the reallocation of funds, no new projects will be submitted for the program. Measure Description - Q2 Projects Under Construction - 12 Rehabilitation/Reconstruction Projects with Final Inspection - 7 Harris County - Buyout and Acquisition Program In Quarter 2 2021, 120 buyout applications were submitted totaling over $23 million in projects and forty-eight offers were made to owners. The County previously had until June 30, 2021 to submit sites to the GLO and received an extension to September 30, 2021. In the reporting period, 37 projects were approved totaling $4.3 million. During the quarter, the County continued their outreach thru regular newsletters in both English and Spanish, including posting buyout information on Harris County&apos;s Recovery website in both languages. Measure Description - Q2 Reviewing Applicant Eligibility/Property Assessment - 0 Projects Received by GLO - 120 GLO Approved for Buyout - 37 Low-to-Moderate (LMI) Projects - 37 Harris County - Reimbursement Program During the reporting period, Harris County had 428 applications under review and 202 new projects underway (approved) for the Reimbursement Program. Since the program started, 899 projects were approved by the GLO and County issued 251 checks to homeowners totaling $9.9 million. County has until September 30, 2021 to submit projects to the GLO. Measure Description - Q2 Reviewing Applicant Eligibility/Property Assessment - 123 Projects Received by GLO - 202 GLO Approved for Reimbursement - 208 Low-to-Moderate (LMI) Projects - 97 Harris County - Affordable Rental Program During the reporting period, GLO approved one multifamily project. To date, sixteen (16) projects have been approved with a total of 2,506 units of which 2,231 will be LMI units. In Quarter 2 2021, Harris County had construction underway for ten (10) affordable rental projects. The GLO has completed an Affirmatively Furthering Fair Housing (AFFH) review for each project as part of the eligibility review phase and prior to project approval. Measure Description - Q2 GLO Approved - 1 In Construction - 1 Harris County - Single Family New Construction In total, eight (8) projects have been approved and are in the design/ engineering and/or environmental review phases. Three (3) built inventory projects are in construction. One (1) project was submitted this quarter. The County had until June 30, 2021 to submit remainder of projects to the GLO but requested and received an extension to September 30, 2021. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. In the quarter, one AFFH review was completed. Measure Description - Q2 Applications Received - 1 In Review/Pending Additional Information - 1 GLO approved - 1 Harris County - Commercial Buyout Program No expenditures this period. In Quarter 2 2021, County continued to submit commercial buyout projects to the GLO and twenty-one (21) were submitted totaling nearly $7 million in projects. County had until June 30, 2021 to submi,t sites to the GLO and received an extension to September 30, 2021. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan; for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County&apos;s as Disaster Risk Reduction Areas (DRRA). Measure Description - Q2 Projects Received by GLO - 21 In Review/ Pending Additional Information - 12 GLO Approved - 9 Harris County - Method of Distribution Infrastructure Program To date, 25 infrastructure projects have been submitted of which 21 have been approved and one completed construction and is in the closeout phase. During the reporting period, Harris County had engineering design underway on 17 projects and environmental review underway for 13 projects. For the 21 approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Harris County - Competitive Application Infrastructure Program To date, 15 applications have been submitted, 11 have been approved, including one (1) public services project. Two (2) drainage projects are under construction and are over 65% complete. During the reporting period, Harris County had an environmental review underway for 5 projects. For the ten (10) approved infrastructure projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Harris County - Planning In Quarter 2 2021, seven (7) planning studies are currently in progress and eight (8) planning projects are in the procurement and start up phase. Four (4) planning studies are complete of which three are in the closeout phase. County is in initial planning phase for two new studies under this activity.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2021-07-01 | 2021 Q4 | A comprehensive review of activity descriptions and location descriptions, resulting in updates for the descriptions for the majority of activities in order to be more consistent and concise. Similarly, projected performance measures were reviewed and updated to create more standard measures across activity types. 9 new activities created this quarter. Houston new contract 21-134-000-C788 went into effect this quarter, updating activity scope, budgets and projected performance measures. All Hurricane Harvey programs are underway. Texas Back in Business and Subrecipient buyout programs are seeing increases in activity. Action Plan Amendment 9 is with HUD for review. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 510 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q3 2021, GLO completed 11 such reviews. AFFORDABLE RENTAL PROGRAM: Project count currently at 77 in total, with 38 projects under construction, 38 substantially completed construction and only one project remaining in the due diligence process. COVID has caused both material and labor shortages and slowdown. Nevertheless, construction has continued across the board with a large number of construction completions and closeouts scheduled for Q4 2021 onwards. The Affordable Rental Team work has developed the closeout process to officially close projects out. All projects have submitted AFHMP (Fair Housing Marketing Plans) to the ARP team, which will be reviewed during their first compliance monitoring periods, which are currently being scheduled. ECONOMIC REVITALIZATION PROGRAM The ERP Program received 2714 application before the deadline of March 3, 2020, at 12:01 am. There are currently 1,231 applications in underwriting review. There have been 210 voluntary withdrawals. There have been 364 applicants that were determined to be ineligible. In Q3 2021 the program approved $5,400,000.00 in Grant Awards to 37 applicants who committed to support 113 jobs. Measure Description Q3 GLO Approved - 37 HOMEOWNER ASSISTANCE PROGRAM During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q3, GLO was in the process of reviewing 9 projects for eligibility, had approved 351 Homeowner Assistance Program applications for assistance, completed construction on 359 households, had construction underway on 612 houses and approved 1267 payment requests. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Measure Description Q3 Applications Received - 0 Reviewing Applicant Eligibility/Property Assessment - 9 GLO Approved for Construction - 351 Reconstruction HMID Low/Mod - 241 Reconstruction HMID UN - 69 Reconstruction SMID Low/Mod - 30 Reconstruction SMID UN - 5 Rehabilitation HMID Low/Mod - 11 Rehabilitation HMID UN - 3 Rehabilitation SMID Low/Mod - 0 Rehabilitation SMID UN - 0 Total LMI Projects - 282 Total UN Projects - 77<br,nbsp; HOMEOWNER REIMBURSEMENT PROGRAM At the end of the Third Quarter of 2021, the Homeowner Reimbursement Program was completed and has served to total of 2968 homeowners with ~$86.14M in reimbursement grants. The monitoring process will continue into Q4 and close-out of the program has begun. Measure Description Q3 Reimbursement Approved - 1 Total Outlays of Reimbursements - $43,501.24 LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM 109 Grantee draws were approved for $11,096,611.05. 0 Buyout Contracts Executed. Measure Description - Local Buyout/Acquisition Q3 Program Guidelines Approved - 1 AUGF broad review complete (Authority to use grant funds) - 2 Measure Description - Local Infrastructure Q3 Contracts Executed - 1 "Kick-off" - 1 Environmental Review Initiated - 1 AUGF Issued - 15 Construction Initiated/Bid Advertised - 6 Construction Complete - 1 COCC Complete - 1 PLANNING Planning operations are ongoing. GLO Homeowners Assistance Program - City of Houston During the reporting period, GLO approved applications for 229 new projects, construction started on 64 homes, and construction was completed (final inspection) on 57 homes. The GLO methodology for reporting completed rehabilitation and reconstruction projects in DRGR is to report once the final inspection is complete. To date, 174 rehabilitation or reconstruction projects have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description Q3 Applications Received - 240 GLO Application Approvals - 229 Reconstruction HMID Low/Mod Applications Approved - 207 Reconstruction HMID UN Applications Approved - 20 Rehabilitation HMID Low/Mod Applications Approved - 2 Rehabilitation HMID UN Applications Approved - 0 Projects Under Construction - 64 Projects with Construction Completed (Final Inspection) - 57 GLO Homeowners Assistance Program - Harris County During the reporting period, GLO approved applications for 44 new projects, construction started on 39 homes, and construction was completed (final inspection) on 37 homes. The GLO methodology for reporting completed rehabilitation and reconstruction projects in DRGR is to report once the final inspection is complete. To date, 81 rehabilitation or reconstruction projects have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description Q3 Applications Received - 47 GLO Application Approvals - 44 Reconstruction HMID Low/Mod Applications Approved - 33 Reconstruction HMID UN Applications Approved - 9 Rehabilitation HMID Low/Mod Applications Approved - 2 Rehabilitation HMID UN Applications Approved - 0 Projects Under Construction - 39 Projects with Construction Completed (Final Inspection) - 37 Houston - Homeowners Assistance Program During the reporting period, the City of Houston issued notice to proceed to construction on 3 projects, reimbursed 1 homeowner (not yet reportable in DRGR) and completed final inspection on 22 rehabilitation or reconstu,tion projects (21 for low-to-moderate income households and 1 for non-low-to-moderate income households). Measure Description Q3 City of Houston Reviewing Applicant Eligibility/Property Assessment - 100 Applications Submitted to the GLO - 133 Applications Approved by GLO - 96 Reconstruction HMID Low/Mod Applications Approved - 1 Reconstruction HMID UN Applications Approved - 0 Rehabilitation HMID Low/Mod Applications Approved - 1 Rehabilitation HMID UN Applications Approved - 0 Reimbursement HMID Low/Mod Applications Approved - 31 Reimbursement HMID UN Applications Approved - 64 Projects Under Construction - 3 Rehabilitation or Reconstruction Projects with Final Inspection - 22 Projects with Reimbursement Checks Issued - 1 Houston - Single Family Development Program During the reporting period, the City of Houston continues to develop the Notice of Funding Availability to select developers. The City of Houston submitted one application to the GLO for eligibility review and this project was conditionally approved in September. As projects proceed, the City works to include AFFH measures in the approved projects as reported. All awarded Developers will be required to conduct an AFFH review. The City will conduct its own AFFH review and identify High Opportunity Areas including Census Tracts with lower levels of minority concentration and low poverty rates to focus land acquisition efforts. The GLO will also conduct its own AFFH review. Measure Description Q3 Applications Approved by the GLO - 1 Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Construction began on four multifamily projects. Including the new projects under construction, the City of Houston currently has 20 total projects under construction including 4 within Q3. The City of Houston continued with implementation of its Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. This plan is further supported by the Multifamily Rental Program Guidelines and Standard Operating Procedures to ensure access to program benefits. The guidelines and Standard Operating Procedures require that each awarded application be evaluated by the City of Houston and the GLO to confirm compliance with Affirmatively Furthering Fair Housing (AFFH) requirements. Projects must also have a correctly completed Affirmative Fair Housing Marketing Plan in place. During the reporting period, the City of Houston submitted an AFFH evaluation for two projects and the GLO issued AFFH evaluation conditional approval letters for three projects. Additionally, in September 2021, the city held two Fair Housing for Landlords and Property Managers workshops to provide training on responsibilities under local and federal fair housing law. Measure Description Q3 Applications Received by City of Houston - 12 City of Houston Reviewing Application Eligibility - 12 Applications Submitted to GLO - 2 Applications Approved by GLO - 5 Household Units Approved - 696 Projects Under Construction - 4 Projects with Construction Completed - 0 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program and submitted the first 6 applications to the GLO for eligibility reviw.,The City of Houston developed an Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. The plan ensures that outreach and communication efforts reach eligible homeowners and renters from all racial, ethnic, national origin, religious, familial status, disabled, and gender groups. The plan puts particular emphasis on successful outreach to LMI areas and those communities with minority concentrations that were affected by Hurricane Harvey. This plan is further supported by the Small Rental Program Guidelines and Standard Operating Procedures to ensure access to program benefits. The guidelines and Standard Operating Procedures require that each awarded application be evaluated by the City of Houston and the GLO to confirm compliance with Affirmatively Furthering Fair Housing (AFFH) requirements. Projects must also have a correctly completed Affirmative Fair Housing Marketing Plan in place. During the reporting period, the City of Houston submitted an AFFH evaluation for 6 projects and GLO began AFFH evaluations for these 6 projects. Measure Description Q3 Applications Submitted to GLO - 6 Houston - Homebuyer Assistance Program During the reporting period, the City of Houston accepted applications from 149 down payment assistance applicants, and reviewed eligibility of 216 applicants. Additionally, the City of Houston provided down payment assistance for 36 applicants, who are in the closeout phase and not yet reportable in DRGR. As projects proceed, the City works to include AFFH measures in the approved projects as reported. Measure Description Q3 Applications Received by City of Houston - 149 City of Houston Reviewing Applicant Eligibility - 216 Applications Submitted to GLO - 77 Applications Approved by GLO - 73 LMI Applications Approved by GLO - 31 UN Applications Approved by GLO - 42 Homebuyer Households - Received Down payment Assistance - 36 Houston - Buyout Program During the reporting period, the GLO approved 2 applications for eligibility. Additionally, the City of Houston acquired 1 property and has initiated the relocation of tenant households residing at the property. As projects proceed, the City works to include AFFH measures in the approved projects as reported. Measure Description Q3 Applications Approved by GLO - 2 Houston - Public Services During the reporting period, the City of Houston continued to implement 18 public service programs (NOFA 1 with 1 year contract extensions for all programs due to COVID impact on clients) with 1,031 participants who began services. Additionally, 346 beneficiaries completed public service programs, and are in the closeout phase and are not yet reportable in DRGR. With the issuance of NOFA 2, the city received and is evaluating 21 new applications. As projects proceed, the City works to include AFFH measures in the approved projects as reported. Measure Description Q3 Applications Received by City of Houston - 21 City of Houston Reviewing Application Eligibility - 21 Number of Participants who began Services - 1031 Number of Beneficiaries who Completed Services - 346 Number of Participants who Exited/Did not Complete - 38 Number of Projects Completed - 0 Houston - Economic Development Program During the reporting period, the City of Houston received 30app,ications to the HEDP program, began or completed eligibility review on 30 applications, submitted 10 to the GLO for eligibility review, and received GLO eligibility approval for 19 applications. The HEDP Guidelines ensure that the program affirmatively furthers fair housing through its commitment to creating jobs and economic opportunity for LMI persons and communities. Measure Description Q3 Applications Received by City of Houston - 30 City of Houston Reviewing Applicant Eligibility - 30 Applications Submitted to GLO - 10 Applications Approved by GLO - 19 Loans Issued - 0 Houston - Planning During the reporting period, the City of Houston continued development of RFPs for planning studies. The City of Houston released 1 RFP/Q for planning work and completed 1 planning project, which is in the closeout phase and not yet reportable in DRGR. Measure Description Q3 Projects Approved by GLO - 1 RFP/Qs Published - 1 Planning Activities Initiated - 2 Planning Activities Completed (Not yet Reportable in DRGR)- 1 Harris County - Homeowner Assistance Program No reimbursement requests for expenditures were submitted this quarter. County held a Tri-Party event during the quarter to promote homeowner completion of document signing. To date, Harris County issued notices to proceed on construction for 19 projects and completed final inspection on 8 rehabilitation or reconstruction projects. Due to the reallocation of funds, no new HAP projects will be submitted for the program. Measure Description Q3 Projects Under Construction - 7 Rehabilitation/Reconstruction Projects with Final Inspection - 1 Harris County - Buyout and Acquisition Program In Quarter 3 2021, buyout applications were submitted totaling over $13 million in projects and 23 offers were made to owners in the involuntary buyout programs. The County had until September 30, 2021 to submit buyout sites to the GLO. In the reporting period, 112 projects were approved totaling over $23 million. During the quarter, 62 buyout projects were transferred from the Harvey 57M allocation to the Harvey 5B allocation for budgetary purposes, per the County&apos;s request. During the quarter, the County continued their outreach through regular newsletters in both English and Spanish and posting buyout information on Harris County&apos;s Recovery website in both languages. In addition, the County held a resource fair and went door-to-door in several buyout areas to provide information and answer questions about the program. Measure Description Q3 Reviewing Applicant Eligibility/Property Assessment - 0 Projects Received by GLO - 137 GLO Approved for Buyout - 112 Low-to-Moderate (LMI) Projects - 112 Harris County - Reimbursement Program During the quarter, 135 new projects were underway (approved) for the Reimbursement Program. Since the program started, 1,031 projects were approved by the GLO and County issued 293 checks to homeowners totaling $10.6 million. County had until September 30, 2021 to submit projects to the GLO. Measure Description Q3 Reviewing Applicant Eligibility/Property Assessment - 0 Projects Received by GLO - 170 GLO Approved for Reimbursement - 135 Low-to-Moderate (LMI) Projects - 55 Harris County - Affordable Rental Program To date, sixteen (16) projects hav bee, approved with a total of 2,506 units of which 2,231 will be LMI units. In Quarter 3 2021, Harris County had construction underway for twelve (12) affordable rental projects. The GLO has completed an Affirmatively Furthering Fair Housing (AFFH) review for each project as part of the eligibility review phase and prior to project approval. Measure Description Q3 GLO Approved - 0 In Construction - 2 Harris County - Single Family New Construction In total, eight (8) projects have been approved and are in the design/ engineering/ environmental review/ acquisition phases. Three (3) built inventory projects are in progress with five (5) homes completed and three (3) under construction. Two (2) projects were submitted by the September 30, 2021 deadline. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Measure Description Q3 Applications Received - 2 In Review/Pending Additional Information - 2 GLO approved - 1 Harris County - Commercial Buyout Program No expenditures were submitted for reimbursement this quarter. In Quarter 3 2021, County continued to submit commercial buyout projects to the GLO and six (6) were submitted totaling nearly $1 million in projects. County had until September 30, 2021 to submit commercial buyout sites to the GLO and all applications were submitted by the deadline. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan; for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County as Disaster Risk Reduction Areas (DRRA). Measure Description Q3 Projects Received by GLO - 7 In Review/ Pending Additional Information - 0 GLO Approved - 9 Harris County - Method of Distribution Infrastructure Program To date, 25 infrastructure projects have been submitted of which 22 have been approved and one completed construction and is in the closeout phase. During the reporting period, Harris County had engineering design underway on 16 projects and environmental review underway for 11 projects. For the 22 approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description Q3 GLO Approved - 1 Harris County - Competitive Application Infrastructure Program To date, 15 applications have been submitted, 13 have been approved, including one (1) public services project. Of the 13, two were approved this quarter; one is a drainage improvements project and the other is a health center. Two (2) drainage projects are under construction and are over 70% complete; another project has a NTP and will be starting construction in Quarter 4 2021. During the reporting period, Harris County had environmental review and engineering/ design underway for six (6) projects. For the twelve (12) approved infrastructure projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter; of the twelve, two (2) were completed this quarter. Measure Description Q3 GLO Approved - 2 Harris County - Planning In Quarter 3 2021, twelve (12) planning studies are currently in progress and two, (2) planning projects are in the procurement and start up phase. Five (5) planning studies are complete of which four are in the closeout phase. County is in initial planning phase for two new studies under this activity. Measure Description Q3 In Progress - 4
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2021-10-01 | 2022 Q1 | 3 new activities were added during the quarter. All Hurricane Harvey programs are underway. Action Plan Amendment 9 approved 11/1/2021. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 523 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q4 2021, GLO completed 13 such reviews. AFFORDABLE RENTAL PROGRAM Project count currently at 77 in total, with 33 projects under construction, 43 substantially completed construction and only one project remaining in the due diligence process. COVID has caused both material and labor shortages and slowdown. Nevertheless, construction has continued across the board with a large number of construction completions and closeouts scheduled for Q4 2021 onwards. The Affordable Rental Team work has developed the closeout process to officially close projects out. All projects have submitted AFHMP (Fair Housing Marketing Plans) to the ARP team, which will be reviewed during their first compliance monitoring periods, which are currently being scheduled. CITY OF HOUSTON See Attachment A HARRIS COUNTY See Attachment B ECONOMIC REVITALIZATION PROGRAM In Q4 2021 the program approved $13,400,000.00 in Grant Awards to 86 applicants who committed to support 273 jobs. Measure Description - Q4 GLO Approved - 86 HOMEOWNER ASSISTANCE PROGRAM During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q4, GLO was in the process of reviewing 79 projects for eligibility, had approved 158 Homeowner Assistance Program applications for assistance, completed construction on 421 households, had construction underway on 492 houses and approved 974 payment requests. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Measure Description - Q4 Applications Received - 0 Reviewing Applicant Eligibility/Property Assessment - 35 GLO Approved for Construction - 158 Reconstruction HMID Low/Mod - 309 Reconstruction HMID UN - 75 Reconstruction SMID Low/Mod - 20 Reconstruction SMID UN - 16 Rehabilitation HMID Low/Mod - 6 Rehabilitation HMID UN - 4 Rehabilitation SMID Low/Mod - 0 Rehabilitation SMID UN - 0 Total LMI Projects - 335 Total UN Projects - 95 LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM 51 TIGR Subrecipient draws were approved for $1,803,454.41. 67 DR Billing Subrecipient draws were approved for $9,473,810.80. Measure Description - Local Buyout/Acquisition - Q4 AUGF broad review complete (Authority to use grant funds) - 1 Measure Description - Local Infrastructure - Q4 Environmental Review Initiated - 1 AUGF Issued - 4 Construction Initiated/Bid Advertised - 1 COCC Complete - 2 PLANNING Planning operations are ongoing. GLO Homeowners Assistance Program - City of Houston During the reporting period, GLO approved applications for 266 new projects, ,nstruction started on 93 homes, and construction was completed (final inspection) on 77 homes. The GLO methodology for reporting completed rehabilitation and reconstruction projects in DRGR is to report once the final inspection is complete. To date, 251 rehabilitation or reconstruction projects have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description Q4 Applications Received - 294 GLO Application Approvals - 266 Reconstruction HMID Low/Mod Applications Approved - 235 Reconstruction HMID UN Applications Approved - 30 Rehabilitation HMID Low/Mod Applications Approved - 1 Rehabilitation HMID UN Applications Approved - 0 Projects Under Construction - 93 Projects with Construction Completed (Final Inspection) - 77 GLO Homeowners Assistance Program - Harris County During the reporting period, GLO approved applications for 65 new projects, construction started on 28 homes, and construction was completed (final inspection) on 42 homes. The GLO methodology for reporting completed rehabilitation and reconstruction projects in DRGR is to report once the final inspection is complete. To date, 123 rehabilitation or reconstruction projects have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q4 Applications Received - 72 GLO Application Approvals - 65 Reconstruction HMID Low/Mod Applications Approved - 48 Reconstruction HMID UN Applications Approved - 16 Rehabilitation HMID Low/Mod Applications Approved - 1 Rehabilitation HMID UN Applications Approved - 0 Projects Under Construction - 28 Projects with Construction Completed (Final Inspection) - 42 Houston - Homeowners Assistance Program During the reporting period, the City of Houston reimbursed 9 homeowners (not yet reportable in DRGR) and completed final inspection on 9 rehabilitation or reconstruction projects (all of which were for low-to-moderate income households). Measure Description - Q4 City of Houston Reviewing Applicant Eligibility/Property Assessment - 0 Applications Submitted to the GLO - 61 Applications Approved by GLO - 71 Reconstruction HMID Low/Mod Applications Approved - 2 Reimbursement HMID Low/Mod Applications Approved (May include applications also approved for Rehabilitation) - 30 Reimbursement HMID UN Applications Approved (May include applications also approved for Rehabilitation) - 40 Rehabilitation or Reconstruction Projects with Final Inspection - 9 Projects with Reimbursement Checks Issued (Not yet Reportable in DRGR) - 9 Houston - Single Family Development Program During the reporting period, the City of Houston released its Notice of Funding Availability to select developers and acquired property for the first project. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Construction began on two multifamily projects. Including the new projects under construction, the City of Houston currently has 22 total projects under construction. The City of Houston continued with implementation of its Affirmative Fair HousingM,rketing and Outreach Plan for its housing programs. Measure Description - Q4 Projects Under Construction - 2 Projects with Construction Completed (Not yet Reportable in DRGR) - 2 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The GLO completed AFFH evaluations for 5 of the 6 projects. Houston - Homebuyer Assistance Program During the reporting period, the City of Houston accepted applications from 132 down payment assistance applicants, and reviewed eligibility of 153 applicants. Additionally, the City of Houston provided down payment assistance for 31 applicants, who are in the closeout phase and not yet reportable in DRGR. Measure Description - Q4 Applications Received by City of Houston - 132 City of Houston Reviewing Applicant Eligibility - 153 Applications Submitted to GLO - 47 Applications Approved by GLO - 51 LMI Applications Approved by GLO - 29 UN Applications Approved by GLO 22 Homebuyer Households who have Received Down payment Assistance (Not yet Reportable in DRGR) - 31 Houston - Buyout Program During the City of Houston acquired 1 property and has worked on relocating tenants at two properties. Houston - Public Services During the reporting period, the City of Houston continued to implement 18 public service programs (NOFA 1 with 1 year contract extensions for all programs) with 776 participants who began services. Additionally, 552 beneficiaries completed public service programs, and are in the closeout phase and are not yet reportable in DRGR. The city continues to process the applications received under NOFA 2 and is preparing to submit applications to the GLO. Measure Description - Q4 Number of Participants who began Services - 776 Number of Beneficiaries who Completed Services (Not yet Reportable in DRGR) - 552 Number of Participants who Exited/Did not Complete - 64 Houston - Economic Development Program During the reporting period, the City of Houston received 109 applications to the HEDP program, began or completed eligibility review on 109 applications, submitted 21 to the GLO for eligibility review, and received GLO eligibility approval for 15 applications. Measure Description - Q4 Applications Received by City of Houston - 109 City of Houston Reviewing Applicant Eligibility - 109 Applications Submitted to GLO - 21 Applications Approved by GLO - 15 Houston - Planning During the reporting period, the City of Houston continued development of RFPs for planning studies. The City of Houston released 1 RFP/Q for planning work. The City of Houston completed the Rent Insecurity Survey Study during Q2 2021, and the GLO reimbursed the City for all CDBG-DR costs associated with the study during Q4 2021. Measure Description - Q4 RFP/Qs Published - 1 Harris County - Homeowner Assistance Program Twenty-two reimbursement requests for expenditures were submitted this quarter. To date, Harris County issued notices to proceed for construction for 21 projects and completed final inspection on 13 rehabilitation or reconstruction projects. Due to the reallocation of funds, no new HAP projects will be submitted for the program. ,easure Description - Q4 Projects Under Construction - 2 Rehabilitation or Reconstruction Projects with Final Inspection - 5 Harris County - Buyout and Acquisition Program To date, 137 offers were made to owners in the involuntary residential buyout program. The County had until December 15, 2021 to provide outstanding eligibility documentation for submitted buyout sites and County received an extension to February 1, 2022. In the reporting period, 91 projects were approved totaling over $19 million. During the quarter, the County continued to outreach to the community via a newsletter in both English and Spanish and posted buyout information on Harris County&apos;s Recovery website in both languages. Measure Description - Q4 GLO Approved for Buyout - 91 Low-to-Moderate (LMI) Projects - 91 Harris County - Reimbursement Program During the quarter, 77 new projects were underway (approved) for the Reimbursement Program. Since the program started, 1,099 projects were approved by the GLO and County issued 361 checks to homeowners totaling $13.3 million. County had until December 15, 2021 to submit remaining eligibility documentation for submitted projects to the GLO and later received an extension to February 1, 2022. Measure Description - Q4 Projects Received by GLO - 4 GLO Approved for Reimbursement - 77 Low-to-Moderate (LMI) Projects - 46 Harris County - Affordable Rental Program To date, sixteen (16) projects have been approved with a total of 2,506 units of which 2,231 will be LMI units. In Quarter 4 2021, Harris County had construction underway for thirteen (13) affordable rental projects of which eight (8) are at least 50% construction complete. The GLO has completed an Affirmatively Furthering Fair Housing (AFFH) review for each project as part of the eligibility review phase and prior to project approval. Measure Description - Q4 In construction - 1 Harris County - Single Family New Construction In total, nine (9) projects have been approved and are in the design/ engineering/ environmental review/ acquisition phases. Three (3) built inventory projects are in progress with five (5) homes completed and three (3) under construction. Two (2) projects were submitted by the September 30, 2021 deadline. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Harris County - Commercial Buyout Program No expenditures were submitted for reimbursement this quarter. In Quarter 4 2021, County continued to respond to eligibility review requests from the GLO and has until February 1, 2022 to resolve all outstanding eligibility items. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan; for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County as Disaster Risk Reduction Areas (DRRA). Measure Description - Q4 GLO Approved - 9 Harris County - Method of Distribution Infrastructure Program To date, 25 infrastructure projects have been submitted of which 22 have been approved and one completed construction and is in the closeout phase. During the reporting period, Harris County had engineering design underway, on 15 projects and environmental reviews underway for 10 projects. In the quarter, construction started for one drainage project. Two projects are in construction bid phase and three additional projects are anticipated to bid out in Quarter 1 2022. For the 22 approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. One public facility project was completed this quarter. Measure Description - Q4 In Construction - 1 Harris County - Competitive Application Infrastructure Program To date, 15 applications have been submitted, 13 have been approved, including one (1) public services project. Two (2) drainage projects are under construction and are over 90% complete; another project started construction in Quarter 4 2021 and is 27% complete. During the reporting period, Harris County had environmental reviews and engineering/ design underway for four (4) projects. For the twelve (12) approved infrastructure projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q4 In Construction - 1 Harris County - Planning In Quarter 4 2021, eleven (11) planning studies were in progress and one (1) planning project is in the procurement and start up phase. To date, eighteen planning studies have begun of which seven (7) planning studies are complete. Five (5) of the seven (7) are in the closeout phase. County is in initial planning phase for two new studies under this activity. Measure Description - Q4 In Progress - 5
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2022-01-01 | 2022 Q2 | Action Plan Amendment 10 received no public comment and is being prepared for submittal to HUD for approval. All programs are currently underway. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 525 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q1 2022, GLO completed 2 such reviews. AFFORDABLE RENTAL PROGRAM: Project count currently at 77 in total, with 25 projects under construction, 51 substantially completed construction and only 1 project remaining in the due diligence process. COVID has caused both material and labor shortages and slowdown. Nevertheless, construction has continued across the board with a large number of construction completions and closeouts scheduled for Q2 2022 onwards. The Affordable Rental Team work has developed the closeout process to officially close projects out. All projects have submitted AFHMP (Fair Housing Marketing Plans) to the ARP team, which will be reviewed during their first compliance monitoring periods, which are currently being scheduled. CITY OF HOUSTON See Attachment A HARRIS COUNTY See Attachment B ECONOMIC REVITALIZATION PROGRAM In Q1 2022 the program approved $7,600,000.00 in Grant Awards to 55 applicants who committed to support 158 jobs. Measure Description - Q1 GLO Approved - 55 HOMEOWNER ASSISTANCE PROGRAM During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q1, GLO was in the process of reviewing 138 projects for eligibility, had approved 161 Homeowner Assistance Program applications for assistance, completed construction on 312 households, had construction underway on 521 houses and approved 1080 payment requests. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Measure Description - Q1 Applications Received - 0 Reviewing Applicant Eligibility/Property Assessment - 138 GLO Approved for Construction - 161 Reconstruction HMID Low/Mod - 219 Reconstruction HMID UN - 59 Reconstruction SMID Low/Mod - 14 Reconstruction SMID UN - 2 Rehabilitation HMID Low/Mod - 13 Rehabilitation HMID UN - 5 Rehabilitation SMID Low/Mod - 0 Rehabilitation SMID UN - 0 Total LMI Projects - 246 Total UN Projects - 66 LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM 126 TIGR PRs were approved for $7,373,045.42. 44 DR Billing Draws were approved for $8,299,226.91. Measure Description - Local Buyout/Acquisition - Q1 AUGF broad review complete (Authority to use grant funds) - 1 Measure Description - Local Infrastructure - Q1 Construction Initiated/Bid Advertised - 2 PLANNING Planning operations are ongoing. GLO Homeowners Assistance Program - City of Houston During the reporting period, GLO approved applications for 351 new projects, construction started on 132 homes, and construction was co,leted (final inspection) on 83 homes. The GLO methodology for reporting completed rehabilitation and reconstruction projects in DRGR is to report once the final inspection is complete. To date, 334 rehabilitation or reconstruction projects have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q1 Applications Received - 365 GLO Application Approvals - 351 Reconstruction HMID Low/Mod Applications Approved - 306 Reconstruction HMID UN Applications Approved - 41 Rehabilitation HMID Low/Mod Applications Approved - 4 Rehabilitation HMID UN Applications Approved - 0 Projects Under Construction - 132 Projects with Construction Completed (Final Inspection) - 83 GLO Homeowners Assistance Program - Harris County During the reporting period, GLO approved applications for 45 new projects, construction started on 18 homes, and construction was completed (final inspection) on 23 homes. The GLO methodology for reporting completed rehabilitation and reconstruction projects in DRGR is to report once the final inspection is complete. To date, 146 rehabilitation or reconstruction projects have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q1 Applications Received - 48 GLO Application Approvals - 45 Reconstruction HMID Low/Mod Applications Approved - 34 Reconstruction HMID UN Applications Approved - 11 Rehabilitation HMID Low/Mod Applications Approved - 0 Rehabilitation HMID UN Applications Approved - 0 Projects Under Construction - 18 Projects with Construction Completed (Final Inspection) - 23 Harvey 5b Houston Programs - Attachment A Houston - Homeowners Assistance Program During the reporting period, the City of Houston reimbursed 133 homeowners (not yet reportable in DRGR). Data Measure Description - Q1 City of Houston Reviewing Applicant Eligibility/Property Assessment - 47 Applications Submitted to the GLO - 72 Applications Approved by GLO - 86 Reimbursement HMID Low/Mod Applications Approved (May include applications also approved for Rehabilitation) - 30 Reimbursement HMID UN Applications Approved (May include applications also approved for Rehabilitation) - 56 Projects with Reimbursement Checks Issued (Not yet Reportable in DRGR) - 133 Houston - Single Family Development Program During the reporting period, the City of Houston closed its Notice of Funding Availability to select a developer for its first project and began due diligence in identifying additional sites for the program. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Construction began on two multifamily projects. Including the new projects under construction, the City of Houston currently has 17 total projects under construction and 7 with construction complete but not yet reportable in DRGR. The City of Houston continued with implementation of its Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. Measure Description - Q1 Applications Submitted to GLO - 2<r,Applications Approved by GLO - 1 Household Units Approved - 149 Projects Under Construction - 2 Projects with Construction Completed (Not yet Reportable in DRGR) - 5 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The GLO issued eligibility approval on five applications. Measure Description - Q1 Applications Submitted to GLO - 2 Applications Approved by GLO - 5 Household Units Approved by GLO - 31 Houston - Homebuyer Assistance Program During the reporting period, the City of Houston accepted applications from 113 down payment assistance applicants, and reviewed eligibility of 116 applicants. Additionally, the City of Houston provided down payment assistance for 21 applicants, who are in the closeout phase and not yet reportable in DRGR. Measure Description - Q1 Applications Received by City of Houston - 113 City of Houston Reviewing Applicant Eligibility - 116 Applications Submitted to GLO - 64 Applications Approved by GLO - 60 LMI Applications Approved by GLO - 14 UN Applications Approved by GLO - 46 Homebuyer Households who have Received Down payment Assistance (Not yet Reportable in DRGR) - 21 Houston - Buyout Program During the quarter, the City of Houston has worked on relocating tenants from three multifamily properties. Houston - Public Services During the reporting period, the City of Houston continued to implement 18 public service programs with 604 participants who began services. Additionally, 417 beneficiaries completed public service programs, and are in the closeout phase and are not yet reportable in DRGR. The city&apos;s contract with six agencies ended during the previous quarter and the city and the GLO are working to closeout those projects. The city determined it would re-release NOFA 2, and plans to do so during Q2 2022. Measure Description - Q1 Number of Participants who began Services - 604 Number of Beneficiaries who Completed Services (Not yet Reportable in DRGR) - 417 Number of Participants who Exited/Did not Complete - 153 Houston - Economic Development Program During the reporting period, the City of Houston received 72 applications to the HEDP program, began or completed eligibility review on 39 applications, submitted 35 to the GLO for eligibility review, and received GLO eligibility approval for 32 applications. Seven jobs were created during the quarter. Measure Description - Q4 Applications Received by City of Houston - 72 City of Houston Reviewing Applicant Eligibility - 39 Applications Submitted to GLO - 35 Applications Approved by GLO - 32 Jobs Created - 7 Houston - Planning During the reporting period, the City of Houston continued development of RFPs for planning studies and undertook planning study work. The City of Houston initiated one planning study. Measure Description - Q1 Planning Activities Initiated - 1 Harvey 5b Harris County Programs - Attachment B Harris County - Homeowner Assistance Program Four (4) reimbursement requests for expenditures were paid in Quarter 1 2022. To date, Harris County issued notices to proceed for construction for 41 projects and completed final inspection on 17 rha,ilitation or reconstruction projects. Harris County worked to move approved projects into construction by hosting tri-party signing events and working with the Purchasing Department to issue Purchase Orders. The County anticipates most projects will be in construction by the end of April 2022. Due to the reallocation of funds, no new HAP projects will be submitted for the program. Measure Description - Q1 Projects Under Construction - 20 Rehabilitation or Reconstruction Projects with Final Inspection - 4 Harris County - Buyout and Acquisition Program To date, 154 offers were made to owners in the involuntary residential buyout program. The County had until February 1, 2022 to provide outstanding eligibility documentation for submitted buyout sites and all projects were approved by the end of Quarter 1 2022. In the reporting period, 75 projects were approved totaling over $9 million. Measure Description - Q1 Projects Received by GLO - 1 GLO Approved for Buyout - 75 Low-to-Moderate (LMI) Projects - 75 Harris County - Reimbursement Program During the quarter, 11 new projects were underway (approved) for the Homeowner Reimbursement Program. Since the program started, 1,100 projects were approved by the GLO and County issued 471 checks to homeowners totaling $16,710,310. Measure Description - Q1 GLO Approved for Reimbursement - 11 Low-to-Moderate (LMI) Projects - 8 Harris County - Affordable Rental Program To date, sixteen (16) projects have been approved with a total of 2,506 units of which 2,231 will be LMI units. In Quarter 1 2022, Harris County had construction underway for thirteen (13) affordable rental projects of which eight (8) are at least 50% construction complete. Three projects are close to 100% completion and have begun the lease up phase. The GLO has completed an Affirmatively Furthering Fair Housing (AFFH) review for each project as part of the eligibility review phase and prior to project approval. Harris County - Single Family New Construction In total, ten (10) projects have been approved and are in the design/ engineering/ environmental review/ acquisition phases. Three (3) built inventory projects are in progress with eight (8) homes acquired and undergoing retrofitting for accessibility and visitability. One project with a total of three homes in a High Opportunity Area was approved in Quarter 1 2022. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Harris County anticipates selling the homes to LMI households in Quarter 2 2022. Measure Description - Q1 GLO Approved - 1 Harris County - Commercial Buyout Program In Q1 2022, County continued to respond to eligibility review requests from the GLO and had until February 1, 2022 to resolve all outstanding eligibility items. All projects were approved by the end of the quarter, including four (4) projects that were approved during the quarter. The County made 38 offers and has purchased four properties to date. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan; for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County as Disaster Risk Redu,ction Areas (DRRA). Measure Description - Q1 GLO Approved - 4 Harris County - Method of Distribution Infrastructure Program To date, 25 infrastructure projects have been submitted of which 23 have been approved; of the 23 approved projects, one has completed construction and is in the closeout phase. During the reporting period, one project totaling $5.5 million was approved. Harris County had engineering design underway on 15 projects. Four (4) projects are in construction bid phase and five (5) additional projects are anticipated to bid out for construction in Quarter 2 2022. For the 23 approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q1 GLO Approved - 1 Harris County - Competitive Application Infrastructure Program To date, 15 applications have been submitted and approved. Three (3) projects are under construction and one (1) is construction complete and is in the closeout phase. GLO approved two (2) drainage projects totaling $17.8 million this quarter. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q1 GLO Approved - 2 In Construction - 1 Harris County - Planning In Quarter 1 2022, eleven (11) planning studies were in progress. To date, eighteen planning studies have begun of which seven (7) planning studies are complete. Five (5) of the seven (7) are in the closeout phase. County is in initial planning phase for four (4) new studies under this activity.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2022-04-01 | 2022 Q3 | Action Plan Amendment 10 approved by HUD June 15, 2022. This amendment reallocated funds within Harris County and Houston programs and updated program requirements. All programs are currently underway. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 526 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q2 2022, GLO completed 1 such reviews. AFFORDABLE RENTAL PROGRAM: Project count currently at 77 in total, with 25 projects under construction, 51 substantially completed construction and only 1 project remaining in the due diligence process. COVID has caused both material and labor shortages and slowdown. Nevertheless, construction has continued across the board with a large number of construction completions and closeouts scheduled for Q3 2022 onwards. All projects have submitted AFHMP (Fair Housing Marketing Plans) to the ARP team, which will be reviewed during their first compliance monitoring periods, which are currently being undertaken. ECONOMIC REVITALIZATION PROGRAM In Q2 2022 the program approved $11,150,000.00 in Grant Awards to 71 applicants who committed to support 234 jobs. Measure Description Q2 GLO Approved 71 HOMEOWNER ASSISTANCE PROGRAM During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q2, GLO was in the process of reviewing 122 projects for eligibility, had approved 100 Homeowner Assistance Program applications for assistance, completed construction on 311 households, had construction underway on 427 houses and approved 761 payment requests. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Measure Description Q2 Reviewing Applicant Eligibility/Property Assessment 122 GLO Approved for Construction 100 Reconstruction HMID Low/Mod 207 Reconstruction HMID UN 54 Reconstruction SMID Low/Mod 17 Reconstruction SMID UN 4 Rehabilitation HMID Low/Mod 19 Rehabilitation HMID UN 10 Total LMI Projects 243 Total UN Projects 68 LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM 192 TIGR PRs were approved for $24,686,193.35. 6 DR Billing Draws were approved for $378,038.95. PLANNING Planning operations are ongoing. GLO Homeowners Assistance Program - City of Houston During the reporting period, GLO approved applications for 316 new projects, construction started on 106 homes, and construction was completed (final inspection) on 143 homes. The GLO methodology for reporting completed projects in DRGR is to report once the final inspection is complete. To date, 477 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description Q2 Applications Received 304 GLO Application Approvals 316 Reconstruction HMID Low/Mod Ap,ications Approved 262 Reconstruction HMID UN Applications Approved 40 Rehabilitation HMID Low/Mod Applications Approved 13 Rehabilitation HMID UN Applications Approved 1 Projects Under Construction 106 Projects with Construction Completed (Final Inspection) 143 GLO Homeowners Assistance Program - Harris County During the reporting period, GLO approved applications for 69 new projects, construction started on 18 homes, and construction was completed (final inspection) on 27 homes. The GLO methodology for reporting completed projects in DRGR is to report once the final inspection is complete. To date, 173 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description Q2 Applications Received 66 GLO Application Approvals 69 Reconstruction HMID Low/Mod Applications Approved 51 Reconstruction HMID UN Applications Approved 17 Rehabilitation HMID UN Applications Approved 1 Projects Under Construction 18 Projects with Construction Completed (Final Inspection) 27 Harvey 5b Houston Programs Houston - Homeowners Assistance Program During the reporting period, the City of Houston reimbursed 98 homeowners (not yet reportable in DRGR). Measure Description Q2 City of Houston Reviewing Applicant Eligibility/Property Assessment 36 Applications Submitted to the GLO 53 Applications Approved by GLO 58 Reimbursement HMID Low/Mod Applications Approved (May include applications also approved for Rehabilitation) 23 Reimbursement HMID UN Applications Approved (May include applications also approved for Rehabilitation) 35 Projects Under Construction 4 Rehabilitation or Reconstruction Projects with Final Inspection 1 Projects with Reimbursement Checks Issued (Not yet Reportable in DRGR) 98 Houston - Single Family Development Program During the reporting period, the city submitted 2 initial acquisition applications to the GLO, which are currently under review. The city continued to finalize a contract with a developer for the first project. Measure Description Q2 Applications Submitted to the GLO 2 Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. The City of Houston currently has 17 total projects under construction and 7 with construction complete but not yet reportable in DRGR. The City of Houston received GLO approval for 2 project applications and 3 CDBG-DR budget amendments. The City of Houston continued with implementation of its Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. Measure Description Q2 Applications Approved by GLO 2 Household Units Approved 174 Houston - Small Rental Program During the reorting period, the City of Houston continued to implement its Small Rental Program. The city has encountered delays in the permitting process for some projects, challenges navigating increased construction costs, which has necessitated rebidding. In this quarter, the city submitted 2 additional applications to the GLO for review. Measure Descripto, Q2 Applications Submitted to GLO 2 Houston - Homebuyer Assistance Program During the reporting period, the City of Houston accepted applications from 151 down payment assistance applicants, and reviewed eligibility of 197 applicants. Additionally, the City of Houston provided down payment assistance for 39 applicants, who are in the closeout phase and not yet reportable in DRGR. Measure Description Q2 Applications Received by City of Houston 151 City of Houston Reviewing Applicant Eligibility 197 Applications Submitted to GLO 47 Applications Approved by GLO 36 LMI Applications Approved by GLO 15 UN Applications Approved by GLO 21 Homebuyer Households who have Received Down payment Assistance (Not yet Reportable in DRGR) 39 Houston - Buyout Program During the quarter, the City of Houston has worked on relocating tenants from 2 multifamily properties which have approximately 523 remaining tenants. The city completed relocation of 1 household. One property/project is vacant and pending demolition. Measure Description Q2 Households Relocated 1 Houston - Public Services During the reporting period, the City of Houston continued to implement 11 public service programs with 543 participants who began services. Eight of the 11 agencies that continued services closed out during the quarter. Additionally, 1,322 beneficiaries completed public service programs, and are in the closeout phase and are not yet reportable in DRGR. The city and the GLO are working to closeout projects. Measure Description Q2 Number of Participants who began Services 543 Number of Beneficiaries who Completed Services (Not yet Reportable in DRGR) 1322 Number of Participants who Exited/Did not Complete 162 Number of Projects Completed (Not yet Reportable in DRGR) 8 Houston - Economic Development Program During the reporting period, the City of Houston received 162 applications to the HEDP program, began or completed eligibility review on 85 applications, submitted 39 to the GLO for eligibility review, and received GLO eligibility approval for 38 applications. 22 jobs were created during the quarter. Measure Description Q2 Applications Received by City of Houston 162 City of Houston Reviewing Applicant Eligibility 85 Applications Submitted to GLO 39 Applications Approved by GLO 38 Jobs Created 22 Businesses Assisted 19 Houston - Planning During the reporting period, the City of Houston continued contract negotiations for planning studies and undertook planning study work. The City of Houston entered into contracts to implement 3 planning studies and completed 1 planning study, not yet reportable in DRGR. Measure Description Q2 Planning Activities Initiated 3 Planning Activities Completed (Not yet Reportable in DRGR) 1 Harvey 5b Harris County Programs Harris County - Homeowner Assistance Program To date, Harris County issued notices to proceed for construction for sixty-two (62) projects and completed final inspection on twenty-six (26) rehabilitation or reconstruction projects. Harris County worked to move approved projects into construction by working with homeowner associations and municipalities within Harris County to expedite the permit review and approval process. TheCo,nty anticipates most projects will be in construction by the end of Quarter 3 2022. Due to the reallocation of funds, no new HAP projects will be submitted for the program. Measure Description Q2 Projects Under Construction 21 Rehabilitation or Reconstruction Projects with Final Inspection 9 Harris County - Buyout and Acquisition Program To date, one hundred seven (107) buyout properties were closed on. A relocation and buyout program resource fair was held on April 30, 2022 with over one hundred twenty-five (125) households in attendance. Harris County sent out monthly newsletters in English and Spanish to provide information on relocation benefits, rental assistance, housing options and other resources. In June, the County set up a mobile office located in one of the buyout areas. Due to the completion of the eligibility review phase, no new buyout sites will be submitted for the program. Harris County - Reimbursement Program Since the program started, Harris County issued six hundred eighty-three (683) checks to homeowners totaling $23,616,896. Due to the completion of the eligibility review phase, no new reimbursement projects will be submitted for the program. Harris County - Affordable Rental Program To date, sixteen (16) projects have been approved with a total of 2,506 units of which 2,232 will be LMI units. In Quarter 2 2022, Harris County had construction underway for thirteen (13) affordable rental projects of which ten (10) are at least 50% construction complete. Three (3) projects are close to 100% completion and have begun the lease up phase. The GLO has completed an Affirmatively Furthering Fair Housing (AFFH) review for each project as part of the eligibility review phase and prior to project approval. Harris County continued with implementation of its Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. Harris County - Single Family New Construction In total, ten (10) projects have been approved and are in the design/ engineering/ environmental review/ acquisition phases. Three (3) built inventory projects are in progress with eight (8) homes acquired and undergoing retrofitting for accessibility and visitability. One project with a total of thirty (30) homes was approved in Quarter 2 2022. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Harris County anticipates selling the homes to LMI households in Quarter 2 2022. Measure Description Q2 GLO Approved 1 Harris County - Commercial Buyout Program The County has closed on eight (8) of the thirty (30) commercial buyout properties to date. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan; for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County as Disaster Risk Reduction Areas (DRRA). Harris County - Method of Distribution Infrastructure Program To date, twenty-five (25) infrastructure projects have been submitted of which twenty-three (23) have been approved; of the twenty-three (23) approved projects, one (1) has completed construction and is in the closeout phase. &n,bsp;Harris County had engineering design underway on fifteen (15) projects. Three (3) projects are in construction bid phase and four (4) are in construction. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description Q2 In Construction 3 Harris County - Competitive Application Infrastructure Program To date, sixteen (16) applications have been submitted and thirteen (13) are approved and active. Two (2) projects are under construction and two (2) are construction complete and in the closeout phase. Two (2) projects are in the bid phase, four (4) projects are in the engineering/design phase, two (2) projects are in the start up phase, and one (1) project is in the eligibility review phase. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Harris County - Planning In Quarter 2 2022, eleven (11) planning studies were in progress. To date, nineteen (19) planning studies have begun of which eight (8) planning studies are complete and are in the closeout phase. County is in initial planning phase for four (4) new studies under this activity. Measure Description Q2 In Progress 1
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2022-07-01 | 2022 Q4 | OVERALL NARRATIVE All programs are underway. The GLO is working on Action Plan Amendment (APA) 11 to reallocate funds within the City of Houston programs. After prescribed public comment requirements the APA will be provided to HUD for approval. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 544 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q3 2022, GLO completed 18 such reviews. AFFORDABLE RENTAL PROGRAM: Construction continues on the remaining projects in our portfolio. COVID has caused both material and labor shortages and slowdown, and continues to have a negative impact on projects still under construction. Nevertheless, construction has continued across the board with a large number of construction completions and closeouts scheduled for Q3 2022 onwards. All projects have submitted AFHMP (Fair Housing Marketing Plans) to the ARP team, which will be reviewed during their first compliance monitoring periods, which are currently being undertaken. CITY OF HOUSTON See Attachment A HARRIS COUNTY See Attachment B ECONOMIC REVITALIZATION PROGRAM In Q3 2022 the program approved $12,900,000.00 in Grant Awards to 87 applicants who committed to support 267 jobs. Measure Description Q3 GLO Approved 87 HOMEOWNER ASSISTANCE PROGRAM During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q3, Texas General Land Office was in the process of reviewing 12 projects for eligibility, had approved 100 Homeowner Assistance Program applications for assistance, completed construction on 261 households, had construction underway on 283 houses and approved 914 payment requests. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Measure Description Q3 Reviewing Applicant Eligibility/Property Assessment 12 GLO Approved for Construction 100 Reconstruction HMID Low/Mod 166 Reconstruction HMID UN 46 Reconstruction SMID Low/Mod 16 Reconstruction SMID UN 2 Rehabilitation HMID Low/Mod 21 Rehabilitation HMID UN 9 Rehabilitation SMID Low/Mod 1 Rehabilitation SMID UN 0 Total LMI Projects 204 Total UN Projects 57 LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM "120 TIGR PRs for infrastructure approved for $11,541,686.21. 8 TIGR PRs for LBAP approved for $1,449,833.57." Measure Description - Local Buyout/Acquisition Q3 Buyout Completed LMI 2 Measure Description - Local Infrastructure Q3 Closeout Underway 12 PLANNING Planning operations are ongoing. GLO Homeowners Assistance Program - City of Housto,/strong> During the reporting period, Texas General Land Office (GLO) approved applications for 21 new projects, construction started on 123 homes, and construction was completed (final inspection) on 116 homes. The GLO methodology for reporting completed projects in DRGR is to report once the final inspection is complete. To date, 593 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description Q3 Applications Received 198 GLO Application Approvals 211 Reconstruction HMID Low/Mod Applications Approved 173 Reconstruction HMID UN Applications Approved 26 Rehabilitation HMID Low/Mod Applications Approved 10 Rehabilitation HMID UN Applications Approved 2 Projects Under Construction 123 Projects with Construction Completed (Final Inspection) 116 GLO Homeowners Assistance Program - Harris County During the reporting period, GLO approved applications for 26 new projects, construction started on 32 homes, and construction was completed (final inspection) on 21 homes. The GLO methodology for reporting completed projects in DRGR is to report once the final inspection is complete. To date, 194 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description Q3 Applications Received 16 GLO Application Approvals 26 Reconstruction HMID Low/Mod Applications Approved 20 Reconstruction HMID UN Applications Approved 6 Projects Under Construction 32 Projects with Construction Completed (Final Inspection) 21 Harvey 5b Houston Programs - Attachment A Houston - Homeowners Assistance Program During the reporting period, the City of Houston reimbursed 60 homeowners (not yet reportable in DRGR) and completed final inspection on one rehabilitation/reconstruction project. The city has a deadline of November 15, 2022 for all remaining applications to be submitted and approved by the GLO. Per the contract revision notice issued by the GLO to the city on August 19, 2022, due to the city&apos;s failure to meet contractual benchmarks, the GLO is revising the city&apos;s budget for this program. Measure Description Q3 Applications Received by City of Houston 2 Applications Submitted to the GLO 17 Applications Approved by GLO 21 Reimbursement HMID Low/Mod Applications Approved (May include applications also approved for Rehabilitation) 9 Reimbursement HMID UN Applications Approved (May include applications also approved for Rehabilitation) 12 Rehabilitation or Reconstruction Projects with Final Inspection 1 Projects with Reimbursement Checks Issued (Not yet Reportable in DRGR) 60 Houston - Single Family Development Program During the reporting period, the city continued to finalize a contract with a developer for one project, and prepared to release a Notice of Funding Availability on the two other projects. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Proga,. The City of Houston crrently has 17 total projects under construction and 7 with construction complete but not yet reportable in DRGR. The City of Houston received GLO approval for 2 project applications and 1 CDBG-DR budget amendment. The City of Houston continued with implementation of its Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. Per the contract revision notice issued by the GLO to the city on August 19, 2022, due to the city&apos;s failure to meet contractual benchmarks, the GLO is revising the city&apos;s budget for this program. Measure Description Q3 Applications Approved by GLO 2 Household Units Approved 180 Projects Under Construction 1 Projects with Construction Completed (Not yet Reportable in DRGR) 1 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The city has encountered delays in the permitting process for some projects and challenges navigating increased construction costs, which has necessitated rebidding. Per the contract revision notice issued by the GLO to the city on August 19, 2022, due to the city&apos;s failure to meet contractual benchmarks, the GLO is revising the city&apos;s budget for this program. Measure Description Q3 Applications Submitted to GLO 1 Houston - Homebuyer Assistance Program During the reporting period, the City of Houston accepted applications from 79 down payment assistance applicants, and reviewed eligibility of 15 applicants. Additionally, the City of Houston provided down payment assistance for 34 applicants, who are in the closeout phase and not yet reportable in DRGR. The city has a deadline of November 15, 2022 for all remaining applications to be submitted and approved by the GLO. Per the contract revision notice issued by the GLO to the city on August 19, 2022, due to the city&apos;s failure to meet contractual benchmarks, the GLO is revising the city&apos;s budget for this program. Measure Description Q3 Applications Received by City of Houston 79 Applications Reviewed by City of Houston for Eligibility 15 Applications Submitted to GLO 40 Applications Approved by GLO 45 LMI Applications Approved by GLO 29 UN Applications Approved by GLO 16 Homebuyer Households who have Received Down Payment Assistance (Not yet Reportable in DRGR) 34 Houston - Buyout Program During the quarter, the City of Houston has worked on relocating tenants from 3 multifamily properties which have approximately 816 remaining tenants. The city completed relocation of five households. One property/project is vacant and pending demolition. Measure Description Q3 Number of Households Relocated during Quarter (Not yet reportable in DRGR) 5 Houston - Public Services During the reporting period, the City of Houston continued to implement five public service programs with 89 participants who began services. Two agency contracts ended during the quarter and those projects are in the process of closing out. Additionally, 1,070 beneficiaries completed public service programs, are in the closeout phase, and are not yet reportable in DRGR. The cit and the GLO are working to closeout projects. Per the contract revision notice issued by the GLO to the city on August 19, 2022, due to the city&apos;s failure to meet contractualbe,chmarks, the GLO is revising the city&apos;s budget for this program. Finally, one project was withdrawn by the agency over the past quarter. While no CDBG-DR funds were reimbursed for the project prior to withdrawal, in previous quarters the agency&apos;s measures were reported as part of the program&apos;s overall narrative, including 505 beneficiaries who started services, 492 that completed services, and 13 that exited/did not complete services. These measures are no longer considered part of the potential accomplishments for the program. Measure Description Q3 Number of Participants who began Services during Quarter 89 Number of Beneficiaries who Completed Services during Quarter (Not yet Reportable in DRGR) 1070 Number of Participants who Exited/Did not Complete during Quarter 17 Projects Completed (Not yet Reportable in DRGR) 2 Houston - Economic Development Program During the reporting period, the City of Houston received 35 applications to the HEDP program, began or completed eligibility review on 48 applications, submitted 44 to the GLO for eligibility review, and received GLO eligibility approval for 45 applications. 14 jobs were created during the quarter. The city has a deadline of November 15, 2022 for all remaining applications to be submitted and approved by the GLO. Per the contract revision notice issued by the GLO to the city on August 19, 2022, due to the city&apos;s failure to meet contractual benchmarks, the GLO is revising the city&apos;s budget for this program. Measure Description Q3 Applications Received by City of Houston 35 Applications Reviewed by City of Houston for Eligibility 48 Applications Submitted to GLO 44 Applications Approved by GLO 45 Number of Jobs Created during Quarter 14 Businesses Assisted 12 Houston - Planning During the reporting period, the City of Houston continued contract negotiations for planning studies and undertook planning study work. The City of Houston entered into contracts to implement 2 planning studies. Measure Description Q3 Planning Activities Initiated 2 Harvey 5b Harris County Programs - Attachment B Harris County - Homeowner Assistance Program To date, Harris County issued notices to proceed for construction for one hundred four (104) projects and completed final inspection on forty-eight (48) rehabilitation or reconstruction projects. Harris County worked to move approved projects into construction by working with homeowner associations and municipalities within Harris County to expedite the permit review and approval process. Due to the reallocation of funds, no new HAP projects will be submitted for the program. Measure Description Q3 Projects Under Construction 42 Rehabilitation or Reconstruction Projects with Final Inspection 22 Harris County - Buyout and Acquisition Program To date, one hundred forty (140) buyout properties were closed on. Relocation and buyout program resource fairs wee held on July 23rd, September 20th, and September 22nd. Harris County sent out email newsletters in English and Spanish to provide information on relocation benefits, housing options and other resources. In August and September, the County set up a mobile office in a few of the buyout areas including Greens Road, Allen Fields, and Gulfbak R,ad). Due to the completion of the eligibility review phase, no new buyout sites will be submitted for the program. Measure Description Q3 Number of structures demolished 2 Harris County - Reimbursement Program Since the program started, Harris County issued seven hundred seventy-six (776) checks to homeowners totaling $33,741,826.59. Due to the completion of the eligibility review phase, no new reimbursement projects will be submitted for the program. Measure Description Q3 Projects with Reimbursement Checks Issued 130 Harris County - Affordable Rental Program To date, sixteen (16) projects have been approved with a total of 2,506 units of which 2,232 will be LMI units. In Quarter 3 2022, Harris County had construction underway for thirteen (13) affordable rental projects of which three (3) are now 100% construction complete and in the lease up phase and eight (8) at least 50% construction complete. The GLO has completed an Affirmatively Furthering Fair Housing (AFFH) review for each project as part of the eligibility review phase and prior to project approval. Harris County continued with implementation of its Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. Measure Description Q3 Projects with Construction Completed 3 Harris County - Single Family New Construction In total, ten (10) projects have been approved and are in the design/ engineering/ environmental review/ acquisition phases. Three (3) built inventory projects are in progress with eight (8) homes acquired and undergoing retrofitting for accessibility and visitability. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Harris County anticipates selling the homes to LMI households in Quarter 4 2022. Harris County - Commercial Buyout Program The County has closed on seven (7) of the thirty (30) commercial buyout properties to date and continues to work on relocation and demolition. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan; for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County as Disaster Risk Reduction Areas (DRRA). Harris County - Method of Distribution Infrastructure Program To date, twenty-five (25) infrastructure projects have been submitted of which twenty-three (23) have been approved; of the twenty-three (23) approved projects, one (1) has completed construction and is in the closeout phase. Harris County has engineering design underway on ten (10) projects. Six (6) projects are in construction bid phase and six (6) are in construction. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description Q3 In Construction 2 Harris County - Competitive Application Infrastructure Program To date, sixteen (16) applications have been submitted and fourteen (14) are approved and active. Two (2) projects are under construction and one (1) project is construction complete and in the closeout phase. Two (2) projects are in the bid out ph,ase for construction, six (6) projects are in the engineering/design phase, and two (2) projects are in the start up phase. The public services transit project is underway. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description Q3 GLO Approved 1 Harris County - Planning In Quarter 3 2022, eleven (11) planning studies were in progress. To date, nineteen (19) planning studies have begun of which eight (8) planning studies are complete and are in the closeout phase. County is in the initial planning phase for four (4) new planning studies under this activity. Measure Description Q3 Planning Activities Initiated 1
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2022-10-01 | 2023 Q1 | OVERALL NARRATIVE All programs, except PREPS, are underway. Several multifamily affordable rental complexes have completed construction with closeout documentation underway. Several HAP COGs are nearly completion of their projects and will be in closeout in the coming quarters. Action Plan Amendment 11, which reallocates funds in the City of Houston programs, was submitted to HUD during the quarter. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 597 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q4 2022, GLO completed 53 such reviews. AFFORDABLE RENTAL PROGRAM: Construction continues on the remaining projects in our portfolio. Four more projects reached substantial completion during Q4 2022. The final uncontracted project in the ARP Harvey $5bn portfolio was executed and the kick-off meeting and NTP is scheduled for Q1 2023. All projects have submitted AFHMP (Fair Housing Marketing Plans) to the ARP team, which will be reviewed during their first compliance monitoring periods, which are currently being undertaken. CITY OF HOUSTON See Attachment A HARRIS COUNTY See Attachment B ECONOMIC REVITALIZATION PROGRAM In Q4 2022 the ERP program approved $11,950,000.00 in Grant Awards to 74 applicants who committed to support 233 jobs. Measure Description - Q4 GLO Approved - 74 HOMEOWNER ASSISTANCE PROGRAM During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q4, GLO was in the process of reviewing 3 projects for eligibility, had approved 7 Homeowner Assistance Program applications for assistance, completed construction on 164 households, had construction underway on 197 houses and approved 1032 payment requests. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Measure Description - Q4 Reviewing Applicant Eligibility/Property Assessment - 3 GLO Approved for Construction - 7 Reconstruction HMID Low/Mod - 92 Reconstruction HMID UN - 40 Reconstruction SMID Low/Mod - 8 Reconstruction SMID UN - 3 Rehabilitation HMID Low/Mod - 15 Rehabilitation HMID UN - 6 Rehabilitation SMID Low/Mod - 0 Rehabilitation SMID UN - 0 Total LMI Projects - 115 Total UN Projects - 49 Homeowner Reimbursement Program The Homeowner Reimbursement Program related to Harvey has concluded and GLO is in the process of completing final Voucher disbursements. HRP received 6,885 applications. As of the end of Q4, GLO had approved 2,968 for disbursement and 3,917 had been determined to be ineligible or withdrew from HRP. GLO will complete all closeout activities for the program in 2023 after final voucher adjustments are complete. LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM "15 TIGR LBAP PRs approved for $1,,8,003.93. 175 TIGR INF PRs approved for $19,976,974. 3 DR Billing draws approved for $223,854.25." Measure Description - Local Infrastructure - Q4 Closeout Underway - 1 PLANNING There were 11 open contracts for this allocation. No major changes for any of the contracts during the last quarter. Major studies that are ongoing include Regional Basin Flood Study (RBFS), Community Health and Resource Management (CHARM), TDIS, and USACE-support for the RBFS. GLO Homeowners Assistance Program - City of Houston During the reporting period, GLO approved applications for 79 new projects, construction started on 165 homes, and construction was completed (final inspection) on 129 homes. To date, 722 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q4 Applications Received - 70 GLO Application Approvals - 79 Reconstruction HMID Low/Mod Applications Approved - 64 Reconstruction HMID UN Applications Approved - 12 Rehabilitation HMID Low/Mod Applications Approved - 2 Rehabilitation HMID UN Applications Approved - 1 Projects Under Construction - 165 Projects with Construction Completed (Final Inspection) - 129 GLO Homeowners Assistance Program - Harris County During the reporting period, GLO approved applications for 12 new projects, construction started on 46 homes, and construction was completed (final inspection) on 38 homes. To date, 232 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q4 Applications Received - 14 GLO Application Approvals - 12 Reconstruction HMID Low/Mod Applications Approved - 9 Reconstruction HMID UN Applications Approved - 3 Projects Under Construction - 46 Projects with Construction Completed (Final Inspection) - 38 Harvey 5b Houston Programs - Attachment A Houston - Homeowners Assistance Program During the reporting period, the City of Houston reimbursed 20 homeowners (not yet reportable in DRGR) and completed final inspection on 2 rehabilitation/reconstruction project. The city had a deadline of November 15, 2022 for all remaining applications to be submitted and approved by the GLO. Measure Description - Q4 New Applications Received by City of Houston - 2 New Applications Submitted to the GLO - 24 New Applications Approved by GLO - 29 New Reimbursement HMID Low/Mod Applications Approved (May include applications also approved for Rehabilitation) - 23 New Reimbursement HMID UN Applications Approved (May include applications also approved for Rehabilitation) - 6 New Projects Under Construction - 2 New Rehabilitation or Reconstruction Projects with Final Inspection - 2 New Projects with Reimbursement Checks Issued (Not yet Reportable in DRGR) - 20 Houston - Single Family Development Program During the reporting period, the city reissued Notices of Funding Availability for all three projects. While a respondent had been idn,ified for one of the projects, the contract fell through during negotiations. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. The City of Houston currently has 17 total projects under construction and 8 with construction complete but not yet reportable in DRGR. The City of Houston continued with implementation of its Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. Measure Description - Q4 Projects Under Construction - 1 Projects with Construction Completed (Not yet Reportable in DRGR) - 1 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. Construction started on one Small Rental Program project. Measure Description - Q4 New Projects Under Construction - 1 Houston - Homebuyer Assistance Program During the reporting period, the City of Houston accepted applications from 23 down payment assistance applicants, and reviewed eligibility of 105 applicants. Additionally, the City of Houston provided down payment assistance to 36 applicants, who are in the closeout phase and not yet reportable in DRGR. The city had a deadline of November 15, 2022 for all remaining applications to be submitted and approved by the GLO. Measure Description - Q4 New Applications Received by City of Houston - 23 New Applications Reviewed by City of Houston for Eligibility - 105 New Applications Submitted to GLO - 26 New Applications Approved by GLO - 47 New LMI Applications Approved by GLO - 35 New UN Applications Approved by GLO - 12 New Homebuyer Households who have Received Down Payment Assistance (Not yet Reportable in DRGR) - 36 Houston - Buyout Program During the quarter, the City of Houston has worked on relocating tenants from 3 multifamily properties which have approximately 650 remaining tenant households that the city reports are eligible for relocation benefits that have not yet received relocation benefits and/or been relocated. The city completed relocation of 5 tenant households. One property/project is vacant and pending demolition. Measure Description - Q4 Number of Households Relocated during Quarter (Not yet reportable in DRGR) - 5 Houston - Public Services During the reporting period, all of the city&apos;s public service provider contracts ended. 89 participants began services, additionally, 1,788 beneficiaries completed public service programs, are in the closeout phase, and are not yet reportable in DRGR. The city and the GLO are working to closeout projects. Measure Description - Q4 Number of Participants who began Services during Quarter - 89 Number of Beneficiaries who Completed Services during Quarter (Not yet Reportable in DRGR) - 1788 Number of Participants who Exited/Did not Complete during Quarter - 4 New Projects Completed (Not yet Reportable in DRGR) - 3 Houston - Economic Development Program During the reporting period, the City of Houston received 41 applications to the HEDP program, began or completed eligibility review on 51 applications, sbm,tted 20 to the GLO for eligibility review, and received GLO eligibility approval for 29 applications. 42 jobs were created during the quarter. The city had a deadline of November 15, 2022 for all remaining applications to be submitted and approved by the GLO. Measure Description - Q4 New Applications Received by City of Houston - 41 New Applications Reviewed by City of Houston for Eligibility - 51 New Applications Submitted to GLO - 20 New Applications Approved by GLO - 29 Number of Jobs Created during Quarter - 48 New Businesses Assisted - 41 Houston - Planning During the reporting period, the City of Houston continued contract negotiations for planning studies and undertook planning study work. Harvey 5b Harris County Programs - Attachment B Harris County - Homeowner Assistance Program To date, Harris County issued notices to proceed (NTP) for construction for one hundred twenty-six (126) projects and completed final inspections on seventy-six (76) rehabilitation or reconstruction projects. Harris County worked to move approved projects into construction by working with homeowner associations and municipalities within Harris County to expedite the permit review and approval process; four active projects are pending NTP issuance. Due to the reallocation of funds, no new HAP projects will be submitted for the program. Measure Description - Q4 Projects Under Construction - 22 Rehabilitation or Reconstruction Projects with Final Inspection - 28 Harris County - Buyout and Acquisition Program To date, two hundred two hundred (212) buyout properties were closed on. In addition, thirty-one (31) demolitions have been completed of which twenty-nine (29) are reported in this quarter as it captures previous non-reported data. Harris County sent out email newsletters in English and Spanish to provide information on relocation benefits, the eminent domain process, housing options and other resources. Due to the completion of the eligibility review phase, no new buyout sites will be submitted for the program. Measure Description - Q4 Number of structures demolished - 29 Harris County - Reimbursement Program Since the program started, Harris County issued eight hundred fifty-one (851) checks to homeowners totaling over $37 million. Of the total checks issued, five hundred ninety-eight (598) are being reported in this quarter&apos;s report due to this measure being recently added to the report and to capture previous non-reported data. Due to the completion of the eligibility review phase, no new reimbursement projects will be submitted for the program. Measure Description - Q4 Projects with Reimbursement Checks Issued (not yet reportable in DRGR) - 598 Harris County - Affordable Rental Program To date, fifteen (15) projects have been approved with a total of two thousand two hundred eighteen (2,218) units of which one thousand nine hundred forty-six (1,946) will be LMI units. In Quarter 4 2022, Harris County had construction underway on ten (10) affordable rental projects, three (3) are 100% construction complete and in the lease up phase, and two are pending the start ofcon,truction. During the quarter, the County issued a Request for Applications/ Proposals for additional multifamily projects. The County is currently reviewing the eight (8) application submissions. The GLO has completed an Affirmatively Furthering Fair Housing (AFFH) review for each project as part of the eligibility review phase and prior to project approval. Harris County continued with implementation of its Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. Measure Description - Q4 In construction - 1 Projects Leased Up (Not yet Reportable in DRGR) - 2 Harris County - Single Family New Construction In total, ten (10) projects have been approved and are in the design/ engineering/ environmental review/ acquisition phases. Five (5) built inventory projects are in progress with twenty (20) homes acquired and undergoing retrofitting for accessibility and visitability. Four subdivision projects are in the design phase. One (1) new application was submitted in Quarter 4 2022. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Harris County anticipates selling the homes to LMI households starting in Quarter 1 2023. Measure Description - Q4 Applications Received - 1 In Review/Pending Additional Information - 1 Sites acquired or Under Construction - 2 Harris County - Commercial Buyout Program The County has closed on fourteen (14) of the thirty (30) commercial buyout properties to date and continues to work on relocation and demolition. In total, five (5) demolitions have been completed and are reported in this quarter as it captures previous non-reported data. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan; for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County as Disaster Risk Reduction Areas (DRRA). Measure Description - Q4 Number of properties closed (buyout parcels) - 5 Number of structures demolished - 5 Harris County - Method of Distribution Infrastructure Program To date, twenty-five (25) infrastructure projects have been submitted of which twenty-three (23) have been approved; of the twenty-three (23) approved projects, one (1) has completed construction and is in the closeout phase. Harris County has engineering design underway on seven (7) projects. Seven (7) projects are in construction bid phase and eight (8) are in construction. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q4 In Construction - 2 Harris County - Competitive Application Infrastructure Program To date, sixteen (16) applications have been submitted and fourteen (14) are approved and active. Four (4) projects are under construction and one (1) project is construction complete and in the closeout phase. Three (3) projects are in the bid out phase for construction, four (4) projects are in the engineering/design phase, and one (1) project is in the start up phase. The public services transit project is underway. ,For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q4 In Construction - 1 Harris County - Planning In Quarter 4 2022, eleven (11) planning studies were in progress. To date, nineteen (19) planning studies have begun of which five (5) planning studies are complete and are in the closeout phase and three (3) are closed. County is in the initial planning phase for four (4) new planning studies under this activity. Measure Description - Q4 Planning Activities Initiated - 2 Harris County - Public Services To date, two (2) applications have been submitted of which one (1) has been approved and is pending closeout and the other project is in the eligibility review phase. The Quarter 4 2022 Public Services measures include previous non-reported data as the program and measures were added to the report in Quarter 4. Harris County is in the planning phase for two (2) new Public Services projects, which will support existing Harvey Disaster Recovery program participants. Measure Description - Q4 Projects Received by GLO - 2 In Review/ Pending Additional Information - 1 GLO Approved - 1 Projects Completed (not yet reportable in DRGR) - 1
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2023-01-01 | 2023 Q2 | OVERALL NARRATIVE The GLO is drafting Amendment 12 for the Harvey 5b grant to be posted for public comment. The Homeowner Reimbursement Program has been completed, pending final payments and any revisions if applicable. All other programs are active and underway. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 663 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q1 2023, GLO completed 66 such reviews. STATE PROGRAMS AFFORDABLE RENTAL PROGRAM GLO awarded funds for 72 developments, comprised of 5581 total units, with 4226 (76%) reserved for low-and-moderate income households. All developments in the Harvey $5b allocation portfolio for the Affordable Rental Program is currently either complete or under construction. GLO anticipates that beneficiary data will start to be reported in Q2 2023. While the projected and actual accomplishments for this activity are combined for all developments, the required information for each is identified in the spreadsheet attached to each activity in the DRGR Action Plan Module. ECONOMIC REVITALIZATION PROGRAM In Q1 2023 the ERP program approved $25,700,000.00 in Grant Awards to 83 applicants who committed to support 275 jobs. Of those jobs, 126 were newly created jobs and 149 were retained jobs. HOMEOWNER ASSISTANCE PROGRAM As of the end of Q1, GLO was in the process of reviewing 0 projects for eligibility, had approved 1 Homeowner Assistance Program application for assistance, completed construction on 112 households, had construction underway on 60 houses and approved 735 payment requests. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Measure Description - Q1 Application Received - 1 GLO Approved for Construction - 1 Reconstruction HMID Low/Mod - 80 Reconstruction HMID UN - 13 Reconstruction SMID Low/Mod - 4 Reconstruction SMID UN - 1 Rehabilitation HMID Low/Mod - 11 Rehabilitation HMID UN - 3 Total LMI Projects - 95 Total UN Projects - 17 Homeowner Reimbursement Program The Homeowner Reimbursement Program related to Harvey has concluded and GLO is in the process of completing final Voucher disbursements. GLO will complete all closeout activities for the program in 2023 after final voucher adjustments are complete. LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM 199 contracts were awarded. 7 contracts have received closeout letters. 60 contracts are in the closeout phase. 21 LBAP PRs approved for $1,217,234.89, 137 TIGR INF PRs approved for $17,979,030.52. Measure Description - Local Infrastructure - Q1 Closeout Underway - 6 PLANNING There are 12 open contracts for this allocation. Major studies that are ongoing include Regional Basin Flood Study (RBFS), Community Health and Resources Management (CHARM), Texas Disaster Information System (TDIS), and USACE-support for the RBFS. USACE is curren,y on hold and pending cancellation. One pending Request for Proposal, for Alternative Housing Testing and Implementation is currently with Procurement. GLO Homeowners Assistance Program - City of Houston During the reporting period, GLO approved applications for 80 new projects, construction started on 189 homes, and construction was completed (final inspection) on 193 homes. To date, 915 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q1 Applications Received - 99 GLO Application Approvals - 80 Reconstruction HMID Low/Mod Applications Approved - 71 Reconstruction HMID UN Applications Approved - 5 Rehabilitation HMID Low/Mod Applications Approved - 4 Projects Under Construction - 189 Projects with Construction Completed (Final Inspection) - 193 GLO Homeowners Assistance Program - Harris County During the reporting period, GLO approved applications for 30 new projects, construction started on 36 homes, and construction was completed (final inspection) on 45 homes. To date, 277 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q1 Applications Received - 33 GLO Application Approvals - 30 Reconstruction HMID Low/Mod Applications Approved - 22 Reconstruction HMID UN Applications Approved - 7 Rehabilitation HMID Low/Mod Applications Approved - 1 Projects Under Construction - 36 Projects with Construction Completed (Final Inspection) - 45 Harvey 5b Houston Programs Houston - Homeowners Assistance Program During the reporting period, the City of Houston reimbursed 22 homeowners (not yet reportable in DRGR) and completed final inspection on 3 rehabilitation/reconstruction projects. Measure Description - Q1 New Rehabilitation or Reconstruction Projects with Final Inspection - 3 New Projects with Reimbursement Checks Issued (Not yet Reportable in DRGR) - 22 Houston - Single Family Development Program During the reporting period, the city closed their Notice of Funding Availability and worked on developer selection and contracting for all three projects. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Of the 31 approved projects, the City of Houston currently has 2 projects in pre-construction, 19 projects under construction and 10 projects with construction complete but not yet reportable in DRGR. Measure Description - Q1 Number of Projects Entering Construction During Quarter - 5 New Projects with Construction Completed (Not yet Reportable in DRGR) - 2 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The City of Houston currently has 3 total projects under construction and 0 with construction complete, not yet reportable in DRGR. Measure Description - Q1 New Projects Under Construction - 2 Houston - Homebuyer Assistance Program During th ,eporting period, the City of Houston provided down payment assistance to 11 applicants, who are in the closeout phase and not yet reportable in DRGR. Measure Description - Q1 New Homebuyer Households who have Received Down Payment Assistance (Not yet Reportable in DRGR) - 11 Houston - Buyout Program During the quarter, the City of Houston has worked on relocating tenants from 3 multifamily properties which have approximately 657 remaining tenant households that the city reports are eligible for relocation benefits that have not yet received relocation benefits and/or been relocated. The city has completed relocation of 14 tenant households. One property/project has been demolished. Measure Description - Q1 Number of Households Relocated during Quarter (Not yet reportable in DRGR) - 9 New Structures Demolished (Not yet Reportable in DRGR) - 1 New Projects Complete (Not yet Reportable in DRGR) - 1 Houston - Public Services During the reporting period, the city and GLO continued to work on closing out projects and closing out the program. 234 beneficiaries completed public service programs, are in the closeout phase, and are not yet reportable in DRGR. Measure Description - Q1 Number of Beneficiaries who Completed Services during Quarter (Not yet Reportable in DRGR) - 234 Number of Participants who Exited/Did not Complete during Quarter - 3 Houston - Economic Development Program During the reporting period, eight jobs were created and seven businesses received the final installment of their recovery award. Measure Description - Q1 Number of Jobs Created during Quarter - 8 New Businesses Assisted - 7 Houston - Planning During the reporting period, the City of Houston undertook planning study work. Harvey 5b Harris County Programs Harris County - Homeowner Assistance Program To date, Harris County issued notices to proceed (NTP) for construction for one hundred twenty-eight (128) active projects and completed final inspections on ninety-five (95) rehabilitation or reconstruction projects. Harris County worked to move approved projects into construction by working with homeowner associations and municipalities within Harris County to expedite the permit review and approval process; two active projects are pending NTP issuance. Due to the reallocation of funds, no new HAP projects will be submitted for the program. Measure Description - Q1 Projects Under Construction - 2 Rehabilitation or Reconstruction Projects with Final Inspection - 19 Harris County - Buyout and Acquisition Program To date, two hundred fifty-four (254) buyout properties were closed on out of three hundred fifty-six (356) properties, which represents seventy-one percent (71%) of buyout sites acquired under this program. In addition, thirty-four (34) demolitions have been completed. County continues to relocate households and expenditures are pending submission to the GLO. Harris County sent out an email newsletter in English and Spanish to buyout stakeholders and posted several updates on its Recovery website; updates included information on a new relocation office located within one of the acquired Mobile Home Parks, the eminent domain process, housing options under the Single FamilyNe, Construction Program, the locality incentive, and other resources. Measure Description - Q1 Number of structures demolished - 3 Harris County - Reimbursement Program Since the program started, Harris County issued eight hundred ninety-nine (899) checks to homeowners totaling over $38 million. County anticipates issuing remainder of reimbursement checks to homeowners in Quarter 2 2023. Due to the completion of the eligibility review phase, no new reimbursement projects will be submitted for the program. Measure Description - Q1 Projects with Reimbursement Checks Issued (not yet reportable in DRGR) - 48 Harris County - Affordable Rental Program To date, fifteen (15) projects have been approved with a total of two thousand two hundred eighteen (2,218) units of which one thousand nine hundred forty-six (1,946) will be LMI units. In Quarter 1 2023, Harris County had construction underway on ten (10) affordable rental projects, four (4) are 100% construction complete and in the lease up phase, and one (1) is pending the start of construction. During the quarter, the County evaluated applications/ proposals for additional multifamily projects and submitted one (1) to the GLO for Affirmatively Furthering Fair Housing (AFFH) review. The GLO has completed an Affirmatively Furthering Fair Housing (AFFH) review for each project as part of the eligibility review phase and prior to project approval. Harris County continued with implementation of its Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. Measure Description - Q1 In construction - 1 Projects with Construction Completed (Not yet Reportable in DRGR) - 1 Projects Leased Up (Not yet Reportable in DRGR) - 1 Harris County - Single Family New Construction In total, eleven (11) projects have been approved and are in various phases of implementation; during the quarter, one (1) new built inventory project with a total of thirteen (13) homes was approved by the GLO. Six (6) built inventory projects with thirty-three (33) homes are construction complete and have been acquired by Harris County and are reported in this quarter as it captures previous non-reported data. Three (3) of the thirty-three (33) homes have been sold to LMI households and the County is actively marketing the remainder of homes through its website and to households being served under the Buyout Programs. Three (3) subdivision projects are in the design phase and one (1) is in the bid phase with construction anticipated to begin in April 2023. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Measure Description - Q1 Sites acquired or Under Construction - 1 Projects with Construction Completed - 6 Harris County - Commercial Buyout Program The County has closed on eighteen (18) of the thirty (30) commercial buyout properties to date, which is sixty percent (60%) of sites, and continues to work on relocation and demolition. In total, five (5) demolitions have been completed. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan, for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County as Disaste,r Risk Reduction Areas (DRRA). Measure Description - Q1 Number of properties closed (buyout parcels) - 4 Harris County - Method of Distribution Infrastructure Program To date, twenty-five (25) infrastructure projects have been submitted of which twenty-three (23) have been approved; of the twenty-three (23) approved projects, one (1) has completed construction and is in the closeout phase. Harris County has engineering design underway on four (4) projects. Seven (7) projects are in construction bid phase and eleven (11) are in construction. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q1 In Construction - 3 Harris County - Competitive Application Infrastructure Program Current Quarter Narrative To date, sixteen (16) infrastructure and public services applications have been submitted and fourteen (14) are approved and active. Six (6) projects are under construction and one (1) project is construction complete and in the closeout phase. Five (5) projects are in the engineering/design phase, and one (1) project is in the bid phase for construction. The public services transit project is underway with anticipated completion in Quarter 2 2023. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q1 In Construction - 2 Harris County - Planning In Quarter 1 2023, twelve (12) planning studies were in progress. To date, twenty (20) planning studies have begun of which four (4) planning studies are complete and are in the closeout phase and four (4) are closed. County is in the initial planning phase for three (3) new planning studies under this activity. Harris County - Public Services To date, two (2) applications have been submitted of which one (1) has been approved and is pending closeout and the other project is approved and pending implementation. Harris County is in the planning phase for two (2) new Public Services projects, which will support existing Harvey Disaster Recovery program participants. Measure Description - Q1 GLO Approved - 1
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2023-04-01 | 2023 Q3 | OVERALL NARRATIVE Action Plan Amendment 12 completed the Public Comment period during the quarter and is pending submission and approval by HUD. The Homeowner Reimbursement Program is complete pending final payments and adjustments for DRGR completion. The state Affordable Rental Program has begun reporting completed units as projects complete construction and the lease-up phase. 5 subrecipient contracts are completed, while 4 are pending completion in DRGR. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 750 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q2 2023, GLO completed 85 such reviews. Harvey 5b State Programs Affordable Rental Program Every project in the Harvey $5bn allocation portfolio for the Affordable Rental Program is now either complete, or under construction. The long-term compliance team under the ARP umbrella continues to work with our vendor on building out reporting capabilities to accurately reflect tenant demographic data on both a quarterly and annual basis. ARP is also working with the internal system of record to automate more of the systems in place. Economic Revitalization Program In Q2 2023 the ERP program approved $4,200,000.00 in Grant Awards to 29 applicants who committed to support 84 jobs. Of those jobs, 44 were newly created jobs and 40 were retained jobs. Homeowner Assistance Program "During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q2, GLO was in the process of reviewing 0 projects for eligibility, had approved 1 Homeowner Assistance Program applications for assistance, completed construction on 35 households, had construction underway on 1 houses and approved 344 payment requests. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports." Measure Description - Q2 GLO Approved for Construction - 1 Reconstruction HMID Low/Mod - 20 Reconstruction HMID UN - 5 Reconstruction SMID Low/Mod - 3 Rehabilitation HMID Low/Mod - 4 Rehabilitation HMID UN - 3 Rehabilitation SMID Low/Mod - 27 Rehabilitation SMID UN - 8 Total LMI Projects - 121 Total UN Projects - 25 Homeowner Reimbursement Program The Homeowner Reimbursement Program related to Harvey has concluded and GLO is in the process of completing final Voucher disbursements. GLO will complete all closeout activities for the program in 2023 after final voucher adjustments are complete. Local Buyout and Local Infrastructure Program 199 contracts were awarded with 130 contracts remain active. 10 contracts have received closeout letters. 59 contracts are in the closeout phase. Planning There are 11 open contracts for this allocation. Major studies that are ongoing include Regional Basin Flood Study, Community Health and Resources Management, and Texas Disaster,nformation System. USACE is currently pending cancellation. One pending request for qualifications, for Alternative Housing Testing and Implementation is actively posted for procurement. GLO Homeowners Assistance Program - City of Houston During the reporting period, GLO approved applications for 186 new projects, construction started on 166 homes, and construction was completed (final inspection) on 198 homes. To date, 1,113 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q2 Applications Received - 171 GLO Application Approvals - 186 Reconstruction HMID Low/Mod Applications Approved - 151 Reconstruction HMID UN Applications Approved - 25 Rehabilitation HMID Low/Mod Applications Approved - 10 Projects Under Construction - 166 Projects with Construction Completed (Final Inspection) - 198 GLO Homeowners Assistance Program - Harris County During the reporting period, GLO approved applications for 35 new projects, construction started on 22 homes, and construction was completed (final inspection) on 35 homes. To date, 312 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q2 Applications Received - 35 GLO Application Approvals - 20 Reconstruction HMID Low/Mod Applications Approved - 21 Reconstruction HMID UN Applications Approved - 8 Rehabilitation HMID UN Applications Approved - 1 Projects Under Construction - 22 Projects with Construction Completed (Final Inspection) - 35 Harvey 5b Houston Programs Houston - Homeowners Assistance Program During the reporting period, the City of Houston reimbursed 4 homeowners (not yet reportable in DRGR) and completed final inspection on 1 rehabilitation/reconstruction project. Measure Description - Q2 New Rehabilitation or Reconstruction Projects with Final Inspection - 1 New Projects with Reimbursement Checks Issued (Not yet Reportable in DRGR) - 4 Houston - Single Family Development Program During a meeting between the Texas General Land Office (GLO) and City of Houston on June 21, 2023, the city indicated that it intends to cancel the program. GLO awaits written notification from the city and additional discussions on how funds already reimbursed for land acquisition will be paid back to the GLO. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Of the 31 approved projects, the City of Houston currently has 1 project in pre-construction, 19 projects under construction, 10 projects with construction complete but not yet reportable in DRGR, and 1 project completed, fully expended, and reported. Measure Description - Q2 Number of Projects Entering Construction During Quarter - 1 New Projects with Construction Completed (Not yetR,portable in DRGR) - 1 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The City of Houston currently has 3 total projects under construction and 0 with construction complete, not yet reportable in DRGR. Houston - Homebuyer Assistance Program During the reporting period, the City of Houston provided down payment assistance to 8 applicants, who are in the closeout phase and not yet reportable in DRGR. Measure Description - Q2 New Homebuyer Households who have Received Down Payment Assistance (Not yet Reportable in DRGR) 8 Houston - Buyout Program During the quarter, the City of Houston has worked on relocating tenants from 3 multifamily properties which have approximately 656 remaining tenant households that the city reports are eligible for relocation benefits that have not yet received relocation benefits and/or been relocated. The city has completed relocation of 15 tenant households. One property/project has been demolished. Measure Description - Q2 Number of Households Relocated during Quarter (Not yet reportable in DRGR) - 1 Houston - Public Services During the reporting period, the city and GLO continued to work on closing out the program. Houston - Economic Development Program During the reporting period, 14 jobs were created and ten businesses received the final installment of their recovery award. An additional 32 businesses received their first award installment during this quarter. Measure Description - Q2 Number of Jobs Created during Quarter - 14 New Businesses Assisted - 10 Houston - Planning During the reporting period, the City of Houston undertook planning study work. Measure Description - Q2 New Planning Activities Completed (Not yet Reportable in DRGR) - 1 Harvey 5b Harris County Programs Harris County - Homeowner Assistance Program To date, Harris County issued notices to proceed (NTP) for construction for one hundred twenty-five (125) active projects and completed final inspections on one hundred eighteen (118) rehabilitation or reconstruction projects. Seven (7) projects remain in the construction phase. Due to the reallocation of funds, no new HAP projects will be submitted for the program. Measure Description - Q2 Rehabilitation or Reconstruction Projects with Final Inspection - 23 Harris County - Buyout and Acquisition Program To date, three hundred four (304) buyout properties were closed on out of three hundred fifty-six (356) properties, which represents eighty-five percent (85%) of buyout sites acquired under this program. In addition, seventy-three (73) demolitions have been completed. County continues to relocate households and expenditures are pending submission to the GLO. Harris County posted a newsletter in English and Spanish to its Recovery website which included information on tw R,location Field Offices and information on additional case management services being provided through the Commissioners&apos; offices and a nonprofit organization to assist residents in the relocation process. Additionally the County held a Housing Fair on April 20th which partnered with the Single Family New Construction Program to provide information on new homes available through the program. Measure Description - Q2 Number of households relocated - 2 Number of structures demolished - 39 Harris County - Reimbursement Program Since the program started, Harris County issued nine hundred forty-seven (947) checks to homeowners totaling over $41.5 million. County anticipates issuing the last four (4) reimbursement checks to homeowners in Quarter 3 2023 after the mitigation measures are met. Due to the completion of the eligibility review phase, no new reimbursement projects will be submitted for the program. Measure Description - Q2 Projects with Reimbursement Checks Issued (not yet reportable in DRGR) - 48 Harris County - Affordable Rental Program To date, fifteen (15) projects have been approved with a total of two thousand two hundred eighteen (2,218) units of which one thousand nine hundred forty-six (1,946) will be LMI units. In Quarter 2 2023, Harris County had construction underway on ten (10) affordable rental projects and five (5) are 100% construction complete. During the quarter, the County evaluated applications/ proposals for additional multifamily projects and submitted one (1) to the GLO for eligibility review. The GLO has completed an Affirmatively Furthering Fair Housing (AFFH) review for each project as part of the eligibility review phase and prior to project approval. Harris County continued with implementation of its Affirmative Fair Housing Marketing and Outreach Plan for its housing programs. Measure Description - Q2 In construction - 1 Projects with Construction Completed (Not yet Reportable in DRGR) - 1 Harris County - Single Family New Construction In total, ten (10) projects have been approved and are in various phases of implementation. One built inventory project with two homes is complete and pending closeout. To date, seven (7) of the thirty-three (33) built inventory homes have been sold to LMI households and the County is actively marketing the remainder of homes through its website and to households being served under the Buyout Programs. Three (3) subdivision projects are in the design and permitting phase and one (1) is in construction. Three (3) new built inventory project applications were submitted to the GLO in Quarter 2 2023. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Measure Description - Q2 Applications Received - 3 In Review/Pending Additional Information - 3 Sites acquired or Under Construction - 1 Harris County - Commercial Buyout Program The County has closed on twenty (20) of the thirty (30) commercial buyout pro,perties to date, which is sixty-seven percent (67%) of sites, and continues to work on relocation and demolition. Six (6) demolitions are complete. Of the thirty-one (31) relocations, twelve (12) have relocated and nineteen (19) are pending relocation. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan; for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County as Disaster Risk Reduction Areas (DRRA). Measure Description - Q2 Number of properties closed (buyout parcels) - 4 Number of structures demolished - 1 Harris County - Method of Distribution Infrastructure Program To date, twenty-five (25) infrastructure projects have been submitted of which twenty-three (23) have been approved; of the twenty-three (23) approved projects, one (1) has completed construction and is in the closeout phase. Harris County has engineering design underway on one (1) project. Seven (7) projects are in construction bid phase and fourteen (14) are in construction. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q2 In Construction - 3 Harris County - Competitive Application Infrastructure Program To date, sixteen (16) infrastructure and public services applications have been submitted and fourteen (14) are approved and active. Five (5) projects are under construction and three (3) projects are construction complete and in the closeout phase. Two (2) project is in the bid phase for construction and two (2) are in the design phase. One (1) is pending withdrawal. The public services transit project is underway with anticipated completion in Quarter 2 2024. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q2 In Construction - 1 Projects Completed (not yet reportable in DRGR) - 3 Harris County - Planning In Quarter 2 2023, nine (9) planning studies were in progress. To date, twenty-one (21) planning studies have begun of which eight (8) planning studies are complete and are in the closeout phase and four (4) are closed. County is in the initial planning phase for two (2) new planning studies under this activity. Measure Description - Q2 Planning Activities Completed - 4 Harris County - Public Services To date, three (3) applications have been submitted of which two (2) have been approved. One (1) is pending closeout and the other project is in the implementation phase with closeout anticipated in Quarter 2 2024. Harris County is in the planning phase for one (1) additional new Public Services project, which will support existing Harvey Disaster Recovery program participants. Measure Description - Q2 Projects Received by GLO - 1 In Review/ Pending Additional Information - 1 In Progress - 1
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2023-07-01 | 2023 Q4 | OVERALL NARRATIVE Action Plan Amendment 12 was approved by HUD during the quarter and included the creation of a new project, the Harris County Flood Control District Project, as well as several project and activity budget changes. Several of the subrecipient Local Infrastructure contracts were completed during the quarter with others in and nearing the closeout phase. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 791 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q3 2023, GLO completed 41 such reviews. AFFORDABLE RENTAL PROGRAM: Every project in the Harvey $5bn allocation portfolio for the Affordable Rental Program is now either complete, or under construction. More than half the portfolio has undergone at least one affordbility desk review, and all completed projects have had annual reviews. ARP is also working with the internal system of record to automate more of the systems in place. ECONOMIC REVITALIZATION PROGRAM In Q3 2023 the ERP program approved $150,000.00 in Grant Awards to 1 applicant who committed to support 3 jobs. Of those jobs, 2 were newly created jobs and 1 was a retained job. Application processing has been completed at this point. In addition, as of Q3 2023 for ERP 394 applicants have met closeout requirements. Those 394 applicants have created/retained 1240 jobs at 94% LMI. HOMEOWNER ASSISTANCE PROGRAM During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q3, GLO was in the process of reviewing 0 projects for eligibility, had approved 0 Homeowner Assistance Program applications for assistance, completed construction on 14 households, had construction underway on 82 houses and approved 49 payment requests. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Measure Description - Q3 Reconstruction HMID Low/Mod - 6 Reconstruction HMID UN - 1 Rehabilitation HMID Low/Mod - 1 Rehabilitation HMID UN - 6 Total LMI Projects - 7 Total UN Projects - 7 LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM 199 contracts were awarded with 113 contracts remain active. 16 contracts have received closeout letters. 70 contracts are in the closeout phase. PLANNING There are still 11 open contracts for this allocation. Major studies that are ongoing include Regional Basin Flood Study, Community Health and Resources Management, and Texas Disaster Information System. GLO HOMEOWNER ASSISTANCE PROGRAM - CITY OF HOUSTON During the reporting period, GLO approved applications for 184 new projects, construction started on 159 homes, and construction was completed (final inspection) on 152 homes. To date, 1,265 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q3 Applications Received - 174 GLO Application Approvals - 184 Reconstruction HMID Low/Mod,pplications Approved - 148 Reconstruction HMID UN Applications Approved - 25 Rehabilitation HMID Low/Mod Applications Approved - 9 Rehabilitation HMID UN Applications Approved - 2 Projects Under Construction - 159 Projects with Construction Completed (Final Inspection) - 152 GLO HOMEOWNER ASSISTANCE PROGRAM - HARRIS COUNTY During the reporting period, GLO approved applications for 38 new projects, construction started on 21 homes, and construction was completed (final inspection) on 16 homes. To date, 328 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q3 Applications Received - 31 GLO Application Approvals - 38 Reconstruction HMID Low/Mod Applications Approved - 31 Reconstruction HMID UN Applications Approved - 6 Rehabilitation HMID Low/Mod Applications Approved - 1 Projects Under Construction - 21 Projects with Construction Completed (Final Inspection) - 16 HARVEY 5B CITY OF HOUSTON PROGRAMS Houston - Homeowners Assistance Program Current Quarter Narrative During the reporting period, the City of Houston reimbursed 2 homeowners (not yet reportable in DRGR). Measure Description - Q3 New Projects with Reimbursement Checks Issued - 2 Houston - Single Family Development Program On August 4, 2023, the City of Houston notified the GLO of its intent to terminate the Single Family Development Program. The City is in the process of canceling the program and selling the three acquired properties in order to repay funds to the GLO for costs reimbused to date that are no longer eligible. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Of the 31 approved projects, the City of Houston currently has 20 projects under construction, 9 projects with construction complete but not yet reportable in DRGR, and 2 projects completed, fully expended, and reported. Measure Description - Q3 Number of Projects Entering Construction During Quarter - 1 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The City of Houston currently has 3 total projects under construction and 0 with construction complete, not yet reportable in DRGR. Houston - Homebuyer Assistance Program During the reporting period, the City of Houston continued to implement its Homebuyer Assistance Program and began preparing for program closeout. Measure Description - Q3 New Homebuyer Households who have Received Down Payment Assistance (Not yet Reportable in DRGR) Houston - Buyout Program During the quarter, the City of Houston has worked on relocating tenants from 3 multifamily properties which have approximately 566 remaining tenant households that the city reports are eligible for relocation benefits that have not yet received relocation benefits and/or been relocated. The city has cop,eted relocation of 33 tenant households. One property/project has been demolished. Measure Description - Q3 Number of Households Relocated during Quarter (Not yet reportable in DRGR) - 18 Houston - Public Services During the reporting period, the city and GLO continued to work on closing out the program. Houston - Economic Development Program During the reporting period, 16 jobs were created and 13 businesses received the final installment of their recovery award. An additional 3 businesses received their first award installment during this quarter. Measure Description - Q3 Number of Jobs Created during Quarter - 16 New Businesses Assisted - 13 Houston - Planning During the reporting period, the City of Houston undertook planning study work. HARVEY 5B HARRIS COUNTY PROGRAMS Harris County - Homeowner Assistance Program To date, Harris County issued notices to proceed (NTP) for construction for one hundred twenty-five (125) active projects and completed final inspections on all of them. Due to the reallocation of funds, no new HAP projects will be submitted for the program. The Homeowner Assistance Program is in the closeout phase and pending the submission of final expenditures to the GLO. Measure Description - Q3 Rehabilitation or Reconstruction Projects with Final Inspection - 11 Harris County - Buyout and Acquisition Program To date, three hundred seventeen (317) buyout properties were closed on out of three hundred fifty-eight (358) properties, which represents eighty-nine percent (89%) of buyout sites acquired under the program. In addition, one twenty-two (122) demolitions have been completed. County continues to relocate households, and expenditures are pending submission to the GLO. Harris County posted a newsletter in English and Spanish to its Recovery website, which included information on relocation assistance, relocation timelines, and homes available through the Single Family New Construction Program (SFNCP). Measure Description - Q3 Number of households relocated - 2 Number of structures demolished - 49 Harris County - Reimbursement Program Since the program started, Harris County issued nine hundred forty-eight (948) checks to homeowners totaling $40.9 million. Two (2) homeowners are pending assistance. Due to the completion of the eligibility review phase, no new reimbursement projects will be submitted for the program. Measure Description - Q3 Projects with Reimbursement Checks Issued (not yet reportable in DRGR) - 1 Harris County - Affordable Rental Program To date, fifteen (15) projects have been approved with a total of two thousand two hundred eighteen (2,218) units of which one thousand nine hundred forty-six (1,946) will be LMI units. In Quarter 3 2023, Harris County had construction underway on six (6) affordable rental projects and nine (9) are 100% construction complete and in the closeout phase. One rehabilitation project is in eligibility review. Measure Description - Q3 Projects with Construction Completed (Not yetRe,ortable in DRGR) - 4 Projects Leased Up (Not yet Reportable in DRGR) - 3 Harris County - Single Family New Construction In total, nine (9) projects have been approved and are active and in various phases of implementation. One built inventory project with two homes is complete and pending closeout. To date, seven (7) of the thirty-three (33) built inventory homes have been sold to LMI households and the County is actively marketing the remainder of homes through its website and to households being served under the buyout programs. Two (2) subdivision projects are in the permitting phase and one (1) is under construction. Three (3) new built inventory project applications with forty-one homes were submitted to the GLO in Quarter 2 2023 and are under eligibility review. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Harris County - Commercial Buyout Program The County has closed on twenty-five (25) of the thirty-one (31) commercial buyout properties to date, which is eighty-one percent (81%) of sites, and continues to work on relocation and demolition. Eight (8) demolitions are complete. Of the thirty-one (31) relocations, one (1) has fully relocated, sixteen (16) have closed on the replacement property, and fourteen (14) are pending relocation. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan; for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County as Disaster Risk Reduction Areas (DRRA). Measure Description - Q3 Number of properties closed (buyout parcels) - 5 Number of businesses relocated - 1 Number of structures demolished - 2 Harris County - Method of Distribution Infrastructure Program To date, twenty-five (25) infrastructure projects have been submitted of which twenty-three (23) have been approved; of the twenty-three (23) approved projects, one (1) has completed construction complete. Seven (7) projects are in construction bid phase and fifteen (15) are in construction. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q3 In Construction - 1 Harris County - Competitive Application Infrastructure Program To date, sixteen (16) infrastructure and public services applications have been submitted and thirteen (13) are approved and active. Five (5) projects are under construction and three (3) projects are construction complete and in the closeout phase. Four (4) projects are in the bid phase for construction. The public services transit project concluded in Quarter 2 2023 and is in the closeout phase. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Harris County - Planning In Quarter 3 2023, nine (9) planning studies were in progress. To date, twenty-two (22) planning studies have begun of which six (6) planning studies are complet,e and are in the closeout phase and seven (7) are closed. County is in the initial planning phase for one (1) new planning study under this activity. Measure Description - Q3 Planning Activities Completed - 1 Harris County - Public Services To date, three (3) applications have been submitted of which two (2) have been approved. One (1) is pending closeout and the other project is in the implementation phase with closeout anticipated in Quarter 2 2024. One (1) is in the eligibility review phase.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2023-10-01 | 2024 Q1 | OVERALL NARRATIVE: During the quarter, forty-six amendments and one contract closeout were executed. Several programs are nearing completion and fully drawing the allocated funding, including ERP, HAP and ARP. The subrecipient Local Infrastructure program has drawn roughly half of the allocated funding as the majority of contracts have completed construction and are in the closeout phase. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 830 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q4 2023, GLO completed 39 such reviews. Affordable Rental Pprogram: Active construction projects drop off as they are completed. Q4 2023 saw 3 projects finish construction and program expects there will be additional closeouts in the upcoming quarters. ARO continues to request closeouts often. Economic Revitalization Program: In Q4 2023 the ERP program approved no applications. Application processing has been completed at this point. In addition, as of Q4 2023 for ERP 461 applicants have met closeout requirements. Those 461 applicants have created/retained 1438 jobs at 94% LMI. Homeowner Assistance Program: During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q4, GLO was in the process of reviewing 0 projects for eligibility, had approved 0 Homeowner Assistance Program applications for assistance, completed construction on 9 households, had construction underway on 85 houses and approved 37 payment requests. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Measure Description - Q4 Reconstruction HMID Low/Mod - 3 Reconstruction HMID UN - 1 Reconstruction SMID Low/Mod - 2 Rehabilitation HMID Low/Mod - 2 Rehabilitation HMID UN - 1 Total LMI Projects - 7 Total UN Projects - 2 Local Buyout and Local Infrastructure Program: 54 contracts remain active, 20 have received closeout letters and 125 are in the closeout phase. Planning: There are 5 open contracts for this allocation, including the Lower Rio Grande Valley (LRGV) region of the River Basin Flood Study (RBFS) and the Technical Flood Model Reviewer. An additional 6 studies utilizing this funding are in the early phases of scope development. GLO Homeowners Assistance Program - City of Houston: During the reporting period, GLO approved applications for 426 new projects, construction started on 108 homes, and construction was completed (final inspection) on 157 homes. To date, 1,422 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q4 Applications Received - 434 GLO Application Approvals - 426 Reconstruction HMID Low/Mod Applications Approved - 296 Reconstruction HMID UN Applications Approved - 69 Rehabilitation HMID Low/Mod Applications Approved - 54 Rehabilitation HMID,N Applications Approved - 7 Projects Under Construction - 108 Projects with Construction Completed (Final Inspection) - 157 GLO Homeowners Assistance Program - Harris County: During the reporting period, GLO approved applications for 94 new projects, construction started on 15 homes, and construction was completed (final inspection) on 21 homes. To date, 349 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q4 Applications Received - 95 GLO Application Approvals - 94 Reconstruction HMID Low/Mod Applications Approved - 76 Reconstruction HMID UN Applications Approved - 13 Rehabilitation HMID Low/Mod Applications Approved - 3 Rehabilitation HMID UN Applications Approved - 2 Projects Under Construction - 15 Projects with Construction Completed (Final Inspection) - 21 Harvey 5b Houston Direct Allocation Programs: Houston - Homeowners Assistance Program: During the reporting period, the City of Houston reimbursed 3 homeowners (not yet reportable in DRGR). Measure Description - Q4 New Projects with Reimbursement Checks Issued (Not yet Reportable in DRGR) - 3 Houston - Single Family Development Program: On August 4, 2023, the City of Houston notified the GLO of its intent to terminate the Single Family Development Program. The City is in the process of canceling the program and selling the three acquired properties in order to repay funds to the GLO for costs reimbused to date that are no longer eligible. Houston - Multifamily Rental Program: Current Quarter Narrative During the reporting period, the City of Houston continued to implement its Multifamily Program. Of the 31 approved projects, the City of Houston currently has 14 projects under construction, 13 projects with construction complete but not yet reportable in DRGR, and 4 projects completed, fully expended, and reported. Measure Description - Q4 New Projects with Construction Completed (Not yet Reportable in DRGR) - 6 Houston - Small Rental Program: During the reporting period, the City of Houston continued to implement its Small Rental Program. The City of Houston currently has 3 total projects under construction and 0 with construction complete, not yet reportable in DRGR. Houston - Homebuyer Assistance Program: During the reporting period, the City of Houston assisted two applicants with down payment assistance. Additionally, the City continued to prepare for program closeout. Measure Description - Q4 New Homebuyer Households who have Received Down Payment Assistance (Not yet Reportable in DRGR) - 2 Houston - Buyout Program: During the quarter, the City of Houston has worked on relocating tenants from 3 multifamily properties which have approximately 548 remaining tenant households that the city reports are eligible for relocation benefits that have not yet received relocation benefits and/or been relocated. The city has completed relocatin,of 54 tenant households. One property/project has been demolished. Measure Description - Q4 Number of Households Relocated during Quarter (Not yet reportable in DRGR) - 21 Houston - Public Services: During the reporting period, the city and GLO continued to work on closing out the program. Houston - Economic Development Program During the reporting period, 26 jobs were created and 20 businesses received the final installment of their recovery award. An additional 8 businesses received their first award installment during this quarter. Measure Description - Q4 Number of Jobs Created during Quarter - 26 New Businesses Assisted - 20 Houston - Planning: During the reporting period, the City of Houston undertook planning study work. Harvey 5b Harris County Direct Allocation Programs: Harris County - Homeowner Assistance Program: The Homeowner Assistance Program is in the closeout phase and pending the submission of final expenditures to the GLO. In total, Harris County completed one hundred twenty-five (125) homes. Harris County - Buyout and Acquisition Program: To date, three hundred thirty-nine (339) buyout properties were closed on out of three hundred sixty-one (361) properties, which represents ninety-four percent (94%) of buyout sites acquired under the program. In addition, one hundred fifty-six (156) demolitions have been completed. County continues to relocate households, and expenditures are pending submission to the GLO. Harris County posted newsletters in English and Spanish to its Recovery website, which included information on relocation assistance, timeline for relocation benefits, the SAFE Program, a housing fair at the Greens Road Mobile Home Park, and homes available through the Single Family New Construction Program (SFNCP). Measure Description - Q4 Number of households relocated - 2 Number of structures demolished - 34 Harris County - Reimbursement Program Since the program started, Harris County issued nine hundred fifty (950) checks to homeowners totaling $40.95 million. The program is in the closeout phase and pending the submission of final expenditures to the GLO. Measure Description - Q4 Projects with Reimbursement Checks Issued (not yet reportable in DRGR) - 2 Harris County - Affordable Rental Program: To date, sixteen (16) projects have been approved with a total of two thousand four hundred sixty-six (2,466) units of which two thousand one hundred ninety-four (2,194) will be LMI units. In Quarter 4 2023, Harris County had construction underway on five (5) affordable rental projects and ten (10) are 100% construction complete and in the closeout phase. One rehabilitation project was approved this quarter with anticipated completion in December 2024. Measure Description - Q4 GLO approved - 1 Projects with Construction Completed (Not yet Reportable in DRGR) - 1 Projects Leased Up (Not yet Reportable in DRGR) - 2 Harris County - Single Family New Construction In ot,l, nine (9) projects have been approved and are active and in various phases of implementation. Four (4) built inventory projects with eleven (11) homes are complete and pending closeout. To date, twenty-seven (27) of the thirty-eight (38) built inventory homes have been sold to LMI households and the County is actively marketing the remainder of homes through its website and to households being served under the buyout programs. Two (2) of the three subdivision projects are in the permitting and bid phases and one (1) is under construction. Three (3) new built inventory project applications with thirty-eight (38) homes were submitted to the GLO in Quarter 2 2023 and are under eligibility review. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. The Quarter 4 2023 measure for sites acquired or under construction includes previous non-reported data as the measure changed in 2022. Measure Description - Q4 Sites acquired or Under Construction - 3 Harris County - Commercial Buyout Program: The County has closed on twenty-eight (28) of the thirty-two (32) commercial buyout properties to date, which is eighty-eight percent (88%) of sites, and continues to work on relocation and demolition. Ten (10) demolitions are complete. Of the thirty-three (33) relocations, five (5) have fully relocated, twenty-one (21) have closed on the replacement property, and twelve (12) are pending relocation. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan; for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County as Disaster Risk Reduction Areas (DRRA). Measure Description - Q4 Number of properties closed (buyout parcels) - 3 Number of businesses relocated - 2 Number of structures demolished - 2 Harris County - Method of Distribution Infrastructure Program: To date, twenty-five (25) infrastructure projects have been submitted of which twenty-three (23) have been approved; of the twenty-three (23) approved projects, three (3) are construction complete. Two (2) projects are in the award/ pre-construction phase and eighteen (18) are in construction. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q4 In Construction - 5 Projects Completed (not yet reportable in DRGR) - 2 Harris County - Competitive Application Infrastructure Program: To date, sixteen (16) infrastructure and public services applications have been submitted and thirteen (13) are approved and active. Five (5) projects are under construction and four (4) projects are construction complete and in the closeout phase. Three (3) projects are in the bid phase for construction. The public services transit project concluded in Quarter 2 2023 and is in the closeout phase. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q4 In Construction ,- 1 Projects Completed (not yet reportable in DRGR) - 1 Harris County - Planning: To date, twenty-two (22) planning studies have begun of which four (4) are in progress and eighteen (18) are complete (eight (8) planning studies are complete and in the closeout phase; ten (10) are closed and 100% expensed). In Quarter 4 2023, one (1) new planning study is under eligibility review. The Quarter 4 2023 Planning measure includes previous non-reported data as the measure changed in 2022. Measure Description - Q4 Planning Activities Completed - 11 Harris County - Public Services: To date, three (3) applications have been submitted and approved. The projects are in various phases of implementation; one is in the closeout phase, one is in the implementation phase, and one is in the bid phase. All of the projects are anticipated to be completed in Quarter 3 2024. Measure Description - Q4 GLO Approved - 1
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2024-01-01 | 2024 Q2 | OVERALL NARRATIVE Eight subrecipient and four HRP activities were administratively closed and completed in DRGR during the quarter. The project and activities for the newly created Harris County Flood Control District project have been created and are expecting draws in the upcoming quarter for project costs. Many of the state-ran programs are nearing completion and will be in the closeout phases once all construction has been completed. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 866 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q1 2024, GLO completed 36 such reviews. AFFORDABLE RENTAL PROGRAM Eight projects were administratively closed Q1 2024. More closeouts will follow, and the GLO expects only 2 projects will continue to be under construction by the end of this fiscal year. ECONOMIC REVITALIZATION PROGRAM In Q1 2024, the ERP program approved no applications. Application processing has been completed at this point. In addition, as of Q1 2024 for ERP 526 applicants have met closeout requirements. Those 526 applicants have created/retained 1652 jobs at 94% LMI. HOMEOWNER ASSISTANCE PROGRAM During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q1, GLO was in the process of reviewing 0 projects for eligibility, had approved 0 Homeowner Assistance Program applications for assistance, and completed construction on 6 households. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Measure Description - Q1 Reconstruction HMID Low/Mod - 5 Reconstruction HMID UN - 1 Total LMI Projects - 5 Total UN Projects - 1 LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM 58 contracts remain active, 20 have received closeout letters, and 121 are in the closeout phase. PLANNING There are currently 11 open contracts for this funding source, including the River Basin Flood Studies. One additional contract is pending execution. GLO Homeowners Assistance Program - City of Houston During the reporting period, GLO approved applications for 30 new projects, construction started on 111 homes, and construction was completed (final inspection) on 120 homes. To date, 1,542 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q1 Applications Received - 14 GLO Application Approvals - 30 Reconstruction HMID Low/Mod Applications Approved - 22 Reconstruction HMID UN Applications Approved - 4 Rehabilitation HMID Low/Mod Applications Approved - 4 Projects Under Construction - 111 Projects with Construction Completed (Final Inspection) - 120 GLO Homeowners Assistance Program - Harris County During the reportng period,GLO approved applications for 8 new projects, construction started on 23 homes, and construction was completed (final inspection) on 22 homes. To date, 371 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q1 Applications Received - 2 GLO Application Approvals - 8 Reconstruction HMID Low/Mod Applications Approved - 6 Reconstruction HMID UN Applications Approved - 2 Projects Under Construction - 23 Projects with Construction Completed (Final Inspection) - 22 Harvey 5b Houston Programs Houston - Homeowners Assistance Program During the reporting period, the City of Houston reimbursed 3 homeowners. As of March 27, the City has provided reimbursement for 496 households. Measure Description - Q1 New Projects with Reimbursement Checks Issued (Not yet Reportable in DRGR) - 3 Houston - Single Family Development Program On August 4, 2023, the City of Houston notified the GLO of its intent to terminate the Single Family Development Program. The City is in the process of canceling the program and selling the three acquired properties in order to repay funds to the GLO for costs reimbursed to date that are no longer eligible. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Of the 31 approved projects, the City of Houston currently has 12 projects under construction, 12 projects with construction complete but not yet reportable in DRGR, and 7 projects completed, fully expended, and reported. Measure Description - Q1 New Projects with Construction Completed (Not yet Reportable in DRGR) - 2 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The City of Houston currently has 5 total projects under construction and 0 with construction complete. Measure Description - Q1 New Projects Under Construction - 2 Houston - Homebuyer Assistance Program During the reporting period, the City continued to prepare for program closeout. All approved applicants have been assisted. Houston - Buyout Program During the quarter, the City of Houston has worked on relocating tenants from 3 multifamily properties which have approximately 413 remaining tenant households that the city reports are eligible for relocation benefits that have not yet received relocation benefits and/or been relocated. The City has completed relocation of 183 tenant households. One property/project has been demolished. Measure Description - Q1 Number of Households Relocated during Quarter (Not yet reportable in DRGR) - 129 Houston - Public Services During the reporting period, the city and GLO continued to work on closing out the program. Houston - Economic Development Program During the reporting period, 13 jobs were created and 13 businesses received the final instllment of h,ir recovery award. Measure Description - Q1 Number of Jobs Created during Quarter - 13 New Businesses Assisted - 13 Houston - Planning During the reporting period, the City of Houston undertook planning study work. Measure Description - Q1 New Planning Activities Completed - 2 Harvey 5b Harris County Programs Harris County - Homeowner Assistance Program The Homeowner Assistance Program is in the closeout phase and pending the submission of final expenditures to the GLO. In total, Harris County completed one hundred twenty-five (125) homes. Harris County - Buyout and Acquisition Program To date, three hundred forty-nine (349) buyout properties were closed on out of three hundred sixty-one (361) properties. This represents ninety-seven percent (97%) of buyout sites acquired under the program; the buyout areas include five (5) mobile housing unit (MHU) parks. Relocation activities are ongoing. The acquisition activity is considered an area benefit as the County has designated target areas to buyout repetitively flooded properties and to use these areas as green/open space for flood control structures and water retention areas; therefore, beneficiaries under the acquisition activity will be reported after all sites have been acquired. As of Quarter 1 2024, two hundred two (202) demolitions have been completed. Of the anticipated six hundred forty-nine (649) households being relocated, approximately sixty percent (60%) have been relocated and the remainder are in search of a replacement property. Harris County posted a newsletter in English and Spanish to its Recovery website, which included updates on the program, the SAFE Program, the inspection process, and homes available through the Single Family New Construction Program (SFNCP). Measure Description - Q1 Projects Received by GLO - 1 Number of structures demolished - 46 Harris County - Reimbursement Program Since the program started, Harris County issued nine hundred forty-five (945) checks to homeowners totaling $40.74 million. The program is in the closeout phase and pending the submission of final expenditures to the GLO. Since the previous report, five projects were deemed ineligible and funds will be recaptured for two of the five projects with processed payment requests. Harris County - Affordable Rental Program To date, sixteen (16) projects have been approved with a total of two thousand four hundred sixty-six (2,466) units of which two thousand one hundred ninety-four (2,194) will be LMI units. In Quarter 1 2024, Harris County had construction underway on four (4) affordable rental projects and eleven (11) are 100% construction complete and in the closeout phase. One (1) rehabilitation project is anticipated to start construction in Quarter 2 2024. Measure Description - Q1 Projects with Construction Completed (Not yet Reportable in DRGR) - 1 Harris County - Single Family New Construction In total, ten (10) projects have been approved and are active and in various phases of implementation. Five (5) built inventory projects with twenty-fou (24) homesar, complete and pending closeout. To date, thirty-two (32) of the planned fifty-eight (58) built inventory homes have been sold to LMI households and the County is actively marketing the remainder of homes through its website and to households being served under the buyout programs. Additionally, two (2) new built inventory project applications with thirteen (13) homes are pending eligibility approval; the projects are anticipated to be completed by Quarter 3 2024. Two (2) of the subdivision projects are under construction. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Measure Description - Q1 GLO approved - 1 Harris County - Commercial Buyout Program The County has closed on twenty-nine (29) of the thirty-two (32) commercial buyout properties to date, which is ninety-one percent (91%) of sites, and continues to work on relocation and demolition. Seventeen (17) demolitions are complete. Of the thirty-three (33) relocations, twenty-two (22) have closed on the replacement property and of those, ten (10) have fully relocated. The remaining eleven (11) that have not closed on a replacement property are pending relocation. The County has developed an Affirmative Fair Housing Marketing and Outreach Plan; for the Commercial Buyout Program, the target audience is limited to targeted areas identified by the County as Disaster Risk Reduction Areas (DRRA). Measure Description - Q1 Number of properties closed (buyout parcels) - 1 Number of structures demolished - 7 Harris County - Method of Distribution Infrastructure Program To date, twenty-five (25) infrastructure projects have been submitted of which twenty-two (22) have been approved; of the twenty-two (22) approved projects, three (3) are construction complete and the other ninteen (19) are in construction. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q1 In Construction - 2 Harris County - Competitive Application Infrastructure Program To date, sixteen (16) infrastructure and public services applications have been submitted and thirteen (13) are approved and active, one (1) had been withdrawn. Eight (8) projects are under construction and four (4) projects are construction complete and in the closeout phase. The public services transit project concluded in Quarter 2 2023 and is in the closeout phase. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q1 In Construction - 3 Harris County - Planning To date, twenty-three (23) planning studies have begun of which four (4) are in progress and nineteen (19) are complete (six (6) planning studies are complete and in the closeout phase; thirteen (13) are closed and 100% expensed). Measure Description - Q1 Planning Activities Completed - 1 Harris County - Public Services , To date, three (3) applications have been submitted and approved. The projects are in various phases of implementation; one is in the closeout phase and two are in the implementation phase. Measure Description - Q1 In Progress - 1
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2024-04-01 | 2024 Q3 | OVERALL NARRATIVE During the reporting period, state programs such as HAP, ERP, and ARP are nearing completion. The GLO is working to collect all the required data and will be reflected in DRGR in the coming quarters. The GLO is also working towards reallocating deobligated funding from awards that were not fully utilized. The Harris County Flood Control District project is expected to begin drawing in the upcoming quarter. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 901 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q2 2024, GLO completed 35 such reviews. AFFORDABLE RENTAL PROGRAM 2 projects were adminstratively closed in Q2 2024. 4 projects remain under construction with 2 finishing in 2024 FY. 14 are currently pending closeout documents. ECONOMIC REVITALIZATION PROGRAM In Q2 2024 the ERP program approved no applications. Application processing has been completed at this point. In addition, as of Q2 2024 for ERP 533 applicants have met closeout requirements. Those 533 applicants have created/retained 1747 jobs at 94% LMI. HOMEOWNER ASSISTANCE PROGRAM During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q2, GLO was in the process of reviewing 0 projects for eligibility, had approved 0 Homeowner Assistance Program applications for assistance, and completed construction on 1 households. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Measure Description - Q2 Reconstruction HMID UN - 1 LOCAL BUYOUT AND LOCAL INFRASTRUCTURE PROGRAM 34 contracts remain active, 35 have received closeout letters and 130 are in the closeout phase. PLANNING There are currently 10 open contracts for this funding source, including the River Basin Flood Studies. Two additional contracts are pending execution. GLO Homeowners Assistance Program - City of Houston During the reporting period, GLO approved applications for 9 new projects, construction started on 8 homes, and construction was completed (final inspection) on 122 homes. To date, 1664 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q2 Applications Received - 8 GLO Application Approvals - 9 Reconstruction HMID Low/Mod Applications Approved - 4 Reconstruction HMID UN Applications Approved - 4 Rehabilitation HMID Low/Mod Applications Approved - 0 Rehabilitation HMID UN Applications Approved - 1 Projects Under Construction - 8 Projects with Construction Completed (Final Inspection) - 122 GLO Homeowners Assistance Program - Harris County During the reporting period, GLO approved applications for 3 new projects, construction started on 1 homes, and construction was completed (final inspection) on 0 homes. To date, 371 homes have completed final inspection. As projects are unde,ay, the GLO works to include AFFH measures in the approved projects as reported. Measure Description - Q2 Applications Received - 3 GLO Application Approvals - 3 Reconstruction HMID Low/Mod Applications Approved - 3 Reconstruction HMID UN Applications Approved - 0 Rehabilitation HMID Low/Mod Applications Approved - 0 Rehabilitation HMID UN Applications Approved - 0 Projects Under Construction - 1 Projects with Construction Completed (Final Inspection) - 0 Harvey 5b Houston Programs Houston - Homeowners Assistance Program During the reporting period, the City of Houston continued to draw funds and finish projects in the HoAP program. In total, 740 homeowners were assisted with reconstruction, rehabilitation, and/or reimbursement. Houston - Single Family Development Program On August 4, 2023, the City of Houston notified the GLO of its intent to terminate the Single Family Development Program. As of July 2024, the City is exploring options for proceeding with one of the three SFDP projects. If approved by the GLO, the Contract will be amended to extend the timeline of the SFDP, modify beneficiaries, and establish appropriate spending benchmarks. The City is in the process of selling the other two acquired properties in order to repay funds to the GLO for costs reimbused to date that are no longer eligible. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Of the 31 approved projects, the City of Houston currently has 11 projects under construction, 8 projects with construction complete but not yet reportable in DRGR, and 12 projects completed, fully expended, and reported. During the reporting period, seven (7) units that were previously reported as vacant in completed developments have been leased, and their beneficiary information is included on this report. Measure Description - Q2 New Projects with Construction Completed (Not yet Reportable in DRGR) - 1 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The City of Houston currently has 5 total projects under construction and 0 with construction complete. Houston - Homebuyer Assistance Program During the reporting period, the City continued to prepare for program closeout. All approved applicants have been assisted. Houston - Buyout Program Current Quarter Narrative During the quarter, the City of Houston has worked on relocating tenants from 3 multifamily properties which have approximately 412 remaining tenant households that the city reports are eligible for relocation benefits that have not yet received relocation benefits and/or been relocated. The city has completed relocation of 184 tenant households. One property/project has been demolished. Measure Description - Q2 Number of Households Relocated during Quarter (Not yet reportable in DRGR) - 1 Houston - Public Services During the reporting period, the city and GLO documented the complei,n and closing of the program with the Program Completion Notification issued to the City on May 3, 2024. Houston - Economic Development Program During the reporting period, 16 jobs were created at 15 businesses receiving the final installment of their recovery award. To date, 185 jobs have been created by this program. Measure Description - Q2 Number of Jobs Created during Quarter - 16 New Businesses Assisted - 15 Houston - Planning During the reporting period, the City of Houston undertook planning study work. 1 planning activity completed this quarter, and an additional 2 were previously completed and received payment this quarter and included in the report below. Measure Description - Q2 New Planning Activities Completed - 3 Harvey 5b Harris County Programs Harris County - Homeowner Assistance Program The Homeowner Assistance Program is in the closeout phase and pending the submission of final expenditures to the GLO. In total, Harris County completed one hundred twenty-five (125) homes. Harris County - Buyout and Acquisition Program To date, three hundred forty-nine (349) buyout properties were closed on out of three hundred sixty (360) properties. This represents ninety-seven percent (97%) of buyout sites acquired under the program; the buyout sites include five (5) MHU parks. Relocation activities are ongoing. The acquisition activity is considered an area benefit as the County has designated target areas to buyout repetitively flooded properties and to use these areas as green/open space for flood control structures and water retention areas; therefore, beneficiaries under the acquisition activity will be reported after all sites have been acquired. As of Quarter 2 2024, two hundred forty (240) demolitions have been completed. Of the anticipated six hundred sixty-four (664) households being relocated, approximately seventy-six percent (76%) have been relocated and the remainder are in search of a replacement property. Harris County posted a newsletter in English and Spanish to its Recovery website, which included updates on the program, safety measures at the mobile home parks, a success story, and homes available through the Single Family New Construction Program (SFNCP). Measure Description - Q2 GLO Approved for Buyout - 1 Low-to-Moderate (LMI) Projects - 1 Number of households relocated - 204 Number of structures demolished - 38 Harris County - Reimbursement Program Since the program started, Harris County issued nine hundred forty-five (945) checks to homeowners totaling $40.74 million. The program is in the closeout phase and pending the submission of final expenditures to the GLO. Harris County - Affordable Rental Program To date, sixteen (16) projects have been approved with a total of 2,466 units of which 2,194 will be LMI units. In Quarter 2 2024, one (1) rehabilitation project began construction and in total, construction was underway on three (3) affordable rental projects. Thirteen (13) projects are 100% construction complete and in the closeout phase. /d,v> Measure Description - Q2 In construction - 1 Projects with Construction Completed (Not yet Reportable in DRGR) - 2 Projects Leased Up (Not yet Reportable in DRGR) - 3 Harris County - Single Family New Construction During Quarter 2 2024, two (2) new built inventory project applications with thirteen (13) homes were approved and the projects are anticipated to be completed by Quarter 3 2024. Additionally, one (1) project was withdrawn. In total, eleven (11) projects have been approved and are active and in various phases of implementation. Five (5) built inventory projects with twenty-four (24) homes are complete and pending closeout. To date, thirty-seven (37) of the planned seventy-one (71) built inventory homes have been sold to LMI households and the County is actively marketing the remainder of homes through its website and to households being served under the Buyout Program. One (1) subdivision project is under construction for the infrastructure improvements; the County plans to bid out construction for the home building for the two subdivision projects (Ella and Vista/ ORchard Place) in Quarter 3 2024. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Measure Description - Q2 GLO approved - 2 Sites acquired or Under Construction - 4 Projects with Construction Completed - 3 Harris County - Commercial Buyout Program The County has closed on thirty (30) of the thirty-two (32) commercial buyout properties to date, which is ninety-four percent (94%) of sites, and continues to work on relocation and demolition. Nineteen (19) demolitions are complete. Of the thirty-four (34) relocations, eighteen (18) have fully relocated, thirteen (13) have closed on the replacement property, and three (3) are pending relocation. Measure Description - Q2 Projects Received by GLO - 1 GLO Approved - 1 Number of properties closed (buyout parcels) - 1 Number of businesses relocated - 5 Number of structures demolished - 2 Harris County - Method of Distribution Infrastructure Program To date, twenty-five (25) infrastructure projects have been submitted of which twenty-three (23) have been approved; of the twenty-three (23) approved projects, eight (8) are construction complete and the other fifteen (15) are in construction. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q2 Projects Completed (not yet reportable in DRGR) - 5 Harris County - Competitive Application Infrastructure Program To date, sixteen (16) infrastructure and public services applications have been submitted and thirteen (13) are approved and active. Seven (7) projects are under construction and five (5) projects are construction complete and in the closeout phase. The public services transit project is in the closeout phase. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed pri,or to the GLO issuing the eligibility approval letter. Measure Description - Q2 Projects Completed (not yet reportable in DRGR) - 1 Harris County - Planning To date, twenty-three (23) planning studies have begun of which four (4) are in progress and nineteen (19) are complete (four (4) planning studies are complete and in the closeout phase; fifteen (15) are closed and 100% expensed). Harris County - Public Services During Quarter 2 2024, one project was withdrawn. In total, the program includes two (2) active projects which are the Section 3 project and the Generation Park On Demand Service (Microtransit) project. They are in various phases of implementation; one (1) is in the closeout phase and one (1) is in the implementation phase.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2024-07-01 | 2024 Q4 | OVERALL NARRATIVE During the reporting period, the bulk of programs and activities are working through the closeout phase as construction projects continue to be completed. The Harris County Flood Control District program has begun to draw funds for projects as they begin to become active and underway. The GLO has also submitted Action Plan Amendment 16 for the inclusion of the Disaster Recovery Reallocation Program in order to utilize deobligated funds. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 918 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q3 2024, GLO completed 17 such reviews. Affordable Rental Program Majority of projects have finished construction and are either closed or pending closeout. The few projects that are still under construction will be completed throughout the remainder of the timeline of the grant. Economic Revitalization Program In Q3 2024, the ERP program approved no applications. Application processing and case management has been completed at this point. As of Q3 2024 for ERP all applicants have met closeout requirements, and all contracts have been closed. The final numbers for the ERP program are that we supported 553 businesses who have created/retained 1747 jobs at 95% LMI. Homeowner Assistance Program During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q3 2024, GLO was in the process of reviewing 0 projects for eligibility, had approved 0 Homeowner Assistance Program applications for assistance, and completed construction on 0 households. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. State-Managed City of Houston Homeowner Assistance Program During the reporting period, GLO approved applications for 1 new projects, construction started on 0 homes, and construction was completed (final inspection) on 107 homes. To date, 1766 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. State-Managed Harris County Homeowner Assistance Program During the reporting period, GLO approved applications for 1 new projects, construction started on 0 homes, and construction was completed (final inspection) on 9 homes. To date, 399 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. State-Managed Harris County Flood Control District HCFCD has submitted a total of 13 projects for CDBG-DR funding. Of these, seven projects are approved and six are under review. Measure Description - Q3 Projects Received by GLO - 13 In Review/ Pending Additional Information - 6 GLO Approved - 7 Local Infrastructure and Buyout Programs "Local Infrastructure Program: 17 contracts remain active, 28 have received closeout letters and 107 are in the closeout phase. Local Buyout Program: 38 contracts remain active,, have received closeout letters and 35 are in the closeout phase." Planning Program There are 10 additional active planning contracts currently underway for the Texas GLO, including Texas Disaster Information System & Regional Basin Flood Study. There are additional planning studies affiliated with the Texas A&M System for the Community Health and Resource Management system with Texas A&M to assist with technological improvements and increase the availability of the program across impacted areas, and for the Standardization of Green Infrastructure in Texas to assist Coastal Resources on a green infrastructure project. Harvey 5b Houston Programs Houston - Homeowners Assistance Program During the reporting period, the City of Houston continued to draw funds for final costs in the HoAP program. In total, 740 homeowners were assisted with reconstruction, rehabilitation, and/or reimbursement. Houston - Single Family Development Program On August 4, 2023, the City of Houston notified the GLO of its intent to terminate the Single Family Development Program. As of August 2024, the City did not receive eligible developers for the one pending project and will not proceed with development of the site. The City is in the process of selling the three acquired properties in order to repay funds to the GLO for costs reimbursed to date that are no longer eligible. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Of the 31 approved projects, the City of Houston currently has 11 projects under construction, 5 projects with construction complete but not yet reportable in DRGR, and 15 projects completed, fully expended, and reported. During the reporting period, sixteen (16) units that were previously reported as vacant in completed developments have been leased, and their beneficiary information is included on this report. Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The City of Houston currently has 4 total projects under construction and 1 with construction complete. Measure Description - Q3 New Projects with Construction Completed (Not yet Reportable in DRGR) - 1 Houston - Homebuyer Assistance Program During the reporting period, the City continued with program closeout. All approved applicants have been assisted. Houston - Buyout Program During the quarter, the City of Houston transferred 592 relocation files to the GLO&apos;s vendor, AECOM, to complete work. To date, AECOM staff have been actively working with 177 of those households and have made payments to 28 of those households. The City completed payments for 4 households that remained under the City&apos;s purview. One property has been demolished. Measure Description - Q3 Number of Households Relocated during Quarter (Not yet reportable in DRGR) - 20 Houston - Public Services The Public Services program is complete. GLO documented the completion and closing of the program with the Program Completion Notification issued to the City on May 3, 202.,/div> Houston - Economic Development Program During the reporting period, 6 jobs were created at 4 businesses receiving the final installment of their recovery award. To date, 191 jobs have been created by this program. The City is working to draw the remaining funds for program closeout in Q1 2025. Measure Description - Q3 Number of Jobs Created during Quarter - 6 New Businesses Assisted - 4 Houston - Planning During the reporting period, the City of Houston completed expenses and reimbursements for the last of its planning studies. The program is continuing with closeout and paying staff time personnel draws. Harvey 5b Harris County Programs Harris County - Homeowner Assistance Program The Homeowner Assistance Program is in the closeout phase and pending the submission of final expenditures to the GLO. In total, Harris County completed one hundred twenty-five (125) homes. Harris County - Buyout and Acquisition Program To date, three hundred forty-nine (349) buyout properties were closed on out of three hundred sixty (360) properties. This represents ninety-seven (97%) of buyout sites acquired under the program; the buyout sites include five (5) MHU parks. Relocation activities are ongoing. The acquisition activity is considered an area benefit as the County has designated target areas to buyout repetitively flooded properties and to use these areas as green/open space for flood control structures and water retention areas; therefore, beneficiaries under the acquisition activity will be reported after all sites have been acquired. As of Quarter 3 2024, two hundred eighty-six (286) demolitions have been completed. Of the anticipated six hundred sixty-seven (667) households being relocated, approximately eighty-one percent (81%) have been relocated and the remainder (one hundred twenty-five (125) households) are in search of a replacement property. Harris County posted newsletters in English and Spanish to its Recovery website, which included updates on the program, an explanation of upcoming deadlines, documentation to submit with relocation claim forms and office locations. Measure Description - Q3 Projects Received by GLO - 2 GLO Approved for Buyout - 2 Low-to-Moderate (LMI) Projects - 2 Number of households relocated - 114 Number of structures demolished - 46 Harris County - Reimbursement Program Since the program started, Harris County issued nine hundred forty-five (945) checks to homeowners totaling $40.74 million. The program is in the closeout phase and pending the submission of final expenditures to the GLO. Harris County - Affordable Rental Program To date, sixteen (16) projects have been approved with a total of 2,466 units of which 2,194 will be LMI units. One (1) rehabilitation project and three (3) new construction projects are underway. Ten (10) projects are 100% construction complete and in the closeout phase and two (2) projects are closed out (100% expensed). Harris County - Single Family New Construction In total, eleven (11) projects have been approved and are active and in various phse, of implementation. Five (5) Model 3 built inventory projects with twenty-four (24) homes are complete and pending closeout. To date, fifty (50) of the planned seventy-one (71) built inventory homes have been sold to LMI households and the County is actively marketing the remainder of homes through its website and to households being served under the Buyout Program. One (1) subdivision project (Ella) is under construction for the infrastructure improvements; the County plans is bidding out the construction for the home building for the two Model 1 subdivision projects (Ella and Vista/ Orchard Place) in Quarter 4 2024. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Harris County - Commercial Buyout Program The County has closed on thirty (30) of the thirty-two (32) commercial buyout properties to date, which is ninety-four percent (94%) of sites, and continues to work on relocation and demolition. Number of properties closed (buyout parcels) includes sites acquired that were not previously reported. Twenty-six (26) demolitions are complete. Of the thirty-seven (37) relocations, twenty-three (23) have fully relocated, eight (8) have closed on the replacement property, and six (6) are pending relocation. Measure Description - Q3 Number of properties closed (buyout parcels) - 7 Number of businesses relocated - 2 Number of structures demolished - 7 Harris County - Method of Distribution Infrastructure Program To date, twenty-five (25) infrastructure projects have been submitted of which twenty-three (23) have been approved; of the approved projects, ten (10) are construction complete and the other thirteen (13) are in construction. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q3 Projects Completed (not yet reportable in DRGR) - 2 Harris County - Competitive Application Infrastructure Program To date, sixteen (16) infrastructure and public services applications have been submitted and thirteen (13) are approved and active. Six (6) projects are under construction and six (6) projects are construction complete and in the closeout phase. The public services transit project is in the closeout phase. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q3 Projects Completed (not yet reportable in DRGR) - 1 Harris County - Planning To date, twenty-three (23) planning studies have begun of which two (2) are in progress and twenty-one (21) are complete (five (5) planning studies are complete and in the closeout phase; sixteen (16) are closed and 100% expensed). Measure Description - Q3 Planning Activities Completed - 2 Harris County - Public Services The Section 3 Public Services project has been completed and was fully expensed and closed out in Quarter 3, 2024. The Generation Park On Demand Service (Microtransit) project is ongoing.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2024-10-01 | 2025 Q1 | OVERALL NARRATIVE During the reporting period, the GLO continues to complete final projects and draws and to administratively close the majority of still active programs, including ERP, HRP and HAP. Action Plan Amendment 16 went into effect this quarter and created the Disaster Recovery Reallocation Program that aims to utilize deobligated funds from previously allocated awards to provide the opportunity for communities with outstanding unmet need to access remaining CDBG-DR funds. Harvey 5b State of Texas Programs Affordable Rental Program There are two remaining construction projects with one expected end of construction date in 2025 and one in 2026. Closeouts will continue to be processed and reported in DRGR. Economic Revitalization Program In Q4 2024 the ERP program approved no applications. Application processing and case management has been completed at this point. As of Q3 2024 for ERP all applicants had met closeout requirements, and all contracts have now been closed. The final numbers for the ERP program are that the GLO supported 553 businesses who have created/retained 1747 jobs at 95% LMI. The closeout work completed in Q4 2024 for the ERP program included formalizing the system of record and completing the After Action Report. Harris County Flood Control District HCFCD has submitted a total of 13 projects for CDBG-DR funding. Of these, 10 of the 13 HCFCD DR project applications have officially been awarded. Measure Description - Q4 Projects Received by GLO - 13 In Review/ Pending Additional Information - 3 GLO Approved - 10 Homeowner Assistance Program During the reporting period, the Homeowner Assistance Program received 2 applications. As of the end of Q4, GLO was in the process of reviewing 0 projects for eligibility, had approved 2 Homeowner Assistance Program applications for assistance, and completed construction on 2 households. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Harvey State-managed City of Houston Homeowner Assistance Program During the reporting period, GLO approved applications for 0 new projects, construction started on 0 homes, and construction was completed (final inspection) on 132 homes. To date, 1868 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Harvey State-managed Harris County Homeowner Assistance Program During the reporting period, GLO approved applications for 0 new projects, construction started on 0 homes, and construction was completed (final inspection) on 24 homes. To date, 419 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Subrecipient Infrastructure & Buyout/Acquisition Programs "Local Infrastructure Program: 65 contracts active, 33 are closed and 53 are in various states of the closeout review. Local Buyout Program: 26 contracts active, 11 are closed and 9 are in various states of the closeout review. " ,div> Harvey 5b Houston Programs Houston - Homeowners Assistance Program During the reporting period, the City of Houston continued to draw funds for final costs in the HoAP program. In total, 740 homeowners were assisted with reconstruction, rehabilitation, and/or reimbursement. Houston - Single Family Development Program On August 4, 2023, the City of Houston notified the GLO of its intent to terminate the Single Family Development Program. As of August 2024, the City did not receive eligible developers for the one pending project and will not proceed with development of the site. The GLO has received a partial repayment of ineligible acquisition costs in the amount of $8,000,000 from the City in October 2024. City is in the process of repaying the GLO for two of the acquired properties and selling the third acquired property in order to repay funds to the GLO for costs reimbursed to date that are no longer eligible. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Of the 31 approved projects, the City of Houston currently has 7 projects under construction, 6 projects with construction complete but not yet reportable in DRGR, and 18 projects completed, fully expended, and reported. Measure Description - Q4 New Projects with Construction Completed (Not yet Reportable in DRGR) - 4 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The City of Houston currently has 4 total projects under construction and 1 with construction complete and fully expended. Houston - Homebuyer Assistance Program During the reporting period, the City continued with program closeout. All 488 approved applicants have been assisted. Houston - Buyout Program During the quarter, the City of Houston transferred 643 relocation files to the GLO&apos;s vendor, AECOM, to complete work. To date, AECOM staff have been actively working with 177 of those households and have made payments to 28 of those households. The City completed payments for 3 households that remained under the City&apos;s purview. One property has been demolished. Houston - Public Services The Public Services program is complete. GLO documented the completion and closing of the program with the Program Completion Notification issued to the City on May 3, 2024. Houston - Economic Development Program During the reporting period, the City continues to focus on closing project files to complete program closeout by May 31, 2025. Houston - Planning During the reporting period, the City of Houston is continuing with program closeout and paying staff time personnel draws. Harvey 5b Harris County Programs Harris County - Homeowner Assistance Program The Homeowner Assistance Program is in the closeout phase and pending the submission of final expenditures to the GLO. In total, Harris County completed one hundred twenty-five (125) homes. Harris County - Buyout and Acquisition Program</dv, To date, three hundred fifty-six (356) buyout properties were closed on out of three hundred sixty (360) properties. This represents ninety-nine (99%) of buyout sites acquired under the program; the buyout sites include five (5) MHU parks. Relocation activities are ongoing. The acquisition activity is considered an area benefit as the County has designated target areas to buyout repetitively flooded properties and to use these areas as green/open space for flood control structures and water retention areas; therefore, beneficiaries under the acquisition activity will be reported after all sites have been acquired. As of Quarter 4 2024, three hundred two (302) demolitions have been completed. Of the anticipated six hundred sixty-eight (668) households being relocated, approximately eighty-six percent (86%) have been relocated and the remainder (ninety-two (92) households) are in search of a replacement property. Harris County maintained program information in English and Spanish on its Recovery website, which included an update on its office location and benefits matrix. Data Measure Description - Q4 Number of households relocated - 73 Number of structures demolished - 16 Harris County - Reimbursement Program Since the program started, Harris County issued nine hundred forty-five (945) checks to homeowners totaling $40.74 million. The program is in the closeout phase and pending the submission of final expenditures to the GLO. Harris County - Affordable Rental Program To date, sixteen (16) projects have been approved with a total of 2,466 units of which 2,194 will be LMI units. One (1) rehabilitation project and three (3) new construction projects are underway and are over 90% construction complete. Nine (9) projects are 100% construction complete and in the closeout phase and three (3) projects are closed out (100% expensed). Harris County - Single Family New Construction In total, eleven (11) projects have been approved and are active and in various phases of implementation. Six (6) Model 3 built inventory projects with thirty-eight (38) homes are complete and pending closeout. To date, fifty-six (56) of the planned seventy-one (71) built inventory homes have been sold to LMI households and the County is actively marketing the remainder of homes through its pipeline of applicants and to households being served under the Buyout Program. One (1) subdivision project (Ella) is under construction for the infrastructure improvements; the County anticipates bidding out the home construction for Ella in Quarter 1 2025.In Quarter 4 2024, the County bid out the construction for the home building for one Model 1 subdivision projects (Vista/ Orchard Place) and construction is anticipated to start in Quarter 1 2025. The GLO completed an Affirmatively Furthering Fair Housing (AFFH) review for each approved project as part of the eligibility review phase and prior to project approval. Harris County - Commercial Buyout Program The County has closed on thirty (30) of the thirty-two (32) commercial buyout properties to date, which is ninety-four percent (94%) of sites, and continues to work on relocation and demolition. Twenty-seven (27) demolitions are complete. Of the thirty-six (36) relocations, twenty-six (26) have fully relocated, seven (7) have reloc,ated and are pending closeout, and three (3) are pending relocation. Measure Description - Q4 Number of structures demolished - 1 Harris County - Method of Distribution Infrastructure Program To date, twenty-five (25) infrastructure projects have been submitted of which twenty-three (23) have been approved; of the approved projects, eleven (11) are construction complete and the other twelve (12) are in construction. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Measure Description - Q4 Projects Completed (not yet reportable in DRGR) - 1 Harris County - Competitive Application Infrastructure Program To date, sixteen (16) infrastructure and public services applications have been submitted and thirteen (13) are approved and active. Six (6) projects are under construction and six (6) projects are construction complete and in the closeout phase. The public services transit project is in the closeout phase. For the approved projects, an Affirmatively Furthering Fair Housing (AFFH) review was completed prior to the GLO issuing the eligibility approval letter. Harris County - Planning To date, all twenty-three (23) planning studies have been completed. Six (6) planning studies are complete and in the closeout phase; seventeen (17) are closed and 100% expensed). Data Measure Description - Q4 Planning Activities Completed - 2 Harris County - Public Services The Section 3 Public Services project has been completed and was fully expensed and closed out in Quarter 3 2024. The Generation Park On Demand Service (Microtransit) project is ongoing.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2025-01-01 | 2025 Q2 | OVERALL NARRATIVE During the reporting period, there was a major revision of existing payments originally drawn from temporary activities in the Administration project to both Local Infrastructure and Local Buyout projects&apos; grantee support activities for state costs in support of activity delivery. There were also recaptured funds from the Houston Single Family Development Program for disallowed costs. Other still active programs are largely in various states of closeout. The Disaster Recovery Reallocation Program projects will be reviewed for eligibility and contracting in Q2 2025. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 934 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q1 2025, GLO completed 3 such reviews. Affordable Rental Program Two remaining construction projects with one end of construction date in 2025 and one in 2026. All others are processing final administrative documents for closeouts. Economic Revitalization Program As of Q3 2024 for ERP all applicants have preliminary met all closeout requirements, and all contracts have been closed. The final numbers for the ERP program are that we supported 553 businesses who have created/retained 1747 jobs at 95% LMI. The closeout work continues to be completed in Q1 2025 for the ERP program included formalizing the system of record, confirming completed activities, and completing the After Action Report. Harris County Flood Control District HCFCD has 10 project applications that have been awarded and are underway and 1 project application pending submission. Measure Description - Q1 Projects Received by GLO - 11 In Review/ Pending Additional Information - 1 GLO Approved - 10 Homeowner Assistance Program During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q1, GLO was in the process of reviewing 0 projects for eligibility, had approved 0 Homeowner Assistance Program applications for assistance, and completed construction on 4 households. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Harvey State-managed City of Houston Homeowner Assistance Program During the reporting period, GLO approved applications for 0 new projects, construction started on 114 homes, and construction was completed (final inspection) on 59 homes. To date, 1730 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Harvey State-managed Harris County Homeowner Assistance Program During the reporting period, GLO approved applications for 0 new projects, construction started on 29 homes, and construction was completed (final inspection) on 6 homes. To date, 388 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. <br d,a-mce-bogus="1"> Subrecipient Infrastructure & Buyout/Acquisition Programs Hurricane Harvey funding includes two programs. Local Infrastructure Program - 64 contracts are active, 36 are closed, and 51 are various states of closeout review. Local Buyout Program - 26 contracts are active, 10 are closed, and 10 are in various states of closeout review. Harvey 5b Houston Programs Houston - Homeowners Assistance Program During the reporting period, the City of Houston continued to draw funds for final costs in the HoAP program. In total, 740 homeowners were assisted with reconstruction, rehabilitation, and/or reimbursement. The remainder of draws for the HoAP program are project delivery costs. The GLO received six at the end of March, most of which are currently under review or have been issued RFIs. The Program Completion Report is under review and is pending resolution of final draws. Houston - Single Family Development Program On February 28, 2025, the GLO received a check for $12,523,137.63 for the Cityscape (West Orem) property. Due to the reimbursement of the disallowed acquisition costs, the City has now completed the repayment process. As a result, there is a negative balance of ($ 33,887,096.75). On January 31, 2025, GLO notified the City that the unpaid balance of $3,138,536.15 indicated on the Hardy Yards Project Site Seller&apos;s Statement was due to GLO. GLO must receive this debt by June 30, 2025. Once this has been accomplished, the closeout process will commence. The GLO confirmed on 4/08/2025 that it had received the repayment of $41,896,713.19 in project acquisition funds for Hardy Yards, Stella Link, and Cityscape (West Orem) properties. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Of the 31 approved projects, the City of Houston currently has 5 projects under construction, 6 projects with construction complete but not yet reportable in DRGR, and 19 projects completed, fully expended, and reported. Measure Description - Q1 New Projects with Construction Completed (Not yet Reportable in DRGR) - 1 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The City of Houston currently has 2 total projects under construction, 2 construction complete, and 1 (closed out) construction complete and fully expended. Houston - Homebuyer Assistance Program During the reporting period, the program was closed out on March 11th. All draws during this period were project delivery related. Houston - Buyout Program During the quarter, the City of Houston transferred 643 relocation files to the GLO&apos;s vendor, AECOM, to complete work. To date, AECOM staff have been actively working with 177 of those households and have made payments to 26 of those households for this quarter. One property has been demolished. Houston - Public Services The Public Services program is complete. GLO documented the completion ad,closing of the program with the Program Completion Notification issued to the City on May 3, 2024. Houston - Economic Development Program During the reporting period, the City continues to focus on closing project files to complete program closeout by May 31, 2025. Houston - Planning The GLO sent the Planning Program Closeout letter to the City on March 5th. Harvey 5b Harris County Programs Harris County - Homeowner Assistance Program GLO provided feedback on the Countyâ¿¿s closeout report and requested revisions following the submittal of the final project delivery draws. Harris County - Buyout and Acquisition Program To date, three hundred fifty-eight (358) buyout properties were closed on out of three hundred sixty (360) properties. This represents ninety-nine (99%) of buyout sites acquired under the program; the buyout sites include five (5) MHU parks. Relocation activities are ongoing. The acquisition activity is considered an area benefit as the County has designated target areas to buyout repetitively flooded properties and to use these areas as green/open space for flood control structures and water retention areas; therefore, beneficiaries under the acquisition activity will be reported after all sites have been acquired. As of Quarter 1 2025, three hundred and seventeen (317) demolitions have been completed. Of the anticipated six hundred sixty-seven (667) households being relocated, approximately eighty-nine percent (89%) have been relocated and the remainder seventy one (71) households are in search of a replacement property. Harris County maintained program information in English and Spanish on its Recovery website, which included an update on its office location and benefits matrix. Measure Description - Q1 Number of households relocated - 10 Number of structures demolished - 2 Harris County - Reimbursement Program Since the program started, Harris County issued nine hundred forty-five (945) checks to homeowners totaling $40.74 million. GLO provided feedback on the County&apos;s closeout report and pending the submission of final expenditures to the GLO. Harris County - Affordable Rental Program To date, sixteen (16) projects have been approved with a total of 2,374 units of which 2,154 will be LMI units. Three (3) new construction projects are under construction and are over 95% complete. Nine (9) projects are 100% construction complete and in the closeout phase and four (4) projects are closed out (100% expensed). Measure Description - Q1 Projects Leased Up (Not yet Reportable in DRGR) - 1 Harris County - Single Family New Construction The County is prepping to close out 6 built inventory projects and is submitting revised project closeout reports; 2 projects are 100% expensed/closed in TIGR. 2 acreage sites are in construction phase. Vista/Orchard Place: Infrastructure construction is complete. Home construction has begun. Ella project: Infrastructure improvements are underway and is at 60%, construction complete, and HC anticipates bidding out the Ella home construction in Q2 2025. Harris County - Commercial Buyout Program The County has closed on thirty (30) of the thirty-two (32) commercial buyout properties to date, which is ninety-four percent (94%) of sites, and continues to work on relocation and demolition. Twenty-seven (27) demolitions are complete. Of the thirty-six (36) relocations, twenty-six (26) have fully relocated, seven (7) have relocated and are pending closeout, and three (3) are pending relocation. Measure Description - Q1 Number of businesses relocated - 4 Number of structures demolished - 1 Harris County - Method of Distribution Infrastructure Program To date, of the twenty-three (23) approved projects, three (3) are under closeout review, nineteen (19) are at 75% - 100% of construction complete and one (1) is under 75% construction complete. Measure Description - Q1 Projects Received by GLO - 25 GLO Approved - 23 In Construction - 20 Projects Completed (not yet reportable in DRGR) - 3 Harris County - Competitive Application Infrastructure Program To date, of the thirteen (13) approved projects, two (2) are in closeout review, nine (9) have 75%-100% construction complete and two (2) are under 75% construction complete. Measure Description - Q1 Projects Received by GLO - 16 GLO Approved - 13 In Construction - 11 Projects Completed (not yet reportable in DRGR) - 2 Harris County - Planning To date, all twenty-three (23) planning studies have been completed. 2 are complete and in the closeout phase; 21 are closed and 100% expended. GLO is waiting for the County to submit final draws and the program completed in Q2 2025. Harris County - Public Services To date, three (3) applications have been submitted and approved. The projects are in various phases of implementation; one is in the closeout phase and two are in the implementation phase. Measure Description - Q1 In Progress - 1
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2025-04-01 | 2025 Q3 | OVERALL NARRATIVE During the reporting period, the GLO continued to review contract completion documents as the majority of existing programs are in or nearing the closeout phase. One program, the Disaster Recovery Reallocation Program, is underway as the GLO is continuing to review for eligibility and undergoing contracting. DRGR Activities have been created for the known awarded population as of the end of the quarter. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 940 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q2 2025, GLO completed 6 such reviews. Affordable Rental Program Two remaining construction projects with one end of construction date in 2025 and one in 2026. All others are processing final administrative documents for closeouts. Economic Revitalization Program The closeout work continues to be completed in Q1 2025 for the ERP program included formalizing the system of record, confirming completed activities, and completing the After-Action Report. Harris County Flood Control District Harris County Flood Control District has ten (10) Flood and Drainage projects awarded and underway. One (1) project application is still pending approval. Homeowner Assistance Program During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q2, GLO was in the process of reviewing 0 projects for eligibility, had approved 0 Homeowner Assistance Program applications for assistance, and completed construction on 0 households. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Program accomplishments were reconciled with the data in the Texas Integrated Grant Reporting System during the quarter. Harvey State-managed City of Houston Homeowner Assistance Program During the reporting period, GLO approved applications for 0 new projects, construction started on 64 homes, and construction was completed (final inspection) on 101 homes. To date, 1790 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Harvey State-managed Harris County Homeowner Assistance Program During the reporting period, GLO approved applications for 0 new projects, construction started on 7 homes, and construction was completed (final inspection) on 13 homes. To date, 391 homes have completed final inspection. As projects are underway, the GLO works to include AFFH measures in the approved projects as reported. Subrecipient Infrastructure & Buyout/Acquisition Programs Local Infrastructure Program - 33 contracts are active, 38 are closed, and 82 are in various states of closeout review. Local Buyout Program - 8 contracts are active, 16 are closed, and 24 are in various states of closeout review. Harvey 5b Houston Direct All,ation Programs Houston - Homeowners Assistance Program The remainder of draws for the HoAP program are project delivery costs. The GLO received six draws in early April, all of which were issued RFIs. As of 7/09/2025, Amendment 4 to the contract allowed funds to be reallocated to Unmet Needs Reimbursement Program activities. The Program Completion Report will be approved pending resolution of four final draws. Houston - Single Family Development Program On February 28, 2025, the GLO received a check for $12,523,137.63 for the Cityscape (West Orem) property. Due to the reimbursement of the disallowed acquisition costs, the City has now completed the repayment process. As a result, there is a negative balance of ($ 33,887,096.75). On January 31, 2025, GLO notified the City that the unpaid balance of $3,138,536.15 indicated on the Hardy Yards Project Site Seller&apos;s Statement was due to GLO. The GLO confirmed on 4/08/2025 that it had received the repayment of $41,896,713.19 in project acquisition funds for Hardy Yards, Stella Link, and Cityscape (West Orem) properties. On June 27, 2025, the City notified the GLO that the TIRZ repayment check for $3,138,536.15 related to the Single-Family development program had been sent. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Of the 31 approved projects, the City of Houston currently has 2 projects under construction, 7 projects with construction complete but not yet reportable in DRGR, and 22 projects completed, fully expended, and reported. Measure Description - Q2 New Projects with Construction Completed (Not yet Reportable in DRGR) - 7 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The City of Houston currently has 1 project under construction, 2 construction complete, and 2 (closed out) construction complete and fully expended, 1 being reported this quarter. Measure Description - Q2 New Projects with Construction Completed (Not yet Reportable in DRGR) - 2 Houston - Homebuyer Assistance Program This program was closed out on March 11th. All draws during the current quarter were project implementation costs paid to professional services vendor. Houston - Buyout Program Overall, the City of Houston transferred 757 relocation files to date. During the past quarter, the Vendor updated GLO with new tenants that the City had unaccounted for. Out of the 757 relocation files, 324 tenants are ineligible/withdrawn from the program. 246 tenants have not been located. To date, AECOM staff have been actively working with 187 of those households and have made payments to 20 of those households for this quarter. One property has been demolished and the 2 remaining properties are scheduled to be demolished by the end of this year. Houston - Public Services The Public Services program is complete. GLO documented the completion and closing of the r,gram with the Program Completion Notification issued to the City on May 3, 2024. Houston - Economic Development Program During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Harvey Economic Development Program (HEDP). All projects are complete and repayment for Houston HEDP from the City. Houston - Planning The GLO sent the Planning Program Closeout letter to the City in previous quarter. Harvey 5b Harris County Direct Allocation Programs Harris County - Homeowner Assistance Program GLO completed review of the closeout report and forwarded to the County requesting updates by July 15th, 2025. Harris County - Buyout and Acquisition Program Three hundred and fifty-eight (358) buyout properties have been closed out of three hundred and sixty (360) properties. The program remains at ninety-nine precent (99%) of sites acquired. The buyout sites include five (5) MHU parks. Six hundred and thirty-three (633) of the six hundred and sixty-six (666) relocations have secured replacement housing at ninety-five percent (95%) with thirty-three (33) are continuing in search of replacement housing. Three hundred and forty-four (344) sites have demolition complete. Measure Description - Q2 Number of households relocated - 38 Number of structures demolished - 27 Harris County - Reimbursement Program GLO completed review of the closeout report and forwarded to the County requesting updates by July 15th, 2025. Harris County - Affordable Rental Program To date, sixteen (16) projects have been approved with a total of 2,374 units of which 2,154 will be LMI units. Three (3) new construction projects are under construction and are over 95% complete. Thirteen (13) projects are 100% construction complete and 100 % expensed and in the closeout phase. Measure Description - Q2 Projects Leased Up (Not yet Reportable in DRGR) - 1 Harris County - Single Family New Construction The County will close out 6 built inventory projects and is submitting revised project closeout reports; 3 projects are 100% expensed/closed in TIGR. 2 acreage sites are in construction phase. Vista/Orchard Place: Infrastructure construction is complete. Home construction has begun. Ella project: Infrastructure improvements are underway and is at 60% construction complete, and HC anticipates bidding out the Ella home construction in Q2 2025. Measure Description - Q2 Projects with Construction Completed - 2 Harris County - Commercial Buyout Program The Commercial Buyout Program has closed on thirty-one (31) of the thirty-two (32) properties which is ninety-seven percent (97%) of sites. Twenty-nine (29) sites have been demolished. Of the thirty-six (36) relocations, thirty-three (33) have relocated and three (3) are still pending relocation. Measure Description - Q2 Number of properties clos,ed (buyout parcels) - 1 Number of businesses relocated - 3 Number of structures demolished - 2 Harris County - Method of Distribution Infrastructure Program To date, of the twenty-three (23) approved projects, four (4) are under closeout review, eleven (11) are at 100% of construction complete and seven (7) are above 75% construction complete and one (1) is under 75% construction complete. Measure Description - Q2 Projects Completed (not yet reportable in DRGR) - 4 Harris County - Competitive Application Infrastructure Program To date, of the thirteen (13) approved projects, three (3) are in closeout review, five (5) are at 100% construction complete, four (4) are above 75% complete and one (1) is under 75% construction complete. Measure Description - Q2 Projects Completed (not yet reportable in DRGR) - 3 Harris County - Planning The twenty three (23) Planning Studies have been completed and 100% expensed and the final two (2) studies are completed with the final closeout expenditures will be captured in Q3 2025. Harris County - Public Services The final Public Service project, Generation Park On Demand Service (Micro transit) is complete and closeout activities are anticipated to begin August 2025.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2025-07-01 | 2025 Q4 | OVERALL NARRATIVE During the reporting period, the majority of programs are still underway, and the Disaster Recovery Reallocation Program round one contracts were executed and activities are currently underway. The GLO is performing a data reconciliation of all Single Family housing programs to verify project data and ensure accurate reporting in the DRGR system to prepare for program closeouts. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 942 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q3 2025, GLO completed 2 such reviews. Affordable Rental Program During the reporting period, the program had construction underway for two multifamily housing projects. Future quarters will bring more closeouts. Economic Revitalization Program The GLO is continuing to work on the closeout of this program, including formalizing the system of record, confirming completed activities, and completing the After-Action Report. Harris County Flood Control District The Harris County Flood Control District has ten (10) projects approved and underway, and there is one (1) project application under review. Homeowner Assistance Program During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q3, GLO was in the process of reviewing 0 projects for eligibility, had approved 0 Homeowner Assistance Program applications for assistance, and completed construction on 0 households. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Additionally, the GLO is actively reconciling costs for projects that received funding from both the Harvey and Mitigation allocations in the GLO system of record as well as DRGR. The GLO expects to resume reporting of accomplishments in subsequent quarters. Harvey State-managed City of Houston Homeowner Assistance Program During the reporting period, the City of Houston continued to make progress on ongoing projects. No households were completed during the quarter. Additionally, the GLO is actively reconciling costs for projects that received funding from both the Harvey and Mitigation allocations in the GLO system of record as well as DRGR. The GLO expects to resume reporting of accomplishments in subsequent quarters. Harvey State-managed Harris County Homeowner Assistance Program During the reporting period, the Harris County continued to make progress on ongoing projects. No households were completed during the quarter. Additionally, the GLO is actively reconciling costs for projects that received funding from both the Harvey and Mitigation allocations in the GLO system of record as well as DRGR. The GLO expects to resume reporting of accomplishments in subsequent quarters. The negative expenditure balance for the quarter is a result of this reconciliation. Subrecipient Infrastructure & Buyout/Acquisition Programs Local Infrastructure Program - 43 contracts are active, 57 are closed, and 108 are in vario, states of closeout review. Local Buyout Program - 6 contracts are active, 18 are closed, and 24 are in various states of closeout review. Harvey 5b Houston Programs Houston - Homeowners Assistance Program All draws in this quarter are for project delivery costs. All draws previously placed in Request for Information (RFI) status were approved. Houston - Single Family Development Program The GLO is expecting the City of Houston&apos;s closeout letter for SFDP this quarter. All costs this quarter were for implemenation and adminstration. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Of the 31 approved projects, the City of Houston has 1 project under construction, 3 projects with construction complete but not yet reportable in DRGR, and 27 projects completed, fully expended and reported. Measure Description - Q3 New Projects with Construction Completed (Not yet Reportable in DRGR) - 3 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The City of Houston currently has 2 projects (closed out) construction complete and fully expended and 3 projects construction complete. Measure Description - Q3 New Projects with Construction Completed (Not yet Reportable in DRGR) - 3 Houston - Homebuyer Assistance Program All expenses during the current quarter were for project implementation costs paid to the professional services vendor and GLO staff payroll. Houston - Homebuyer Assistance Program 2.0 The City of Houston submitted 53 applications for this quarter, with all 53 having been reviewed and approved by GLO. Measure Description - Q3 New Applications Submitted to GLO - 53 New Applications Approved by GLO - 53 New LMI Applications Approved by GLO - 34 New UN Applications Approved by GLO - 19 Houston - Buyout Program Overall, the City of Houston transferred 757 relocation files to date. During the past quarter, the Vendor updated GLO with new tenants that the City had unaccounted for. Out of the 757 relocation files, 324 tenants are ineligible/withdrawn from the program. 246 tenants have not been located. AECOM made payments to 93 relocation payments for this quarter. One property has been demolished and the 2 remaining properties are scheduled to be demolished by the end of this year. Measure Description - Q3 Number of Households Relocated during Quarter (Not yet reportable in DRGR) - 4 New Structures Demolished (Not yet Reportable in DRGR) - 4 Houston - Public Services The Public Services program is complete with the City and under GLO reconciliation. Houston - Economic Development Program During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Harvey Economic Development Program (HEDP). All projects are complete and GLO received and processed the final project delivery dra ,t the end of September 2025. Houston - Planning The GLO had vendor costs associated with part of the closeout for the Planning program and GLO salary costs. Harvey 5b Harris County Programs Harris County - Homeowner Assistance Program The closeout revisions were received by the County are under review. Harris County - Buyout and Acquisition Program For 2025 Q3: Three hundred and fifty-eight (358) buyout properties have been closed out of three hundred and sixty (360) properties. The program remains at ninety-nine precent (99%) of sites acquired. The buyout sites include five (5) MHU parks. Six hundred and fifty (650) of the six hundred and sixty-six (666) relocations have secured replacement housing (98%) and sixteen (16) are continuing in search of replacement housing. Three hundred and forty-nine (349) sites have demolition complete. Measure Description - Q3 Number of households relocated - 17 Number of structures demolished - 5 Harris County - Reimbursement Program The closeout revisions were received by the County are under review. Harris County - Affordable Rental Program All sixteen (16) projects have completed construction with six (6) 100% expensed and in closeout. The final 10 (ten) projects are pending final expenditures. Measure Description - Q3 Projects with Construction Completed (Not yet Reportable in DRGR) - 2 Harris County - Single Family New Construction 7 projects have been closed and are 100% expensed. Vista Model 1 projects are in various phases of construction and are expected to be completed by the end of 2025. Ella Infrastructure improvements are underway and are at 90% construction complete. Harris County - Commercial Buyout Program The Commercial Buyout Program has closed on 100% of the thirty-two (32) properties and twenty-nine (29) sites have been demolished. Of the thirty-six (36) relocations, thirty-three (33) have relocated and three (3) are still pending relocation. Measure Description - Q3 Number of properties closed (buyout parcels) - 1 Harris County - Method of Distribution Infrastructure Program Harris County has (23) approved projects with (20) at 100% construction complete, of those four (4) have closeout documents submitted under review. Two (2) projects are above 75% construction complete and one (1) is above 50% construction complete. Harris County - Competitive Application Infrastructure Program Harris County has the thirteen (13) approved projects with nine (9) projects at 100% construction complete, five (5) have closeout documents submitted under review, and four (4) are above 75% construction complete. Harris County - Planning The twenty three (23) Planning Studies have been completed and 100% expensed and the final (1) study are complete. The final closeout expenditures are pending from Harris County. Harris County - Public Services The final Public Service project, Generation Park On Demand Service (Micro transit) is complete and pending closeout documents f,rom Harris County.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2025-10-01 | 2026 Q1 | OVERALL NARRATIVE During the reporting period, all programs are in or nearing the closeout phase and the GLO is reviewing and reconciling costs in preparation. The majority of draws are coming from the Harris County and Houston direct allocation programs as the GLO is reimbursing the entities for completed projects. Additionally, the Local Infrastructure program collectively drew more than twelve million dollars as the still active contracts are completing or near completing construction. GLO&apos;s efforts to Affirmatively Furthering Fair Housing: To-date across all grants, GLO has completed 944 AFFH reviews of subrecipient and multifamily projects being considered for funding to determine whether projects are consistent with goals of affirmatively furthering fair housing. Within Q4 2025, GLO completed 2 such reviews. Affordable Rental Program During the reporting period, the program had construction underway for two multifamily housing projects. Future quarters will bring more closeouts. Additionally, 6 projects, previously awarded, were cancelled and funds drawn were recaptured and returned to HUD due to ineligible costs from incomplete construction. Economic Revitalization Program This program is completed, but financial costs are still being reconciled. During the reporting period, indirect cost reimbursement was conducted for salaries and wages expense for fiscal years 2021-2025. Harris County Flood Control District The Harris County Flood Control District has ten (10) projects approved and one (1) project application under review. One (1) approved project has construction underway. Homeowner Assistance Program During the reporting period, the Homeowner Assistance Program received 0 applications. As of the end of Q4, GLO was in the process of reviewing 0 projects for eligibility, had approved 0 Homeowner Assistance Program applications for assistance, and completed construction on 0 households. Some Projects being reviewed for eligibility may be duplicated in multiple quarter reports. Harvey State-managed City of Houston Homeowner Assistance Program During the reporting period, all households in this program&apos;s portfolio have completed construction. Currently, overall, 1,745 households received reconstruction/rehabilitation benefits. The GLO is continuing to reconcile this program for closeout, and as part of this, some households may transfer to be reported under the Mitigation Housing Oversubscription program, but the total number of households between all City of Houston state-managed programs will not change. Harvey State-managed Harris County Homeowner Assistance Program During the reporting period, all households in this program&apos;s portfolio have completed construction. Currently, overall, 384 households received reconstruction/rehabilitation benefits. The GLO is continuing to reconcile this program for closeout, and as part of this, some households may transfer to be reported under the Mitigation Housing Oversubscription program, but the total number of households between all Harris County state-managed programs will not change. Subrecipient Infrastructure & Buyout/Acquisition Programs Local Infrastructure Program - 38 contracts are activ,and 112 are in various states of closeout review. Local Buyout Program -2 contracts are active, 18 are closed, and 43 are in various states of closeout review. Harvey 5b Houston Direct Allocation Programs Houston - Homeowners Assistance Program During the reporting period, the GLO worked towards closeout with the City of Houston. Houston - Single Family Development Program The GLO is expecting the City of Houston&apos;s closeout letter for SFDP in the upcoming quarter. Houston - Multifamily Rental Program During the reporting period, the City of Houston continued to implement its Multifamily Program. Of the 31 approved projects, the City of Houston has 3 projects with construction complete but not yet reportable in DRGR, and 28 projects completed, fully expended and reported. Measure Description - Q4 New Projects with Construction Completed (Not yet Reportable in DRGR) - 3 Houston - Small Rental Program During the reporting period, the City of Houston continued to implement its Small Rental Program. The City of Houston currently has 5 projects completed Houston - Homebuyer Assistance Program The HbAP program is in final reconciliation with the GLO. Houston - Homebuyer Assistance Program 2.0 During the reporting period, the GLO received 89 applications and 19 were HbAP 2.0 projects were completed. Measure Description - Q4 New Applications Submitted to GLO - 89 New Applications Approved by GLO - 60 New LMI Applications Approved by GLO - 37 New UN Applications Approved by GLO - 23 New Homebuyer Households who have Received Down Payment Assistance (Not yet Reportable in DRGR) - 23 Houston - Buyout Program For this quarter, payments were made to 4 tenants for the Imperial Valley property. Expenses also accounted for the City of Houston&apos;s consulting fees and abatement for the Clarewood and Imperial Valley Property, administrative costs for the vendor, GLO payroll expenses, and the demolition of the Clarewood property. The Clarewood property was demolished November 7, 2025. Houston - Public Services The Public Services program is complete with the City and under GLO reconciliation. Houston - Economic Development Program During the reporting period, the GLO worked towards closeout with the City of Houston. Houston - Planning The Planning program is complete with the City and under GLO reconciliation. Harvey 5b Harris County Direct Allocation Programs Harris County - Homeowner Assistance Program The closeout revisions were received and are under review by the GLO. Harris County - Buyout and Acquisition Program Three hundred and fifty-eight (358) buyout properties have been closed out of three hundred and sixty (360) properties. The program remains at ninety-nine precent (99%) of sites acquired. The buyout sites include five (5) MHU parks. Six hundred and fifty-two (652) of the six hundred and sixty-six (666) relocations have secured replacem,ent housing at ninety-eight percent (98%) and twelve (12) are continuing in search of replacement housing. Three hundred and fifty-five (355) sites have demolition complete. Measure Description - Q4 Number of households relocated - 2 Number of structures demolished - 6 Harris County - Reimbursement Program The closeout revisions were received and are under review by the GLO. Harris County - Affordable Rental Program The seventeen (17) approved projects are 100% expensed with six (6) ready to closeout. Eleven (11) projects have construction complete and are pending final expenditures. Harris County - Single Family New Construction Seven (7) projects have been closed and are 100% expensed. Vista Model 1 projects are in various phases of construction and are expected to be completed late February 2026. Harris County is planning a walk-though of the property Mar/April 2026. Ella Infrastructure improvements are underway and the County is on track to complete construction by the end of February 2026. Harris County - Commercial Buyout Program The Commercial Buyout Program has closed on 100% of the thirty-two (32) properties and all thirty-two (32) sites have been demolished. Of the thirty-six (36) relocations, all thirty-six (36) have relocated and 100% complete. Measure Description - Q4 Number of businesses relocated - 3 Number of structures demolished - 3 Harris County - Method of Distribution Infrastructure Program Harris County has twenty-three (23) approved projects with three (3) at 100% expensed and ready for closeout. Eighteen (18) projects are above 75% expensed and two (2) are above 50% expensed Fifteen (15) of those have construction complete and are pending final expenditure reimbursements. Measure Description - Q4 Projects Completed (not yet reportable in DRGR) - 1 Harris County - Competitive Application Infrastructure Program Harris County has thirteen (13) approved projects with four (4) at 100% expensed and ready to closeout. Eight (8) projects are above 75% expensed and one (1) is above 50% expensed. Six (6) of those projects have construction complete and pending final expenditures reimbursements. Measure Description - Q4 Projects Completed (not yet reportable in DRGR) - 1 Harris County - Planning Harris County has submitted the Grant Closeout Report for its Planning Program. It is currently under review with the GLO Harris County - Public Services Harris County has submitted the Grant Closeout Report for its Public Service Program. It is currently under review with the GLO.
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2026-01-01 | 2026 Q2 | 0
P-17-TX-48-HIM1 | Texas | Texas - GLO | 2026-04-01 | 2026 Q3 | 0