## A32 - QPR - Activity Progress N
Page by:
Program: DR CDBG
Appropriation: 2017 Hurricanes Harvey, Irma and Maria
Grantee State: TX
Grantee: Texas - GLO
Grant: P-17-TX-48-HIM1
Activity Number | Activity Title | Activity Type | Activity Responsible Org | QPR Report Period Begin Date |  | QPR Activity Narrative (Abr)
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2019-04-01 | 2019 Q3
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2019-07-01 | 2019 Q4
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2019-10-01 | 2020 Q1 | During this period, Project Management Services were provided for the Local Infrastructure Program.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2020-01-01 | 2020 Q2 | 89382.76 - Payroll Allocation
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2020-04-01 | 2020 Q3 | Spending for this DRGR Activity is a combination of GLO payroll costs and Vendor Project Management services for the operations of the Local Infrastructure Program. These costs are captured here in the short term given changing DRGR Activity budgets for the program and will be distributed to individual subrecipient DRGR Activities in the future.77,367.51 - Payroll Allocation
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2020-07-01 | 2020 Q4 | 99737.97 - Payroll Allocations
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2020-10-01 | 2021 Q1 | $136216.28 - Payroll Allocations.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2021-01-01 | 2021 Q2 | 92510.98 - Payroll Allocations.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2021-04-01 | 2021 Q3 | Payroll Allocation
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2021-07-01 | 2021 Q4 | Project delivery costs. 269503.49 - Payroll Allocations.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2021-10-01 | 2022 Q1 | Holding activity for payroll and project delivery costs. 217534.82 - Payroll Allocations.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2022-01-01 | 2022 Q2 | 244117.07 - Payroll Allocations.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2022-04-01 | 2022 Q3 | 366667.32 - Payroll Allocations.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2022-07-01 | 2022 Q4 | Expenditures related to project management vendor assistance procured to support delivery of subrecipient programs. 250324.4 - Payroll allocation costs in support of activity delivery.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2022-10-01 | 2023 Q1 | Vendor costs associated with grant administration and support, as well as 494573.32 - Payroll allocation costs in support of activity delivery.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2023-01-01 | 2023 Q2 | Vendor costs associated with grant administration and support, as well as 250084.59 - Payroll allocation costs in support of activity delivery.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2023-04-01 | 2023 Q3 | Vendor costs associated with grant administration and support, as well as 504527.76 - State costs in support of activity delivery.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2023-07-01 | 2023 Q4 | Vendor costs associated with grant administration and support, as well as $352192.75 - State costs in support of activity delivery.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2023-10-01 | 2024 Q1 | Vendor costs associated with grant administration and support, as well as 108342.85 - State costs in support of activity delivery.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-01-01 | 2024 Q2 | Vendor costs associated with grant administration and support, as well as 101966.46 - Quarterly expenditure related to state costs in support of activity delivery.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended. Costs will be reallocated proportional amongst the grantee support activities.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-07-01 | 2024 Q4 | Final activity delivery costs that were in process prior to new activities created. Following this quarter, all costs will be revised to the applicable activities and this activity will be deleted.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-10-01 | 2025 Q1 | Final draws allowable under this activity. Following this quarter, costs will begin to be revised to the applicable grantee support activities that contain all activity delivery costs for the Local Infrastructure Program.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures to this activity were appropriately revised to the Grantee Support activities.
ADMIN[INF PD HOLDING] | Administration | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-04-01 | 2025 Q3 | Deobligated funds as costs previously applied to this activity is being reallocated to the Grantee Support activities for the Local Infrastructure Program.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2019-07-01 | 2019 Q4
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2020-01-01 | 2020 Q2 | 14759.84 - Payroll Allocation
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2020-04-01 | 2020 Q3 | Payroll Allocation
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2020-07-01 | 2020 Q4 | 16225.51 - Payroll Allocations
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2020-10-01 | 2021 Q1 | Payroll Allocations.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2021-01-01 | 2021 Q2 | Payroll Allocations.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2021-04-01 | 2021 Q3 | Payroll Allocations
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2021-07-01 | 2021 Q4 | Project delivery costs. Payroll Allocations.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2021-10-01 | 2022 Q1 | Payroll Allocations.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2022-01-01 | 2022 Q2 | Payroll Allocations.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2022-04-01 | 2022 Q3 | 69517.47 - Payroll Allocations.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2022-07-01 | 2022 Q4 | Expenditures related to project management vendor assistance procured to support delivery of subrecipient programs. 55888.23 - Payroll allocation costs in support of activity delivery.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2022-10-01 | 2023 Q1 | Vendor costs associated with grant administration and support, as well as 106847.08 - Payroll allocation costs in support of activity delivery.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2023-01-01 | 2023 Q2 | Vendor costs associated with grant administration and support, as well as 49804.55 - Payroll allocation costs in support of activity delivery.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2023-04-01 | 2023 Q3 | Vendor costs associated with grant administration and support, as well as 119342.21 - State costs in support of activity delivery.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2023-07-01 | 2023 Q4 | Vendor costs associated with grant administration and support, as well as $85213.56 - State costs in support of activity delivery.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2023-10-01 | 2024 Q1 | Vendor costs associated with grant administration and support, as well as 32280.33 - State costs in support of activity delivery.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2024-01-01 | 2024 Q2 | Vendor costs associated with grant administration and support, as well as 35549.95 - Quarterly expenditure related to state costs in support of activity delivery.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended. Costs will be reallocated proportional amongst the grantee support activities.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2024-07-01 | 2024 Q4 | Final activity delivery costs that were in process prior to new activities created. Following this quarter, all costs will be revised to the applicable activities and this activity will be deleted.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2024-10-01 | 2025 Q1 | Final draws allowable under this activity. Following this quarter, costs will begin to be revised to the applicable grantee support activities that contain all activity delivery costs for the Local Buyout and Acquisition Program.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures to this activity were appropriately revised to the Grantee Support activities.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2025-04-01 | 2025 Q3 | Deobligated funds as costs previously applied to this activity is being reallocated to the Grantee Support activities for the Local Buyout and Acquisition Program.
ADMIN[LBAP PD HOLDING] | Administration | Acquisition - buyout of residential properties | Texas General Land Office | 2025-07-01 | 2025 Q4 | Reduced the activity budget and obligation to what has been drawn previously. The GLO continues to work to revise these costs to the applicable activities and then cancel this placeholder.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2018-07-01 | 2018 Q4 | During the reporting period the Texas General Land Office continued the administration of the Harvey 5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2018-10-01 | 2019 Q1
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2019-01-01 | 2019 Q2 | During the reporting period the Texas General Land Office continued the administration of the Harvey grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period the Texas General Land Office continued the administration of the Harvey 5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period the Texas General Land Office continued the administration of the Harvey 5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, the Texas General Land Office continued the administration of the Harvey 5B grant. Negative expenditure is the result of a correction to payments made prior to the activities being available to draw at the start of the grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period the Texas General Land Office continued the administration of the Harvey 5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, the Texas General Land Office continued the administration of the Harvey 5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period the Texas General Land Office continued the administration of the Harvey 5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period the Texas General Land Office continued the administration of the Harvey5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, the Texas General Land Office continued the administration of the Harvey5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2021-04-01 | 2021 Q3 | During the reporting period the Texas General Land Office continued the administration of the Harvey5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2021-07-01 | 2021 Q4 | During the reporting period, the Texas General Land Office continued the administration of the Harvey 5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2021-10-01 | 2022 Q1 | During the reporting period the Texas General Land Office continued the administration of the Harvey5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2022-01-01 | 2022 Q2 | During the reporting period the Texas General Land Office continued the administration of the Harvey5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2022-04-01 | 2022 Q3 | During the reporting period the Texas General Land Office continued the administration of the Harvey5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2022-07-01 | 2022 Q4 | During the reporting period the Texas General Land Office continued the administration of the Harvey5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2022-10-01 | 2023 Q1 | During the reporting period the Texas General Land Office continued the administration of the Harvey5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2023-01-01 | 2023 Q2 | During the reporting period the Texas General Land Office continued the administration of the Harvey5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2023-04-01 | 2023 Q3 | During the reporting period the Texas General Land Office continued the administration of the Harvey5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2023-07-01 | 2023 Q4 | During the reporting period the Texas General Land Office continued the administration of the Harvey5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2023-10-01 | 2024 Q1 | During the reporting period the Texas General Land Office continued the administration of the Harvey5B grant. Total Disbursed amount does not equal the summation of vouchers completed. Adjustment entered for quarterly expenditures in order for Total Funds Expended to Total Disbursed as supported by the F45 voucher report.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2024-01-01 | 2024 Q2 | During the reporting period the Texas General Land Office continued the administration of the Harvey5B grant. Total Disbursed amount does not equal the summation of vouchers completed. Quarterly expenditures entered in order for Total Funds Expended to equal Total Disbursed as supported by the F45 voucher report.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2024-04-01 | 2024 Q3 | Continued administration services for the Harvey5B grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2024-07-01 | 2024 Q4 | Final activity delivery costs that were in process prior to new activities created. Following this quarter, all costs will be revised to the applicable activities and this activity will be deleted.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2024-10-01 | 2025 Q1 | Continued administration of the Hurricane Harvey 5b grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2025-01-01 | 2025 Q2 | Continued administration of the Hurricane Harvey 5b grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2025-04-01 | 2025 Q3 | Continued administration of the Hurricane Harvey 5b grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2025-07-01 | 2025 Q4 | The GLO continued administration of the Hurricane Harvey $5b grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2025-10-01 | 2026 Q1 | The GLO continued administration of the Hurricane Harvey $5b grant.
ADMINISTRATION | Administration | Administration | Texas General Land Office | 2026-01-01 | 2026 Q2
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2019-04-01 | 2019 Q3
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2019-07-01 | 2019 Q4 | Construction underway on 23 ARP projects. None completed/closed out this quarter.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2019-10-01 | 2020 Q1 | All projects that received allocations are either currently being processed to execute contracts or under construction throughout Q4 2019.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the quarter, there were 70 Projects Total - All on schedule to be completed by or before Q4 2021. 54403.01 - Payroll Allocation
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting perod, there were 69 HMID projects in total, construction underway or reaching completion on 55, with 14 due to start construction this coming quarter. 42,370.77 - Payroll Allocation
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2020-07-01 | 2020 Q4 | 67 HMID projects in total, construction complete on 6, construction underway on 50, with 11 due to start construction in Q4. 51908.04 - Payroll Allocations
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2020-10-01 | 2021 Q1 | Construction is still pressing ahead on all projects with executed contracts. Delays have been encountered due to COVID impact on materials and manpower but no projects have suffered significant delays or indicated they are unable to complete their contractual requirements $96855.38 - Payroll Allocations.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2021-01-01 | 2021 Q2 | Construction is still pressing ahead on all projects with executed contracts. Delays have been encountered due to COVID impact on materials and manpower but no projects have suffered significant delays or indicated they are unable to complete their contractual requirements. All but 1 HMID projects are now either under construction or have substantially completed construction. 77789.45 - Payroll Allocations.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2021-04-01 | 2021 Q3 | Construction is still pressing ahead on all projects with executed contracts. Delays have been encountered due to COVID impact on materials and manpower but no projects have suffered significant delays or indicated they are unable to complete their contractual requirements. All but 1 HMID projects are now either under construction or have substantially completed construction. 85889.92 - Payroll Allocations
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2021-07-01 | 2021 Q4 | Projects under construction and draws being submitted monthly for construction reimbursement. 97567.49 - Payroll Allocations.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2021-10-01 | 2022 Q1 | Projects under construction and regularly submitting reimbursement requests. 56262.77 - Payroll Allocations.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2022-01-01 | 2022 Q2 | Construction continues on multiple projects as we look to complete construction on the Harvey ARP portfolio by the end of 2023. 63366.17 - Payroll Allocations.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2022-04-01 | 2022 Q3 | Construction continues on multiple projects as we look to complete construction on the Harvey ARP portfolio by the end of 2023. 97813.05 - Payroll Allocations.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2022-07-01 | 2022 Q4 | Construction continues on multiple projects as we look to complete construction on the Harvey ARP portfolio by the end of 2023. 39533.32 - Payroll allocation costs in support of activity delivery.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2022-10-01 | 2023 Q1 | Draws paid for construction costs for projects not yet complete, as well as retainage payments for those projects recently completed and moving towards closeout. 110563.22 - Payroll allocation costs in support of activity delivery.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2023-01-01 | 2023 Q2 | Of 65 contracted projects, 13 remain under construction and funds continue to be reimbursed for both projects under construction and for retainage draws on completed projects. Ingleside Village, Silverleaf at Rockport and Valley View Estates all reached substantial construction during Q1 2023. 77563.37 - Payroll allocation costs in support of activity delivery.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2023-04-01 | 2023 Q3 | 9 projects remain under construction, the rest are awaiting closeout. ARP is inputting all previously uncounted beneficiaries for Q2 2023 so the report is heretofore correct. 119 were completed in 2021 and 387 were completed in 2022. 174111.47 - State costs in support of activity delivery.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2023-07-01 | 2023 Q4 | 9 projects remain under construction, the rest are awaiting closeout. ARP is regularly closing contracts which reflect in Q3 and will continue to do so as contracts close. $130583.63 - State costs in support of activity delivery.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2023-10-01 | 2024 Q1 | Another 3 projects have finished construction, leaving only 6 active. Multiple contracts were closed during the reporting period and ARP expects more to be closed in Q1 2024. 51553.1 - State costs in support of activity delivery. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2024-01-01 | 2024 Q2 | 8 projects were closed in Q1, with multiple in closeout process. 4 Remain under construction and the other 15 are in closeout process. 44778.16 - Quarterly expenditure related to state costs in support of activity delivery.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the reporting period, the developers submitted grant closeout documents for 2 projects, a total of 41 of 80 are now closed.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2024-07-01 | 2024 Q4 | During the reporting period, the Affordable Rental Program had more than 50% of construction complete for 3 of its projects. The program also had grant closeout documents under review for 12 projects. The Silverleaf at Orange project was administratively closed. 514039.95 - Quarterly expenditure for state costs in support of activity delivery.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2024-10-01 | 2025 Q1 | During the reporting period, the program completed additional projects and only 2 remain under construction at the close of 2024. The program administratively closed an additional 2 projects. 176593.69 - Quarterly expenditure for state costs in support of activity delivery.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, one project was administratively closed and two remain under construction. 198259.02 - Quarterly expenditure for state costs in support of activity delivery.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, draws were paid to 3 projects for project delivery. One of these projects is currently under construction. 78239.56 - State costs in support of activity delivery.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, 2 projects were construction underway. 28335.97 - State costs in support of activity delivery.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, 2 projects were still underway. No new projects were completed. 5 projects previously in this portfolio were cancelled and funds were recaptured and returned to HUD due to becoming ineligible from incomplete construction. 39700.46 - State costs in support of activity delivery.
ARP_HMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2026-01-01 | 2026 Q2
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2019-04-01 | 2019 Q3
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2019-07-01 | 2019 Q4
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2019-10-01 | 2020 Q1 | All projects that received allocations are either currently being processed to execute contracts or under construction throughout Q4 2019.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the quarter, there were 9 projects total. All on schedule to be completed by or before Q4 2021. 3102.11 - Payroll Allocation
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting perod, there were 9 SMID projects in total, construction underway on 7 and the final 2 will begin construction this coming quarter. 2,522.39 Payroll Allocation
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2020-07-01 | 2020 Q4 | 9 SMID projects in total, construction complete on 2, construction underway on 5 and the final 2 will begin construction in Q4. 3050.66 - Payroll Allocations
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2020-10-01 | 2021 Q1 | Construction is still pressing ahead on all projects with executed contracts. Delays have been encountered due to COVID impact on materials and manpower but no projects have suffered significant delays or indicated they are unable to complete their contractual requirements $5855.85 - Payroll Allocations.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2021-01-01 | 2021 Q2 | Construction is still pressing ahead on all projects with executed contracts. Delays have been encountered due to COVID impact on materials and manpower but no projects have suffered significant delays or indicated they are unable to complete their contractual requirements. Of the 9 SMID projects in the Harvey portfolio, 2 have substantially completed construction, ready to officially closeout in Q2 2021, and the remaining 7 are all under construction and making good progress. 4671.82 - Payroll Allocations.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2021-04-01 | 2021 Q3 | Construction is still pressing ahead on all projects with executed contracts. Delays have been encountered due to COVID impact on materials and manpower but no projects have suffered significant delays or indicated they are unable to complete their contractual requirements. 6 projects are under construction while 3 are complete. 5108.61 - Payroll Allocations
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2021-07-01 | 2021 Q4 | Projects under construction and draws being submitted monthly for construction reimbursement. 5795.99 - Payroll Allocations.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2021-10-01 | 2022 Q1 | Projects under construction and regularly submitting reimbursement requests. 3345.33 - Payroll Allocations.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2022-01-01 | 2022 Q2 | Construction continues on multiple projects as we look to complete construction on the Harvey ARP portfolio by the end of 2023. 3769.99 - Payroll Allocations.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2022-04-01 | 2022 Q3 | Construction continues on multiple projects as we look to complete construction on the Harvey ARP portfolio by the end of 2023. 4877.81 - Payroll Allocations.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2022-07-01 | 2022 Q4 | Construction continues on multiple projects as we look to complete construction on the Harvey ARP portfolio by the end of 2023. 2023.84 - Payroll allocation costs in support of activity delivery.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2022-10-01 | 2023 Q1 | Draws paid for construction costs for projects not yet complete, as well as retainage payments for those projects recently completed and moving towards closeout. 5566.01 - Payroll allocation costs in support of activity delivery.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2023-01-01 | 2023 Q2 | All seven SMID projects are now complete and leasing up while the ARP team works to move these projects into the long-term compliance monitoring program. 3038.7 - Payroll allocation costs in support of activity delivery.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2023-04-01 | 2023 Q3 | All projects have completed construction and are awaiting closeout. ARP is inputting all previously uncounted beneficiaries for Q2 2023 so the report is heretofore correct. An additional 8 were completed in 2022. 5737.18 - State costs in support of activity delivery.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2023-07-01 | 2023 Q4 | All projects have completed construction and are being completed and closed out. $4325.67 - State costs in support of activity delivery.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2023-10-01 | 2024 Q1 | All projects in SMID are completed and continue to be closed. State funds spent for administration of the contracts. 1726.25 - State costs in support of activity delivery.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2024-01-01 | 2024 Q2 | No closeouts this quarter, one project remains to receive retainage. 1475.49 - Quarterly expenditure related to state costs in support of activity delivery.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2024-07-01 | 2024 Q4 | No closeouts this quarter, the one project remaining to be closed. Quarterly expenditure related to state costs in support of activity delivery. 4895.15 - Quarterly expenditure for state costs in support of activity delivery.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2024-10-01 | 2025 Q1 | All contracts are closed or cancelled.
ARP_SMID_LMI | Affordable Rental Program | Affordable Rental Housing | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, all contracts have completed construction and are closed. The GLO continues to work on closing the remaining projects in this program and reconciliation. 1 project previously in this portfolio were cancelled and funds were recaptured and returned to HUD due to becoming ineligible from incomplete construction. 2670.71 - State costs in support of activity delivery.
DRRP_HMID_LMI_GranteeSupport[H5b]_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2026-01-01 | 2026 Q2
DRRP_HMID_LMI_GranteeSupport[H5b]_MFH | Multifamily Rental Housing | Affordable Rental Housing | Texas General Land Office | 2026-01-01 | 2026 Q2
DRRP_HMID_LMI_GranteeSupport[H5b]_SI | Street Improvements | Construction/reconstruction of streets | Texas General Land Office | 2026-01-01 | 2026 Q2
DRRP_HMID_LMI_GranteeSupport[H5b]_WSF | Water and Sewer Facility Improvements | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2026-01-01 | 2026 Q2
DRRP[H5b]_HMID_LMH_25-142-001-F191_GalvestonHA_MF | Multifamily Rehabilitation | Affordable Rental Housing | Galveston Housing Authority | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMH_25-142-002-F206_HarrisCoHA_MF | Multifamily New Construction | Affordable Rental Housing | Harris County Housing Authority | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMH_25-142-003-F207_PAHA_MF | Multifamily Rehabilitation | Affordable Rental Housing | Housing authority of the city of port arthur | 2025-10-01 | 2026 Q1 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMH_25-142-004-F208_PAHA_MF | Multifamily Rehabilitation | Affordable Rental Housing | Housing authority of the city of port arthur | 2025-10-01 | 2026 Q1 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMH_25-142-005-F209_PAHA_MF | Multifamily Rehabilitation | Affordable Rental Housing | Housing authority of the city of port arthur | 2025-10-01 | 2026 Q1 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-001-F192_Ames_SI | Street Improvements | Construction/reconstruction of streets | Ames | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-001-F192_Ames_SI | Street Improvements | Construction/reconstruction of streets | Ames | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Ames completed environmental review for its street improvements project.
DRRP[H5b]_HMID_LMI_25-143-001-F192_Ames_SI | Street Improvements | Construction/reconstruction of streets | Ames | 2026-01-01 | 2026 Q2
DRRP[H5b]_HMID_LMI_25-143-002-F338_Ames_F&D | Flood and Drainage Improvements | Rehabilitation/reconstruction of a public improvement | Ames | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-002-F338_Ames_F&D | Flood and Drainage Improvements | Rehabilitation/reconstruction of a public improvement | Ames | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Ames had environmental review underway for its flood and Drainage improvements project.
DRRP[H5b]_HMID_LMI_25-143-002-F338_Ames_F&D | Flood and Drainage Improvements | Rehabilitation/reconstruction of a public improvement | Ames | 2026-01-01 | 2026 Q2
DRRP[H5b]_HMID_LMI_25-143-003-F339_Baytown_F&D | Flood and Drainage Improvements | Rehabilitation/reconstruction of a public improvement | City of Baytown | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-004-F340_Baytown_SI | Street Improvements | Construction/reconstruction of streets | City of Baytown | 2026-01-01 | 2026 Q2
DRRP[H5b]_HMID_LMI_25-143-005-F341_Cleveland_SF | Sewer Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-005-F341_Cleveland_SF | Sewer Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2026-01-01 | 2026 Q2
DRRP[H5b]_HMID_LMI_25-143-006-F342_Cleveland_WF | Water Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-006-F342_Cleveland_WF | Water Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2026-01-01 | 2026 Q2
DRRP[H5b]_HMID_LMI_25-143-007-F343_Cleveland_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-007-F343_Cleveland_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2026-01-01 | 2026 Q2
DRRP[H5b]_HMID_LMI_25-143-008-F344_Dayton_SI | Street Improvements | Construction/reconstruction of streets | Dayton | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-008-F344_Dayton_SI | Street Improvements | Construction/reconstruction of streets | Dayton | 2025-10-01 | 2026 Q1 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-008-F344_Dayton_SI | Street Improvements | Construction/reconstruction of streets | Dayton | 2026-01-01 | 2026 Q2
DRRP[H5b]_HMID_LMI_25-143-009-F345_Dayton_SI | Street Improvements | Construction/reconstruction of streets | Dayton | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-009-F345_Dayton_SI | Street Improvements | Construction/reconstruction of streets | Dayton | 2026-01-01 | 2026 Q2
DRRP[H5b]_HMID_LMI_25-143-010-F346_Jasper_SF | Sewer Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Jasper | 2025-10-01 | 2026 Q1 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-010-F346_Jasper_SF | Sewer Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Jasper | 2026-01-01 | 2026 Q2
DRRP[H5b]_HMID_LMI_25-143-011-F347_Jasper_WF | Water Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Jasper | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-011-F347_Jasper_WF | Water Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Jasper | 2026-01-01 | 2026 Q2
DRRP[H5b]_HMID_LMI_25-143-012-F348_Kirbyville_SF | Sewer Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-013-F349_Kirbyville_SF | Sewer Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-013-F349_Kirbyville_SF | Sewer Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2026-01-01 | 2026 Q2
DRRP[H5b]_HMID_LMI_25-143-014-F350_Pasadena_SF | Sewer Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Pasadena, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-015-F351_Pasadena_SI | Street Improvements | Construction/reconstruction of streets | Pasadena, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
DRRP[H5b]_HMID_LMI_25-143-016-F352_Pasadena_SI | Street Improvements | Construction/reconstruction of streets | Pasadena, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2019-04-01 | 2019 Q3
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2019-10-01 | 2020 Q1 | Program development ongoing.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period no new projects closed and there are 30 underway. 8783.19 - Payroll Allocation
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2020-04-01 | 2020 Q3 | Contract milestone 1: Program Development. 13,509.69 - Payroll Allocation
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2020-07-01 | 2020 Q4 | Program Administration costs. 17671.5 - Payroll Allocations
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2020-10-01 | 2021 Q1 | Payments for Phase I - Program Development and Phase II - Marketing and Outreach. $61730.26 - Payroll Allocations.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2021-01-01 | 2021 Q2 | Application eligibility and recommended award amount are now being submitted by the vendor. 48074.22 - Payroll Allocations.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2021-04-01 | 2021 Q3 | Current awards are approximately 90% HMID and 10% SMID. Expenditures are a fraction of total awards because awards are made in partial payments due to HUD&apos;s requirement that grant funding cannot be provided in advance of need. 61434.13 - Payroll Allocations
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2021-07-01 | 2021 Q4 | Administration fees and grant awards provided to applicants. 77673.4 - Payroll Allocations. Beneficiaries for this activity will be reported in the following quarters as Action Plan projected measures were incorrect and missing values.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2021-10-01 | 2022 Q1 | Awards are being made to businesses to support job creation and retention. 42197.44 - Payroll Allocations.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2022-01-01 | 2022 Q2 | Awards are being made to businesses to support job creation and retention. 20564.22 - Payroll Allocations.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2022-04-01 | 2022 Q3 | Awards are being made to businesses to support job creation and retention. 30385.1 - Payroll Allocations.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2022-07-01 | 2022 Q4 | Awards are being made to businesses to support job creation and retention. 17568.47 - Payroll allocation costs in support of activity delivery. Corrections made to performance measures to get an accurate to date figure.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2022-10-01 | 2023 Q1 | Awards are continuing to be made to businesses to support job creation and retention, as well as oversight of previously awarded funds to ensure progress on job creation and retention. 36414.31 - Payroll allocation costs in support of activity delivery.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2023-01-01 | 2023 Q2 | 83 HMID applications were approved by GLO in Q1 2023 totaling $25,700,000.00. Expenditures include 1st, 2nd and 3rd grant installment payments. 18201.66 - Payroll allocation costs in support of activity delivery.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2023-04-01 | 2023 Q3 | 28 HMID applications were approved by GLO in Q2 2023 totaling $4,000,000.00. Expenditures include 1st, 2nd and 3rd grant installment payments. 40324.7 - State costs in support of activity delivery.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2023-07-01 | 2023 Q4 | One HMID application was approved for $150,000 to create two new jobs and retain one job. Expenditures include 1st, 2nd, and 3rd installments. $30861.59 - State costs in support of activity delivery.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2023-10-01 | 2024 Q1 | No additional HMID applications were approved. Expenditures include 2nd and 3rd installment payments for ongoing projects. 10175.48 - State costs in support of activity delivery.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2024-01-01 | 2024 Q2 | No additional HMID applications were approved. Expenditures include 2nd and 3rd installment payments for ongoing projects. 8351.81 - Quarterly expenditure related to state costs in support of activity delivery.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2024-04-01 | 2024 Q3 | No additional HMID applications were approved. Expenditures include 2nd and 3rd installment payments for ongoing projects.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2024-07-01 | 2024 Q4 | During the reporting period, the program has largely concluded and is able to report all accomplishments and beneficiaries. Over the following quarters, finals payments will occur and the program will enter the closeout phase to collect all required documentation. 74446.29 - Quarterly expenditure for state costs in support of activity delivery.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2024-10-01 | 2025 Q1 | During the quarter, adjustments to previous vouchers were conducted, increasing the disbursed amount. This program is in the closeout phase as final indirect costs continue to be drawn. 10721.63 - Quarterly expenditure for state costs in support of activity delivery.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2025-01-01 | 2025 Q2 | This program is in the closeout phase as final indirect costs continue to be drawn and the GLO works to collect all required documentation and close the program. 3045.5 - Quarterly expenditure for state costs in support of activity delivery.
ERP_HMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, indirect cost reimbursement was conducted for salaries and wages expense for fiscal years 2021-2025
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2019-04-01 | 2019 Q3
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2019-10-01 | 2020 Q1 | Program development ongoing.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period no new projects closed and there are 10 underway. 2195.80 - Payroll Allocation
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2020-04-01 | 2020 Q3 | Contract milestone 2: Program Outreach and Marketing. 1,706.83 - Payroll Allocation
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2020-07-01 | 2020 Q4 | Program Administration costs. 832.98 - Payroll Allocations
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2020-10-01 | 2021 Q1 | Payments for Phase I - Program Development and Phase II - Marketing and Outreach. $1443.17 - Payroll Allocations.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2021-01-01 | 2021 Q2 | Application eligibility and recommended award amount are now being submitted by the vendor. 1122.94 - Payroll Allocations.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2021-04-01 | 2021 Q3 | Current awards are approximately 90% HMID and 10% SMID. Expenditures are a fraction of total awards because awards are made in partial payments due to HUD&apos;s requirement that grant funding cannot be provided in advance of need. 1433.37 - Payroll Allocations
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2021-07-01 | 2021 Q4 | Administration fees and grant awards provided to applicants. 3672.28 - Payroll Allocations. Beneficiaries for this activity will be reported in the following quarters as Action Plan projected measures were incorrect and missing values.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2021-10-01 | 2022 Q1 | Awards are being made to businesses to support job creation and retention. 3105.24 - Payroll Allocations.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2022-01-01 | 2022 Q2 | Awards are being made to businesses to support job creation and retention. 1394.37 - Payroll Allocations.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2022-04-01 | 2022 Q3 | Awards are being made to businesses to support job creation and retention. 1066.2 - Payroll Allocations.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2022-07-01 | 2022 Q4 | Awards are being made to businesses to support job creation and retention. 2800.76 - Payroll allocation costs in support of activity delivery. Corrections made to performance measures to get an accurate to date figure.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2022-10-01 | 2023 Q1 | Awards are continuing to be made to businesses to support job creation and retention, as well as oversight of previously awarded funds to ensure progress on job creation and retention. 3462.05 - Payroll allocation costs in support of activity delivery.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2023-01-01 | 2023 Q2 | No SMID applications were approved by GLO in Q1 2023. Expenditures include 2nd and 3rd grant installment payments. 3389.87 - Payroll allocation costs in support of activity delivery.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2023-04-01 | 2023 Q3 | One SMID application was approved by GLO in Q1 2023 totaling $200,000.00. Expenditures include 2nd and 3rd grant installment payments. 714.07 - State costs in support of activity delivery.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2023-07-01 | 2023 Q4 | No SMID applications were approved. Costs related to 2nd and 3rd installments. $461.74 - State costs in support of activity delivery.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2023-10-01 | 2024 Q1 | No additional SMID applications were approved. Expenditures include 2nd and 3rd installment payments for ongoing projects. 100.71 - State costs in support of activity delivery.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2024-01-01 | 2024 Q2 | No additional SMID applications were approved. Expenditures include 2nd and 3rd installment payments for ongoing projects. 110.86 - Quarterly expenditure related to state costs in support of activity delivery.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2024-04-01 | 2024 Q3 | No additional SMID applications were approved. Expenditures include 2nd and 3rd installment payments for ongoing projects.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2024-07-01 | 2024 Q4 | During the reporting period, the program has largely concluded and is able to report all accomplishments and beneficiaries. Over the following quarters, finals payments will occur and the program will enter the closeout phase to collect all required documentation. 1085.75 - Quarterly expenditure for state costs in support of activity delivery.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2024-10-01 | 2025 Q1 | This program is in the closeout phase as final indirect costs continue to be drawn. 149.07 - Quarterly expenditure for state costs in support of activity delivery.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2025-01-01 | 2025 Q2 | This program is in the closeout phase as final indirect costs continue to be drawn and the GLO works to collect all required documentation and close the program. 19.4 - Quarterly expenditure for state costs in support of activity delivery.
ERP_SMID_LMI | Economic Revitalization Program | Econ. development or recovery activity that creates/retains jobs | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, indirect cost reimbursement was conducted for salaries and wages expense for fiscal years 2021-2025
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 0 additional projects were completed of 2 total projects. 0 projects are underway. 120.09 - Payroll Allocation
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 1 additional projects were completed of 5 total projects. 4 projects are underway. 247.00 - Payroll Allocation
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 5 additional projects were completed of 7 total projects. 1 projects are underway. 415.2 - Payroll Allocations
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 6 additional projects were completed of 10 total projects. 1 projects are underway. $784.68 - Payroll Allocations.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 1 additional projects were completed of 2 total projects. 1 projects are underway. 638.72 - Payroll Allocations.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 1 additional projects were completed out of 2 total projects managed during the reporting period. 1 projects are underway. 508.16 - Payroll Allocations.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 1 additional projects were completed out of 1 total projects managed during the reporting period. 0 projects are underway. 431.5 - Payroll Allocations.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 0 additional projects were completed out of 1 total projects managed during the reporting period. 1 projects are underway. 380.73 - Payroll Allocations.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 0 additional projects were completed out of 1 total projects managed during the reporting period. 1 projects are underway. 286.42 - Payroll Allocations.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 1 additional projects were completed out of 2 total projects managed during the reporting period. 1 projects are underway. 422.98 - Payroll Allocations.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 1 additional projects were completed out of 1 total projects managed during the reporting period. 0 projects are underway. 301.31 - Payroll allocation costs in support of activity delivery.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 590.33 - Payroll allocation costs in support of activity delivery.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 377.16 - Payroll allocation costs in support of activity delivery.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | Activities are underway, no reportable changes during this quarter. 765.12 - State costs in support of activity delivery.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $618.58 - State costs in support of activity delivery.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter 289.18 - State costs in support of activity delivery.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 335.56 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 3242.48 - Quarterly expenditure for state costs in support of activity delivery.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter.
HAP[AACOG]_SMID_LMI | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 211.41 - State costs in support of activity delivery.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 0 additional projects were completed of 1 total projects. 1 projects are underway. 60.05 - Payroll Allocation
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 1 additional project was completed of 1 total projects. 0 projects are underway. 95.26 - Payroll Allocation
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 1 additional projects were completed of 3 total projects. 0 projects are underway. 138.4 - Payroll Allocations
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 2 additional projects were completed of 4 total projects. 1 projects are underway. $261.58 - Payroll Allocations.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 1 additional projects were completed of 1 total projects. 0 projects are underway. 194.28 - Payroll Allocations.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 0 additional projects were completed out of 0 total projects managed during the reporting period. 0 projects are underway. 153.33 - Payroll Allocations.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | Activities are underway, no reportable changes during this quarter. 137.36 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | Activities are underway, no reportable changes during this quarter. 108.25 - Payroll Allocations.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | Activities are underway, no reportable changes during this quarter. 71.62 - Payroll Allocations.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | Activities are underway, no reportable changes during this quarter. 115.92 - Payroll Allocations.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | Activities are underway, no reportable changes during this quarter. 53.22 - Payroll allocation costs in support of activity delivery.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 124.48 - Payroll allocation costs in support of activity delivery.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | During the reporting period, the activity budget and obligation was reduced.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter.
HAP[AACOG]_SMID_UN | HAP - AACOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 58.72 - State costs in support of activity delivery.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 1 project is underway.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 1 project(s) was underway
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 2 project(s) was underway.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 2 additional projects were completed of 2 total projects. 0 projects are underway. Correction to split costs on previous payments.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 2 additional projects were completed of 2 total projects. 0 projects are underway. 190.51 - Payroll Allocation
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 2 additional projects were completed of 2 total projects. 0 projects are underway. 276.79 - Payroll Allocations
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 2 additional projects were completed of 6 total projects. 0 projects are underway. $348.74 - Payroll Allocations.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 0 additional projects were completed of 1 total projects. 1 projects are underway. 319.35 - Payroll Allocations.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 1 additional projects were completed out of 3 total projects managed during the reporting period. 2 projects are underway. 260.11 - Payroll Allocations
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 2 additional projects were completed out of 2 total projects managed during the reporting period. 0 projects are underway. 215.74 - Payroll Allocations.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 0 additional projects were completed out of 0 total projects managed during the reporting period. 0 projects are underway. 174.18 - Payroll Allocations.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | Activities are underway, no reportable changes during this quarter. 125.32 - Payroll Allocations.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | Activities are underway, no reportable changes during this quarter. 196.76 - Payroll Allocations.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | Activities are underway, no reportable changes during this quarter. 106.38 - Payroll allocation costs in support of activity delivery.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 231.68 - Payroll allocation costs in support of activity delivery.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 99.26 - Payroll allocation costs in support of activity delivery.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | Activities are underway, no reportable changes during this quarter. 208.7 - State costs in support of activity delivery.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $171.7 - State costs in support of activity delivery.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 86.59 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 632.47 - Quarterly expenditure for state costs in support of activity delivery.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter.
HAP[BVCOG]_SMID_LMI | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 93.96 - State costs in support of activity delivery.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During thre reporting period, 1 project is underway.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 1 project(s) was underway
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 1 project(s) was underway.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 1 additional projects were completed of 1 total projects. 0 projects are underway. 40.81 - Payroll Allocation
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 1 additional project was completed of 1 total projects. 0 projects are underway. 38.21 - Payroll Allocation
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 1 additional projects were completed of 1 total projects. 0 projects are underway. 46.14 - Payroll Allocations
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 1 additional projects were completed of 2 total projects. 0 projects are underway. $87.2 - Payroll Allocations.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | Projects have not begun and are in the planning stage. 69.21 - Payroll Allocations.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | Projects have not begun and are in the planning stage. 46.58 - Payroll Allocations
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | Activities are underway, no reportable changes during this quarter. 30.81 - Payroll Allocations.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | Activities are underway, no reportable changes during this quarter. 24.86 - Payroll Allocations.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 0 additional projects were completed out of 0 total projects managed during the reporting period. 0 projects are underway. 17.92 - Payroll Allocations.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | Activities are underway, no reportable changes during this quarter. 53.92 - Payroll Allocations.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | Activities are underway, no reportable changes during this quarter. 35.49 - Payroll allocation costs in support of activity delivery.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 71.54 - Payroll allocation costs in support of activity delivery.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | During the reporting period, the activity budget and obligation was reduced.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter.
HAP[BVCOG]_SMID_UN | HAP - BVCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 23.49 - State costs in support of activity delivery.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period 14 applications where received, none have been approved. During the reporting period, 2 projects are underway.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 2 project(s) was underway
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 2 project(s) was underway.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 1 additional projects were completed of 2 total projects. 1 projects are underway. 160.90 - Payroll Allocation
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 1 additional project was completed of 4 total projects. 1 projects are underway. 228.72 - Payroll Allocation
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 2 additional projects were completed of 4 total projects. 1 projects are underway. 322.92 - Payroll Allocations
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 3 additional projects were completed of 5 total projects. 0 projects are underway. $435.96 - Payroll Allocations.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | Projects have not begun and are in the planning stage. 319.35 - Payroll Allocations.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | Projects have not begun and are in the planning stage. 260.11 - Payroll Allocations
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | Activities are underway, no reportable changes during this quarter. 215.74 - Payroll Allocations.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | Activities are underway, no reportable changes during this quarter. 174.18 - Payroll Allocations.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | Activities are underway, no reportable changes during this quarter 125.31 - Payroll Allocations / Correction to payments out of incorrect DRGR activities.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | Activities are underway, no reportable changes during this quarter. 215.56 - Payroll Allocations.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | Activities are underway, no reportable changes during this quarter. 141.82 - Payroll allocation costs in support of activity delivery.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 285.93 - Payroll allocation costs in support of activity delivery.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 138.96 - Payroll allocation costs in support of activity delivery.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | Activities are underway, no reportable changes during this quarter. 209.04 - State costs in support of activity delivery.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $152.09 - State costs in support of activity delivery.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 32.47 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 519.89 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 669.64 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 922.81 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 513.37 - State costs in support of activity delivery.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 225.65 - State costs in support of activity delivery.
HAP[CAPCOG]_HMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 58.72 - State costs in support of activity delivery.
HAP[CAPCOG]_HMID_UN-02182022160330 | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
HAP[CAPCOG]_HMID_UN-02182022160330 | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4
HAP[CAPCOG]_HMID_UN-02182022160330 | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3
HAP[CAPCOG]_HMID_UN-02182022160330 | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | Projects have not begun and are in the planning stage.
HAP[CAPCOG]_HMID_UN-02182022160330 | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1
HAP[CAPCOG]_HMID_UN-02182022160330 | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2
HAP[CAPCOG]_HMID_UN-02182022160330 | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | Activities are underway, no reportable changes during this quarter.
HAP[CAPCOG]_HMID_UN-02182022160330 | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | Activity cancelled and deleted.
HAP[CAPCOG]_HMID_UN-02182022160330 | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Expenditures and MID expenditures were successfully removed by HUD after the GLO requested assistance due to DRGR errors. Activity will be deleted again.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 2 projects are underway.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 2 project(s) was underway
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 2 project(s) was underway.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 2 additional projects were completed of 4 total projects. 1 projects are underway. 201.70 - Payroll Allocation
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 3 additional projects were completed of 5 total projects. 1 projects are underway. 304.60 - Payroll Allocation
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 4 additional projects were completed of 8 total projects. 0 projects are underway. 461.32 - Payroll Allocations
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 5 additional projects were completed of 12 total projects. 2 projects are underway. $915.48 - Payroll Allocations.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 2 additional projects were completed of 3 total projects. 1 projects are underway. 721.26 - Payroll Allocations.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 1 additional projects were completed out of 1 total projects managed during the reporting period. 0 projects are underway. 614.94 - Payroll Allocations
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 0 additional projects were completed out of 1 total projects managed during the reporting period. 1 projects are underway. 538.01 - Payroll Allocations.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 0 additional projects were completed out of 2 total projects managed during the reporting period. 2 projects are underway. 464.08 - Payroll Allocations.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 1 additional projects were completed out of 2 total projects managed during the reporting period. 1 projects are underway. 340.1 - Payroll Allocations.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 1 additional projects were completed out of 1 total projects managed during the reporting period. 0 projects are underway. 538.85 - Payroll Allocations.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | Activities are underway, no reportable changes during this quarter. 354.48 - Payroll allocation costs in support of activity delivery.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 714.72 - Payroll allocation costs in support of activity delivery.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 436.7 - Payroll allocation costs in support of activity delivery.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | Activities are underway, no reportable changes during this quarter. 696.53 - State costs in support of activity delivery.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $567.11 - State costs in support of activity delivery.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 303.08 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 3132.79 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 848.44 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 1826 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 756.61 - State costs in support of activity delivery.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 225.65 - State costs in support of activity delivery.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 199.67 - State costs in support of activity delivery.
HAP[CAPCOG]_SMID_LMI | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | Projects have not begun and are in the Planning stage. 57.72 - Payroll Allocation
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | Projects have not begun and are in the planning stage. 133.46 - Payroll Allocation
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | Projects have not begun and are in the planning stage. 184.54 - Payroll Allocations
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 0 additional projects were completed of 0 total projects. 0 projects are underway. $261.58 - Payroll Allocations.
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 2 additional projects were completed of 3 total projects. 1 projects are underway. 207.61 - Payroll Allocations.
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 0 additional projects were completed out of 0 total projects managed during the reporting period. 0 projects are underway. 176.33 - Payroll Allocations
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 1 additional projects were completed out of 1 total projects managed during the reporting period. 0 projects are underway. 123.28 - Payroll Allocations.
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 0 additional projects were completed out of 0 total projects managed during the reporting period. 0 projects are underway. 99.54 - Payroll Allocations.
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 0 additional projects were completed out of 0 total projects managed during the reporting period. 0 projects are underway. 71.62 - Payroll Allocations.
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | Activities are underway, no reportable changes during this quarter. 53.92 - Payroll Allocations.
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | Activities are underway, no reportable changes during this quarter. 35.51 - Payroll allocation costs in support of activity delivery.
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 71.56 - Payroll allocation costs in support of activity delivery.
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | During the reporting period, the activity budget and obligation was reduced.
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter.
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion.
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter.
HAP[CAPCOG]_SMID_UN | HAP - CAPCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 58.72 - State costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period 14 applications where received, none have been approved. During the reporting period, 164 projects are underway.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 223 project(s) was underway
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 343 project(s) was underway.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 282 additional projects were completed of 438 total projects. 117 projects are underway. 21000.96 - Payroll Allocation
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 371 additional projects were completed of 488 total projects. 35 projects are underway. 24,118.62 - Payroll Allocation
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 407 additional projects were completed of 545 total projects. 57 projects are underway. 38289.94 - Payroll Allocations
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 474 additional projects were completed of 667 total projects. 57 projects are underway. $76901.15 - Payroll Allocations.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 53 additional projects were completed of 117 total projects. 64 projects are underway. 55943.54 - Payroll Allocations.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 54 additional projects were completed out of 109 total projects managed during the reporting period. 55 projects are underway. 43875.15 - Payroll Allocations
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 46 additional projects were completed out of 147 total projects managed during the reporting period. 101 projects are underway. 41047.3 - Payroll Allocations.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 76 additional projects were completed out of 151 total projects managed during the reporting period. 75 projects are underway. 35990.13 - Payroll Allocations.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 65 additional projects were completed out of 166 total projects managed during the reporting period. 101 projects are underway. 27155.46 - Payroll Allocations.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 48 additional projects were completed out of 163 total projects managed during the reporting period. 115 projects are underway. 40354.43 - Payroll Allocations.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 83 additional projects were completed out of 152 total projects managed during the reporting period. 69 projects are underway. 26475.71 - Payroll allocation costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 47 additional projects were completed out of 92 total projects managed during the reporting period. 45 projects are underway. 53435.96 - Payroll allocation costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | 38 additional projects were completed out of 38 total projects managed during the reporting period. 0 projects are underway. 30787.24 - Payroll allocation costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 6 additional projects were completed out of 13 total projects managed during the reporting period. 7 projects are underway. 59142.25 - State costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | 3 additional projects were completed out of 7 total projects managed during the reporting period. 4 projects are underway. $46497.28 - State costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 23510.22 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 247941.21 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 66656.88 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 81375.33 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 37152.16 - State costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 15101.59 - State costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 19720.71 - State costs in support of activity delivery.
HAP[CBCOG]_HMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 56 projects are underway.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 69 project(s) was underway
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 96 project(s) was underway.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 71 additional projects were completed of 132 total projects. 44 projects are underway. 7581.79 - Payroll Allocation
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 95 additional projects were completed of 144 total projects. 19 projects are underway. 8,020.44 - Payroll Allocation
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 115 additional projects were completed of 165 total projects. 19 projects are underway. 13286.15 - Payroll Allocations
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 133 additional projects were completed of 209 total projects. 26 projects are underway. $26156.64 - Payroll Allocations.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 21 additional projects were completed of 48 total projects. 27 projects are underway. 19212.37 - Payroll Allocations.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 25 additional projects were completed out of 45 total projects managed during the reporting period. 20 projects are underway. 14669.05 - Payroll Allocations
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 18 additional projects were completed out of 48 total projects managed during the reporting period. 30 projects are underway. 13523.11 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 25 additional projects were completed out of 52 total projects managed during the reporting period. 27 projects are underway. 11807.62 - Payroll Allocations.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 24 additional projects were completed out of 56 total projects managed during the reporting period. 32 projects are underway. 8932.46 - Payroll Allocations.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 15 additional projects were completed out of 52 total projects managed during the reporting period. 37 projects are underway. 13234.32 - Payroll Allocations.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 22 additional projects were completed out of 45 total projects managed during the reporting period. 23 projects are underway. 8878.43 - Payroll allocation costs in support of activity delivery.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 21 additional projects were completed out of 29 total projects managed during the reporting period. 8 projects are underway. 17773.02 - Payroll allocation costs in support of activity delivery.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | 5 additional projects were completed out of 5 total projects managed during the reporting period. 0 projects are underway. 10262.42 - Payroll allocation costs in support of activity delivery.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 2 additional projects were completed out of 5 total projects managed during the reporting period. 3 projects are underway. 19137.1 - State costs in support of activity delivery.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | 1 additional projects were completed out of 3 total projects managed during the reporting period. 2 projects are underway. $15228.93 - State costs in support of activity delivery.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 7955.92 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 83198.88 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 22737.21 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 28550.06 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. 11848.12 - State costs in support of activity delivery.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 4442.57 - State costs in support of activity delivery.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 6176.72 - State costs in support of activity delivery.
HAP[CBCOG]_HMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 8 projects are underway.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 13 project(s) was underway
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 23 project(s) was underway.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 18 additional projects were completed of 28 total projects. 9 projects are underway. 1295.91 - Payroll Allocation
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 26 additional projects were completed of 30 total projects. 1 projects are underway. 1,483.66 - Payroll Allocation
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 28 additional projects were completed of 33 total projects. 2 projects are underway. 2352.75 - Payroll Allocations
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 30 additional projects were completed of 44 total projects. 4 projects are underway. $4795.45 - Payroll Allocations.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 6 additional projects were completed of 11 total projects. 5 projects are underway. 3435.39 - Payroll Allocations.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 5 additional projects were completed out of 10 total projects managed during the reporting period. 5 projects are underway. 2517.84 - Payroll Allocations
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 5 additional projects were completed out of 6 total projects managed during the reporting period. 1 projects are underway. 2143.3 - Payroll Allocations.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 1 additional projects were completed out of 1 total projects managed during the reporting period. 0 projects are underway. 2072.94 - Payroll Allocations.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 0 additional projects were completed out of 8 total projects managed during the reporting period. 8 projects are underway. 1628.96 - Payroll Allocations.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 5 additional projects were completed out of 10 total projects managed during the reporting period. 5 projects are underway. 2385.76 - Payroll Allocations.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 3 additional projects were completed out of 5 total projects managed during the reporting period. 2 projects are underway. 1488.64 - Payroll allocation costs in support of activity delivery.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 2 additional projects were completed out of 3 total projects managed during the reporting period. 1 projects are underway. 3061.81 - Payroll allocation costs in support of activity delivery.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 1746.8 - Payroll allocation costs in support of activity delivery.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 1 additional projects were completed out of 1 total projects managed during the reporting period. 0 projects are underway. 3236 - State costs in support of activity delivery.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $2523.28 - State costs in support of activity delivery.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 1277.28 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 13321.14 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 3236.6 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 5477.1 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 3042.74 - State costs in support of activity delivery.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 1330.45 - State costs in support of activity delivery.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 1139.25 - State costs in support of activity delivery.
HAP[CBCOG]_SMID_LMI | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 2 project(s) was underway
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 5 project(s) was underway.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 2 additional projects were completed of 9 total projects. 4 projects are underway. 453.54 - Payroll Allocation
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 6 additional projects were completed of 10 total projects. 0 projects are underway. 456.89 - Payroll Allocation
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 6 additional projects were completed of 10 total projects. 1 projects are underway. 691.99 - Payroll Allocations
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 7 additional projects were completed of 11 total projects. 0 projects are underway. $1395.01 - Payroll Allocations.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | Projects have not begun and are in the planning stage. 963.09 - Payroll Allocations.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 0 additional projects were completed out of 0 total projects managed during the reporting period. 0 projects are underway. 630.24 - Payroll Allocations
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 1 additional projects were completed out of 2 total projects managed during the reporting period. 1 projects are underway. 647.22 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 1 additional projects were completed out of 2 total projects managed during the reporting period. 1 projects are underway. 571.1 - Payroll Allocations.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 0 additional projects were completed out of 0 total projects managed during the reporting period. 0 projects are underway. 429.61 - Payroll Allocations.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 1 additional projects were completed out of 2 total projects managed during the reporting period. 1 projects are underway. 700.5 - Payroll Allocations.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 0 additional projects were completed out of 1 total projects managed during the reporting period. 1 projects are underway. 460.8 - Payroll allocation costs in support of activity delivery.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 1 additional projects were completed out of 1 total projects managed during the reporting period. 0 projects are underway. 929.11 - Payroll allocation costs in support of activity delivery.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 476.41 - Payroll allocation costs in support of activity delivery.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | Activities are underway, no reportable changes during this quarter. 766.11 - State costs in support of activity delivery.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $620.68 - State costs in support of activity delivery.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 335.56 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 3478.39 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 480.92 - Quarterly expenditure for state costs in support of activity delivery.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 211.41 - State costs in support of activity delivery.
HAP[CBCOG]_SMID_UN | HAP - CBCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 13 projects are underway.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 54 project(s) was underway
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 91 project(s) was underway.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 71 additional projects were completed of 245 total projects. 97 projects are underway. 8219.65 - Payroll Allocation
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 152 additional projects were completed of 317 total projects. 77 projects are underway. 11,299.97 - Payroll Allocation
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 26 additional projects were completed of 49 total projects. 9 projects are underway. 14531.72 - Payroll Allocations
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 249 additional projects were completed of 463 total projects. 38 projects are underway. $43812.81 - Payroll Allocations.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 28 additional projects were completed of 87 total projects. 59 projects are underway. 33251.33 - Payroll Allocations.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 41 additional projects were completed out of 115 total projects managed during the reporting period. 74 projects are underway. 27575.64 - Payroll Allocations
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 45 additional projects were completed out of 116 total projects managed during the reporting period. 71 projects are underway. 23965.83 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 54 additional projects were completed out of 102 total projects managed during the reporting period. 48 projects are underway. 19969.14 - Payroll Allocations.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 33 additional projects were completed out of 67 total projects managed during the reporting period. 34 projects are underway. 14678.65 - Payroll Allocations.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 17 additional projects were completed out of 37 total projects managed during the reporting period. 20 projects are underway. 22402.96 - Payroll Allocations.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 7 additional projects were completed out of 20 total projects managed during the reporting period. 13 projects are underway. 14425.21 - Payroll allocation costs in support of activity delivery.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 5 additional projects were completed out of 15 total projects managed during the reporting period. 10 projects are underway. 29318.5 - Payroll allocation costs in support of activity delivery.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | 4 additional projects were completed out of 4 total projects managed during the reporting period. 0 projects are underway. 15423.4 - Payroll allocation costs in support of activity delivery.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 1 additional projects were completed out of 8 total projects managed during the reporting period. 7 projects are underway. 25971.04 - State costs in support of activity delivery.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | 1 additional projects were completed out of 7 total projects managed during the reporting period. 6 projects are underway. $18880.92 - State costs in support of activity delivery.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | 2 additional projects were completed out of 8 total projects managed during the reporting period. 6 projects are underway. 6916.78 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 43780.75 - Quarterly expenditure for state costs in support of activity delivery.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 9813.62 - Quarterly expenditure for state costs in support of activity delivery.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 18668.05 - Quarterly expenditure for state costs in support of activity delivery.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 10154.8 - State costs in support of activity delivery.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 4442.57 - State costs in support of activity delivery.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 9636.13 - State costs in support of activity delivery.
HAP[DETCOG]_HMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 3 project(s) was underway
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 12 project(s) was underway.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 8 additional projects were completed of 28 total projects. 13 projects are underway. 1073.26 - Payroll Allocation
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 16 additional projects were completed of 39 total projects. 11 projects are underway. 2,050.29 - Payroll Allocation
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 22 additional projects were completed of 42 total projects. 9 projects are underway. 3598.33 - Payroll Allocations
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 28 additional projects were completed of 69 total projects. 9 projects are underway. $7542.08 - Payroll Allocations.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 2 additional projects were completed of 15 total projects. 13 projects are underway. 5464.06 - Payroll Allocations.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 11 additional projects were completed out of 22 total projects managed during the reporting period. 11 projects are underway. 4470.66 - Payroll Allocations
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 6 additional projects were completed out of 13 total projects managed during the reporting period. 7 projects are underway. 3532.88 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 11 additional projects were completed out of 20 total projects managed during the reporting period. 9 projects are underway. 2925.07 - Payroll Allocations.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 6 additional projects were completed out of 13 total projects managed during the reporting period. 7 projects are underway. 2148.09 - Payroll Allocations.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 5 additional projects were completed out of 9 total projects managed during the reporting period. 4 projects are underway. 3362.07 - Payroll Allocations.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 2 additional projects were completed out of 5 total projects managed during the reporting period. 3 projects are underway. 2303.82 - Payroll allocation costs in support of activity delivery.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 0 additional projects were completed out of 4 total projects managed during the reporting period. 4 projects are underway. 4576.48 - Payroll allocation costs in support of activity delivery.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | 3 additional projects were completed out of 3 total projects managed during the reporting period. 0 projects are underway. 2520.95 - Payroll allocation costs in support of activity delivery.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | Activities are underway, no reportable changes during this quarter. 4282.06 - State costs in support of activity delivery.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $3145.37 - State costs in support of activity delivery.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 1190.68 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 7333.2 - Quarterly expenditure for state costs in support of activity delivery.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 1069.11 - Quarterly expenditure for state costs in support of activity delivery.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 1826 - Quarterly expenditure for state costs in support of activity delivery.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 1017.39 - State costs in support of activity delivery.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 443.5 - State costs in support of activity delivery.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 1491.59 - State costs in support of activity delivery.
HAP[DETCOG]_HMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 1 project(s) was underway
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 7 project(s) was underway.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 4 additional projects were completed of 25 total projects. 12 projects are underway. 761.39 - Payroll Allocation
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 14 additional projects were completed of 34 total projects. 11 projects are underway. 3,478.84 - Payroll Allocation
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 3 additional projects were completed of 4 total projects. 1 projects are underway. 7335.07 - Payroll Allocations
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 29 additional projects were completed of 59 total projects. 10 projects are underway. $5318.59 - Payroll Allocations.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 6 additional projects were completed of 15 total projects. 9 projects are underway. 3970.69 - Payroll Allocations.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 7 additional projects were completed out of 14 total projects managed during the reporting period. 7 projects are underway. 3242.29 - Payroll Allocations
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 5 additional projects were completed out of 9 total projects managed during the reporting period. 4 projects are underway. 2852.18 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 4 additional projects were completed out of 8 total projects managed during the reporting period. 4 projects are underway. 2386.34 - Payroll Allocations.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 3 additional projects were completed out of 8 total projects managed during the reporting period. 5 projects are underway. 1754.27 - Payroll Allocations.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 2 additional projects were completed out of 5 total projects managed during the reporting period. 3 projects are underway. 2692.81 - Payroll Allocations.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 3 additional projects were completed out of 3 total projects managed during the reporting period. 0 projects are underway. 1736.73 - Payroll allocation costs in support of activity delivery.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 3527.65 - Payroll allocation costs in support of activity delivery.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 1985 - Payroll allocation costs in support of activity delivery.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | Activities are underway, no reportable changes during this quarter. 3446.05 - State costs in support of activity delivery.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $2440.87 - State costs in support of activity delivery.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | 1 additional projects were completed out of 1 total projects managed during the reporting period. 0 projects are underway.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 703.58 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 5113.9 - Quarterly expenditure for state costs in support of activity delivery.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 2115.17 - Quarterly expenditure for state costs in support of activity delivery.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 4042.37 - Quarterly expenditure for state costs in support of activity delivery.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 1494.51 - State costs in support of activity delivery.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 443.5 - State costs in support of activity delivery.
HAP[DETCOG]_SMID_LMI | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 1115.76 - State costs in support of activity delivery.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 1 project(s) was underway
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 3 project(s) was underway.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 1 additional projects were completed of 3 total projects. 2 projects are underway. 220.95 - Payroll Allocation
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 2 additional projects were completed of 3 total projects. 1 projects are underway. 474.64 - Payroll Allocation
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 144 additional projects were completed of 189 total projects. 18 projects are underway. 830.38 - Payroll Allocations
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 2 additional projects were completed of 5 total projects. 0 projects are underway. $523.18 - Payroll Allocations.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 0 additional projects were completed of 2 total projects. 2 projects are underway. 319.35 - Payroll Allocations.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 1 additional projects were completed out of 2 total projects managed during the reporting period. 1 projects are underway. 260.11 - Payroll Allocations
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 1 additional projects were completed out of 2 total projects managed during the reporting period. 1 projects are underway. 215.74 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 1 additional projects were completed out of 1 total projects managed during the reporting period. 0 projects are underway. 174.18 - Payroll Allocations.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 0 additional projects were completed out of 0 total projects managed during the reporting period. 0 projects are underway. 125.33 - Payroll Allocations.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | Activities are underway, no reportable changes during this quarter. 196.75 - Payroll Allocations.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | Activities are underway, no reportable changes during this quarter. 106.37 - Payroll allocation costs in support of activity delivery.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 231.67 - Payroll allocation costs in support of activity delivery.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 138.96 - Payroll allocation costs in support of activity delivery.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | Activities are underway, no reportable changes during this quarter. 278.29 - State costs in support of activity delivery.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $204.5 - State costs in support of activity delivery.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 86.59 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 564.23 - Quarterly expenditure for state costs in support of activity delivery.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 428.93 - Quarterly expenditure for state costs in support of activity delivery.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 922.8 - Quarterly expenditure for state costs in support of activity delivery.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 513.37 - State costs in support of activity delivery.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 225.65 - State costs in support of activity delivery.
HAP[DETCOG]_SMID_UN | HAP - DETCOG | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 82.22 - State costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 49 projects are underway.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 69 project(s) was underway
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 126 project(s) was underway.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 105 additional projects were completed of 160 total projects. 40 projects are underway. 7991.13 - Payroll Allocation
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 133 additional projects were completed of 173 total projects. 12 projects are underway. 7,734.39 - Payroll Allocation
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 40 additional projects were completed of 56 total projects. 7 projects are underway. 11256.32 - Payroll Allocations
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 150 additional projects were completed of 211 total projects. 28 projects are underway. $26418.73 - Payroll Allocations.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 24 additional projects were completed of 35 total projects. 11 projects are underway. 18726.21 - Payroll Allocations.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 5 additional projects were completed out of 13 total projects managed during the reporting period. 8 projects are underway. 14444.82 - Payroll Allocations
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 6 additional projects were completed out of 10 total projects managed during the reporting period. 4 projects are underway. 12792.18 - Payroll Allocations.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 3 additional projects were completed out of 7 total projects managed during the reporting period. 4 projects are underway. 9537.42 - Payroll Allocations.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 0 additional projects were completed out of 17 total projects managed during the reporting period. 17 projects are underway. 6623.28 - Payroll Allocations.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 10 additional projects were completed out of 31 total projects managed during the reporting period. 21 projects are underway. 9563.94 - Payroll Allocations.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 12 additional projects were completed out of 27 total projects managed during the reporting period. 15 projects are underway. 6291.13 - Payroll allocation costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 14 additional projects were completed out of 25 total projects managed during the reporting period. 11 projects are underway. 12685.11 - Payroll allocation costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | 9 additional projects were completed out of 9 total projects managed during the reporting period. 0 projects are underway. 6768.83 - Payroll allocation costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 1 additional projects were completed out of 2 total projects managed during the reporting period. 1 projects are underway. 12595.84 - State costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $9755.62 - State costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 4730.25 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 49230.71 - Quarterly expenditure for state costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 13458.38 - Quarterly expenditure for state costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 20353.74 - Quarterly expenditure for state costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. 10137.26 - State costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 4224.72 - State costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 4674.46 - State costs in support of activity delivery.
HAP[GCRPC]_HMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 12 projects are underway.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 15 project(s) was underway
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 35 project(s) was underway.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 28 additional projects were completed of 45 total projects. 10 projects are underway. 2531.14 - Payroll Allocation
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 36 additional projects were completed of 50 total projects. 3 projects are underway. 2,471.69 - Payroll Allocation
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 34 additional projects were completed of 41 total projects. 2 projects are underway. 4013.52 - Payroll Allocations
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 46 additional projects were completed of 64 total projects. 6 projects are underway. $8631.92 - Payroll Allocations.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 6 additional projects were completed of 10 total projects. 4 projects are underway. 5952.74 - Payroll Allocations.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 3 additional projects were completed out of 5 total projects managed during the reporting period. 2 projects are underway. 4474.91 - Payroll Allocations
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 2 additional projects were completed out of 2 total projects managed during the reporting period. 0 projects are underway. 3936.19 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 0 additional projects were completed out of 0 total projects managed during the reporting period. 0 projects are underway. 3158.92 - Payroll Allocations.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 0 additional projects were completed out of 7 total projects managed during the reporting period. 7 projects are underway. 2291.31 - Payroll Allocations.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 2 additional projects were completed out of 15 total projects managed during the reporting period. 13 projects are underway. 3414.65 - Payroll Allocations.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 11 additional projects were completed out of 21 total projects managed during the reporting period. 10 projects are underway.2303.82 - Payroll allocation costs in support of activity delivery.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 7 additional projects were completed out of 9 total projects managed during the reporting period. 2 projects are underway. 4602.28 - Payroll allocation costs in support of activity delivery.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | 1 additional projects were completed out of 1 total projects managed during the reporting period. 0 projects are underway. 2600.35 - Payroll allocation costs in support of activity delivery.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 2 additional projects were completed out of 4 total projects managed during the reporting period. 2 projects are underway. 4836.45 - State costs in support of activity delivery.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | 2 additional projects were completed out of 2 total projects managed during the reporting period. 0 projects are underway. $3795.77 - State costs in support of activity delivery.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 1915.91 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 19391.73 - Quarterly expenditure for state costs in support of activity delivery.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 3665.45 - Quarterly expenditure for state costs in support of activity delivery.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 5868.36 - Quarterly expenditure for state costs in support of activity delivery.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 2511.86 - State costs in support of activity delivery.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 886.97 - State costs in support of activity delivery.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 1609.04 - State costs in support of activity delivery.
HAP[GCRPC]_HMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 10 projects are underway.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 17 project(s) was underway
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 29 project(s) was underway.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 26 additional projects were completed of 40 total projects. 8 projects are underway. 1725.56 - Payroll Allocation
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 30 additional projects were completed of 40 total projects. 4 projects are underway. 2,845.07 - Payroll Allocation
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 7 additional projects were completed of 8 total projects. 1 projects are underway. 5212.97 - Payroll Allocations
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 35 additional projects were completed of 44 total projects. 1 projects are underway. $5449.35 - Payroll Allocations.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 1 additional projects were completed of 4 total projects. 3 projects are underway. 3909.01 - Payroll Allocations.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 3 additional projects were completed out of 3 total projects managed during the reporting period. 0 projects are underway. 2887.45 - Payroll Allocations
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | Activities are underway, no reportable changes during this quarter. 2459.47 - Payroll Allocations.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | Activities are underway, no reportable changes during this quarter. 1955.83 - Payroll Allocations.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | Activities are underway, no reportable changes during this quarter. 1432.06 - Payroll Allocations.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 2 additional projects were completed out of 9 total projects managed during the reporting period. 7 projects are underway. 2039.41 - Payroll Allocations.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 5 additional projects were completed out of 11 total projects managed during the reporting period. 6 projects are underway.1364.59 - Payroll allocation costs in support of activity delivery.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 5 additional projects were completed out of 10 total projects managed during the reporting period. 5 projects are underway. 2734.26 - Payroll allocation costs in support of activity delivery.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | 4 additional projects were completed out of 4 total projects managed during the reporting period. 0 projects are underway. 1746.8 - Payroll allocation costs in support of activity delivery.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 2 additional projects were completed out of 2 total projects managed during the reporting period. 0 projects are underway. 3305.25 - State costs in support of activity delivery.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $2576.17 - State costs in support of activity delivery.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 1190.68 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 11840.67 - Quarterly expenditure for state costs in support of activity delivery.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 2775.47 - Quarterly expenditure for state costs in support of activity delivery.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 4945.59 - Quarterly expenditure for state costs in support of activity delivery.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 2538.72 - State costs in support of activity delivery.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 1112.6 - State costs in support of activity delivery.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 1115.76 - State costs in support of activity delivery.
HAP[GCRPC]_SMID_LMI | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 5 project(s) was underway
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 5 project(s) was underway.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 5 additional projects were completed of 7 total projects. 2 projects are underway. 535.16 - Payroll Allocation
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 7 additional projects were completed of 7 total projects. 0 projects are underway. 778.14 - Payroll Allocation
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 448 additional projects were completed of 1122 total projects. 213 projects are underway. 1383.97 - Payroll Allocations
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 7 additional projects were completed of 9 total projects. 1 projects are underway. $1177.02 - Payroll Allocations.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 1 additional projects were completed of 1 total projects. 0 projects are underway. 851.36 - Payroll Allocations.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 0 additional projects were completed out of 0 total projects managed during the reporting period. 0 projects are underway. 508.16 - Payroll Allocations / Adjustments to correct invoice splits
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | Activities are underway, no reportable changes during this quarter. 445.56 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | Activities are underway, no reportable changes during this quarter. 437.96 - Payroll Allocations.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 0 additional projects were completed out of 2 total projects managed during the reporting period. 2 projects are underway. 340.11 - Payroll Allocations.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 1 additional projects were completed out of 4 total projects managed during the reporting period. 3 projects are underway. 476.84 - Payroll Allocations.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 2 additional projects were completed out of 3 total projects managed during the reporting period. 1 projects are underway.336.76 - Payroll allocation costs in support of activity delivery.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 2 additional projects were completed out of 2 total projects managed during the reporting period. 0 projects are underway. 661.79 - Payroll allocation costs in support of activity delivery.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 377.16 - Payroll allocation costs in support of activity delivery.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | Activities are underway, no reportable changes during this quarter. 695.87 - State costs in support of activity delivery.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $536.19 - State costs in support of activity delivery.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter. 270.61 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 2730.12 - Quarterly expenditure for state costs in support of activity delivery.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 428.93 - Quarterly expenditure for state costs in support of activity delivery.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 922.82 - Quarterly expenditure for state costs in support of activity delivery.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 513.37 - State costs in support of activity delivery.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 225.65 - State costs in support of activity delivery.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 258.39 - State costs in support of activity delivery.
HAP[GCRPC]_SMID_UN | HAP - GCRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | In prior quarters, funds were drawn down from the activity Administration. During the reporting period, the GLO approved 166 applications and issued notice to proceed to construction on 47 low to moderate income households. The GLO also made payments to vendors working on the program.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | In prior quarters, funds were drawn down from the activity Administration. During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 10 homes for low-to-moderate-income households. The GLO updated their methodology for reporting completed rehabilitation and reconstruction projects in DRGR. Previously, GLO reported completed projects once the CDBG-DR funds were fully expensed. The methodology has been updated to report on completed rehabilitation and reconstruction projects once the final inspection is completed. The performance measures and associated demographic information have been updated to reflect all rehabilitation and reconstruction projects that have received final inspection as of the end of the reporting period. To date, final inspection has been completed on 37 low-to-moderate income homeowner assistance projects, 24 of which received final inspection during the reporting period. 2417.33 - Payroll Allocations
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 37 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 62 low-to-moderate income homeowner assistance projects, 24 of which received final inspection during the reporting period. 23184.84 - Payroll Allocations
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 67 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 97 low-to-moderate income homeowner assistance projects, 35 of which received final inspection during the reporting period. 25207.05 - Payroll Allocations.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 55 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 113 low-to-moderate income homeowner assistance projects, 16 of which received final inspection during the reporting period. 19784.47 - Payroll Allocations.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 48 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 137 low-to-moderate income homeowner assistance projects, 24 of which received final inspection during the reporting period. 15574.06 - Payroll Allocations.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The Texas General Land Office also made payments to vendors working on the program. During the reporting period the Texas General Land Office paid for costs associated with the rehabilitation/reconstruction of approximately 51 homes for low-to-moderate income households. The Texas General Land Office reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 153 low-to-moderate income homeowner assistance projects, 16 of which received final inspection during the reporting period. 13418.55 - Payroll allocation costs in support of activity delivery.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 55 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 178 low-to-moderate income homeowner assistance projects, 25 of which received final inspection during the reporting period. 23432.74 - Payroll allocation costs in support of activity delivery.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 101 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 214 low-to-moderate income homeowner assistance projects, 36 of which received final inspection during the reporting period. 22265.99 - Payroll allocation costs in support of activity delivery.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 70 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 246 low-to-moderate income homeowner assistance projects, 32 of which received final inspection during the reporting period. 60154.96 - State costs in support of activity delivery.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 48 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 259 low-to-moderate income homeowner assistance projects, 13 of which received final inspection during the reporting period. $36929.79 - State costs in support of activity delivery.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 29 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 278 low-to-moderate income homeowner assistance projects, 19 of which received final inspection during the reporting period.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 24 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 295 low-to-moderate income homeowner assistance projects, 17 of which received final inspection during the reporting period. 7071.19 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 163 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 295 low-to-moderate income homeowner assistance projects, 0 of which received final inspection during the reporting period.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 18 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 319 low-to-moderate income homeowner assistance projects, 8 of which received final inspection during the reporting period. Of the 8 project completed this quarter for Harris HAP LMI, 7 were entirely HAP funded, 1 was majority (>=50 percent) funded by HAP. 26523.12 - Quarterly expenditure for state costs in support of activity delivery.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 16 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 336 low-to-moderate income homeowner assistance projects, 21 of which received final inspection during the reporting period. 21 projects were entirely funded by this program, and none were majority funded from HOS. All performance measures and beneficiaries are reported under the majority funding activity.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the quarter, additional households were reported as completed.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 1 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 307 low-to-moderate income homeowner assistance projects, 8 of which received final inspection during the reporting period. During the reporting period 8 projects were funded by this activity and completed this quarter. All performance measures and beneficiaries are reported under this funding activity.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, the Harris County continued to make progress on ongoing projects. No households were completed during the quarter. Additionally, the GLO is actively reconciling costs for projects that received funding from both the Harvey and Mitigation allocations in the GLO system of record as well as DRGR. The GLO expects to resume reporting of accomplishments in subsequent quarters. The negative expenditure balance for the quarter is a result of this reconciliation.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, all households have completed construction. Overall, for this activity, a total of 304 households received a rehabilitation/reconstruction benefit.
HAP[Harris]_HMID_LMI | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | In prior quarters, funds were drawn down from the activity Administration. During the reporting period, the GLO approved 48 applications and issued notice to proceed to construction on 12 urgent need income households. The GLO also made payments to vendors working on the program.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | In prior quarters, funds were drawn down from the activity Administration. During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 2 homes for non-low-to-moderate-income households. The GLO updated their methodology for reporting completed rehabilitation and reconstruction projects in DRGR. Previously, GLO reported completed projects once the CDBG-DR funds were fully expensed. The methodology has been updated to report on completed rehabilitation and reconstruction projects once the final inspection is completed. The performance measures and associated demographic information have been updated to reflect all rehabilitation and reconstruction projects that have received final inspection as of the end of the reporting period. To date, final inspection has been completed on 6 non low-to-moderate income homeowner assistance projects, 3 of which received final inspection during the reporting period. 996.49 - Payroll Allocations
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 8 homes for non low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 19 non low-to-moderate income homeowner assistance projects, 13 of which received final inspection during the reporting period. 7603.07 - Payroll Allocations
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 18 homes for non low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 26 non low-to-moderate income) homeowner assistance projects, 7 of which received final inspection during the reporting period. 7800.1 - Payroll Allocations.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 14 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 33 urgent need homeowner assistance projects, 7 of which received final inspection during the reporting period. 6182.81 - Payroll Allocations.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 13 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 36 urgent need homeowner assistance projects, 3 of which received final inspection during the reporting period. 14897.57 - Payroll Allocations.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The Texas General Land Office also made payments to vendors working on the program. During the reporting period the Texas General Land Office paid for costs associated with the rehabilitation/reconstruction of approximately 14 homes for urgent need households. The Texas General Land Office reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 41 urgent need homeowner assistance projects, 5 of which received final inspection during the reporting period. 8579.11 - Payroll allocation costs in support of activity delivery.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 22 homes for non low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 54 non low-to-moderate income homeowner assistance projects, 13 of which received final inspection during the reporting period. 18158.31 - Payroll allocation costs in support of activity delivery.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 30 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 63 urgent need homeowner assistance projects, 9 of which received final inspection during the reporting period. 7673.48 - Payroll allocation costs in support of activity delivery.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 14 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 66 urgent need homeowner assistance projects, 3 of which received final inspection during the reporting period. 7345.03 - State costs in support of activity delivery.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 7 homes for non low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 69 non low-to-moderate income homeowner assistance projects, 3 of which received final inspection during the reporting period. $12238.02 - State costs in support of activity delivery.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 5 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 71 urgent need homeowner assistance projects, 2 of which received final inspection during the reporting period.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 5 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 76 urgent need homeowner assistance projects, 5 of which received final inspection during the reporting period. 5908.22 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 22 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 76 urgent need homeowner assistance projects, 0 of which received final inspection during the reporting period.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 4 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 80 urgent need homeowner assistance projects, 1 of which received final inspection during the reporting period. Of the 1 project completed this quarter for Harris HAP UN, 1 was entirely HAP funded, 0 were majority (>=50 percent) funded by HAP. 22161.08 - Quarterly expenditure for state costs in support of activity delivery.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 0 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 83 urgent need homeowner assistance projects, 3 of which received final inspection during the reporting period. 3 projects were entirely funded by this program, and none were majority funded from HOS. All performance measures and beneficiaries are reported under the majority funding activity.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 1 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 81 urgent need homeowner assistance projects, 1 of which received final inspection during the reporting period.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 78 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 84 urgent need homeowner assistance projects, 5 of which received final inspection during the reporting period. During the reporting period 5 projects were funded by this activity and completed this quarter. All performance measures and beneficiaries are reported under this funding activity.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, the Harris County continued to make progress on ongoing projects. No households were completed during the quarter. Additionally, the GLO is actively reconciling costs for projects that received funding from both the Harvey and Mitigation allocations in the GLO system of record as well as DRGR. The GLO expects to resume reporting of accomplishments in subsequent quarters. The negative expenditure balance for the quarter is a result of this reconciliation.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, all households have completed construction. Overall, for this activity, a total of 80 households received a rehabilitation/reconstruction benefit.
HAP[Harris]_HMID_UN | HC HAP State Run | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 98 projects are underway.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 91 project(s) was underway
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 208 project(s) was underway.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 137 additional projects were completed of 707 total projects. 254 projects are underway. 49725.20 - Payroll Allocation
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 274 additional projects were completed of 960 total projects. 297 projects are underway. 60,455.15 - Payroll Allocation
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 85 additional projects were completed of 263 total projects. 47 projects are underway. 75749.49 - Payroll Allocations
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 601 additional projects were completed of 1442 total projects. 178 projects are underway. $144780.68 - Payroll Allocations.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 103 additional projects were completed of 281 total projects. 178 projects are underway. 105404.03 - Payroll Allocations.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 96 additional projects were completed out of 327 total projects managed during the reporting period. 231 projects are underway. 88246.69 - Payroll Allocations
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 89 additional projects were completed out of 340 total projects managed during the reporting period. 251 projects are underway. 77477.86 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 147 additional projects were completed out of 349 total projects managed during the reporting period. 202 projects are underway. 62987.56 - Payroll Allocations.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 124 additional projects were completed out of 257 total projects managed during the reporting period. 133 projects are underway. 45951.27 - Payroll Allocations.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 82 additional projects were completed out of 165 total projects managed during the reporting period. 83 projects are underway. 70342.08 - Payroll Allocations.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 36 additional projects were completed out of 101 total projects managed during the reporting period. 65 projects are underway. 45808.63 - Payroll allocation costs in support of activity delivery.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 20 additional projects were completed out of 75 total projects managed during the reporting period. 55 projects are underway. 92711.03 - Payroll allocation costs in support of activity delivery.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | 20 additional projects were completed out of 20 total projects managed during the reporting period. 0 projects are underway. 51093.72 - Payroll allocation costs in support of activity delivery.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 8 additional projects were completed out of 47 total projects managed during the reporting period. 39 projects are underway. 77980.83 - State costs in support of activity delivery.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | 3 additional projects were completed out of 40 total projects managed during the reporting period. 37 projects are underway. $58813.49 - State costs in support of activity delivery.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | 3 additional projects were completed out of 39 total projects managed during the reporting period. 36 projects are underway. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | 3 additional projects were completed out of 38 total projects managed during the reporting period. 35 projects are underway. 22471.4 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 161451.42 - Quarterly expenditure for state costs in support of activity delivery.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | 2 additional project(s) were completed out of 39 total project(s) managed during the reporting period. 37 project(s) are underway. 42520.75 - Quarterly expenditure for state costs in support of activity delivery.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | 3 additional project(s) were completed out of 5 total project(s) managed during the reporting period. 2 project(s) are underway. 74874.18 - Quarterly expenditure for state costs in support of activity delivery.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. 37531.24 - State costs in support of activity delivery.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 16003.26 - State costs in support of activity delivery.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 26453.59 - State costs in support of activity delivery.
HAP[HGAC]_HMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 16 projects are underway.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 10 project(s) was underway
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 27 project(s) was underway.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 16 additional projects were completed of 147 total projects. 47 projects are underway. 12440.19 - Payroll Allocation
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 46 additional projects were completed of 227 total projects. 59 projects are underway. 13,997.35 - Payroll Allocation
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 22 additional projects were completed of 57 total projects. 9 projects are underway. 17484.21 - Payroll Allocations
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 106 additional projects were completed of 341 total projects. 43 projects are underway. $35181.28 - Payroll Allocations.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 21 additional projects were completed of 53 total projects. 32 projects are underway. 29322.69 - Payroll Allocations.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 16 additional projects were completed out of 76 total projects managed during the reporting period. 60 projects are underway. 26509.62 - Payroll Allocations
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 24 additional projects were completed out of 79 total projects managed during the reporting period. 55 projects are underway. 18608.43 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 26 additional projects were completed out of 74 total projects managed during the reporting period. 48 projects are underway. 15314.6 - Payroll Allocations.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 27 additional projects were completed out of 67 total projects managed during the reporting period. 40 projects are underway. 11223.79 - Payroll Allocations.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 19 additional projects were completed out of 52 total projects managed during the reporting period. 33 projects are underway. 17419.5 - Payroll Allocations.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 13 additional projects were completed out of 36 total projects managed during the reporting period. 23 projects are underway. 11642.96 - Payroll allocation costs in support of activity delivery.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 7 additional projects were completed out of 24 total projects managed during the reporting period. 17 projects are underway. 23338.68 - Payroll allocation costs in support of activity delivery.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | 2 additional projects were completed out of 2 total projects managed during the reporting period. 0 projects are underway. 13775.85 - Payroll allocation costs in support of activity delivery.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 3 additional projects were completed out of 21 total projects managed during the reporting period. 18 projects are underway. 17750.84 - State costs in support of activity delivery.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | 2 additional projects were completed out of 18 total projects managed during the reporting period. 16 projects are underway. $13722.87 - State costs in support of activity delivery.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | 1 additional projects were completed out of 17 total projects managed during the reporting period. 16 projects are underway. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | 1 additional projects were completed out of 16 total projects managed during the reporting period. 15 projects are underway. 5455.48 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 43204.41 - Quarterly expenditure for state costs in support of activity delivery.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 8985.24 - Quarterly expenditure for state costs in support of activity delivery.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | 1 additional project(s) were completed out of 3 total project(s) managed during the reporting period. 2 project(s) are underway. 16310.53 - Quarterly expenditure for state costs in support of activity delivery.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. 8633.42 - State costs in support of activity delivery.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 3781.25 - State costs in support of activity delivery.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 5461.36 - State costs in support of activity delivery.
HAP[HGAC]_HMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 3 projects are underway.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 4 project(s) was underway
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 13 project(s) was underway.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 8 additional projects were completed of 29 total projects. 12 projects are underway. 1167.14 - Payroll Allocation
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 19 additional projects were completed of 44 total projects. 5 projects are underway. 2,693.87 - Payroll Allocation
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 5 additional projects were completed of 12 total projects. 2 projects are underway. 4890.04 - Payroll Allocations
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 27 additional projects were completed of 87 total projects. 18 projects are underway. $7236.49 - Payroll Allocations.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 11 additional projects were completed of 32 total projects. 21 projects are underway. 6329.53 - Payroll Allocations.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 4 additional projects were completed out of 32 total projects managed during the reporting period. 28 projects are underway. 5863 - Payroll Allocations
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 17 additional projects were completed out of 38 total projects managed during the reporting period. 21 projects are underway. 5176.94 - Payroll Allocations.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 15 additional projects were completed out of 29 total projects managed during the reporting period. 14 projects are underway. 4144.34 - Payroll Allocations.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 10 additional projects were completed out of 15 total projects managed during the reporting period. 5 projects are underway. 3025.23 - Payroll Allocations.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 6 additional projects were completed out of 13 total projects managed during the reporting period. 7 projects are underway. 4581.22 - Payroll Allocations.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 5 additional projects were completed out of 7 total projects managed during the reporting period. 2 projects are underway. 3048.12 - Payroll allocation costs in support of activity delivery.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 1 additional projects were completed out of 2 total projects managed during the reporting period. 1 projects are underway. 6120.24 - Payroll allocation costs in support of activity delivery.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout. 3354.65 - Payroll allocation costs in support of activity delivery.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 8 additional projects were completed out of 47 total projects managed during the reporting period. 39 projects are underway. 5778.31 - State costs in support of activity delivery.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $4367.33 - State costs in support of activity delivery.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | 1 additional projects were completed out of 2 total projects managed during the reporting period. 1 projects are underway.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter 1223.15 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 9094.90 - Quarterly expenditure for state costs in support of activity delivery.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 2115.17 - Quarterly expenditure for state costs in support of activity delivery.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 4573.89 - Quarterly expenditure for state costs in support of activity delivery.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 2538.71 - State costs in support of activity delivery.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 1112.58 - State costs in support of activity delivery.
HAP[HGAC]_SMID_LMI | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 1902.67 - State costs in support of activity delivery.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 1 project is underway.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 1 project(s) was underway
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 3 project(s) was underway.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 2 additional projects were completed of 8 total projects. 2 projects are underway. 508.93 - Payroll Allocation
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 3 additional projects were completed of 12 total projects. 2 projects are underway. 722.73 - Payroll Allocation
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 339 additional projects were completed of 567 total projects. 58 projects are underway. 1153.32 - Payroll Allocations
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 6 additional projects were completed of 19 total projects. 2 projects are underway. $1612.93 - Payroll Allocations.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 3 additional projects were completed of 5 total projects. 2 projects are underway. 1840.18 - Payroll Allocations.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 1 additional projects were completed out of 8 total projects managed during the reporting period. 7 projects are underway. 1967.68 - Payroll Allocations
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 2 additional projects were completed out of 7 total projects managed during the reporting period. 5 projects are underway. 1159.75 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 5 additional projects were completed out of 8 total projects managed during the reporting period. 3 projects are underway. 944.32 - Payroll Allocations.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 2 additional projects were completed out of 4 total projects managed during the reporting period. 2 projects are underway. 698.13 - Payroll Allocations.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 2 additional projects were completed out of 2 total projects managed during the reporting period. 0 projects are underway. 1077.68 - Payroll Allocations.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | Activities are underway, no reportable changes during this quarter. 708.9 - Payroll allocation costs in support of activity delivery.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 0 additional projects were completed out of 1 total projects managed during the reporting period. 1 projects are underway. 1429.38 - Payroll allocation costs in support of activity delivery.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | 1 additional projects were completed out of 1 total projects managed during the reporting period. 0 projects are underway. 853.55 - Payroll allocation costs in support of activity delivery.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 3 additional projects were completed out of 21 total projects managed during the reporting period. 18 projects are underway. 1461.96 - State costs in support of activity delivery.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $1166.71 - State costs in support of activity delivery.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | Activities are underway, no reportable changes during this quarter. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter 454.62 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 3215.04 - Quarterly expenditure for state costs in support of activity delivery.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 669.64 - Quarterly expenditure for state costs in support of activity delivery.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 922.8 - Quarterly expenditure for state costs in support of activity delivery.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 513.37 - State costs in support of activity delivery.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 225.63 - State costs in support of activity delivery.
HAP[HGAC]_SMID_UN | HAP - HGAC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 434.56 - State costs in support of activity delivery.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | In prior quarters, funds were drawn down from the activity Planning. During the reporting period, the GLO approved 350 applications and issued notice to proceed to construction on 163 low to moderate income households. The GLO also made payments to vendors working on the program.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | In prior quarters, funds were drawn down from the activity Planning. During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 40 homes for low-to-moderate-income households. The GLO updated their methodology for reporting completed rehabilitation and reconstruction projects in DRGR. Previously, GLO reported completed projects once the CDBG-DR funds were fully expensed. The methodology has been updated to report on completed rehabilitation and reconstruction projects once the final inspection is completed. The performance measures and associated demographic information have been updated to reflect all rehabilitation and reconstruction projects that have received final inspection as of the end of the reporting period. To date, final inspection has been completed on 107 low-to-moderate income homeowner assistance projects, 58 of which received final inspection during the reporting period. 4837.09 - Payroll Allocations
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 89 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 156 low-to-moderate income homeowner assistance projects, 49 of which received final inspection during the reporting period. 33019.53 - Payroll Allocations
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 123 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 221 low-to-moderate income homeowner assistance projects, 65 of which received final inspection during the reporting period. 35152.28 - Payroll Allocations.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 146 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 298 low-to-moderate income homeowner assistance projects, 77 of which received final inspection during the reporting period. 28594.18 - Payroll Allocations.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 202 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 436 low-to-moderate income homeowner assistance projects, 138 of which received final inspection during the reporting period. 36755.2 - Payroll Allocations.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The Texas General Land Office also made payments to vendors working on the program. During the reporting period the Texas General Land Office paid for costs associated with the rehabilitation/reconstruction of approximately 273 homes for low-to-moderate income households. The Texas General Land Office reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 540 low-to-moderate income homeowner assistance projects, 104 of which received final inspection during the reporting period. 24582.97 - Payroll allocation costs in support of activity delivery.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 231 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 658 low-to-moderate income homeowner assistance projects, 118 of which received final inspection during the reporting period. 47161.64 - Payroll allocation costs in support of activity delivery.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 321 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 835 low-to-moderate income homeowner assistance projects, 177 of which received final inspection during the reporting period. 57411.7 - Payroll allocation costs in support of activity delivery.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | $48,094,325.87 in expenditures from Q1 2023, entered into DRGR in Q2 2023 due to DRGR error not allowing the previous quarter&apos;s entry. During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 334 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 1,013 low-to-moderate income homeowner assistance projects, 178 of which received final inspection during the reporting period. 105491.01 - State costs in support of activity delivery.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 324 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 1,152 low-to-moderate income homeowner assistance projects, 139 of which received final inspection during the reporting period. $51948.04 - State costs in support of activity delivery.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 220 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 1292 low-to-moderate income homeowner assistance projects, 140 of which received final inspection during the reporting period.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 166 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 1405 low-to-moderate income homeowner assistance projects, 113 of which received final inspection during the reporting period. 29997.79 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 23 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 1510 low-to-moderate income homeowner assistance projects, 105 of which received final inspection during the reporting period.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 116 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 1602 low-to-moderate income homeowner assistance projects, 97 of which received final inspection during the reporting period. Of the 97 project completed this quarter for City of Houston HAP LMI, 89 were entirely HAP funded, 8 were majority (>=50 percent) funded by HAP. 82090.58 - Quarterly expenditure for state costs in support of activity delivery.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 127 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 1681 low-to-moderate income homeowner assistance projects, 107 of which received final inspection during the reporting period. 107 projects were entirely funded by this program, and none were majority funded from HOS. All performance measures and beneficiaries are reported under the majority funding activity.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period 1 projects were funded by this activity and completed this quarter. All performance measures and beneficiaries are reported under this funding activity.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 4 homes for low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 1612 low-to-moderate income homeowner assistance projects, 86 of which received final inspection during the reporting period. During the reporting period 86 projects were funded by this activity and completed this quarter. All performance measures and beneficiaries are reported under this funding activity.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Houston continued to make progress on ongoing projects. No households were completed during the quarter. Additionally, the GLO is actively reconciling costs for projects that received funding from both the Harvey and Mitigation allocations in the GLO system of record as well as DRGR. The GLO expects to resume reporting of accomplishments in subsequent quarters.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, all households have completed construction. Overall, for this activity, a total of 1,574 households received a rehabilitation/reconstruction benefit.
HAP[Houston]_HMID_LMI | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | In prior quarters, funds were drawn down from the activity Planning. During the reporting period, the GLO approved 54 applications and issued notice to proceed to construction on 24 non low to moderate income households. The GLO also made payments to vendors working on the program.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | In prior quarters, funds were drawn down from the activity Planning. During the reporting period, payments were made as a result of approved applications and construction draw submissions. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 3 homes for non-low-to-moderate-income households. The GLO updated their methodology for reporting completed rehabilitation and reconstruction projects in DRGR. Previously, GLO reported completed projects once the CDBG-DR funds were fully expensed. The methodology has been updated to report on completed rehabilitation and reconstruction projects once the final inspection is completed. The performance measures and associated demographic information have been updated to reflect all rehabilitation and reconstruction projects that have received final inspection as of the end of the reporting period. To date, final inspection has been completed on 10 non low-to-moderate income homeowner assistance projects, 5 of which received final inspection during the reporting period. 711.94 - Payroll Allocations
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 13 homes for non low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 18 non low-to-moderate income homeowner assistance projects, 8 of which received final inspection during the reporting period. 4001.31 - Payroll Allocations
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 20 homes for non low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 30 non low-to-moderate income homeowner assistance projects, 12 of which received final inspection during the reporting period. 4184.02 - Payroll Allocations.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 16 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 36 urgent need homeowner assistance projects, 6 of which received final inspection during the reporting period. 3570.25 - Payroll Allocations.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 19 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 41 urgent need homeowner assistance projects, 5 of which received final inspection during the reporting period. 4179.39 - Payroll Allocations.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The Texas General Land Office also made payments to vendors working on the program. During the reporting period the Texas General Land Office paid for costs associated with the rehabilitation/reconstruction of approximately 24 homes for urgent need households. The Texas General Land Office reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 53 urgent need homeowner assistance projects, 12 of which received final inspection during the reporting period. 3094.25 - Payroll allocation costs in support of activity delivery.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 26 homes for non low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 64 non low-to-moderate income homeowner assistance projects, 11 of which received final inspection during the reporting period. 5661.64 - Payroll allocation costs in support of activity delivery.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 27 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 80 urgent need homeowner assistance projects, 16 of which received final inspection during the reporting period. 8662.27 - Payroll allocation costs in support of activity delivery.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | $3,822,560.28 in expenditures from Q1 2023, posted in Q2 2023 due to DRGR error not allowing the previous quarter&apos;s entry. During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 33 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 100 urgent need homeowner assistance projects, 20 of which received final inspection during the reporting period. 11086.38 - State costs in support of activity delivery.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 34 homes for non low-to-moderate income households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 113 non low-to-moderate income homeowner assistance projects, 13 of which received final inspection during the reporting period. $14357.54 - State costs in support of activity delivery.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 31 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 130 urgent need homeowner assistance projects, 17 of which received final inspection during the reporting period.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 15 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 137 urgent need homeowner assistance projects, 7 of which received final inspection during the reporting period. 15064.16 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 5 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 154 urgent need homeowner assistance projects, 17 of which received final inspection during the reporting period.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 14 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 164 urgent need homeowner assistance projects, 10 of which received final inspection during the reporting period. Of the 10 project completed this quarter for City of Houston HAP UN, 9 were entirely HAP funded, 1 was majority (>=50 percent) funded by HAP. 41223.69 - Quarterly expenditure for state costs in support of activity delivery.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 16 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 187 urgent need homeowner assistance projects, 25 of which received final inspection during the reporting period. 25 projects were entirely funded by this program, and 0 were majority funded from HOS. All performance measures and beneficiaries are reported under the majority funding activity.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 5 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 171 urgent need homeowner assistance projects, 10 of which received final inspection during the reporting period. During the reporting period 10 projects were funded by this activity and completed this quarter. All performance measures and beneficiaries are reported under this funding activity.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, payments were made as a result of approved applications and construction draw submissions. The GLO also made payments to vendors working on the program. During the reporting period the GLO paid for costs associated with the rehabilitation/reconstruction of approximately 688 homes for urgent need households. The GLO reports completed rehabilitation and reconstruction projects in DRGR once the final inspection is completed. To date, final inspection has been completed on 178 urgent need homeowner assistance projects, 15 of which received final inspection during the reporting period. During the reporting period 15 projects were funded by this activity and completed this quarter. All performance measures and beneficiaries are reported under this funding activity.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Houston continued to make progress on ongoing projects. No households were completed during the quarter. Additionally, the GLO is actively reconciling costs for projects that received funding from both the Harvey and Mitigation allocations in the GLO system of record as well as DRGR. The GLO expects to resume reporting of accomplishments in subsequent quarters.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, all households have completed construction. Overall, for this activity, a total of 171 households received a rehabilitation/reconstruction benefit.
HAP[Houston]_HMID_UN | City of Houston HAP | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 76 projects are underway.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 88 project(s) was underway
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 178 project(s) was underway.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 131 additional projects were completed of 385 total projects. 147 projects are underway. 17373.24 - Payroll Allocation
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 250 additional projects were completed of 527 total projects. 100 projects are underway. 20,674.69 - Payroll Allocation
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 339 additional projects were completed of 567 total projects. 58 projects are underway. 28002.4 - Payroll Allocations
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 384 additional projects were completed of 673 total projects. 69 projects are underway. $62732.17 - Payroll Allocations.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 63 additional projects were completed of 130 total projects. 67 projects are underway. 49827.73 - Payroll Allocations.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | 45 additional projects were completed out of 130 total projects managed during the reporting period. 85 projects are underway. 48127.4 - Payroll Allocations
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 66 additional projects were completed out of 103 total projects managed during the reporting period. 37 projects are underway. 53390.86 - Payroll Allocations.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 35 additional projects were completed out of 73 total projects managed during the reporting period. 38 projects are underway. 40342.06 - Payroll Allocations.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 10 additional projects were completed out of 105 total projects managed during the reporting period. 95 projects are underway. 27262.89 - Payroll Allocations.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 69 additional projects were completed out of 127 total projects managed during the reporting period. 58 projects are underway. 38226.88 - Payroll Allocations.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 49 additional projects were completed out of 84 total projects managed during the reporting period. 35 projects are underway. 24614.96 - Payroll allocation costs in support of activity delivery.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 21 additional projects were completed out of 49 total projects managed during the reporting period. 28 projects are underway. 50028.06 - Payroll allocation costs in support of activity delivery.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | 20 additional projects were completed out of 20 total projects managed during the reporting period. 0 projects are underway. 23383.2 - Payroll allocation costs in support of activity delivery.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 8 additional projects were completed out of 17 total projects managed during the reporting period. 9 projects are underway. 38128.1 - State costs in support of activity delivery.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activities are underway, no reportable changes during this quarter. $28414.99 - State costs in support of activity delivery.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | 2 additional projects were completed out of 9 total projects managed during the reporting period. 7 projects are underway. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter 9179.07 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activities are underway, no reportable changes during this quarter
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 80837.84 - Quarterly expenditure for state costs in support of activity delivery.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 22925.97 - Quarterly expenditure for state costs in support of activity delivery.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 34509.54 - Quarterly expenditure for state costs in support of activity delivery.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 16006.27 - State costs in support of activity delivery.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 7111.2 - State costs in support of activity delivery.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 15163.71 - State costs in support of activity delivery.
HAP[SETRPC]_HMID_LMI | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period, 27 projects are underway.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period 28 project(s) was underway
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 49 project(s) was underway.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period, 42 additional projects were completed of 142 total projects. 46 projects are underway. 6702.39 - Payroll Allocation
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period, 75 additional projects were completed of 173 total projects. 27 projects are underway. 7,380.39 - Payroll Allocation
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period, 95 additional projects were completed of 185 total projects. 17 projects are underway. 10056.88 - Payroll Allocations
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period, 108 additional projects were completed of 228 total projects. 18 projects are underway. $21753.65 - Payroll Allocations.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, 14 additional projects were completed of 40 total projects. 26 projects are underway. 26399.96 - Payroll Allocations.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | 22 additional projects were completed out of 44 total projects managed during the reporting period. 22 projects are underway. 13855.85 - Payroll Allocations. Revisions to performance measures and demographics occurred due to overreporting in previous quarters.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-10-01 | 2022 Q1 | 17 additional projects were completed out of 33 total projects managed during the reporting period. 16 projects are underway. 11240.92 - Payroll Allocations.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-01-01 | 2022 Q2 | 7 additional projects were completed out of 34 total projects managed during the reporting period. 27 projects are underway. 8055.38 - Payroll Allocations.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | 23 additional projects were completed out of 39 total projects managed during the reporting period. 16 projects are underway. 12527.39 - Payroll Allocations.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | 7 additional projects were completed out of 22 total projects managed during the reporting period. 15 projects are underway. 8240.46 - Payroll allocation costs in support of activity delivery.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | 11 additional projects were completed out of 20 total projects managed during the reporting period. 9 projects are underway. 16615.65 - Payroll allocation costs in support of activity delivery.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | 5 additional projects were completed out of 5 total projects managed during the reporting period. 0 projects are underway. 7939.97 - Payroll allocation costs in support of activity delivery.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-04-01 | 2023 Q3 | 1 additional projects were completed out of 6 total projects managed during the reporting period. 5 projects are underway. 11325.86 - State costs in support of activity delivery.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | 2 additional projects were completed out of 5 total projects managed during the reporting period. 3 projects are underway. $8731.49 - State costs in support of activity delivery.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1 | 1 additional projects were completed out of 3 total projects managed during the reporting period. 2 projects are underway. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-01-01 | 2024 Q2 | Activities are underway, no reportable changes during this quarter 3204.01 - Quarterly expenditure related to state costs in support of activity delivery.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-04-01 | 2024 Q3 | 1 additional projects were completed out of 2 total projects managed during the reporting period. 1 projects are underway.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activities are underway, no reportable changes during this quarter. 26586.47 - Quarterly expenditure for state costs in support of activity delivery.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activities are underway, no reportable changes during this quarter. 7948.59 - Quarterly expenditure for state costs in support of activity delivery.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Activities are underway, no reportable changes during this quarter. 9350.52 - Quarterly expenditure for state costs in support of activity delivery.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-04-01 | 2025 Q3 | Activities are underway, no reportable changes during this quarter. There are currently no projects within this portfolio as the program nears completion. 2781.96 - State costs in support of activity delivery.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Activities are underway, no reportable changes during this quarter. 1112.58 - State costs in support of activity delivery.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | Activities are underway, no reportable changes during this quarter. 4580.5 - State costs in support of activity delivery.
HAP[SETRPC]_HMID_UN | HAP - SETRPC | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2026-01-01 | 2026 Q2
HC_ProgramIncomeTransfer | HC Program Income Transfer Activity | Program Income Transfer to CDBG Entitlement | Harris, County | 2023-10-01 | 2024 Q1
HC_ProgramIncomeTransfer | HC Program Income Transfer Activity | Program Income Transfer to CDBG Entitlement | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, a total amount of $8,955,179.92 was transferred in HUD&apos;s DRGR to IDIS to the County&apos;s CDBG/Entitlement Program as reported by HC PI Q4 2024 report .
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2019-04-01 | 2019 Q3
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2019-07-01 | 2019 Q4
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2020-01-01 | 2020 Q2 | Grantee continues administrative services of the Harvey Round 1 grant.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2020-04-01 | 2020 Q3 | During the reporting period, Harris County and the GLO continued to carry out administrative services for the County&apos;s housing and infrastructure programs.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2020-07-01 | 2020 Q4 | During the reporting period, Harris County continues to carry out administrative services for HAP, HRP, and buyout program.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2020-10-01 | 2021 Q1
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2021-01-01 | 2021 Q2
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2021-04-01 | 2021 Q3 | During the reporting period, Harris County continued to carry out administrative services for its housing and non-housing programs and planning activities.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed payroll costs associated with administering the grant. Payroll Allocations.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed costs associated with the administration of Harris County&apos;s programs. Payroll Allocations.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed payroll and vendor costs associated with administering the grant. Payroll allocation costs in support of activity delivery.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2022-10-01 | 2023 Q1 | The GLO reimbursed costs associated with the administration of Harris County&apos;s programs. 56475.14 - Payroll allocation costs in support of activity delivery.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2023-01-01 | 2023 Q2 | Negative expenditures for this quarter reflect a payroll allocation correction for GLO oversight.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with the administration of Harris County&apos;s programs.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2024-01-01 | 2024 Q2 | Activity&apos;s budget was adjusted to be comprised of both child grants, no change to the overall amount.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with the administration of Harris County&apos;s programs.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with the administration of Harris County&apos;s programs.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with the administration of Harris County&apos;s programs.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with the administration of Harris County programs.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with the administration of Harris County programs.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2025-07-01 | 2025 Q4 | Fully obligated this activity.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed administrative costs for four (4) payment requests.
HCADMIN_DA_NA_19-147-002-B490 | Administration | Administration | Harris, County | 2026-01-01 | 2026 Q2
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2019-04-01 | 2019 Q3
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2019-07-01 | 2019 Q4
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2020-07-01 | 2020 Q4
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2021-01-01 | 2021 Q2 | During the reporting period, Harris County had nine projects in construction, ranging from 3% to 45% complete, for its affordable rental program. The GLO reimbursed the County for acquisition costs associated with one multifamily rental project. The County submitted an additional $6.5 million in expenditures during the quarter that are pending review and approval.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2021-04-01 | 2021 Q3 | During the reporting period, Harris County had ten projects in construction, ranging from 0% to 63% complete, for its affordable rental program. The GLO reimbursed the County for acquisition and construction costs associated with four multifamily rental projects.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed Harris County for acquisition and construction costs associated with six multifamily developments, which are underway.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed Harris County for acquisition and construction costs associated with nine multifamily developments, which are underway.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed Harris County for acquisition and construction costs associated with 12 multifamily developments. Additionally, the GLO reimbursed costs associated with the delivery of the Affordable Rental Program. 3084.75 - Payroll Allocations.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed Harris County for acquisition and construction costs associated with ten (10) affordable rental properties, which are underway. The GLO also reimbursed costs associated with the delivery of the Affordable Rental Program and vendor costs associated with environmental reviews. 15698.7 - Payroll Allocations.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for construction costs associated with eight (8) affordable rental properties, which are underway. The Texas General Land Office also reimbursed costs associated with the delivery of the Affordable Rental Program and vendor costs associated with environmental reviews.9614.22 - Payroll allocation costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with twelve (12) affordable rental properties, which are underway. The GLO also reimbursed costs associated with the delivery of the Affordable Rental Program. 20779.61 - Payroll allocation costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with seven (7) affordable rental properties, which are underway. The GLO also reimbursed costs associated with the delivery of the Affordable Rental Program. 5227.91 - Payroll allocation costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with twelve (12) affordable rental properties, which are underway. The GLO also reimbursed costs associated with the delivery of the Affordable Rental Program. 11007.17 - State costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with twelve (12) affordable rental properties, which are underway. The GLO also reimbursed costs associated with the delivery of the Affordable Rental Program. $16558 - State costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with twelve (12) affordable rental properties, which are underway. The GLO also reimbursed costs associated with the delivery of the Affordable Rental Program. The Seaside Lodge project, which is dually funded with funds from the 2016 Floods grant, is complete and the County was reimbursed under that allocation&apos;s funding. Once the County is reimbursed with funding from this grant in Q1 2024, the beneficiaries will be reported.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with eleven (11) affordable rental properties, which are underway. The GLO also reimbursed costs associated with the delivery of the Affordable Rental Program. 3310.34 - Quarterly expenditure related to state costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with twelve (12) affordable rental properties, which are underway. Two (2) projects were completed and had retainage draws paid. The GLO also reimbursed costs associated with the delivery of the Affordable Rental Program.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with eight (8) affordable rental properties, which are underway. The GLO also reimbursed costs associated with the delivery of the Affordable Rental Program. 42346.77 - Quarterly expenditure for state costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with eight (8) affordable rental properties, which are underway. One project, Arbor at Wayforest, completed the closeout process in this quarter. The GLO also reimbursed costs associated with the delivery of the Affordable Rental Program. 15082.53 - Quarterly expenditure for state costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with ten (10) affordable rental properties, which are underway or completed. The GLO also reimbursed costs associated with the delivery of the Affordable Rental Program. 16446.89 - Quarterly expenditure for state costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with nine (9) affordable rental properties, which are underway or completed. The GLO also reimbursed costs associated with the delivery of the Affordable Rental Program. 10963.04 - State costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with three (3) affordable rental property which is complete. 5205.72 - State costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with two (2) affordable rental properties. 12800.98 - State costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490 | HC Affordable Rental Program | Affordable Rental Housing | Harris, County | 2026-01-01 | 2026 Q2
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2021-10-01 | 2022 Q1 | Public service activity added to the Harris County Affordable Rental Program.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, ARP funds were incorrectly drawn from the ARP Public Services activity. The $2,412,092.57 should have been drawn from the Affordable Rental Program (rental activity), instead of the Affordable Rental Program - Public Services activity, and will be corrected in the Quarter 2 2022 QPR.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2022-04-01 | 2022 Q3 | The negative expenditure shown in the period is a correction from a voucher error in the previous quarter. Costs moved to HCARP_DA_LMI_19-147-002-B490.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the ARP-related Public Services program. 2751.17 - State costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the ARP-related Public Services program. $3627.31 - State costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the ARP-related Public Services program.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the ARP-related Public Services program. 194.89 - Quarterly expenditure related to state costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the ARP-related Public Services program. Two hundred thirty-five (235) individuals have completed the program and an additional twenty-seven (27) are underway.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the ARP-related Public Services program. Two hundred forty-nine (249) individuals have completed the program and an additional nine (9) are underway. 2493.09 - Quarterly expenditure for state costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the ARP-related Public Services program. Two hundred fifty-seven (257) individuals have completed the program. 907.05 - Quarterly expenditure for state costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with the administration of Public Services Affordable Rental program. 1130.98 - Quarterly expenditure for state costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with the administration of Public Services Affordable Rental program. 811.38 - State costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with the administration of Public Services Affordable Rental program. 400.27 - State costs in support of activity delivery.
HCARP_DA_LMI_19-147-002-B490_PS | HC Affordable Rental Program | Public services | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with the administration of Public Services Affordable Rental program. 753.64 - State costs in support of activity delivery.
HCBP_DA_LMH_19-147-002-B490_HA | HC Buyout & Acquisition | Homeownership Assistance to low- and moderate-income | Harris, County | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
HCBP_DA_LMH_19-147-002-B490_HA | HC Buyout & Acquisition | Homeownership Assistance to low- and moderate-income | Harris, County | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained changes to the performance statement.
HCBP_DA_LMH_19-147-002-B490_HA | HC Buyout & Acquisition | Homeownership Assistance to low- and moderate-income | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Residential Buyout program.
HCBP_DA_LMH_19-147-002-B490_HA | HC Buyout & Acquisition | Homeownership Assistance to low- and moderate-income | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Buyout program. 46.02 - State costs in support of activity delivery.
HCBP_DA_LMH_19-147-002-B490_HA | HC Buyout & Acquisition | Homeownership Assistance to low- and moderate-income | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Residential Buyout Program. $61.5 - State costs in support of activity delivery.
HCBP_DA_LMH_19-147-002-B490_HA | HC Buyout & Acquisition | Homeownership Assistance to low- and moderate-income | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Residential Buyout Program.
HCBP_DA_LMH_19-147-002-B490_HA | HC Buyout & Acquisition | Homeownership Assistance to low- and moderate-income | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Residential Buyout Program. 29.51 - Quarterly expenditure related to state costs in support of activity delivery.
HCBP_DA_LMH_19-147-002-B490_HA | HC Buyout & Acquisition | Homeownership Assistance to low- and moderate-income | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Residential Buyout Program. 126.8 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained changes to the performance statement.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Residential Buyout program.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Buyout program. 2547.79 - State costs in support of activity delivery.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Residential Buyout Program. $2608.03 - State costs in support of activity delivery.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated incentives for five (5) households, as well as costs associated with delivering the Residential Buyout Program.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed incentive costs for nine (9) households, as well as costs associated with delivering the Residential Buyout Program. 576.64 - Quarterly expenditure related to state costs in support of activity delivery.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed incentive costs for eighty-eight (88) households, as well as costs associated with delivering the Residential Buyout Program.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed incentive costs for one hundred twenty-five (125) households, as well as costs associated with delivering the Residential Buyout Program. 13739.3 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed incentive costs associated with thirty-six (36) households, as well as costs associated with delivering the Residential Buyout Program. 6194.7 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed incentive costs associated with sixty-four (64) households, as well as costs associated with delivering the Residential Buyout Program. 9997.52 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed incentive costs associated with one hundred and seventy-nine (179) households, as well as costs associated with delivering the Residential Buyout Program. 8518.82 - State costs in support of activity delivery.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed incentive costs associated with one hundred and thirty (130) households, as well as costs associated with delivering the Residential Buyout Program. 4772.96 - State costs in support of activity delivery.
HCBP_DA_LMHI_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed incentive costs associated with one hundred and eleven (111) households for the Residential Buyout Program- Housing Incentives. 12356.82 - State costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2019-04-01 | 2019 Q3
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2020-04-01 | 2020 Q3 | During the reporting period, Harris County had applications under review and no new projects underway for its Buyout Program.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2020-07-01 | 2020 Q4
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2021-01-01 | 2021 Q2
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2021-04-01 | 2021 Q3 | During the reporting period, Harris County continued to carry out buyout activities and submitted 120 projects in the quarter to the GLO for eligibility review.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2021-10-01 | 2022 Q1 | The GLO reimbursed vendor costs associated with environmental reviews. Voucher adjustment moved funds from Urgent Need activity to LMI activity due to the Low to Moderate Area designation of buyout areas.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Buyout Program. Payroll Allocations.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Residential Buyout Program. The GLO also reimbursed vendor costs associated with environmental reviews. 9644.92 - Payroll Allocations.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed costs associated with delivering the Residential Buyout Program and vendor costs associated with environmental reviews. 4087.63 - Payroll allocation costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed costs associated with two (2) buyout properties, along with costs for delivering the Residential Buyout Program and vendor costs associated with environmental reviews. 11211.59 - Payroll allocation costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed costs associated with thirty-five (35) buyout properties, along with costs for delivering the Residential Buyout Program. 5494.05 - Payroll allocation costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with eighty (80) buyout properties, along with costs for delivering the Residential Buyout Program. 2436.28 - State costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with fifty-one (51) buyout properties, along with costs for delivering the Residential Buyout Program. $3397.15 - State costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with one hundred eight (108) buyout properties, along with costs for delivering the Residential Buyout Program.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with seventy-nine (79) buyout properties, along with costs for delivering the Residential Buyout Program. 2100.58 - Quarterly expenditure related to state costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with three hundred fifty-five (355) buyout properties, along with costs for delivering the Residential Buyout Program.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with three hundred fifty-two (352) buyout properties, along with costs for delivering the Residential Buyout Program. 31167.05 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with one hundred seventy-three (173) buyout properties, along with costs for delivering the Residential Buyout Program. 9563.69 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with two hundred and eight (208) buyout properties, along with costs for delivering the Residential Buyout Program. 15510.08 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with three hundred and fifty-nine (359) buyout properties, along with costs for delivering the Residential Buyout Program. 12585.39 - State costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with two hundred and sixty eight (268) buyout properties, along with costs for delivering the Residential Buyout Program. 6818.83 - State costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with two hundred and sixty (206) buyout properties for the Residential Buyout Program- Acquisition. 17656.6 - State costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_ACQ | HC Buyout & Acquisition | Acquisition - buyout of residential properties | Harris, County | 2026-01-01 | 2026 Q2
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained changes to the performance statement.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed vendor costs associated with environmental reviews.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Residential Buyout program.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed relocation assistance costs associated with 1 buyout property, along with costs for delivering the Residential Buyout Program.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed relocation assistance costs associated with eighteen (18) buyout properties, along with costs for delivering the Residential Buyout Program. $5477.06 - State costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed relocation assistance costs associated with ninety (90) buyout properties, along with costs for delivering the Residential Buyout Program.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with sixty-three (63) buyout relocations, along with costs for delivering the Residential Buyout Program. 3195.4 - Quarterly expenditure related to state costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with five hundred eighteen (518) buyout relocations, along with costs for delivering the Residential Buyout Program.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with two hundred twenty-one (221) buyout relocations, along with costs for delivering the Residential Buyout Program. 46874.74 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with four hundred seventy-four (474) buyout relocations, along with costs for delivering the Residential Buyout Program. 14466.35 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with one hundred two (102) buyout relocations, along with costs for delivering the Residential Buyout Program. 23635.45 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with three hundred thirty-eight (338) buyout relocations, along with costs for delivering the Residential Buyout Program. 19771.91 - State costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with four hundred nineteen (419) buyout relocations, along with costs for delivering the Residential Buyout Program. 10890.35 - State costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with three hundred sixty-six (366) buyout relocations, along with costs for delivering the Residential Buyout Program- Relocation Assistance. 28358.06 - State costs in support of activity delivery.
HCBP_DA_LMI_19-147-002-B490_RA | HC Buyout & Acquisition | Relocation payments and assistance | Harris, County | 2026-01-01 | 2026 Q2
HCBP_DA_UN_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed incentive costs for two (2) households, as well as costs associated with delivering the Residential Buyout Program. 30.84 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_UN_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed incentive costs for one (1) household, as well as costs associated with delivering the Residential Buyout Program. 86.41 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_UN_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed incentive costs for one (1) household, as well as costs associated with delivering the Residential Buyout Program. 193.84 - Quarterly expenditure for state costs in support of activity delivery.
HCBP_DA_UN_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed incentive costs for two (2) households, as well as costs associated with delivering the Residential Buyout Program. 151.01 - State costs in support of activity delivery.
HCBP_DA_UN_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed incentive costs for four (4) households, as well as costs associated with delivering the Residential Buyout Program. 74.44 - State costs in support of activity delivery.
HCBP_DA_UN_19-147-002-B490_HI | HC Buyout & Acquisition | Housing incentives to encourage resettlement | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed incentive costs for four (4) households in the Urgent Need Residential Buyout Program- Housing Incentives. 326.92 - State costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Commercial Buyout program. 116.18 - Payroll Allocations.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed costs associated with delivering the Residential Buyout Program and vendor costs associated with environmental reviews.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed costs associated with four (4) buyout properties, along with costs for delivering the Commercial Buyout Program. 116.18 - Payroll allocation costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed costs associated with three (3) buyout properties, along with costs for delivering the Commercial Buyout Program. 350.65 - Payroll allocation costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with seven (7) buyout properties, along with costs for delivering the Commercial Buyout Program. 145.1 - State costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with two (2) buyout properties, along with costs for delivering the Commercial Buyout Program. $1313.5 - State costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with fourteen (14) buyout properties, along with costs for delivering the Commercial Buyout Program.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with seven (7) buyout properties, along with costs for delivering the Commercial Buyout Program. 412.48 - Quarterly expenditure related to state costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with fourteen (14) buyout properties, along with costs for delivering the Commercial Buyout Program.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with thirty (30) buyout properties, along with costs for delivering the Commercial Buyout Program. 5153.3 - Quarterly expenditure for state costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with twenty-five (25) properties, along with costs for delivering the Commercial Buyout Program. 2246.41 - Quarterly expenditure for state costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with eighteen (18) properties, along with costs for delivering the Commercial Buyout Program. 2396.04 - Quarterly expenditure for state costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with twenty-five (25) properties, along with costs for delivering the Commercial Buyout Program. 1837.49 - State costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with thirty-two (32) properties, along with costs for delivering the Commercial Buyout Program. 1420.23 - State costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with eighteen (18) properties, along with costs for delivering the Commercial Buyout Program. 3321.35 - State costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_ACQ | HC Commercial Buyout | Acquisition - general | Harris, County | 2026-01-01 | 2026 Q2
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained changes to the performance statement.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed relocation assistance costs associated with nineteen (19) buyout properties, along with costs for delivering the Commercial Buyout Program.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs for delivering the Commercial Buyout Program. $128.12 - State costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs for delivering the Commercial Buyout Program.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with eight (8) commercial buyout relocations, along with costs for delivering the Commercial Buyout Program. 438.3 - Quarterly expenditure related to state costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with twenty-six (26) commercial buyout relocations, along with costs for delivering the Commercial Buyout Program.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with four (4) commercial buyout relocations, along with costs for delivering the Commercial Buyout Program. 5557.49 - Quarterly expenditure for state costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with three (3) commercial buyout relocations, along with costs for delivering the Commercial Buyout Program. 2410.92 - Quarterly expenditure for state costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with nine (9) commercial buyout relocations, along with costs for delivering the Commercial Buyout Program. 2613.38 - Quarterly expenditure for state costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with eight (8) commercial buyout relocations, along with costs for delivering the Commercial Buyout Program. 2033.72 - State costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with eighteen (18) commercial buyout relocations, along with costs for delivering the Commercial Buyout Program. 1592.56 - State costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with thirteen (13) commercial buyout relocations, along with costs for delivering the Commercial Buyout Program. 3873.55 - State costs in support of activity delivery.
HCComBP_DA_LMI_19-147-002-B490_RA | HC Commercial Buyout | Relocation payments and assistance | Harris, County | 2026-01-01 | 2026 Q2
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2020-04-01 | 2020 Q3
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with two flood and drainage projects, which are underway.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with two flood and drainage projects, which are underway.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with one flood and drainage project, which is underway. Additionally, the GLO reimbursed costs associated with the delivery of the Competitive Infrastructure Program. 300.22 - Payroll Allocations.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with 2 flood and drainage projects. The GLO also reimbursed costs associated with the delivery of the Competitive Infrastructure program. 922.47 - Payroll Allocations.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for costs associated with one (1) flood and drainage project. The Texas General Land Office also reimbursed costs associated with the delivery of the Competitive Infrastructure Program. 513.07 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. 1078.29 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. 449.86 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with two (2) flood and drainage projects, along with costs associated with delivering the Competitive Infrastructure program.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. Quarterly expenditure related to state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 9383.75 - Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 2574.61 - Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with two (2) Flood and Drainage projects, along with costs for delivering the Competitive Infrastructure Program. 294.58 - State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with one (1) Flood and drainage projects, along with costs for delivering the Competitive Infrastructure Program. 919.45 - State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2026-01-01 | 2026 Q2
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2021-01-01 | 2021 Q2
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2021-10-01 | 2022 Q1 | The GLO reimbursed vendor costs associated with environmental reviews.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with one public facility project. Additionally, the GLO reimbursed costs associated with the delivery of the Competitive Infrastructure Program, including an environmental review. 400.29 - Payroll Allocations.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. The GLO also reimbursed vendor costs associated with environmental reviews. 1230.02 - Payroll Allocations.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for costs associated with one (1) public facility project. The Texas General Land Office also reimbursed costs associated with the delivery of the Competitive Infrastructure Program. 684.08 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) public facility project. The GLO also reimbursed costs associated with the delivery of the Competitive Infrastructure Program. 1437.73 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) public facility project. The GLO also reimbursed costs associated with the delivery of the Competitive Infrastructure Program and vendor costs associated with environmental reviews. 1199.62 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with four (4) public facilities projects, along with costs associated with delivering the Competitive Infrastructure program.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. Quarterly expenditure related to state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with three (3) public facilities projects, along with costs of delivering the Competitive Infrastructure Program.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with one (1) public facilities project, along with costs of delivering the Competitive Infrastructure Program. 10218.59 - Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with three (3) public facilities projects, along with costs of delivering the Competitive Infrastructure Program. 1528.36 - Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with three (3) public facilities projects, along with costs of delivering the Competitive Infrastructure Program. 3090.14 - Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with three (3) public facilities projects, along with costs of delivering the Competitive Infrastructure Program. 1162.32 - State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with three (3) Public Facilities projects, along with costs for delivering the Competitive Infrastructure Program 353.59 - State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 1103.62 - State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2026-01-01 | 2026 Q2
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2019-07-01 | 2019 Q4
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2020-07-01 | 2020 Q4 | During the reporting period, Harris County continued to carry out its Public Services project.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2020-10-01 | 2021 Q1 | During the reporting period, Harris County continued to carry out its public services project.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2021-01-01 | 2021 Q2 | During the reporting period, Harris County had one (1) public services transit project underway for its Competitive Infrastructure program. 9,788 riders were served in Quarter 1 2021. The County submitted an additional $2.2 million in expenditures during the quarter for the Competitive Infrastructure program that are pending review and approval.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2021-04-01 | 2021 Q3 | During the reporting period, Harris County had 1 public services transit project underway for its Competitive Infrastructure program. 7,125 riders were served in Quarter 2 2021.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with one Public Service transit project, which is underway.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with one Public Service transit project, which is underway.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed Harris County for construction costs associated with one public service project. Additionally, the GLO reimbursed costs associated with the delivery of the Competitive Infrastructure Program. 50.04 - Payroll Allocations.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. 153.74 - Payroll Allocations.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for costs associated with one (1) public services project. The Texas General Land Office also reimbursed costs associated with the delivery of the Competitive Infrastructure Program. 85.51 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. 179.71 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. 149.95 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with one (1) public services project, along with costs associated with delivering the Competitive Infrastructure program.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. Quarterly expenditure related to state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 1703.42 - Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 514.75 - Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 58.9 - State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_PS | Public Services | Public services | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 183.83 - State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2021-01-01 | 2021 Q2
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2021-10-01 | 2022 Q1 | The GLO reimbursed vendor costs associated with environmental reviews.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Competitive Infrastructure Program. Payroll Allocations.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. 307.49 - Payroll Allocations.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed costs associated with delivering the Competitive Infrastructure program.171.02 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) sewer facility project. The GLO also reimbursed costs associated with the delivery of the Competitive Infrastructure Program. 359.43 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) sewer facility project. The GLO also reimbursed costs associated with the delivery of the Competitive Infrastructure Program. 299.9 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with one (1) sewer facilities project, along with costs associated with delivering the Competitive Infrastructure program. $916.65 - State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with one (1) sewer facilities project, along with costs associated with delivering the Competitive Infrastructure program.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. Quarterly expenditure related to state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with one (1) sewer facilities project, along with costs for delivering the Competitive Infrastructure program. The Sunbelt Fresh Water Supply District - Fairgreen and High Meadow Sewer Improvement project was completed during this reporting period.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 3405.28 - Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 1029.5 - Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 117.79 - State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 367.66 - State costs in support of activity delivery.
HCCompApp_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2026-01-01 | 2026 Q2
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2021-01-01 | 2021 Q2
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Competitive Infrastructure Program. Payroll Allocations.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with delivering the Competitive Infrastructure program. The GLO also reimbursed vendor costs associated with environmental reviews. 461.24 - Payroll Allocations.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed costs associated with delivering the Competitive Infrastructure program.256.53 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. 539.14 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. 899.71 - Payroll allocation costs in support of activity delivery.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. State costs in support of activity delivery.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. State costs in support of activity delivery.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with two (2) flood and drainage projects, along with costs associated with delivering the Competitive Infrastructure program.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure program. Quarterly expenditure related to state costs in support of activity delivery.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with one (1) flood and drainage project, along with costs for delivering the Competitive Infrastructure Program.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with one (1) flood and drainage project, along with costs of delivering the Competitive Infrastructure Program. 5110.08 - Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 1545.13 - Quarterly expenditure for state costs in support of activity delivery.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. State costs in support of activity delivery.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Competitive Infrastructure Program. 176.79 - State costs in support of activity delivery.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Urgent Need Competitive Infrastructure Program. 551.79 - State costs in support of activity delivery.
HCCompApp_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2026-01-01 | 2026 Q2
HCFCD_DA_HMID_LMI_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2024-04-01 | 2024 Q3 | New activity created.
HCFCD_DA_HMID_LMI_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2024-07-01 | 2024 Q4 | During the reporting period, there were no draws expensed. These expenses are for vendor and/or GLO staff time. Quarterly expenditure for state costs in support of activity delivery.
HCFCD_DA_HMID_LMI_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2024-10-01 | 2025 Q1 | During the reporting period, there were no Subrecipient draws were disbursed. These expenses are for vendor and/or GLO staff time. 38444.48 - Quarterly expenditure for state costs in support of activity delivery.
HCFCD_DA_HMID_LMI_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2025-01-01 | 2025 Q2 | During the reporting period, expenses are for vendor and/or GLO staff time. 47126.77 - Quarterly expenditure for state costs in support of activity delivery.
HCFCD_DA_HMID_LMI_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed Harris County Flood Control District for cost associated with project delivery and engineering design for three (3) of their Flood and Drainage projects. The GLO also reimbursed costs associated with the delivery of the program. 19780.42 - State costs in support of activity delivery.
HCFCD_DA_HMID_LMI_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed Harris County Flood Control District for cost associated with project delivery and engineering design for four (4) of their Flood and Drainage projects. The GLO also reimbursed costs associated with the delivery of the program. 11318.91 - State costs in support of activity delivery.
HCFCD_DA_HMID_LMI_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed Harris County Flood Control District for cost associated with five (5) of their Flood and Drainage projects. The GLO also reimbursed costs associated with the Delivery of the program. 22930.05 - State costs in support of activity delivery.
HCFCD_DA_HMID_LMI_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2026-01-01 | 2026 Q2
HCFCD_DA_HMID_UN_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2024-04-01 | 2024 Q3 | New activity created.
HCFCD_DA_HMID_UN_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2024-07-01 | 2024 Q4 | During the reporting period, there were no draws expensed. These expenses are for vendor and/or GLO staff time. Quarterly expenditure for state costs in support of activity delivery.
HCFCD_DA_HMID_UN_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2024-10-01 | 2025 Q1 | During the reporting period, there were no Subrecipient draws were disbursed. These expenses are for vendor and/or GLO staff time. Quarterly expenditure for state costs in support of activity delivery.
HCFCD_DA_HMID_UN_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2025-01-01 | 2025 Q2 | During the reporting period, there were no Subrecipient draws were disbursed. These expenses are for vendor and/or GLO staff time. 31417.71 - Quarterly expenditure for state costs in support of activity delivery.
HCFCD_DA_HMID_UN_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed Harris County Flood Control District for cost associated with engineering design for two (2) of their Urgent Need Flood and Drainage projects. The GLO also reimbursed costs associated with the delivery of the program. 9107.24 - State costs in support of activity delivery.
HCFCD_DA_HMID_UN_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed Harris County Flood Control District for cost associated with engineering design for two (2) of their Urgent Need Flood and Drainage projects. The GLO also reimbursed costs associated with the delivery of the program. 2829.74 - State costs in support of activity delivery.
HCFCD_DA_HMID_UN_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed Harris County Flood Control District for cost associated with engineering design for two (2) of their Urgent Need Flood and Drainage projects. The GLO also reimbursed costs associated with the delivery of the program. 11936.53 - State costs in support of activity delivery.
HCFCD_DA_HMID_UN_24-033-000-E072 | Flood and Drainage | Rehabilitation/reconstruction of public facilities | HARRIS COUNTY FLOOD CONTROL | 2026-01-01 | 2026 Q2
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2019-04-01 | 2019 Q3
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2019-07-01 | 2019 Q4
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-01-01 | 2020 Q2
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-04-01 | 2020 Q3 | During the reporting period, Harris County had applications under review and two projects are underway for its Homeowner Assistance Program.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-07-01 | 2020 Q4 | During the reporting period, Harris County had applications under review and 94 underway for its HAP project.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-10-01 | 2021 Q1
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-01-01 | 2021 Q2
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-04-01 | 2021 Q3
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-07-01 | 2021 Q4 | During the reporting period, HAP projects were underway.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-10-01 | 2022 Q1 | The GLO reimbursed vendor costs associated with environmental reviews.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed Harris County for construction costs related to 5 LMI households. Additionally, the GLO reimbursed costs associated with the delivery of the Homeowner Assistance Program. 4391.72 - Payroll Allocations.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with seventy-eight (78) low-to-moderate income households in the Homeowner Assistance Program. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. 10461.07 - Payroll Allocations.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for costs associated with one-hundred twenty-two (122) low-to-moderate income households in the Homeowner Assistance Program. The Texas General Land Office also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews.5132.31 - Payroll allocation costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with twenty-five (25) low-to-moderate income households in the Homeowner Assistance Program. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. In addition, an adjustment was made in Quarter 4 2022 to move $73,380.46 in funds from the HAP Public Service activity to the HAP Rehabilitation/ Reconstruction activity due to an error in Quarter 3 2022. 13215.98 - Payroll allocation costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with the delivery of the Homeowner Assistance program. 10289.35 - Payroll allocation costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with the delivery of the Homeowner Assistance program. 18686.25 - State costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Assistance Program. $10130.27 - State costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with nine (9) LMI households, as well as costs associated with the delivery of the Homeowner Assistance Program.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with seven (7) LMI households, as well as costs associated with the delivery of the Homeowner Assistance Program. 3129.1 - Quarterly expenditure related to state costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with sixty-one (61) LMI households, as well as costs associated with the delivery of the Homeowner Assistance Program. All projects for this program were reported as complete on the QPR after receiving a final inspection.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with fifty-seven (57) LMI households, as well as costs associated with the delivery of the Homeowner Assistance Program. All projects for this program were reported as complete on the QPR after receiving a final inspection. 27253.57 - Quarterly expenditure for state costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with one hundred one (101) LMI households, as well as costs associated with the delivery of the Homeowner Assistance Program. All projects for this program were reported as complete on the QPR after receiving a final inspection. 11668.94 - Quarterly expenditure for state costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with eighty-two (82) LMI households, as well as costs associated with the delivery of the Homeowner Assistance Program. All projects for this program were reported as complete (100% expended) 14562.52 - Quarterly expenditure for state costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP projects. 2047.67 - State costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP projects. 265.96 - State costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Housing Assistance Program. 3330.38 - State costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2026-01-01 | 2026 Q2
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2021-10-01 | 2022 Q1 | Public service activity added to the Harris County Urgent Need Homeowner Assistance Program.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2022-07-01 | 2022 Q4 | Homeowner Assistance Program (HAP) funds were incorrectly drawn from the HAP Public Services activity. The $73,380.46 should have been drawn from the Homeowner Assistance Program (rehabilitation/ reconstruction activity), instead of the Homeowner Assistance Program - Public Services activity, and will be corrected in the Quarter 4 2022 QPR.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2022-10-01 | 2023 Q1 | In Quarter 3 2022, Homeowner Assistance Program (HAP) funds were incorrectly drawn from the HAP Public Services activity. The $73,380.46 should have been drawn from the Homeowner Assistance Program (rehabilitation/ reconstruction activity), instead of the Homeowner Assistance Program - Public Services activity. The adjustment was made in Quarter 4 2022.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services program.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services Program. $23.6 - State costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services Program.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services Program. 23.72 - Quarterly expenditure related to state costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services project. One hundred fifteen (115) LMI individuals have completed the program. The GLO also reimbursed costs associated with delivering the Public Services project.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services project. One hundred fifteen (115) LMI individuals have completed the program. The GLO also reimbursed costs associated with delivering the Public Services project. 206.59 - Quarterly expenditure for state costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services project. One hundred fifteen (115) LMI individuals have completed the program. 93.7 - Quarterly expenditure for state costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services project. One hundred fifteen (115) LMI individuals have completed the program. 129.38 - Quarterly expenditure for state costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services project. 447.89 - State costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with one (1) HAP-related Public Services project. 132.99 - State costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Housing Assistance Program- Public Services. 32.86 - State costs in support of activity delivery.
HCHAP_DA_LMI_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2026-01-01 | 2026 Q2
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2019-04-01 | 2019 Q3
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2019-07-01 | 2019 Q4
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-01-01 | 2020 Q2
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-04-01 | 2020 Q3 | During the reporting period, Harris County had applications under review and no projects underway for its Homeowner Assistance Program.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-07-01 | 2020 Q4 | During the reporting period, Harris County had applications under review and 25 underway for its HAP project.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-10-01 | 2021 Q1
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-01-01 | 2021 Q2
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-04-01 | 2021 Q3
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-07-01 | 2021 Q4 | During the reporting period, HAP projects were underway.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-10-01 | 2022 Q1 | Harris County revised this activity to reallocate funds to other projects.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Assistance Program. Payroll Allocations.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with twenty-nine (29) non-low-to-moderate income households in the Homeowner Assistance Program. The GLO also reimbursed costs associated with delivering the program and vendor costs associated with environmental reviews. 2615.29 - Payroll Allocations.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for costs associated with one (1) Urgent Need household in the Homeowner Assistance Program. The Texas General Land Office also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews.1158.83 - Payroll allocation costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with twenty-six (26) Urgent Need households in the Homeowner Assistance Program. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. 3179.77 - Payroll allocation costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with the delivery of the Homeowner Assistance program. 2382.24 - Payroll allocation costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with the delivery of the Homeowner Assistance program. 4675.61 - State costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Assistance Program. $2491.37 - State costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with two (2) Urgent-Need households, as well as costs associated with the delivery of the Homeowner Assistance Program.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with two (2) Urgent-Need households, as well as costs associated with the delivery of the Homeowner Assistance Program. 776.33 - Quarterly expenditure related to state costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with twenty-four (24) Urgent Need households, as well as costs associated with the delivery of the Homeowner Assistance Program. All projects for this program were reported as complete on the QPR after receiving a final inspection.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with twenty-four (24) Urgent Need households, as well as costs associated with the delivery of the Homeowner Assistance Program. All projects for this program were reported as complete on the QPR after receiving a final inspection. 6761.55 - Quarterly expenditure for state costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with twelve (12) Urgent Need households, as well as costs associated with the delivery of the Homeowner Assistance Program. All projects for this program were reported as complete on the QPR after receiving a final inspection. 2835.45 - Quarterly expenditure for state costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with twenty three (23) Urgent Need households, as well as costs associated with the delivery of the Homeowner Assistance Program. All projects are completed (100% expensed). 3479.58 - Quarterly expenditure for state costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP projects. 721.62 - State costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP projects. 132.99 - State costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Urgent Need Housing Assistance Program. 816.39 - State costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490 | HC HAP | Rehabilitation/reconstruction of residential structures | Harris, County | 2026-01-01 | 2026 Q2
HCHAP_DA_UN_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2021-10-01 | 2022 Q1 | Public service activity added to the Harris County low to-moderate income Homeowner Assistance Program.
HCHAP_DA_UN_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services program.
HCHAP_DA_UN_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services Program. $23.6 - State costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services Program.
HCHAP_DA_UN_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services Program. 23.72 - Quarterly expenditure related to state costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with the HAP-related Public Services project. Twenty (20) Urgent Need (UN) individuals have completed the program. The GLO also reimbursed costs associated with delivering the Public Services project.
HCHAP_DA_UN_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with the HAP-related Public Services project. Twenty (20) Urgent Need (UN) individuals have completed the program. The GLO also reimbursed costs associated with delivering the Public Services project. 206.57 - Quarterly expenditure for state costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services project. Twenty (20) Urgent Need (UN) individuals have completed the program. 93.7 - Quarterly expenditure for state costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the HAP- Public Service program. 129.38 - Quarterly expenditure for state costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the HAP-related Public Services project. 447.89 - State costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with one (1) Urgent Need HAP-related Public Services project. 132.99 - State costs in support of activity delivery.
HCHAP_DA_UN_19-147-002-B490_PS | HC HAP | Public services | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Urgent Need Housing Assistance Program- Public Services. 32.86 - State costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2019-04-01 | 2019 Q3
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-04-01 | 2020 Q3 | During the reporting period, Harris County had applications under review and 58 underway for its Homeowner Reimbursement Program.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-07-01 | 2020 Q4 | During the reporting period, Harris County completed 1 HRP project and 78 were underway.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-10-01 | 2021 Q1 | During the reporting period, Harris County completed 1 HRP project and 113 were underway.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-01-01 | 2021 Q2
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-04-01 | 2021 Q3 | During the reporting period, GLO reimbursed the County for 4 HRP projects and 202 new projects were submitted this quarter.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-07-01 | 2021 Q4 | During the reporting period, GLO reimbursed Harris County for 31 LMI HRP projects and 52 new projects were submitted this quarter.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-10-01 | 2022 Q1 | During the reporting period, GLO reimbursed Harris County for eighty-three (83) LMI HRP projects and three (3) new projects were submitted this quarter. The GLO reimbursed vendor costs associated with environmental reviews.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, GLO reimbursed Harris County for costs related to 210 LMI HRP projects. Additionally, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement Program. 2238.51 - Payroll Allocations.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with one hundred two (102) low-to-moderate income households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the Homeowner Reimbursement Program and vendor costs associated with environmental reviews. 7221.29 - Payroll Allocations.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for costs associated with one-hundred eighty-one (181) Low-to-Moderate income households in the Homeowner Reimbursement Program. The Texas General Land Office also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews.992.31 - Payroll allocation costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with sixty-five (65) Low-to-Moderate income households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. 6415.19 - Payroll allocation costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with thirty-three (33) Low-to-Moderate income households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. 3451.71 - Payroll allocation costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with sixty-one (61) Low-to-Moderate income households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. 4787.94 - State costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with two hundred forty-two (242) Low-to-Moderate income households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. $4453.93 - State costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with two hundred fifty-eight (258) Low-to-Moderate income households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with four hundred (400) Low-to-Moderate income households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program. 508.66 - Quarterly expenditure related to state costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated the delivery of the Homeowner Reimbursement Program.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement program. All projects in this program are complete. 11325.46 - Quarterly expenditure for state costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement program. All projects in this program are complete. 277.07 - Quarterly expenditure for state costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement program. All projects in this program are complete. 1187.57 - Quarterly expenditure for state costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement program. All projects in this program are complete. 1332.29 - State costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement program. All projects in this program are complete. 165.3 - State costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement program. 767.11 - State costs in support of activity delivery.
HCHRP_DA_LMI_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2026-01-01 | 2026 Q2
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2019-04-01 | 2019 Q3
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-04-01 | 2020 Q3 | During the reporting period, Harris County had applications under review and 46 underway for its Reimbursement Program.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-07-01 | 2020 Q4 | During the reporting period, Harris County had applications under review and 97 underway for its HRP project.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2020-10-01 | 2021 Q1
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-01-01 | 2021 Q2
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-07-01 | 2021 Q4 | During the reporting period, GLO reimbursed Harris County for 50 HRP projects and 118 new projects were submitted this quarter.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2021-10-01 | 2022 Q1 | During the reporting period, GLO reimbursed Harris County for sixteen (16) HRP projects and one (1) new project was submitted this quarter. The GLO reimbursed vendor costs associated with environmental reviews.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, GLO reimbursed Harris County for costs related to 252 non-LMI HRP projects. Additionally, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement Program. 2494.06 - Payroll Allocations.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with forty-nine (49) non-low-to-moderate income households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the Homeowner Reimbursement Program and vendor costs associated with environmental reviews. 8045.63 - Payroll Allocations.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for costs associated with one-hundred ninety (190) Urgent Need households in the Homeowner Reimbursement Program. The Texas General Land Office also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews.1023.78 - Payroll allocation costs in support of activity delivery.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with one hundred seventy-one (171) Urgent Need households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. 7065.74 - Payroll allocation costs in support of activity delivery.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with twenty (20) Urgent Need households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. 3399.69 - Payroll allocation costs in support of activity delivery.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with eighty (80) Urgent Need households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. 4727.01 - State costs in support of activity delivery.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with two hundred forty-five (245) Urgent Need households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. $4396.2 - State costs in support of activity delivery.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with three hundred five (305) Urgent Need households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with four hundred ten (410) Urgent Need households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program. 503.39 - Quarterly expenditure related to state costs in support of activity delivery.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with fifty-two (52) Urgent Need households in the Homeowner Reimbursement Program. The GLO also reimbursed costs associated with the delivery of the program.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement program. All projects in this program are complete. 11179.02 - Quarterly expenditure for state costs in support of activity delivery.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement program. All projects in this program are complete. 221.75 - Quarterly expenditure for state costs in support of activity delivery.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement program. All projects in this program are complete. 815.33 - Quarterly expenditure for state costs in support of activity delivery.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement program. 1108.96 - State costs in support of activity delivery.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Reimbursement program. All projects in this program are complete. 159.27 - State costs in support of activity delivery.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Urgent Need Homeowner Reimbursement program. 795.2 - State costs in support of activity delivery.
HCHRP_DA_UN_19-147-002-B490 | HC Reimbursement | Rehabilitation/reconstruction of residential structures | Harris, County | 2026-01-01 | 2026 Q2
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2019-04-01 | 2019 Q3
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2019-07-01 | 2019 Q4
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2019-10-01 | 2020 Q1
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2020-04-01 | 2020 Q3
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2020-10-01 | 2021 Q1 | During the reporting period, Harris County had engineering design underway for its flood and drainage facilities projects.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2021-01-01 | 2021 Q2
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2021-04-01 | 2021 Q3 | During the reporting period, Harris County had 12 projects underway under this activity. The GLO reimbursed the County for engineering services associated with four Flood and Drainage LMI projects.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2021-07-01 | 2021 Q4 | During the reporting period, GLO reimbursed Harris County for engineering/ design costs associated with three (3) LMI MOD flood and drainage projects.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2021-10-01 | 2022 Q1 | During the reporting period, GLO reimbursed Harris County for engineering/ design costs associated with one (1) LMI MOD flood and drainage projects.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Method of Distribution Infrastructure Program. Payroll Allocations.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with two (2) flood and drainage projects. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program and vendor costs associated with environmental reviews. 1997.75 - Payroll Allocations.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for costs associated with eight (8) flood and drainage projects. The Texas General Land Office also reimbursed costs associated with the delivery of the MOD Infrastructure Program and vendor costs associated with environmental reviews. 1571.3 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with two (2) flood and drainage projects. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program and vendor costs associated with environmental reviews. 3132.16 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with four (4) flood and drainage projects. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program and vendor costs associated with environmental reviews. 3853.13 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with three (3) flood and drainage projects. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program and vendor costs associated with environmental reviews. 13654.31 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with five (5) flood and drainage projects. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program and vendor costs associated with environmental reviews. $7603.19 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with eight (8) flood and drainage projects. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with seven (7) flood and drainage projects. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program. 5846.02 - Quarterly expenditure related to state costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with nine (9) flood and drainage projects, which are all underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with eight (8) flood and drainage projects, which are all underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 24494.65 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with seven (7) flood and drainage projects, which are all underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 9184.47 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with three (3) flood and drainage projects, which are all underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 11076.88 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with three (3) flood and drainage projects, which are all underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 4474.52 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with three (3) flood and drainage projects, which are all underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 2695.71 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) Flood and drainage projects and costs associated with the delivery of the Method of Distribution Infrastructure Program. 4086.26 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Harris, County | 2026-01-01 | 2026 Q2
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2021-01-01 | 2021 Q2
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Method of Distribution Infrastructure Program. Payroll Allocations.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed costs associated with the MOD Infrastructure program. 124.74 - Payroll Allocations.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for costs associated with one (1) public facility project. The Texas General Land Office also reimbursed costs associated with the delivery of the MOD Infrastructure Program. 98.11 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) program. 195.57 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) public facilities project. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program. 481.81 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) program. 1835.13 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) Program. $State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) public facilities project. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) public facilities project. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program. 779.18 - Quarterly expenditure related to state costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) public facilities project, which is underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) public facilities project, which is underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 3264.79 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) public facilities project, which is underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) public facilities project, which is underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 1476.35 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with the delivery of the Public Facilities projects in the Method of Distribution (MOD) flood Infrastructure Program. State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with the delivery of the Public Facilities projects in the Method of Distribution (MOD) flood Infrastructure Program. 359.29 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) Public Facilities project and costs associated with the delivery of the Method of Distribution Infrastructure Program. 544.8 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2026-01-01 | 2026 Q2
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2019-07-01 | 2019 Q4
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2019-10-01 | 2020 Q1
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2020-04-01 | 2020 Q3
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2021-04-01 | 2021 Q3 | During the reporting period, Harris County had 3 projects underway under this activity. The GLO reimbursed the County for engineering services associated with 1 sewer facilities LMI project.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2021-07-01 | 2021 Q4 | During the reporting period, GLO reimbursed Harris County for engineering/ design costs associated with three (3) sewage facilities projects.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2021-10-01 | 2022 Q1 | During the reporting period, GLO reimbursed Harris County for engineering/ design costs associated with two (2) LMI MOD sewage facilities projects.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Method of Distribution Infrastructure Program. Payroll Allocations.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed costs associated with the MOD Infrastructure program. 624.37 - Payroll Allocations.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for costs associated with two (2) sewer projects. The Texas General Land Office also reimbursed costs associated with the delivery of the MOD Infrastructure Program. 491.07 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) program and vendor costs associated with environmental reviews. 978.89 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) program. 1204.2 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) program. 3672.82 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) Program. $2028.07 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with two (2) sewer facilities projects. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) sewer facilities project. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program. 1559.46 - Quarterly expenditure related to state costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) sewer facilities project, which is underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with three (3) sewer facilities projects, which are underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 6534.1 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with two (2) sewer facilities projects, which are underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 2449.98 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with three (3) sewer facilities projects, which are underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 2954.78 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) sewer facilities project, which is underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 1193.61 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with three (3) sewer facilities project, which are both underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 719.08 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with two (2) Sewer Facilities projects and the delivery of the Method of Distribution Infrastructure Program. 1089.62 - State costs in support of activity delivery.
HCMOD_DA_LMI_19-147-002-B490_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Harris, County | 2026-01-01 | 2026 Q2
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2021-01-01 | 2021 Q2
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2021-04-01 | 2021 Q3 | During the reporting period, Harris County had 3 projects underway under this activity. The GLO reimbursed the County for engineering services associated with 1 flood and drainage urgent need project.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2021-10-01 | 2022 Q1 | During the reporting period, GLO reimbursed Harris County for engineering/ design costs associated with two (2) UN MOD flood and drainage projects.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Method of Distribution Infrastructure Program. Payroll Allocations.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the MOD Infrastructure program and vendor costs associated with environmental reviews. 374.55 - Payroll Allocations.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for costs associated with two (2) flood and drainage urgent need projects. The Texas General Land Office also reimbursed costs associated with the delivery of the MOD Infrastructure Program. 294.59 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with two (2) flood and drainage projects. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program and vendor costs associated with environmental reviews. 587.23 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) program. 722.39 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) program. 3672.82 - State costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with two (2) urgent-need flood and drainage projects. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program and vendor costs associated with environmental reviews. $2028.07 - State costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with two (2) flood and drainage projects. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with two (2) flood and drainage projects. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program. 1559.46 - Quarterly expenditure related to state costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) flood and drainage projects, which is underway The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) Program. 6534.07 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with two (2) Urgent Need flood and drainage projects, which are underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 2449.98 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Urgent Need Flood and Drainage Method of Distribution (MOD) Program. 2954.78 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Urgent Need Flood and Drainage projects in the Method of Distribution (MOD) Program. 1193.61 - State costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Urgent Need Flood and Drainage projects in the Method of Distribution (MOD) Program. 719.08 - State costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO also reimbursed costs associated with the delivery of the Method of Distribution Infrastructure Program. 953.74 - State costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Harris, County | 2026-01-01 | 2026 Q2
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2019-10-01 | 2020 Q1
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2020-10-01 | 2021 Q1 | During the reporting period, Harris County had construction underway for its neighborhood facilities project.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2021-01-01 | 2021 Q2
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2021-04-01 | 2021 Q3 | During the reporting period, Harris County had 2 projects underway under this activity. The GLO reimbursed the County for construction costs associated with 1 public facilities - urgent need project.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Method of Distribution Infrastructure Program. Payroll Allocations.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the MOD Infrastructure program. 249.81 - Payroll Allocations.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed costs associated with delivering the Method of Distribution (MOD) program and vendor costs associated with environmental reviews.196.49 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) public facility project. The GLO also reimbursed costs associated with the delivery of the MOD Infrastructure Program. 391.67 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) program. 240.58 - Payroll allocation costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) program. 2752.69 - State costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) Program. $State costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) Program.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) Program. 1168.77 - Quarterly expenditure related to state costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) Program.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) Program. 4897.21 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Method of Distribution (MOD) Program. Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Urgent Need Public Facilities Method of Distribution (MOD) Program. 2214.53 - Quarterly expenditure for state costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Urgent Need Public Facilities Method of Distribution (MOD) Program. State costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) public facilities projects, which are both underway. The GLO also reimbursed costs associated with the delivery of the Method of Distribution (MOD) Infrastructure Program. 538.94 - State costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO also reimbursed costs associated with one (1) public facilities delivery of the Method of Distribution Infrastructure Program. 817.02 - State costs in support of activity delivery.
HCMOD_DA_UN_19-147-002-B490_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Harris, County | 2026-01-01 | 2026 Q2
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2019-04-01 | 2019 Q3 | Housing grantee continues planning services of their Grant.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2019-07-01 | 2019 Q4 | Under the pre-agreement stratagem and during the report period, Harris County continued planning services, completed the Local Needs Assessment, and performed capacity building activities.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2019-10-01 | 2020 Q1 | During the reporting period, Harris County continued planning services and performed capacity building activities.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2020-01-01 | 2020 Q2
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2020-04-01 | 2020 Q3 | During the reporting period, Harris County continued to carry out planning services.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2020-07-01 | 2020 Q4
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2020-10-01 | 2021 Q1 | During the reporting period, Harris County continued to carry out planning projects.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2021-01-01 | 2021 Q2
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2021-04-01 | 2021 Q3 | During the reporting period, Harris County continued to carry out planning projects and 10 studies were underway. The GLO reimbursed the County for a comprehensive affordable housing planning study.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed Harris County for one (1) planning study, which is underway.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed Harris County for three (3) planning studies, which are underway.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed Harris County for three (3) planning studies, which are underway. 1052.59 - Payroll Allocations.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) study, which is pending closeout. The GLO also reimbursed costs associated with delivering the Planning Program. 1967.92 - Payroll Allocations.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for costs associated with six (6) planning studies. The Texas General Land Office also reimbursed payroll and vendor costs associated with the delivery of the program.3366.08 - Payroll allocation costs in support of activity delivery.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with eight (8) planning studies, which are underway or complete. The GLO also reimbursed costs associated with the delivery of the Planning Program. 4668.37 - Payroll allocation costs in support of activity delivery.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with five (5) planning studies, which are underway or complete. The GLO also reimbursed costs associated with the delivery of the Planning Program. 5374.96 - Payroll allocation costs in support of activity delivery.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) planning studies, which is underway. The GLO also reimbursed costs associated with the delivery of the Planning Program. 10591.05 - State costs in support of activity delivery.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with two (2) planning studies, which are complete. The GLO also reimbursed costs associated with the delivery of the Planning Program. $4695.33 - State costs in support of activity delivery.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with eleven (11) planning studies, of which 4 completed. The GLO also reimbursed costs associated with the delivery of the Planning Program. MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to previous DRGR issues. MID Expenditure amount entered corrects the discrepancy in order for reports pulled at the child grant level to be accurate.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with nine (9) planning studies, of which three were completed (100% expensed). The GLO also reimbursed costs associated with the delivery of the Planning Program. 3342.24 - Quarterly expenditure related to state costs in support of activity delivery.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with five (5) planning studies, of which two were completed (100% expensed). The GLO also reimbursed costs associated with the delivery of the Planning Program.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with four (4) planning studies, of which one was completed (100% expensed). The GLO also reimbursed costs associated with the delivery of the Planning Program. 21895.04 - Quarterly expenditure for state costs in support of activity delivery.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with two (2) planning studies, of which one was completed (100% expensed). The GLO also reimbursed costs associated with the delivery of the Planning Program. 14499.14 - Quarterly expenditure for state costs in support of activity delivery.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with six (6) planning studies, of which four are completed (100% expensed). The GLO also reimbursed costs associated with the delivery of the Planning Program. 22688.92 - Quarterly expenditure for state costs in support of activity delivery.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) planning studies. The GLO also reimbursed costs associated with the delivery of the Planning Program. 13559.58 - State costs in support of activity delivery.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) planning studies. The GLO also reimbursed costs associated with the delivery of the Planning Program. 6768.16 - State costs in support of activity delivery.
HCPLAN_DA_NA_19-147-002-B490 | Harris County Planning | Planning | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) planning studies. The GLO also reimbursed costs associated with the delivery of the Planning Program. 10791.44 - State costs in support of activity delivery.
HCPS_DA_LMA_19-147-002-B490 | Public Services Area Benefit | Public services | Harris, County | 2023-10-01 | 2024 Q1 | Activity was created during the quarter to establish beneficiaries and accomplishments for a low-to moderate income area benefit public service project.
HCPS_DA_LMA_19-147-002-B490 | Public Services Area Benefit | Public services | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Public Services program.
HCPS_DA_LMA_19-147-002-B490 | Public Services Area Benefit | Public services | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with one (1) public services project, which is underway. The GLO also reimbursed costs associated with delivering the Public Services Program.
HCPS_DA_LMA_19-147-002-B490 | Public Services Area Benefit | Public services | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs associated with one (1) public services project, which is underway. The GLO also reimbursed costs associated with delivering the Public Services Program. 1170.37 - Quarterly expenditure for state costs in support of activity delivery.
HCPS_DA_LMA_19-147-002-B490 | Public Services Area Benefit | Public services | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with one (1) public services project, which is underway. The GLO also reimbursed costs associated with delivering the Public Services Program. 464.34 - Quarterly expenditure for state costs in support of activity delivery.
HCPS_DA_LMA_19-147-002-B490 | Public Services Area Benefit | Public services | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Public Service Program. 883.5 - Quarterly expenditure for state costs in support of activity delivery.
HCPS_DA_LMA_19-147-002-B490 | Public Services Area Benefit | Public services | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed costs associated with one (1) project of the Public Service Program. 748.79 - State costs in support of activity delivery.
HCPS_DA_LMA_19-147-002-B490 | Public Services Area Benefit | Public services | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Public Service Program. 742.01 - State costs in support of activity delivery.
HCPS_DA_LMA_19-147-002-B490 | Public Services Area Benefit | Public services | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Public Service Program. 852.86 - State costs in support of activity delivery.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2021-10-01 | 2022 Q1 | Increased the Harris County public service program budget according to Action Plan Amendment 9.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Public Services Program. Payroll Allocations.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Public Services program. 1499.35 - Payroll Allocations.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed costs associated with delivering the Public Services program. 1115.56 - Payroll allocation costs in support of activity delivery.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for project delivery costs associated with the Public Services program. 2593.3 - Payroll allocation costs in support of activity delivery.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed Harris County for costs associated with one (1) public services project, as well as costs associated with delivering the Public Services program. 1290.61 - Payroll allocation costs in support of activity delivery.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Public Services program. 1143.3 - State costs in support of activity delivery.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed costs associated with delivering the Public Services program. $1469.09 - State costs in support of activity delivery.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Public Services program.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed costs associated with delivering the Public Services program. 1294.91 - Quarterly expenditure related to state costs in support of activity delivery.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed costs associated with delivering the Public Services Program.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed costs for completing the Section 3 Public Services project, along with costs associated with delivering the Public Services Program. 2817.49 - Quarterly expenditure for state costs in support of activity delivery.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed costs associated with delivering the Public Services Program. 438 - Quarterly expenditure for state costs in support of activity delivery.
HCPS_DA_LMI_19-147-002-B490 | Public Services | Public services | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Public Service Program. 852.88 - State costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2019-04-01 | 2019 Q3
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2020-07-01 | 2020 Q4 | During the reporting period, Harris County completed acquisition for a SF New Construction project.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2020-10-01 | 2021 Q1 | During the reporting period, Harris County completed acquisition for a SF New Construction project.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2021-01-01 | 2021 Q2
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2021-04-01 | 2021 Q3 | During the reporting period, Harris County had 8 projects underway for its Single Family New Construction Program. The GLO reimbursed the County for engineering and design standards for the program and acquisition costs associated with 1 project.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2021-07-01 | 2021 Q4 | During the reporting period, GLO reimbursed Harris County for engineering/ design associated with two SFNCP projects and project delivery costs. Two new projects were submitted in Quarter 3 2021.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2021-10-01 | 2022 Q1 | During the reporting period, GLO reimbursed Harris County for acquisition costs associated with one Single Family New Construction Program project. The GLO reimbursed vendor costs associated with environmental reviews.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2022-01-01 | 2022 Q2 | During the reporting period, GLO reimbursed Harris County for acquisition costs associated with one Single Family New Construction Program project. Additionally, the GLO reimbursed costs associated with the delivery of the Single Family New Construction Program. 1304.55 - Payroll Allocations.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed Harris County for costs associated one (1) development. The GLO also reimbursed costs associated with the delivery of the Single Family New Construction Program. 4834.08 - Payroll Allocations.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed Harris County for project delivery costs. The Texas General Land Office also reimbursed costs associated with the delivery of the Single Family New Construction Program and vendor costs associated with environmental reviews. 3283.56 - Payroll allocation costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed Harris County for one (1) single-family new construction project. The GLO also reimbursed costs associated with the delivery of the Single Family New Construction Program and vendor costs associated with environmental reviews. 5960.78 - Payroll allocation costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed Harris County for two (2) single-family new construction projects. The GLO also reimbursed costs associated with the delivery of the Single Family New Construction Program. 3269.05 - Payroll allocation costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed Harris County for one (1) single-family new construction project. The GLO also reimbursed costs associated with the delivery of the Single Family New Construction Program. 7263.43 - State costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed Harris County for one (1) single-family new construction project. The GLO also reimbursed costs associated with the delivery of the Single Family New Construction Program. $3937.07 - State costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed Harris County for one (1) single-family new construction project. The GLO also reimbursed costs associated with the delivery of the Single Family New Construction Program.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed Harris County for one (1) single-family new construction project. The GLO also reimbursed costs associated with the delivery of the Single Family New Construction Program. 2181.21 - Quarterly expenditure related to state costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed Harris County for one (1) single-family new construction project, which is underway. The GLO also reimbursed costs associated with the delivery of the Single Family New Construction Program.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed Harris County for four (4) single-family new construction projects, which are underway. The GLO also reimbursed costs associated with the delivery of the Single Family New Construction Program. 24583.38 - Quarterly expenditure for state costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed Harris County for five (5) single-family new construction projects, which are underway. The GLO also reimbursed costs associated with the delivery of the Single Family New Construction Program. 8919.46 - Quarterly expenditure for state costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed Harris County for four (4) single-family new construction projects, which are underway. The GLO also reimbursed costs associated with the delivery of the Single Family New Construction Program. 13198.21 - Quarterly expenditure for state costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed Harris County for two (2) single-family new construction projects. The GLO also reimbursed costs associated with the delivery of the Single Family New Construction Program. 6760.41 - State costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Single Family New Construction Program. 5583.99 - State costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed costs associated with two (2) projects of the Single Family New Construction Program. 11376.16 - State costs in support of activity delivery.
HCSFNC_DA_LMI_19-147-002-B490 | HC Single Family New Construction | Construction of new housing | Harris, County | 2026-01-01 | 2026 Q2
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2019-04-01 | 2019 Q3
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2020-01-01 | 2020 Q2 | Housing grantee continues administrative services of their grant.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the HCDD and GLO continued to administer disaster recovery programs in the City of Houston.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City and GLO continued to administer disaster recovery programs in the City of Houston.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the city and GLO continued to administer disaster recovery programs in the City of Houston.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2021-04-01 | 2021 Q3
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed the City of Houston for administration costs associated with public postings and facility costs necessary to administer the grant.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed for costs associated administrative payroll. Payroll Allocations.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed for costs associated with the administration of the City of Houston&apos;s programs. 33649.07 - Payroll Allocations.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the GLO reimbursed payroll costs associated with administering the grant. The city did not submit any new administration payment requests to the GLO during the quarter, which is why expenditures are relatively low compared to previous quarters. 21372.28 - Payroll allocation costs in support of activity delivery.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed for costs associated with the administration of the City of Houston&apos;s programs. 43571.18 - Payroll allocation costs in support of activity delivery.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2023-01-01 | 2023 Q2 | Negative expenditures for this quarter reflect a payroll allocation correction for GLO oversight.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed for costs associated with the administration of the City of Houston&apos;s programs.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed for costs associated with the administration of the City of Houston programs.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed for costs associated with the administration of the City of Houston programs.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed for costs associated with the administration of the City of Houston programs.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed for costs associated with the administration of the City of Houston programs.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed for costs associated with the administration of the City of Houston programs.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed for costs associated with the administration of the City of Houston programs.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed for costs associated with the administration of the City of Houston programs.
HouADMIN_DA_NA_21-134-000-C788 | HOU Administration | Administration | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed for costs associated with the administration of the City of Houston programs.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2019-04-01 | 2019 Q3
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2021-04-01 | 2021 Q3
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed the City of Houston for project delivery costs and the acquisition costs associated with 1 multifamily buyout project, which is still underway.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2021-10-01 | 2022 Q1 | During the report period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Buyout Program. The GLO also reimbursed vendor costs associated with environmental reviews.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the acquisition of one property, property management costs associated with one property, and costs associated with the delivery of the Buyout Program. 2445.51 - Payroll Allocations.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the acquisition of one property, property management costs associated with one property, and costs associated with the delivery of the Buyout Program. The GLO also reimbursed vendor costs associated with environmental reviews. 11159.67 - Payroll Allocations.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed the City of Houston for property management costs associated with one property, and costs associated with the delivery of the Buyout Program. The Texas General Land Office also reimbursed vendor costs associated with environmental reviews. The city did not submit any new Buyout Program payment requests to the Texas General Land Office during the quarter, which is why expenditures are relatively low compared to previous quarters. 9456.32 - Payroll allocation costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed the City of Houston for property management costs associated with one property. The GLO also reimbursed for costs associated with delivery of the program. 17354.94 - Payroll allocation costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed the City of Houston for property management costs associated with one property. The GLO also reimbursed for costs associated with delivery of the program. 12284.59 - Payroll allocation costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Buyout program. 37000.92 - State costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with one buyout project, as well as costs for the delivery of the Buyout program. The negative amount comes from a voucher adjustment to move funds previously expended under the Harvey contract to the 2016 Floods contract. The voucher adjustment was completed in order to allow the GLO to assist with relocation of tenants from one of the buyout properties. $15658.68 - State costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with delivery of the Buyout program.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with delivery of the Buyout program. 774.95 - Quarterly expenditure related to state costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with delivery of the Buyout program.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with delivery of the Buyout program. 2297.38 - Quarterly expenditure for state costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with delivery of the Buyout program. 1254.8 - Quarterly expenditure for state costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with delivery of the Buyout program, payroll expenses of vendor (GrantWorks) and GLO payroll expenses. 1985.37 - Quarterly expenditure for state costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with delivery of the Imperial Valley and Clarewood Property for the Buyout program, payroll expenses of vendor (GrantWorks), City Personnel and GLO payroll expenses. 640.48 - State costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with maintenance of the Clarewood Property for the Buyout program, City of Houston payroll and pension expenses, vendor admin costs, and GLO payroll expenses. 305.12 - State costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with consulting and abatement for two (2) properties (Clarewood and Imperial Valley), GLO payroll expenses, and payroll adjustments from previous months. 197.56 - State costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_ACQ | HOU Buyout | Acquisition - buyout of residential properties | Houston, City of | 2026-01-01 | 2026 Q2
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2023-01-01 | 2023 Q2 | Funds moved from Acquisition to Relocation Assistance activity.
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for relocation assistance costs associated with two tenant households. The GLO also reimbursed for costs associated with delivery of the program.
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for relocation assistance costs associated with eight (8) tenant households. The GLO also reimbursed for costs associated with delivery of the program. $9323.83 - State costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for relocation assistance costs associated with thirty-one (31) tenant households. The GLO also reimbursed for costs associated with delivery of the program.
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for relocation assistance costs associated with twenty-four (24) tenant households. The GLO also reimbursed for costs associated with delivery of the program. 7365.24 - Quarterly expenditure related to state costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for relocation assistance costs associated with 132 tenant households, of which 128 have received their full obligation and marked as complete on this report. The GLO also reimbursed for costs associated with delivery of the program.
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston for relocation assistance costs associated with 4 tenant households which have been fully expensed and marked as complete on this report. Payments were made to AECOM for the City of Houston Relocation Assistance awards associated with 28 households. The GLO reimbursed both the City and AECOM costs associated with delivery of the program. 41004.18 - Quarterly expenditure for state costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed the City of Houston for relocation assistance costs associated with 3 tenant households which have been fully expensed and marked as complete on this report. Payments were made to AECOM for the City of Houston Relocation Assistance awards associated with 24 households. The GLO reimbursed both the City and AECOM costs associated with delivery of the program. 16557.02 - Quarterly expenditure for state costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2025-01-01 | 2025 Q2 | Imperial Valley Property - The relocation expenses for this quarter are for relocation payments to 20 tenants, tenant moving expenses, administrative costs for AECOM to process Uniform Relocation payments, and administrative costs for tenants that did not qualify for the program. Clarewood Property -The relocation expenses for this quarter are for relocation payments to 5 tenants, tenant moving expenses, administrative costs for AECOM to process Uniform Relocation payments for 5 tenants, and administrative costs for tenants that did not qualify for the program. MacGregor Property - The relocation expenses for this quarter are for relocation payments to 1 tenant, and administrative costs for tenants that did not qualify for the program. 23853.57 - Quarterly expenditure for state costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2025-04-01 | 2025 Q3 | Imperial Valley Property -The relocation expenses for this quarter are for relocation payments to 20 tenants. There are also expenditures for tenant moving expenses, administrative costs for AECOM to process Uniform Relocation payments, and administrative costs for tenants that did not qualify for the program for Imperial Valley, Clarewood, and the MacGregor Property. 14556.62 - State costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2025-07-01 | 2025 Q4 | For the Imperial Valley, Clarewood, and MacGregor Property projects, the expenditures for this quarter are for administrative costs for AECOM to process Uniform Relocation payments and administrative costs for tenants that did not qualify for the Harvey Program. 8775.77 - State costs in support of activity delivery.
HouBP_DA_LMI_21-134-000-C788_RA | HOU Relocation Assistance | Relocation payments and assistance | Houston, City of | 2025-10-01 | 2026 Q1 | For the Imperial Valley property, expenditures for this quarter are for relocation payments to 4 tenants, administrative costs to process Uniform Relocation payments, GLO Payroll expenses, payroll adjustments from previous months. 21003.56 - State costs in support of activity delivery.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2019-04-01 | 2019 Q3
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed the City of Houston for project delivery costs associated with implementing the program.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed the City of Houston for assistance to five business applicants in the City of Houston.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed the City of Houston for assistance to 23 business applicants in the City of Houston and completed reimbursement of grants to 5 business applicants. Additionally, the GLO reimbursed costs associated with the delivery of the Economic Development Program. 2329.71 - Payroll Allocations.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed the City of Houston for assistance to 39 business applicants in the City of Houston and completed reimbursement of grants to 19 business applicants. Additionally, the GLO reimbursed costs associated with the delivery of the Economic Development Program. 3150.66 - Payroll Allocations.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed the City of Houston for assistance to 32 business applicants in the City of Houston and completed reimbursement of grants to 12 business applicants. Additionally, the Texas General Land Office reimbursed costs associated with the delivery of the Economic Development Program. The city did not submit any new Economic Development Program payment requests to the Texas General Land Office during the quarter, which is why expenditures are relatively low compared to previous quarters. 6161.92 - Payroll allocation costs in support of activity delivery.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed the City of Houston for assistance to 67 business applicants in the City of Houston and completed reimbursement of grants to 41 business applicants. Additionally, the GLO reimbursed costs associated with the delivery of the program. 8436.11 - Payroll allocation costs in support of activity delivery.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed the City of Houston for assistance to 32 business applicants in the City of Houston and completed reimbursement of grants to 7 business applicants. Additionally, the GLO reimbursed costs associated with the delivery of the program. 12889.19 - Payroll allocation costs in support of activity delivery.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for assistance to 42 business applicants in the City of Houston and completed reimbursement of grants to 10 business applicants. Additionally, the GLO reimbursed costs associated with the delivery of the program. 15353.21 - State costs in support of activity delivery.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for assistance to 16 business applicants in the City of Houston and completed reimbursement of grants to 13 business applicants. Additionally, the GLO reimbursed costs associated with the delivery of the program. $17706.36 - State costs in support of activity delivery.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for assistance to 28 business applicants in the City of Houston and completed reimbursement of grants to 20 business applicants. Additionally, the GLO reimbursed costs associated with the delivery of the program.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for assistance to 13 business applicants, which have all now completed the program. Additionally, the GLO reimbursed costs associated with the delivery of the program. 3920.53 - Quarterly expenditure related to state costs in support of activity delivery.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for assistance to 15 business applicants, which have all now completed the program, creating or retaining 16 jobs. Additionally, the GLO reimbursed costs associated with the delivery of the program.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston for assistance to 4 business applicants, which have all now completed the program, creating or retaining 6 jobs. Additionally, the GLO reimbursed costs associated with the delivery of the program. 44437.03 - Quarterly expenditure for state costs in support of activity delivery.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Harvey Economic Development Program. All projects are complete. 11184.02 - Quarterly expenditure for state costs in support of activity delivery.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Harvey Economic Development Program (HEDP). All projects are complete and repayment for Houston HEDP from the City. 18207.73 - Quarterly expenditure for state costs in support of activity delivery.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Harvey Economic Development Program (HEDP). All projects are complete and repayment for Houston HEDP from the City. 8465.57 - State costs in support of activity delivery.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Harvey Economic Development Program (HEDP). 6904.38 - State costs in support of activity delivery.
HouERP_DA_LMI_21-134-000-C788 | HOU Economic Revitalization | Econ. development or recovery activity that creates/retains jobs | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Harvey Economic Development Program (HEDP). 23411.37 - State costs in support of activity delivery.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2019-04-01 | 2019 Q3
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2019-07-01 | 2019 Q4
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2020-01-01 | 2020 Q2 | During the reporting period, Houston received 42 applications and verified 38 projects for eligibility. 19 total projects have completed by Houston and 9 projects are underway.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the GLO reimbursed the City of Houston for downpayment assistance to 26 low-to-moderate income households.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the GLO reimbursed the City of Houston for downpayment assistance to 33 low-to-moderate income households.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 41 low-to-moderate income households.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the GLO reimbursed the City of Houston for downpayment assistance to 10 low-to-moderate income households.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 46 low-to-moderate income households. A voucher is being adjusted from the HbAP UN activity to the HBAP LMI activity. DRGR Low Actuals not appearing in Q1 2021 QPR, adjustments for Q2 2021.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed the City of Houston for downpayment assistance to 19 low-to-moderate income households. A voucher was adjusted from the HbAP UN activity to the HBAP LMI activity.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed the City of Houston for downpayment assistance to 30 low-to-moderate income households, as well as costs associated with the delivery of the Homebuyer Assistance Program.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 16 low-to-moderate income households, as well as costs associated with the delivery of the Homebuyer Assistance Program. 791.45 - Payroll Allocations.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 9 low-to-moderate income households, as well as costs associated with the delivery of the Homebuyer Assistance Program. 1653.96 - Payroll Allocations.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed the City of Houston for down payment assistance to 7 low-to-moderate income households, as well as costs associated with the delivery of the Homebuyer Assistance Program. The city submitted only two new Homebuyer Program LMI payment requests to the Texas General Land Office during the quarter, which is why expenditures are relatively low compared to previous quarters. 2307.95 - Payroll allocation costs in support of activity delivery.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 6 low-to-moderate income households. The GLO also reimbursed for costs associated with the delivery of the program. 3575.49 - Payroll allocation costs in support of activity delivery.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 14 low-to-moderate income households. The GLO also reimbursed for costs associated with the delivery of the program. 5601.68 - Payroll allocation costs in support of activity delivery.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 21 low-to-moderate income households. The GLO also reimbursed for costs associated with the delivery of the program. 6878.26 - State costs in support of activity delivery.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 4 low-to-moderate income households. The GLO also reimbursed for costs associated with the delivery of the program. $4819.14 - State costs in support of activity delivery.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 3 low-to-moderate income households. The GLO also reimbursed for costs associated with the delivery of the program.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Homebuyer Assistance program. 162.88 - Quarterly expenditure related to state costs in support of activity delivery.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Homebuyer Assistance program.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Homebuyer Assistance program. 7657.7 - Quarterly expenditure for state costs in support of activity delivery.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Homebuyer Assistance program. 1708.43 - Quarterly expenditure for state costs in support of activity delivery.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Homebuyer Assistance program. 6464.9 - Quarterly expenditure for state costs in support of activity delivery.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery and implementation of the Homebuyer Assistance program. 3400.87 - State costs in support of activity delivery.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with implementation of the Homebuyer Assistance program. 180.89 - State costs in support of activity delivery.
HouHBAP_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance to low- and moderate-income | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Homebuyer Assistance program.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2019-04-01 | 2019 Q3
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2019-07-01 | 2019 Q4
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2020-01-01 | 2020 Q2
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the GLO reimbursed the City of Houston for downpayment assistance to 2 non-low-to-moderate income households.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the GLO reimbursed the City of Houston for downpayment assistance to 9 non-low-to-moderate income households.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 9 non-low-to-moderate income households.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the GLO reimbursed the City of Houston for downpayment assistance to 1 non-low-to-moderate income household.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 36 non-low-to-moderate income household. A voucher is being adjusted from the HBAP UN activity to the HBAP LMI activity.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed the City of Houston for downpayment assistance to 10 non-low-to-moderate income households. A voucher was adjusted from the HbAP UN activity to the HBAP LMI activity.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed the City of Houston for downpayment assistance to 43 non-low-to-moderate income households.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed the City of Houston for downpayment assistance to 10 non-low-to-moderate income households, as well as costs associated with the delivery of the Homebuyer Assistance Program. 403.55 - Payroll Allocations.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed the City of Houston for downpayment assistance to 12 urgent need income households, as well as costs associated with the delivery of the Homebuyer Assistance Program. 843.35 - Payroll Allocations.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed the City of Houston for down payment assistance to 16 urgent need income households, as well as costs associated with the delivery of the Homebuyer Assistance Program. Additionally, as part of an annual reconciliation of the data, the Texas General Land Office identified one additional complete project which was not reported at the time of completion, representing down payment assistance for one additional urgent need income household. The performance measures have been updated accordingly. The city submitted only five new Homebuyer Program LMI payment requests to the Texas General Land Office during the quarter, which is why expenditures are relatively low compared to previous quarters. 1609.82 - Payroll allocation costs in support of activity delivery.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 21 urgent need households. The GLO also reimbursed for costs associated with the delivery of the program. 2256.14 - Payroll allocation costs in support of activity delivery.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 20 urgent need households. The GLO also reimbursed for costs associated with the delivery of the program. 4081.41 - Payroll allocation costs in support of activity delivery.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 7 urgent need households. The GLO also reimbursed for costs associated with the delivery of the program. 4627.72 - State costs in support of activity delivery.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 2 urgent need households. The GLO also reimbursed for costs associated with the delivery of the program. $3103.82 - State costs in support of activity delivery.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for down payment assistance to 2 urgent need households. The GLO also reimbursed for costs associated with the delivery of the program.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Homebuyer Assistance program. 67.07 - Quarterly expenditure related to state costs in support of activity delivery.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Homebuyer Assistance program.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Homebuyer Assistance program. 2216.69 - Quarterly expenditure for state costs in support of activity delivery.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Homebuyer Assistance program. 1708.43 - Quarterly expenditure for state costs in support of activity delivery.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Homebuyer Assistance program. 6464.92 - Quarterly expenditure for state costs in support of activity delivery.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery and implementation of the Homebuyer Assistance program. 3400.83 - State costs in support of activity delivery.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with implementation of the Homebuyer Assistance program. 180.89 - State costs in support of activity delivery.
HouHBAP_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance | Homeownership Assistance (with waiver only) | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Homebuyer Assistance program.
HouHBAP-2_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance Round 2 | Homeownership Assistance to low- and moderate-income | Houston, City of | 2025-04-01 | 2025 Q3 | Activity created, budgeted and obligated during the quarter.
HouHBAP-2_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance Round 2 | Homeownership Assistance to low- and moderate-income | Houston, City of | 2025-07-01 | 2025 Q4 | The GLO is currently in the process of reviewing applications submitted by the City of Houston for the HBAP 2.0 program. 2063.17 - State costs in support of activity delivery.
HouHBAP-2_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance Round 2 | Homeownership Assistance to low- and moderate-income | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period the City of Houston had costs associated with eleven (11) projects and reimbursed for costs associated with the delivery of the program. 14512.53 - State costs in support of activity delivery.
HouHBAP-2_DA_LMI_21-134-000-C788 | HOU Homebuyer Assistance Round 2 | Homeownership Assistance to low- and moderate-income | Houston, City of | 2026-01-01 | 2026 Q2
HouHBAP-2_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance Round 2 | Homeownership Assistance (with waiver only) | Houston, City of | 2025-04-01 | 2025 Q3 | Activity created, budgeted and obligated during the quarter.
HouHBAP-2_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance Round 2 | Homeownership Assistance (with waiver only) | Houston, City of | 2025-07-01 | 2025 Q4 | The GLO is currently in the process of reviewing applications submitted by the City of Houston for the HBAP 2.0 program. 1113.87 - State costs in support of activity delivery.
HouHBAP-2_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance Round 2 | Homeownership Assistance (with waiver only) | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period the City of Houston had costs associated with two (2) projects and reimbursed for costs associated with the delivery of the program. 7835.07 - State costs in support of activity delivery.
HouHBAP-2_DA_UN_21-134-000-C788 | HOU Homebuyer Assistance Round 2 | Homeownership Assistance (with waiver only) | Houston, City of | 2026-01-01 | 2026 Q2
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2019-04-01 | 2019 Q3
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2019-07-01 | 2019 Q4
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2020-01-01 | 2020 Q2
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-01-01 | 2021 Q2
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of 54 homeowner assistance projects for low-to-moderate income households. The GLO updated their methodology for reporting completed rehabilitation and reconstruction projects in DRGR. Previously, GLO reported completed projects once the CDBG-DR funds were fully expensed. The methodology has been updated to report on completed rehabilitation and reconstruction projects once the final inspection is completed as reported by the City of Houston to GLO. The performance measures and associated demographic information have been updated to reflect all rehabilitation and reconstruction projects that have received final inspection as of the end of the reporting period. To date, final inspection has been completed on 226 low-to-moderate income homeowner assistance projects, 27 of which received final inspection during the reporting period.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of 46 homeowner assistance projects for low-to-moderate income households. Additionally, 21 reconstructions or rehabilitations for low-to-moderate income households received final inspections this quarter and are complete. To date, final inspection has been completed on 247 low-to-moderate income homeowner assistance projects.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of 85 homeowner assistance projects for low-to-moderate income households. Additionally, 9 reconstructions or rehabilitations for low-to-moderate income households received final inspections this quarter and are complete. To date, final inspection has been completed on 256 low-to-moderate income homeowner assistance projects. The GLO also reimbursed vendor costs associated with environmental reviews.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of 72 homeowner assistance projects for low-to-moderate income households, as well as costs associated with the delivery of the Homeowner Assistance Program. To date, final inspection has been completed on 256 low-to-moderate income homeowner assistance projects. 6524.55 - Payroll Allocations.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of 70 homeowner assistance projects for low-to-moderate income households, as well as costs associated with the delivery of the Homeowner Assistance Program. To date, final inspection has been completed on 257 low-to-moderate income homeowner assistance projects. 15379.14 - Payroll Allocations.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of 33 homeowner assistance projects for low-to-moderate income households, as well as costs associated with the delivery of the Homeowner Assistance Program. Additionally, as part of an annual reconciliation of the data, the Texas General Land Office identified 15 complete projects that were reported as UN projects, but should have been reported as complete LMI projects. The performance measures have been updated accordingly. Additionally, two projects received final inspections but were not reported at the time the final inspection was completed and these complete projects have been added to the performance measures representing rehabilitation or reconstruction assistance to two low-to-moderate income households. The performance measures have been updated accordingly. To date, final inspection has been completed on 258 low-to-moderate income homeowner assistance projects. The city did not submit any new Homeowner Assistance City-Managed LMI payment requests to the Texas General Land Office during the quarter, which is why expenditures are relatively low compared to previous quarters. 12270.83 - Payroll allocation costs in support of activity delivery.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of 42 homeowner assistance projects for low-to-moderate income households. The GLO also reimbursed for costs associated with delivery of the program and vendor costs associated with environmental reviews. To date, final inspection has been completed on 277 low-to-moderate income homeowner assistance projects. 21558.29 - Payroll allocation costs in support of activity delivery.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of 23 homeowner assistance projects for low-to-moderate income households. The GLO also reimbursed for costs associated with delivery of the program and vendor costs associated with environmental reviews. To date, final inspection has been completed on 279 low-to-moderate income homeowner assistance projects. 8812.52 - Payroll allocation costs in support of activity delivery.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of 48 homeowner assistance projects for low-to-moderate income households. The GLO also reimbursed for costs associated with delivery of the program and vendor costs associated with environmental reviews. To date, final inspection has been completed on 280 low-to-moderate income homeowner assistance projects. 11912.54 - State costs in support of activity delivery.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of 56 homeowner assistance projects for low-to-moderate income households. The GLO also reimbursed for costs associated with delivery of the program and vendor costs associated with environmental reviews. To date, final inspection has been completed on 280 low-to-moderate income homeowner assistance projects. $12799 - State costs in support of activity delivery.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of 92 homeowner assistance projects for low-to-moderate income households. The GLO also reimbursed for costs associated with delivery of the program. To date, final inspection has been completed on 280 low-to-moderate income homeowner assistance projects.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of forty (40) homeowner assistance projects for low-to-moderate income households. The GLO also reimbursed for costs associated with delivery of the program. To date, final inspection has been completed on 280 low-to-moderate income homeowner assistance projects. 4921.05 - Quarterly expenditure related to state costs in support of activity delivery.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of thirty-five (35) homeowner assistance projects for low-to-moderate income households, which completes the obligation amount for those projects. The GLO also reimbursed for costs associated with delivery of the program. Final inspection has been completed on all 280 low-to-moderate income homeowner assistance projects.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of two (2) homeowner assistance projects for low-to-moderate income households, which completes the obligation amount for those projects. The GLO also reimbursed for costs associated with delivery of the program. Final inspection has been completed on all 280 low-to-moderate income homeowner assistance projects. 62282.93 - Quarterly expenditure for state costs in support of activity delivery.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed for costs associated with delivery of the program. Final inspection has been completed on all 280 low-to-moderate income homeowner assistance projects. 12745.85 - Quarterly expenditure for state costs in support of activity delivery.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed for costs associated with delivery of the program. Final inspection has been completed on all 280 low-to-moderate income homeowner assistance projects. 6231.56 - Quarterly expenditure for state costs in support of activity delivery.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed for costs associated with delivery and implementation of the program. Final inspection has been completed on all 280 low-to-moderate income homeowner assistance projects. 4276.69 - State costs in support of activity delivery.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed for costs associated with delivery and implementation of the program. 1009.54 - State costs in support of activity delivery.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed for costs associated with delivery of the program. 1664.65 - State costs in support of activity delivery.
HouHoAP[CM]_DA_LMI_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2026-01-01 | 2026 Q2
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2019-04-01 | 2019 Q3
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2019-07-01 | 2019 Q4
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2020-01-01 | 2020 Q2
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-04-01 | 2021 Q3
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding new activities in Q3 2021. One completed household reported during the reporting period, but GLO reimbursement to the City of Houston for construction costs will occur in the proceeding quarters.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Assistance Program. Payroll Allocations.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed costs associated with the delivery of the Homeowner Assistance Program. 2295.96 - Payroll Allocations.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed costs associated with the delivery of the Homeowner Assistance Program. Additionally, as part of an annual reconciliation of the data, the Texas General Land Office identified 15 complete projects that were reported as UN projects, but should have been reported as complete LMI projects. The performance measures associated with this activity have been updated accordingly. The city did not submit any new Homeowner Assistance City-Managed UN payment requests to the Texas General Land Office during the quarter, which is why expenditures are relatively low compared to previous quarters. 1018.42 - Payroll allocation costs in support of activity delivery.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation or reconstruction of 1 homeowner assistance project for urgent need households. The GLO also reimbursed for costs associated with the delivery of the program. To date, final inspection has been completed on 2 urgent need homeowner assistance projects. 2404.96 - Payroll allocation costs in support of activity delivery.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-01-01 | 2023 Q2 | Negative expenditures for this quarter reflect a payroll allocation correction for GLO oversight. 773.93 - Payroll allocation costs in support of activity delivery.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the city-managed Homeowner Assistance program. 115.8 - State costs in support of activity delivery.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the city-managed Homeowner Assistance program. $133.62 - State costs in support of activity delivery.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with reconstruction/rehabilitation of 1 urgent need household, along with the delivery of the city-managed Homeowner Assistance program.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with delivery of the city-managed Homeowner Assistance program. 65.85 - Quarterly expenditure related to state costs in support of activity delivery.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the rehabilitation of one (1) Urgent Need homeowner assistance project, which has now received its full obligation. The GLO also reimbursed costs associated with delivery of the city-managed Homeowner Assistance program. All projects under this program have received a final inspection and are reported as complete.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO also reimbursed costs associated with delivery of the city-managed Homeowner Assistance program. All projects under this program have received a final inspection and are reported as complete. 1509.06 - Quarterly expenditure for state costs in support of activity delivery.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed for costs associated with delivery of the program. Final inspection has been completed on all 2 urgent need homeowner assistance projects. 1748.35 - Quarterly expenditure for state costs in support of activity delivery.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed for costs associated with delivery of the program. Final inspection has been completed on all 2 urgent need homeowner assistance projects. 2077.18 - Quarterly expenditure for state costs in support of activity delivery.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed for costs associated with delivery and implementation of the program. Final inspection has been completed on all 2 urgent need homeowner assistance projects. 1425.56 - State costs in support of activity delivery.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed for costs associated with delivery and implementation of the program. 336.51 - State costs in support of activity delivery.
HouHoAP[CM]_DA_UN_21-134-000-C788 | HOU HAP City Managed Rehab. and Recon. | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed for costs associated with delivery of the program. 17.85 - State costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2019-04-01 | 2019 Q3
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2019-07-01 | 2019 Q4
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2020-01-01 | 2020 Q2 | During the reporting period, Houston received 0 applications and verified 15 projects for eligibility. 8 total projects have been completed by Houston and 3 projects are underway.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2020-04-01 | 2020 Q3
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 19 low-to-moderate income households.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 15 low-to-moderate income households.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 3 low-to-moderate income households.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 6 low-to-moderate income households, 5 of which are complete. DRGR Low Actuals not appearing in Q1 2021 QPR, adjustments for Q2 2021.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 3 low-to-moderate income households, and 4 projects were completed this quarter.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 8 low-to-moderate income households. The GLO also reimbursed vendor costs associated with environmental reviews.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 18 low-to-moderate income households, as well as costs associated with the delivery of the Homeowner Assistance Program. 3618.12 - Payroll Allocations.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 25 low-to-moderate income households, as well as costs associated with the delivery of the Homeowner Assistance Program. The GLO also reimbursed vendor costs associated with environmental reviews. 8528.38 - Payroll Allocations.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed the City of Houston for homeowner reimbursement assistance to 3 low-to-moderate income households, as well as costs associated with the delivery of the Homeowner Assistance Program. Additionally, as part of an annual reconciliation of the data, the Texas General Land Office identified a discrepancy in the cumulative total of complete projects, and therefore has removed one complete project from the performance measures in order to ensure the cumulative complete projects is accurate. The Texas General Land Office also reimbursed vendor costs associated with environmental reviews. The city submitted only three new Homeowner Assistance Reimbursement LMI payment requests to the Texas General Land Office during the quarter, which is why expenditures are relatively low compared to previous quarters. 8369.62 - Payroll allocation costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 49 low-to-moderate income households. The GLO also reimbursed for costs associated with the delivery of the program and vendor costs associated with environmental reviews. 13519.93 - Payroll allocation costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 12 low-to-moderate income households. The GLO also reimbursed for costs associated with the delivery of the program and vendor costs associated with environmental reviews. 6552.51 - Payroll allocation costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 18 low-to-moderate income households. The GLO also reimbursed for costs associated with the delivery of the program and vendor costs associated with environmental reviews. 9759.87 - State costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 6 low-to-moderate income households. The GLO also reimbursed for costs associated with the delivery of the program and vendor costs associated with environmental reviews. $7639.92 - State costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 2 low-to-moderate income households. The GLO also reimbursed for costs associated with the delivery of the program.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 1 low-to-moderate income household. The GLO also reimbursed for costs associated with the delivery of the program. 790.79 - Quarterly expenditure related to state costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 5 low-to-moderate income households, which are all now complete. The GLO also reimbursed for costs associated with the delivery of the program.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 3 low-to-moderate income households, which are all now complete. The GLO also reimbursed for costs associated with the delivery of the program. 9158.01 - Quarterly expenditure for state costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed for costs associated with the delivery of the Homeowner Assistance program. 5260.05 - Quarterly expenditure for state costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed for costs associated with the delivery of the Homeowner Assistance program. 8310.6 - Quarterly expenditure for state costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed for costs associated with the delivery and implementation of the Homeowner Assistance program. 5703.37 - State costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed for costs associated with delivery and implementation of the program. 1346.38 - State costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed for costs associated with delivery of the program. 1229.07 - State costs in support of activity delivery.
HouHoAP[Reimb]_DA_LMI_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2026-01-01 | 2026 Q2
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2019-04-01 | 2019 Q3
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2019-07-01 | 2019 Q4
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2020-01-01 | 2020 Q2
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 15 non-low-to-moderate income households.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 10 non-low-to-moderate income households.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 11 non-low-to-moderate income households.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 9 non-low-to-moderate income households.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 5 non-low-to-moderate income households.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2021-10-01 | 2022 Q1 | During the reporting period the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 6 non-low-to-moderate income households. The GLO also reimbursed vendor costs associated with environmental reviews.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 35 non-low-to-moderate income households, as well as costs associated with the delivery of the Homeowner Assistance Program. 4593.73 - Payroll Allocations.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 43 urgent need income households, as well as costs associated with the delivery of the Homeowner Assistance Program. The GLO also reimbursed vendor costs associated with environmental reviews. 10828.05 - Payroll Allocations.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed the City of Houston for homeowner reimbursement assistance to 16 urgent need income households, as well as costs associated with the delivery of the Homeowner Assistance Program. The Texas General Land Office also reimbursed vendor costs associated with environmental reviews. The city submitted only three new Homeowner Assistance Reimbursement UN payment requests to the Texas General Land Office during the quarter, which is why expenditures are relatively low compared to previous quarters. 11514.44 - Payroll allocation costs in support of activity delivery.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 80 urgent need income households. The GLO also reimbursed for costs associated with the delivery of the program and vendor costs associated with environmental reviews. 18053.53 - Payroll allocation costs in support of activity delivery.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 21 urgent need income households. The GLO also reimbursed for costs associated with the delivery of the program and vendor costs associated with environmental reviews. 8587.49 - Payroll allocation costs in support of activity delivery.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 4 urgent need income households. The GLO also reimbursed for costs associated with the delivery of the program and vendor costs associated with environmental reviews. 11298.28 - State costs in support of activity delivery.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for homeowner reimbursement assistance to 4 urgent need income households. The GLO also reimbursed for costs associated with the delivery of the program and vendor costs associated with environmental reviews. $7560.42 - State costs in support of activity delivery.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston costs associated with the delivery of the program.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston costs associated with the delivery of the program. 263.39 - Quarterly expenditure related to state costs in support of activity delivery.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston costs associated with the delivery of the program.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston costs associated with the delivery of the program. 3008.4 - Quarterly expenditure for state costs in support of activity delivery.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed for costs associated with the delivery of the Homeowner Assistance program. 2324.03 - Quarterly expenditure for state costs in support of activity delivery.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed for costs associated with the delivery of the Homeowner Assistance program. 2077.18 - Quarterly expenditure for state costs in support of activity delivery.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed for costs associated with the delivery and implementation of the Homeowner Assistance program. 1425.56 - State costs in support of activity delivery.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed for costs associated with delivery and implementation of the program. 336.51 - State costs in support of activity delivery.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed for costs associated with delivery of the program. 1551.29 - State costs in support of activity delivery.
HouHoAP[Reimb]_DA_UN_21-134-000-C788 | HOU HAP Reimbursement | Rehabilitation/reconstruction of residential structures | Houston, City of | 2026-01-01 | 2026 Q2
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2019-04-01 | 2019 Q3
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2019-07-01 | 2019 Q4
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2020-01-01 | 2020 Q2 | During the reporting period, Houston received 0 applications and verified 9 projects for eligibility. 0 total projects have completed by Houston and 2 projects are underway.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Houston began work on three multifamily rental projects.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2020-07-01 | 2020 Q4
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the GLO reimbursed the City of Houston for acquisition and construction costs associated with 3 multifamily rental properties, which are still underway.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the GLO reimbursed the City of Houston for acquisition and construction costs associated with 6 multifamily rental properties, which are still underway.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the GLO reimbursed the City of Houston for acquisition and construction costs associated with 10 multifamily rental properties, which are still underway.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed the City of Houston for acquisition and construction costs associated with 7 multifamily rental properties, which are still underway.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed the City of Houston for acquisition and construction costs associated with 9 multifamily rental properties, which are still underway. Additionally, the GLO reimbursed the City of Houston for costs associated with delivering the Multifamily Rental Program. The GLO also reimbursed vendor costs associated with environmental reviews.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed the City of Houston for acquisition and construction costs associated with 14 multifamily rental properties, which are still underway. The GLO also reimbursed costs associated with the delivery of the Homeowner Assistance Program. 5259.41 - Payroll Allocations.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed the City of Houston for acquisition and construction costs associated with 9 multifamily rental properties, which are still underway. The GLO also reimbursed costs associated with the delivery of the Multifamily Rental Program. The GLO also reimbursed vendor costs associated with environmental reviews. 8430.29 - Payroll Allocations.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed the City of Houston for acquisition and construction costs associated with 9 multifamily rental properties, which are still underway. The Texas General Land Office also reimbursed costs associated with the delivery of the Multifamily Rental Program. The Texas General Land Office also reimbursed vendor costs associated with environmental reviews. The city submitted only one new Multifamily Rental Program payment request to the Texas General Land Office during the quarter, which is why expenditures are relatively low compared to previous quarters. 6552.1 - Payroll allocation costs in support of activity delivery.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 5 multifamily rental properties, which are still underway. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. 13056.04 - Payroll allocation costs in support of activity delivery.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 7 multifamily rental properties, which are still underway. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. 9690.44 - Payroll allocation costs in support of activity delivery.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 12 multifamily rental properties, 11 of which are still underway. One project was completed in this quarter. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. 22708.73 - State costs in support of activity delivery. Three housing units reported as completed this quarter are not yet occupied, creating the discrepancy between units and households. Once occupied these will be reported.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 9 multifamily rental properties, 8 of which are still underway. One project was completed in this quarter. The GLO also reimbursed costs associated with the delivery of the program and vendor costs associated with environmental reviews. $29543.02 - State costs in support of activity delivery.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 15 multifamily rental properties, 13 of which are still underway. Two projects were completed in this quarter. The GLO also reimbursed costs associated with the delivery of the program.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 12 multifamily rental properties, 9 of which are still underway. Three projects were completed in this quarter. The GLO also reimbursed costs associated with the delivery of the program. 9433.9 - Quarterly expenditure related to state costs in support of activity delivery.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 12 multifamily rental properties, 7 of which are still underway. Five projects were completed in this quarter. The GLO also reimbursed costs associated with the delivery of the program.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 7 multifamily rental properties, 4 of which are still underway. Three projects were completed in this quarter. The GLO also reimbursed costs associated with the delivery of the program. 85495.15 - Quarterly expenditure for state costs in support of activity delivery.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 5 multifamily rental properties, 2 of which are still underway. Three projects were completed in this quarter. The GLO also reimbursed costs associated with the delivery of the program. 27607.66 - Quarterly expenditure for state costs in support of activity delivery.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 3 multifamily rental properties, all of which are still underway. The GLO also reimbursed costs associated with the delivery of the program. 36817.53 - Quarterly expenditure for state costs in support of activity delivery.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 4 multifamily rental properties. The GLO also reimbursed costs associated with the delivery of the program. 17659.5 - State costs in support of activity delivery.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with four (4) multifamily rental properties. The GLO also reimbursed costs associated with the delivery of the Multifamily Rental program. 6405.79 - State costs in support of activity delivery.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with one (1) multifamily rental properties. The GLO also reimbursed costs associated with the delivery of the Multifamily Rental program. 20441.55 - State costs in support of activity delivery.
HouMFRP_DA_LMI_21-134-000-C788 | HOU Multifamily Rental | Affordable Rental Housing | Houston, City of | 2026-01-01 | 2026 Q2
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2019-04-01 | 2019 Q3
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City incurred planning eligible costs necessary for administering the grant.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the GLO reimbursed the City of Houston for planning eligible costs necessary for administering the grant.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2021-01-01 | 2021 Q2 | A DRGR voucher was revised in January to move a portion of a payment from planning to the homebuyer assistance program. Funds moved to HouHBAP_DA_LMI_19-147-001-B489 in payment correction.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed the City of Houston for general planning costs associated with administrating the grant, as well as costs associated with the implementation of three studies.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the implementation of one study and costs associated with delivering the program. 459.84 - Payroll Allocations.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed the City of Houston for staff time and other costs associated with delivering the program. 4196.07 - Payroll Allocations.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the GLO reimbursed the City of Houston for staff time and work completed on four planning projects. The GLO also reimbursed final payments on two planning projects, which are complete. Finally, the GLO reimbursed payroll and vendor costs associated with delivering the program. The city did not submit any new Planning Program payment requests to the GLO during the quarter, which is why expenditures are relatively low compared to previous quarters. 2032.04 - Payroll allocation costs in support of activity delivery.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with 5 planning studies, 1 of which was completed as of the end of the quarter. The GLO also reimbursed for costs associated with the delivery of the program. 4842.2 - Payroll allocation costs in support of activity delivery.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with 5 planning studies. The GLO also reimbursed for costs associated with the delivery of the program. 3370.5 - Payroll allocation costs in support of activity delivery.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with 7 planning studies and costs associated with the delivery of the program. Funds were also recaptured during the quarter. 9778.05 - State costs in support of activity delivery.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with 4 planning studies and costs associated with the delivery of the program. $7584.79 - State costs in support of activity delivery.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with 6 planning studies and costs associated with the delivery of the program.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with 4 planning studies and costs associated with the delivery of the program. 1470.37 - Quarterly expenditure related to state costs in support of activity delivery.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with 4 planning studies, which are still underway, and costs associated with the delivery of the program.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with 1 planning study, which is now complete, and costs associated with the delivery of the program. 19118.95 - Quarterly expenditure for state costs in support of activity delivery.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Planning program. All Planning studies are complete. 16064.69 - Quarterly expenditure for state costs in support of activity delivery.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Planning program. All Planning studies are complete. 23643.8 - Quarterly expenditure for state costs in support of activity delivery.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO issued payment for costs associated with the implementation of the Planning program. All Planning studies are complete. 11798.57 - State costs in support of activity delivery.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO issued payment for vendor costs associated with the Planning program. All Planning studies are complete. 6051.15 - State costs in support of activity delivery.
HouPLN_DA_NA_21-134-000-C788 | HOU Planning | Planning | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO issued payment for vendor costs associated with the Planning program. All Planning studies are complete. 1175.57 - State costs in support of activity delivery.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2019-04-01 | 2019 Q3
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the GLO reimbursed the City of Houston for three public service programs providing housing counseling and job training to Houstonians, including the completion of services to 7 low-to-moderate income individuals affected by homelessness who received case management and supportive housing services.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the GLO reimbursed the City of Houston for 16 public service programs, which are underway. Additionally, the GLO reimbursed costs associated with the completion of services for 453 low-to-moderate income individuals.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed the City of Houston for 12 public service programs, which are underway. Additionally, the GLO reimbursed costs associated with the completion of services for 87 low-to-moderate income individuals.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the GLO reimbursed the City of Houston for 14 public service programs, which are underway. Additionally, the GLO reimbursed costs associated with the completion of services for 55 low-to-moderate income individuals and for project delivery costs associated with delivering the Public Services program.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed the City of Houston for 13 public service programs, which are underway. Additionally, the GLO reimbursed costs associated with the completion of services for 279 low-to-moderate income individuals and for project delivery costs associated with delivering the Public Services program. 1888.34 - Payroll Allocations.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed the City of Houston for 16 public service programs, which are underway or in the process of closeout. Additionally, the GLO reimbursed costs associated with the completion of services for 446 individuals and for project delivery costs associated with delivering the Public Services program. 8025.75 - Payroll Allocations.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed the City of Houston for 15 public service programs, which are underway or in the process of closeout. Additionally, the Texas General Land Office reimbursed costs associated with the completion of services for 234 individuals and for project delivery costs associated with delivering the Public Services program. The city submitted only two new Public Service Program payment requests to the Texas General Land Office during the quarter, which is why expenditures are relatively low compared to previous quarters. Additionally, one project was withdrawn by the agency during the quarter. Prior to this no CDBG-DR funds were reimbursed for the withdrawn project. 2079.66 - Payroll allocation costs in support of activity delivery.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed the City of Houston for 16 public service programs, 5 of which are underway, and 11 have been completed, resulting in services to an additional 1,948 individuals. Additionally, as the GLO made final payments for public service projects, final beneficiary numbers were reconciled and an additional 576 beneficiaries were served under these programs which had not yet been reported. The GLO also reimbursed costs associated with delivery of the program. 8933.27 - Payroll allocation costs in support of activity delivery.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed the City of Houston for 4 public service programs, resulting in services to an additional 34 individuals. 1886.04 - Payroll allocation costs in support of activity delivery.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for 4 public service programs, resulting in services to an additional 1,990 individuals. 6884.58 - State costs in support of activity delivery.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the deliver of the Public Services program. $5246.16 - State costs in support of activity delivery.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the deliver of the Public Services program. Adjustments made to the beneficiaries and demographics.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Public Services program. 38.33 - Quarterly expenditure related to state costs in support of activity delivery.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Public Services program. The program is complete and all beneficiaries have been reported.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Public Services program. The program is complete and all beneficiaries have been reported. 5587.2 - Quarterly expenditure for state costs in support of activity delivery.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Public Services program. The program is complete and all beneficiaries have been reported. Quarterly expenditure for state costs in support of activity delivery.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Public Services program. The program is complete and all beneficiaries have been reported. 2114.06 - Quarterly expenditure for state costs in support of activity delivery.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO had no reimbursement payments for project delivery services. The program is complete and all beneficiaries have been reported. State costs in support of activity delivery.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO had no reimbursement payments for project delivery services. The program is complete and all beneficiaries have been reported. 172.45 - State costs in support of activity delivery.
HouPS_DA_LMI_21-134-000-C788 | HOU Public Services | Public services | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO had no reimbursement payments for project delivery services. The program is complete and all beneficiaries have been reported.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2019-04-01 | 2019 Q3
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2019-07-01 | 2019 Q4
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2020-01-01 | 2020 Q2
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2021-01-01 | 2021 Q2
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2021-04-01 | 2021 Q3
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed the City of Houston for project delivery costs associated with implementing the program.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2021-10-01 | 2022 Q1 | During the reporting period the GLO reimbursed the City of Houston for costs associated with delivering the Single Family Development Program.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed the City of Houston for acquisition costs, along with costs for delivering the Single Family Development Program. 1714.31 - Payroll Allocations.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs for delivering the Single Family Development Program. The GLO also reimbursed vendor costs associated with environmental reviews. 9800.51 - Payroll Allocations.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed the City of Houston for costs for delivering the Single Family Development Program. The Texas General Land Office also reimbursed vendor costs associated with environmental reviews. The city did not submit any new Single Family Development Program payment requests to the Texas General Land Office during the quarter, which is why expenditures are relatively low compared to previous quarters. 4523.56 - Payroll allocation costs in support of activity delivery.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed the City of Houston for acquisition costs associated with two single family development projects. The GLO also reimbursed costs associated with delivering the program and vendor costs associated with environmental reviews. 11280.51 - Payroll allocation costs in support of activity delivery.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed the City of Houston for acquisition costs associated with two single family development projects. The GLO also reimbursed costs associated with delivering the program and vendor costs associated with environmental reviews. 3872.91 - Payroll allocation costs in support of activity delivery.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Single Family New Development program. 9325.33 - State costs in support of activity delivery.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Single Family New Development program. $8767.47 - State costs in support of activity delivery.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Single Family New Development program.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Single Family New Development program. 1302.96 - Quarterly expenditure related to state costs in support of activity delivery.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Single Family New Development program.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Single Family New Development program. 15254.89 - Quarterly expenditure for state costs in support of activity delivery.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Single Family New Development program. 10362.57 - Quarterly expenditure for state costs in support of activity delivery.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the delivery of the Single Family New Development program and repayments from the City for SFDP. 9085.44 - Quarterly expenditure for state costs in support of activity delivery.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with the implementation of the Single Family New Development program and received program income from the City for the Hardy Yards project. 4019.78 - State costs in support of activity delivery.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed for implementation and administrative costs. 2715.21 - State costs in support of activity delivery.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO reimbursed for administrative costs. 2167 - State costs in support of activity delivery.
HouSFDP_DA_LMI_21-134-000-C788 | HOU Single Family Development | Construction of new housing | Houston, City of | 2026-01-01 | 2026 Q2
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2019-04-01 | 2019 Q3
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2019-07-01 | 2019 Q4
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2020-01-01 | 2020 Q2
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2021-04-01 | 2021 Q3
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO reimbursed the City of Houston for project delivery costs associated with implementing the program.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2021-10-01 | 2022 Q1 | During the reporting period the GLO reimbursed the City of Houston for costs associated with delivering the Small Rental Program.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with delivering the Small Rental Program. 108.71 - Payroll Allocations.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the GLO reimbursed the City of Houston for costs associated with delivering the Small Rental Program. The GLO also reimbursed vendor costs associated with environmental reviews. 1582.09 - Payroll Allocations.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the Texas General Land Office reimbursed the City of Houston for costs associated with delivering the Small Rental Program. The Texas General Land Office also reimbursed vendor costs associated with environmental reviews. The city submitted only two new Small Rental Program payment requests to the Texas General Land Office during the quarter, which is why expenditures are relatively low compared to previous quarters. 3372.98 - Payroll allocation costs in support of activity delivery.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the GLO reimbursed for costs associated with delivery of the program. 4256.95 - Payroll allocation costs in support of activity delivery.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the GLO reimbursed for costs associated with delivery of the program. 1306.86 - Payroll allocation costs in support of activity delivery.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 2 small rental properties, which are still underway. The GLO also reimbursed costs associated with the delivery of the program. 4734.06 - State costs in support of activity delivery.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 1 small rental property, which is still underway. The GLO also reimbursed costs associated with the delivery of the program. $4820.53 - State costs in support of activity delivery.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with 5 small rental properties, which are all underway. The GLO also reimbursed costs associated with the delivery of the program.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with the delivery of the Small Rental program. 1275.88 - Quarterly expenditure related to state costs in support of activity delivery.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with two (2) small rental projects, along with associated with the delivery of the Small Rental program.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with two (2) small rental projects, along with associated with the delivery of the Small Rental program. 12432.14 - Quarterly expenditure for state costs in support of activity delivery.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with two (2) small rental projects, along with associated with the delivery of the Small Rental program. One small rental project is completed this quarter. 3672.07 - Quarterly expenditure for state costs in support of activity delivery.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with two (2) small rental projects, along with associated with the delivery of the Small Rental program. 11971.54 - Quarterly expenditure for state costs in support of activity delivery.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO reimbursed the City of Houston for construction costs associated with three (3) small rental projects, along with associated with the delivery of the Small Rental program. 9475.59 - State costs in support of activity delivery.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO reimbursed the City of Houston for all construction costs associated with all four (4) small rental projects. The GLO also reimbursed costs associated with the delivery of the Small Rental Program . 5669.33 - State costs in support of activity delivery.
HouSRP_DA_LMI_21-134-000-C788 | HOU Small Rental | Affordable Rental Housing | Houston, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the GLO also reimbursed costs associated with the delivery of the Small Rental Program. 8475.01 - State costs in support of activity delivery.
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the review period, funds used to reimburse homeowners for repairs.
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the review period, funds used to reimburse homeowners for repairs
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 260 applicants assisted.
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | The Homeowner Reimbursement Program served 303 HMID-LMI applicants during Q1. 17943.74 - Payroll Allocation
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | The Homeowner Reimbursement Program served 230 HMID-LMI applicants during Q2. 18,551.81 - Payroll Allocation
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | The Homeowner Reimbursement Program served 330 HMID-LMI applicants during Q3. 16477.3 - Payroll Allocations
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | The Homeowner Reimbursement Program served 18 HMID-LMI applicants during Q4. $16211.58 - Payroll Allocations.
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | The Homeowner Reimbursement Program served 47 HMID-LMI applicants during Q1. 10169.35 - Payroll Allocations.
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | The Homeowner Reimbursement Program served 1 HMID-LMI applicants during Q2. 2286.31 - Payroll Allocations
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | The Homeowner Reimbursement Program served 1 HMID-LMI applicants during Q3. 587.1 - Payroll Allocations.
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-04-01 | 2022 Q3 | Undergoing financial reconciliation of the program.
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | Added a 0 to the elevated structures and substantially rehabilitated units measures in the Action Plan module in order to be submitted.
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We are processing final voucher adjustments in preparation for closeout.
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout.
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Unused funds removed per Action Plan Amendment 13
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-10-01 | 2024 Q1
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Correction made to number of beneficiaries served under this activity that was identified during closeout. Activity was reclosed and remains Completed.
HRP_HMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, financial reconciliation is still ongoing. Additionally, revisions are related to a subrogation repayment installment agreement.
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 545 applicants assisted.
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | The Homeowner Reimbursement Program served 616 HMID-UN applicants during Q1. 30636.22 - Payroll Allocation
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | The Homeowner Reimbursement Program served 460 HMID-UN applicants during Q2. 32,901.94 - Payroll Allocation
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | The Homeowner Reimbursement Program served 488 HMID-UN applicants during Q3. 29662.23 - Payroll Allocations
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | The Homeowner Reimbursement Program served 17 HMID-UN applicants during Q4. $27768.34 - Payroll Allocations.
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | The Homeowner Reimbursement Program served 31 HMID-UN applicants during Q1. 17418.81 - Payroll Allocations.
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | The Homeowner Reimbursement Program served 3 HMID-UN applicants during Q2. 3916.13 - Payroll Allocations
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | The Homeowner Reimbursement Program served 0 HMID-UN applicants during Q3. 1002.47 - Payroll Allocations.
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | Added a 0 to the elevated structures and substantially rehabilitated units measures in the Action Plan module in order to be submitted.
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We are processing final voucher adjustments in preparation for closeout.
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout.
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Unused funds removed per Action Plan Amendment 13
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Correction made to number of beneficiaries served under this activity that was identified during closeout. Activity was reclosed and remains Completed.
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-07-01 | 2025 Q4 | Negative expenditure was the result of a subrogation agreement in AY 23.
HRP_HMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, financial reconciliation is still ongoing. Additionally, revisions are related to a subrogation repayment installment agreement.
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 2 applicants assisted.
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | The Homeowner Reimbursement Program served 4 SMID-LMI applicants during Q1. 249.88 - Payroll Allocation
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | The Homeowner Reimbursement Program served 4 SMID-LMI applicants during Q2. 246.57 - Payroll Allocation
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | The Homeowner Reimbursement Program served 4 SMID-LMI applicants during Q3. 215.39 - Payroll Allocations
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | The Homeowner Reimbursement Program served 0 SMID-LMI applicants during Q4. $280.90 - Payroll Allocations.
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | The Homeowner Reimbursement Program served 2 SMID-LMI applicants during Q1. 176.2 - Payroll Allocations.
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | The Homeowner Reimbursement Program served 0 SMID-LMI applicants during Q2. 39.61 - Payroll Allocations
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | The Homeowner Reimbursement Program served 0 SMID-LMI applicants during Q3. 10.64 - Payroll Allocations.
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | Added a 0 to the elevated structures and substantially rehabilitated units measures in the Action Plan module in order to be submitted.
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We are processing final voucher adjustments in preparation for closeout.
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout.
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Unused funds removed per Action Plan Amendment 13
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Correction made to number of beneficiaries served under this activity that was identified during closeout. Activity was reclosed and remains Completed.
HRP_SMID_LMI | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, financial reconciliation is still ongoing. Additionally, revisions are related to a subrogation repayment installment agreement.
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | During the reporting period, 3 applicants assisted.
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | The Homeowner Reimbursement Program served 6 SMID-UN applicants during Q1. 316.44 - Payroll Allocation
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3 | The Homeowner Reimbursement Program served 3 SMID-UN applicants during Q2. 327.79 - Payroll Allocation
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | The Homeowner Reimbursement Program served 5 SMID-UN applicants during Q3. 261.55 - Payroll Allocations
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1 | The Homeowner Reimbursement Program served 0 SMID-UN applicants during Q4. $325.48 - Payroll Allocations.
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-01-01 | 2021 Q2 | The Homeowner Reimbursement Program served 1 SMID-UN applicants during Q1. 204.17 - Payroll Allocations.
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-04-01 | 2021 Q3 | The Homeowner Reimbursement Program served 0 SMID-UN applicants during Q2. 45.91 - Payroll Allocations
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2021-07-01 | 2021 Q4 | The Homeowner Reimbursement Program served 0 SMID-UN applicants during Q3. 12.26 - Payroll Allocations.
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-07-01 | 2022 Q4 | Added a 0 to the elevated structures and substantially rehabilitated units measures in the Action Plan module in order to be submitted.
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2022-10-01 | 2023 Q1 | No reportable changes during this quarter. We are processing final voucher adjustments in preparation for closeout.
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | No reportable changes during this quarter. We will be assessing the activity to prepare for closeout.
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Unused funds removed per Action Plan Amendment 13
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-01-01 | 2025 Q2 | Correction made to number of beneficiaries served under this activity that was identified during closeout. Activity was reclosed and remains Completed.
HRP_SMID_UN | Homeowner Reimbursement Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, financial reconciliation is still ongoing. Additionally, revisions are related to a subrogation repayment installment agreement.
INF_HMID_LMI_20-065-001-B947_Galveston | Street Improvements | Construction/reconstruction of streets | City of Galveston | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-001-B947_Galveston | Street Improvements | Construction/reconstruction of streets | City of Galveston | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Galveston completed environmental review for its street improvement project.
INF_HMID_LMI_20-065-001-B947_Galveston | Street Improvements | Construction/reconstruction of streets | City of Galveston | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-001-B947_Galveston | Street Improvements | Construction/reconstruction of streets | City of Galveston | 2022-01-01 | 2022 Q2 | During the reporting period, a contract amendment was executed in which an end date extension was granted.
INF_HMID_LMI_20-065-001-B947_Galveston | Street Improvements | Construction/reconstruction of streets | City of Galveston | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Galveston submitted their revised project completion report for grant closeout. The PCR is under review with the program area and administrative closeout is underway.
INF_HMID_LMI_20-065-001-B947_Galveston | Street Improvements | Construction/reconstruction of streets | City of Galveston | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-001-B947_Galveston | Street Improvements | Construction/reconstruction of streets | City of Galveston | 2025-01-01 | 2025 Q2 | Activity budget and obligation reduced according to closeout documentation, this activity is fully completed and administratively closed with all accomplishments and beneficiaries reported.
INF_HMID_LMI_20-065-003-B965_Liberty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Liberty | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-003-B965_Liberty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Liberty | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Liberty completed environmental review for its sewer facilities project.
INF_HMID_LMI_20-065-003-B965_Liberty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Liberty | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-003-B965_Liberty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Liberty | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Liberty had construction underway for its sewer facilities project. Construction is near completion.
INF_HMID_LMI_20-065-003-B965_Liberty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Liberty | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Liberty submitted grant closeout documents for its sewer facilities project. The closeout documents are pending review.
INF_HMID_LMI_20-065-003-B965_Liberty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Liberty | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Liberty had grant closeout documents under review for its sewer facilities project.
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2020-01-01 | 2020 Q2 | During the reporting period, the City of Sinton had engineering design and environmental review underway for its sewer facilities project.
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Sinton had environmental review and engineering design underway for its sewer facilities project.
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Sinton had engineering design underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Sinton had engineering design complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Sinton had 50% of construction completed for its Sewer Facilities project.
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Sinton had 50% of construction underway/complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Sinton had 50% of construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Sinton had construction complete and the COCC underway for its sewer facilities project.
INF_HMID_LMI_20-065-004-B995_Sinton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Sinton | 2024-07-01 | 2024 Q4 | During the reporting period, this contract has completed construction and is in the closeout phase.
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2020-10-01 | 2021 Q1 | During the reporting period, Galveston County had environmental review and engineering design underway for its street improvements projects.
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2021-07-01 | 2021 Q4 | During the reporting period, Galveston County had construction procurement underway for its flood and drainage project.
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2021-10-01 | 2022 Q1 | During the reporting period, Galveston County had construction procurement underway for its flood and drainage project.
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2022-01-01 | 2022 Q2 | During the reporting period, Galveston County had construction underway for its flood and drainage activities.
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2022-04-01 | 2022 Q3 | During the reporting period, Galveston County had construction underway for its drainage improvements project.
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2022-10-01 | 2023 Q1 | During the reporting period, Galveston had 90% of construction underway for its flood and drainage facilities improvements project.
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2023-01-01 | 2023 Q2 | During the reporting period, Galveston had 95% of construction underway for its flood and drainage facilities improvements project.
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2023-04-01 | 2023 Q3 | During the reporting period, Galveston County submitted grant closeout documents for its flood and drainage facilities improvements project.
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2023-07-01 | 2023 Q4 | During the reporting period, Galveston County submitted grant closeout documents for its flood and drainage facilities improvements project.
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2024-10-01 | 2025 Q1 | During the reporting period, the County of Galveston had its Flood & Drainage project administratively closed.
INF_HMID_LMI_20-065-006-C004_GalvestonCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Galveston County | 2025-01-01 | 2025 Q2 | Activity budget and obligation reduced according to closeout documentation, this activity is fully completed and administratively closed with all accomplishments and beneficiaries reported.
INF_HMID_LMI_20-065-007-C010_ChambersCounty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Chambers County | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-007-C010_ChambersCounty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Chambers County | 2021-07-01 | 2021 Q4 | During the reporting period, Chambers County had construction procurement underway for its sewer project.
INF_HMID_LMI_20-065-007-C010_ChambersCounty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Chambers County | 2021-10-01 | 2022 Q1 | During the reporting period, Chambers County had construction procurement underway for its sewer facilities project.
INF_HMID_LMI_20-065-007-C010_ChambersCounty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Chambers County | 2022-01-01 | 2022 Q2 | During the reporting period, Chambers County had construction underway for its Sewer Facilities project. They also decided no Environmental Re-eval necessary for their change order.
INF_HMID_LMI_20-065-007-C010_ChambersCounty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Chambers County | 2022-10-01 | 2023 Q1 | During the reporting?period,?Chambers County had 50% of construction?underway/complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-007-C010_ChambersCounty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Chambers County | 2023-01-01 | 2023 Q2 | During the reporting period, Chambers County had construction underway for its sewer facilities project.
INF_HMID_LMI_20-065-007-C010_ChambersCounty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Chambers County | 2023-07-01 | 2023 Q4 | During the reporting period, the Chambers County completed construction and is pending submission of construction completion documentation for its sewer facilities project.
INF_HMID_LMI_20-065-007-C010_ChambersCounty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Chambers County | 2024-04-01 | 2024 Q3 | During the reporting period, the Chambers County had grant closeout documents under review for its sewer facilities project.
INF_HMID_LMI_20-065-007-C010_ChambersCounty | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Chambers County | 2024-07-01 | 2024 Q4 | Closeout underway: During the reporting period, the Chambers County had grant closeout documents approved for its sewer facilities project
INF_HMID_LMI_20-065-008-C011_IowaColony | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Iowa Colony | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-008-C011_IowaColony | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Iowa Colony | 2020-01-01 | 2020 Q2 | During the reporting period, the City of Iowa Colony had environmental review underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-008-C011_IowaColony | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Iowa Colony | 2020-04-01 | 2020 Q3 | During the reporting period, Iowa Colony had environmental review and engineering design underway for it&apos;s Food & Drainage facilities.
INF_HMID_LMI_20-065-008-C011_IowaColony | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Iowa Colony | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Iowa Colony completed engineering design for its flood and drainage project.
INF_HMID_LMI_20-065-008-C011_IowaColony | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Iowa Colony | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-008-C011_IowaColony | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Iowa Colony | 2022-10-01 | 2023 Q1 | During the reporting period, City completed construction and is pending submission of construction completion documentation for its Flood & Drainage Facilities project.
INF_HMID_LMI_20-065-008-C011_IowaColony | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Iowa Colony | 2023-01-01 | 2023 Q2 | Requesting backdating to complete the budget amendment then followed with close out.
INF_HMID_LMI_20-065-008-C011_IowaColony | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Iowa Colony | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-008-C011_IowaColony | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Iowa Colony | 2023-10-01 | 2024 Q1 | During the reporting period, Iowa Colony had Close Out Underway.
INF_HMID_LMI_20-065-008-C011_IowaColony | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Iowa Colony | 2024-04-01 | 2024 Q3 | Final retainage draw has been released, GLO working on close out
INF_HMID_LMI_20-065-009-C022_Cleveland_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-009-C022_Cleveland_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Cleveland had environmental review and engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-009-C022_Cleveland_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Cleveland had construction procurement underway for its flood and drainage facilities improvements project.
INF_HMID_LMI_20-065-009-C022_Cleveland_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Cleveland had construction underway for its flood and drainage facilities improvements project.
INF_HMID_LMI_20-065-009-C022_Cleveland_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Cleveland had construction underway for its flood and drainage facilities improvements project.
INF_HMID_LMI_20-065-009-C022_Cleveland_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Cleveland had construction underway for its flood and drainage facilities improvements project.
INF_HMID_LMI_20-065-009-C022_Cleveland_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Cleveland completed construction for its flood and drainage facilities improvements project. A fund reallocation amendment is in process while the City prepares its closeout documents for submission.
INF_HMID_LMI_20-065-009-C022_Cleveland_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Cleveland amended their contract to adjust the budget between the sewer facilities project and the flood and drainage project.
INF_HMID_LMI_20-065-009-C022_Cleveland_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Cleveland had grant closeout documents under review for its flood and drainage facilities improvements project.
INF_HMID_LMI_20-065-009-C022_Cleveland_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-009-C022_Cleveland_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-009-C022_Cleveland_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cleveland, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Cleveland had grant closeout documents under review for its flood and drainage facilities project.
INF_HMID_LMI_20-065-009-C022_Cleveland_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-009-C022_Cleveland_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Cleveland had environmental review and engineering design underway for its sewer project.
INF_HMID_LMI_20-065-009-C022_Cleveland_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Cleveland had construction procurement underway for its sewer facilities project.
INF_HMID_LMI_20-065-009-C022_Cleveland_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Cleveland had construction underway for its sewer facilities project.
INF_HMID_LMI_20-065-009-C022_Cleveland_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Cleveland had construction underway for its sewer facilities project.
INF_HMID_LMI_20-065-009-C022_Cleveland_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Cleveland amended their contract to adjust the budget between the sewer facilities project and the flood and drainage project.
INF_HMID_LMI_20-065-009-C022_Cleveland_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Cleveland had grant closeout documents under review for its sewer facilities project.
INF_HMID_LMI_20-065-009-C022_Cleveland_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-009-C022_Cleveland_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-009-C022_Cleveland_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cleveland, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Cleveland had grant closeout documents under review for its sewer facilities project.
INF_HMID_LMI_20-065-010-C027_Conroe | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Conroe | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-010-C027_Conroe | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Conroe | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Conroe had construction procurement underway for its sewer facilities project.
INF_HMID_LMI_20-065-010-C027_Conroe | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Conroe | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-010-C027_Conroe | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Conroe | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Conroe had construction underway for its sewer facilities project. Construction is currently at approximately 90% complete.
INF_HMID_LMI_20-065-010-C027_Conroe | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Conroe | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Conroe submitted grant closeout documents for its Sewer Facilities project.
INF_HMID_LMI_20-065-010-C027_Conroe | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Conroe | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-010-C027_Conroe | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Conroe | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Conroe had its F&D project administratively closed.
INF_HMID_LMI_20-065-010-C027_Conroe | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Conroe | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-010-C027_Conroe | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Conroe | 2024-01-01 | 2024 Q2 | During the reporting period, this activity was administratively closed, fully expended, all required closeout data was entered into DRGR and Activity Status changed to Completed.
INF_HMID_LMI_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2020-07-01 | 2020 Q4 | During the reporting period, the Jasper County completed environmental review for its street improvement project.
INF_HMID_LMI_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2021-01-01 | 2021 Q2 | During the reporting period, Jasper had construction underway for its Street Improvement Project.
INF_HMID_LMI_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2021-04-01 | 2021 Q3 | During the reporting period, the Jasper County had construction underway for its Street Improvement project.
INF_HMID_LMI_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2021-07-01 | 2021 Q4 | During the reporting period, Jasper County had construction underway for its street improvements project.
INF_HMID_LMI_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2021-10-01 | 2022 Q1 | During the reporting period, Jasper County completed construction and is pending submission of construction completion documentation for its street improvements project.
INF_HMID_LMI_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2022-01-01 | 2022 Q2 | During the reporting period, Jasper County completed construction and submitted the COCC for its street improvement project.
INF_HMID_LMI_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2022-07-01 | 2022 Q4 | During the reporting period, amendment was completed to process final payments. Costs reallocated to UN activity.
INF_HMID_LMI_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2022-10-01 | 2023 Q1 | During the reporting period, the County completed construction payment and submitted COCCs and As-Builts
INF_HMID_LMI_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-014-C053_Shepherd | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Shepherd | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-014-C053_Shepherd | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Shepherd | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Shepherd had construction procurement underway for its sewer facilities project.
INF_HMID_LMI_20-065-014-C053_Shepherd | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Shepherd | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Shepherd completed construction and submitted the COCC for its Sewer Facilities project.
INF_HMID_LMI_20-065-014-C053_Shepherd | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Shepherd | 2022-10-01 | 2023 Q1 | During the reporting period, administrative closeout was underway.
INF_HMID_LMI_20-065-014-C053_Shepherd | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Shepherd | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-017-C058_Anahuac | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Anahuac | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-017-C058_Anahuac | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Anahuac | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Anahuac completed engineering design for its sewer facilities project.
INF_HMID_LMI_20-065-017-C058_Anahuac | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Anahuac | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Anahuac had construction underway for its Sewer Rehabilitation project.
INF_HMID_LMI_20-065-017-C058_Anahuac | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Anahuac | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Anahuac had 50% of construction completed for its Sewer Facilities project and anticipates construction to be completed by May/June 2021.
INF_HMID_LMI_20-065-017-C058_Anahuac | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Anahuac | 2021-07-01 | 2021 Q4 | During the reporting?period,?the City of Anahuac had 50% of construction?complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-017-C058_Anahuac | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Anahuac | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Anahuac had grant closeout documents under review for its Sewer Facilities project.
INF_HMID_LMI_20-065-017-C058_Anahuac | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Anahuac | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Anahuac had its sewer facilities project administratively closed
INF_HMID_LMI_20-065-018-C064_PolkCounty | Street Improvements | Construction/reconstruction of streets | Polk County | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-018-C064_PolkCounty | Street Improvements | Construction/reconstruction of streets | Polk County | 2020-07-01 | 2020 Q4 | During the reporting period, Polk County completed Engineering design for its street improvements project.
INF_HMID_LMI_20-065-018-C064_PolkCounty | Street Improvements | Construction/reconstruction of streets | Polk County | 2020-10-01 | 2021 Q1 | During the reporting period, Polk County Had construction procurement underway for it&apos;s street improvements project.
INF_HMID_LMI_20-065-018-C064_PolkCounty | Street Improvements | Construction/reconstruction of streets | Polk County | 2021-01-01 | 2021 Q2 | During the reporting period, Polk County had construction underway for it&apos;s Street Improvements projects.
INF_HMID_LMI_20-065-018-C064_PolkCounty | Street Improvements | Construction/reconstruction of streets | Polk County | 2021-04-01 | 2021 Q3 | During the reporting period, Polk County had construction underway for its street improvements project.
INF_HMID_LMI_20-065-018-C064_PolkCounty | Street Improvements | Construction/reconstruction of streets | Polk County | 2022-10-01 | 2023 Q1 | During the reporting period, Polk County had construction underway for its street improvements project.
INF_HMID_LMI_20-065-018-C064_PolkCounty | Street Improvements | Construction/reconstruction of streets | Polk County | 2023-01-01 | 2023 Q2 | During the reporting period, Polk County completed construction and submitted the COCC for its street improvements project.
INF_HMID_LMI_20-065-018-C064_PolkCounty | Street Improvements | Construction/reconstruction of streets | Polk County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-018-C064_PolkCounty | Street Improvements | Construction/reconstruction of streets | Polk County | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-018-C064_PolkCounty | Street Improvements | Construction/reconstruction of streets | Polk County | 2025-10-01 | 2026 Q1 | During the reporting period, Polk County has grant closeout documents under review for its Street Improvement project.
INF_HMID_LMI_20-065-022-C079_EastBernard | Street Improvements | Construction/reconstruction of streets | East Bernard City Hall | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-022-C079_EastBernard | Street Improvements | Construction/reconstruction of streets | East Bernard City Hall | 2020-01-01 | 2020 Q2 | During the reporting period, the City of East Bernard had environmental review and engineering design underway for its street improvement project.
INF_HMID_LMI_20-065-022-C079_EastBernard | Street Improvements | Construction/reconstruction of streets | East Bernard City Hall | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-022-C079_EastBernard | Street Improvements | Construction/reconstruction of streets | East Bernard City Hall | 2020-07-01 | 2020 Q4 | During the reporting period, the City of East Bernard completed environmental review, completed engineering design and had construction procurement underway for its street improvements project.
INF_HMID_LMI_20-065-022-C079_EastBernard | Street Improvements | Construction/reconstruction of streets | East Bernard City Hall | 2020-10-01 | 2021 Q1 | During the reporting period, the City of East Bernard completed engineering design for its street improvement project.
INF_HMID_LMI_20-065-022-C079_EastBernard | Street Improvements | Construction/reconstruction of streets | East Bernard City Hall | 2021-04-01 | 2021 Q3 | During this reporting period, the City of East Bernard had construction underway for its street improvements project.
INF_HMID_LMI_20-065-022-C079_EastBernard | Street Improvements | Construction/reconstruction of streets | East Bernard City Hall | 2021-10-01 | 2022 Q1 | During the reporting period, the City of East Bernard submitted grant closeout documents for its street improvement project.
INF_HMID_LMI_20-065-022-C079_EastBernard | Street Improvements | Construction/reconstruction of streets | East Bernard City Hall | 2022-01-01 | 2022 Q2 | During the reporting period, the City of East Bernard had grant closeout documents under review for its street improvement project .
INF_HMID_LMI_20-065-022-C079_EastBernard | Street Improvements | Construction/reconstruction of streets | East Bernard City Hall | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-022-C079_EastBernard | Street Improvements | Construction/reconstruction of streets | East Bernard City Hall | 2022-10-01 | 2023 Q1 | This expenditure is associated with final closeout costs for approval of the grant completion report, however, this reimbursement was made in August 2022. During the reporting period, the City of East Bernard&apos;s contract was undergoing a pre-closeout administrative amendment to reconcile final performance measures, and budget, and no expenditures were reimbursed in Q4 2022.
INF_HMID_LMI_20-065-022-C079_EastBernard | Street Improvements | Construction/reconstruction of streets | East Bernard City Hall | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-022-C079_EastBernard | Street Improvements | Construction/reconstruction of streets | East Bernard City Hall | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-024-C083_Angleton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Angleton | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-024-C083_Angleton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Angleton | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Angleton completed environmental review for its sewer facilities project.
INF_HMID_LMI_20-065-024-C083_Angleton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Angleton | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-024-C083_Angleton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Angleton | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Angleton had construction underway for its Sewer Facilities.
INF_HMID_LMI_20-065-024-C083_Angleton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Angleton | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Angleton had construction underway for its Sewer Facilities
INF_HMID_LMI_20-065-024-C083_Angleton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Angleton | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Angleton had 50% of construction underway/complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-024-C083_Angleton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Angleton | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Angleton completed construction and submitted the COCC for its Sewer project.
INF_HMID_LMI_20-065-024-C083_Angleton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Angleton | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Angleton had grant closeout documents under review for its Sewer Facilities project.
INF_HMID_LMI_20-065-024-C083_Angleton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Angleton | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-024-C083_Angleton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Angleton | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-024-C083_Angleton | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Angleton | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-025-C086_Mathis | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Mathis, City of | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-025-C086_Mathis | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Mathis, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Mathis had environmental review and engineering design underway for its sewer facilities project.
INF_HMID_LMI_20-065-025-C086_Mathis | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Mathis, City of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-025-C086_Mathis | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Mathis, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Mathis had engineering design complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-025-C086_Mathis | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Mathis, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Mathis completed construction procurement for its sewer project.
INF_HMID_LMI_20-065-025-C086_Mathis | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Mathis, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Mathis completed environmental review and engineering design for its sewer facilities project.
INF_HMID_LMI_20-065-025-C086_Mathis | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Mathis, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Mathis had grant closeout documents under review for its Sewer Facilities project.
INF_HMID_LMI_20-065-025-C086_Mathis | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Mathis, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the city of Mathis has grant closeout documents submitted for its Sewer facilities project.
INF_HMID_LMI_20-065-025-C086_Mathis | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Mathis, City of | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-025-C086_Mathis | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Mathis, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-025-C086_Mathis | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Mathis, City of | 2023-07-01 | 2023 Q4 | Unused funds de-obligated.
INF_HMID_LMI_20-065-025-C086_Mathis | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Mathis, City of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-026-C093_SantaFe_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Santa Fe | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-026-C093_SantaFe_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Santa Fe | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Santa Fe had construction procurement underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-026-C093_SantaFe_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Santa Fe | 2021-04-01 | 2021 Q3 | During this reporting period, the City of Santa Fe had construction procurement underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-026-C093_SantaFe_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Santa Fe | 2021-07-01 | 2021 Q4 | During the reporting period, City of Santa Fe had construction procurement underway for its Flood and Drainage Facilities project. Negative balance for quarterly expenditure is a result of Clarification Form Adjustments.
INF_HMID_LMI_20-065-026-C093_SantaFe_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Santa Fe | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Santa Fe had 50% of construction complete for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-026-C093_SantaFe_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Santa Fe | 2022-01-01 | 2022 Q2 | '- During the reporting period, the City of Santa Fe had 50% of construction complete for its street improvement project.
INF_HMID_LMI_20-065-026-C093_SantaFe_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Santa Fe | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Santa Fe had 50% of construction completed for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-026-C093_SantaFe_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Santa Fe | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Santa Fe completed construction and is pending submission of construction completion documentation for Street Improvement project.
INF_HMID_LMI_20-065-026-C093_SantaFe_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Santa Fe | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Santa Fe had construction complete and the COCC underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-026-C093_SantaFe_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Santa Fe | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Santa Fe had grant closeout documents under review for its Street Improvements project.
INF_HMID_LMI_20-065-026-C093_SantaFe_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Santa Fe | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Santa Fe had its flood and drainage project administratively closed.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Santa Fe had environmental review and engineering design underway for its street improvement project.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Santa Fe had environmental review underway for its street improvement project.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Santa Fe had construction procurement underway for its street improvement project.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Santa Fe had construction procurement underway.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Santa Fe had construction underway for its Street Improvement project.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Santa Fe had 50% of construction complete for its Street Improvements project.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Santa Fe had 50% of construction complete for its street improvements project. Correction to payments out of incorrect DRGR activities.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Santa Fe had 70% of construction completed for its Street Improvements project.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2022-07-01 | 2022 Q4 | During the reporting period, Fayette County has grant closeout documents under review for its Water Facilities project.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Santa Fe had construction complete and the COCC underway for its street improvements project.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Santa Fe had grant closeout documents under review for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2023-04-01 | 2023 Q3 | Amendment reduced scope and de-obligated funds. Area Benefit type corrected.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-026-C093_SantaFe_SI | Street Improvements | Construction/reconstruction of streets | Santa Fe | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Santa Fe had its street improvements project administratively closed.
INF_HMID_LMI_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Nome completed engineering design for its street improvement project.
INF_HMID_LMI_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Nome had 50% of construction underway for its street improvement project.
INF_HMID_LMI_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Nome submitted grant closeout documents for its Street Improvement project.
INF_HMID_LMI_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Nome submitted grant closeout documents for its street improvement project. Review of prior DRGR Vouchers resulted in revisions that lowered the total amount draw for this DRGR Activity.
INF_HMID_LMI_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2024-07-01 | 2024 Q4 | Closeout underway: During the reporting period, the City of Nome had grant closeout documents approved for its street improvements project.
INF_HMID_LMI_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Nome had grant closeout documents approved for its street improvement project.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2020-01-01 | 2020 Q2 | During the reporting period, Fayette County had environmental review and engineering design underway for its water facilities improvement project.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2020-04-01 | 2020 Q3 | During the reporting period, Fayette County had environmental review and engineering design underway for its water facilities project.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Fayette County had construction procurement underway for its water facilities project.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Fayette County had construction underway for its water facilities project.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Fayette County completed construction for its water facilities project.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Fayette County had 50% of construction underway/complete for its water facilities project.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Fayette County completed construction and submitted the COCC for its water facilities project.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2022-04-01 | 2022 Q3 | During the reporting period, Fayette County has grant closeout documents submitted for its water facilities project.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2022-07-01 | 2022 Q4 | During the reporting period, Fayette County has submitted grant closeout documents for its water facilities project.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Fayette County had grant closeout documents under review for its water facilities project.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Fayette County is in the closeout process for its Water Facilities projects.
INF_HMID_LMI_20-065-028-C091_FayetteCounty | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Fayette, County of | 2023-07-01 | 2023 Q4 | Reduced funds expended to correct DRGR error due to parent/child grant rollup calculation.
INF_HMID_LMI_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Dickinson completed environmental review for its flood and drainage project.
INF_HMID_LMI_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Dickinson had construction procurement underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Dickinson had construction underway for it&apos;s Flood and Drainage project.
INF_HMID_LMI_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2021-04-01 | 2021 Q3 | During the reporting period, the city of Dickinson had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Dickinson had construction underway for its Flood and Drainage Facilities project. Review of prior DRGR Vouchers resulted in revisions that lowered the total amount draw for this DRGR Activity.
INF_HMID_LMI_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2022-01-01 | 2022 Q2 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
INF_HMID_LMI_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Dickinson had 70% of construction complete for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Dickinson had 75% of construction completed for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Dickinson had 75% of construction complete for its flood and drainage facilities project.
INF_HMID_LMI_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Dickinson completed construction and is pending submission of construction completion documentation for its flood and drainage project.
INF_HMID_LMI_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Columbus had environmental review and engineering design underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Columbus had construction underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Columbus had 70% of construction underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2021-04-01 | 2021 Q3 | During the reporting period, Columbus had construction underway for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Columbus completed construction for its original flood and drainage project.
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Columbus completed construction procurement for its Flood & Drainage project.
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Columbus completed construction procurement for its Flood Drainage project.
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Columbus had grant closeout documents under review for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Columbus had grant closeout documents under review for its F&D facilities project.
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2023-07-01 | 2023 Q4 | Activity completed.
INF_HMID_LMI_20-065-030-C097_Columbus | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Columbus, City of | 2024-10-01 | 2025 Q1 | During the reporting period, a review was performed and this activity was correctly recategorized as an HMID activity. MID Expenditures were entered to equal the current expenditures. Additionally, this activity is administratively closed.
INF_HMID_LMI_20-065-031-C101_Jasper | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jasper | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-031-C101_Jasper | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jasper | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Jasper completed environmental review for its flood and drainage improvements project.
INF_HMID_LMI_20-065-031-C101_Jasper | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jasper | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Dickinson had construction procurement underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-031-C101_Jasper | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jasper | 2021-01-01 | 2021 Q2 | During the reporting period, Jasper had environmental and engineering underway for its Flood and Drainage Facilities Improvement Project.
INF_HMID_LMI_20-065-031-C101_Jasper | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jasper | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Jasper had construction underway for its Street Improvement project.
INF_HMID_LMI_20-065-031-C101_Jasper | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jasper | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Jasper submitted grant closeout documents for its flood and drainage facilities project. Comments have been made on the closeout packet, awaiting SR update on documents.
INF_HMID_LMI_20-065-031-C101_Jasper | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jasper | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Jasper had its flood and drainage facilities project administratively closed
INF_HMID_LMI_20-065-031-C101_Jasper | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jasper | 2023-07-01 | 2023 Q4 | Activity completed.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Pinehurst completed environmental review and had engineering design underway for its sewer facilities project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Pinehurst had engineering design underway for its sewer facilities project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Pinehurst had preliminary engineering design underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Pinehurst had engineering design underway for its Sewer Facilities Wastewater Treatment Plant project. During the reporting period, the City of Pinehurst completed engineering design and bid advertisement for its Sewer Facilities Collection System project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Pinehurst had construction underway for its sewer facilities project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Pinehurst had construction underway for its sewer project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Pinehurst had construction underway for its sewer facilities project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Pinehurst had 100% construction complete + COCC for Sewer Facility Collection System and 57% construction complete for WWTP.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Pinehurst, construction of the WWTP (Sewer Facility) was 80% completed.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2022-10-01 | 2023 Q1 | During the reporting period, construction was completed and is pending submission of construction completion documentation and final retainage draw.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Pinehurst had construction complete for its Sewer Facility project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Pinehurst | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Pinehurst completed environmental review and had engineering design underway for its street improvement project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Pinehurst had engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Pinehurst had preliminary engineering design underway for its Street Improvements project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Pinehurst had engineering design underway for its Street Improvement project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Pinehurst had construction underway for its street improvements project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Pinehurst had construction underway for its street improvements project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Pinehurst had construction underway for its street improvement project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Pinehurst had 100% construction complete + COCC for Street Improvements project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Pinehurst had construction complete for its Street Improvements project.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-034-C113_Pinehurst_SI | Street Improvements | Construction/reconstruction of streets | Pinehurst | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Brookside had environmental review underway and engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Brookside Village completed environmental review for its street improvement.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Brookside Village had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Brookside Village had construction underway for its Street Improvements.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Brookside completed environmental review and engineering design for its street improvements project.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Brookside Village had 25% of construction underway/complete for its street improvement project.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Brookside had construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2022-10-01 | 2023 Q1 | During the reporting period, the City had 75% of construction underway/complete for its street facilities project.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2023-04-01 | 2023 Q3 | During the reporting period, the City is close to completing construction for its street facilities project.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Brookside had completed construction and is pending submission of construction completion documentation for its Street Improvements project.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Brookside an administrative No-Cost Time Extension to March 31st was initiated to ensure city had time to reconcile budget. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2024-04-01 | 2024 Q3 | Contract is in close out phase, pending review before releasing final retainage draw
INF_HMID_LMI_20-065-037-C118_Brookside | Street Improvements | Construction/reconstruction of streets | CITY OF BROOKSIDE VILLAGE | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Brookside Village had grant closeout documents approved for its street improvement project.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Brookshire had environmental review engineering design underway for its drainage project.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Brookshire completed environmental review for its flood and drainage project.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Brookshire had preliminary engineering design underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Brookshire had construction procurement underway for its flood and drainage project.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Brookshire had construction procurement underway for its flood and drainage facilities improvements project.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Brookshire had construction underway for its flood and drainage project.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Brookshire had 50% of construction underway/complete for its flood and drainage facilities project.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Brookshire had 95% of construction underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2023-04-01 | 2023 Q3 | Amendment reduced projected performance measures. Area Benefit type corrected.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Brookshire received final construction draw for the Rehabilitation/reconstruction of a public improvement.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2024-10-01 | 2025 Q1 | During the reporting period, a review was performed and this activity was correctly recategorized as an HMID activity
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2025-01-01 | 2025 Q2 | During the report period, the City of Brookshire had no expenditures and a previous payment was revised from the Street Improvements activity in this contract, and the budget was reconciled. Closeout is underway.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2025-04-01 | 2025 Q3 | During the reporting period, City of Brookshire submitted their final Project Delivery draw request.
INF_HMID_LMI_20-065-038-C119_Brookshire_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brookshire, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Brookshire submitted their final PD request for payment. Closeout is in the final closeout stages.
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Brookshire completed environmental review for its street improvements project.
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Brookshire had preliminary engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Brookshire had construction procurement underway for its street improvement project.
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Brookshire had construction procurement underway for its street improvements project.
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City if Brookshire had construction underway for its street improvements project.
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Brookshire had 50% of construction underway/complete for its street improvements project.
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Brookshire had 95% of construction underway for its street improvements project.
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2023-04-01 | 2023 Q3 | Amendment reduced projected performance measures. Area Benefit type corrected.
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Brookshire had no activity for the Construction/reconstruction of streets. Closeout underway.
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2024-10-01 | 2025 Q1 | During the reporting period, a review was performed and this activity was correctly recategorized as an HMID activity
INF_HMID_LMI_20-065-038-C119_Brookshire_SI | Street Improvements | Construction/reconstruction of streets | Brookshire, City of | 2025-01-01 | 2025 Q2 | During the report period, the City of Brookshire had no expenditures and a previous payment was revised to the Flood and Drainage activity in this contract, and the budget was reconciled. Closeout is underway.
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Groves completed environmental review for its street improvement project.
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Grove completed engineering design for its street improvement project.
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Grove had engineering design complete for its street improvement project.
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2021-07-01 | 2021 Q4 | During the reporting?period,?the City of Groves had 50% of construction?underway/complete for its street improvement project.
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Groves had 50% of construction underway/complete for its street improvement project.
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2022-01-01 | 2022 Q2 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Groves had 50% of construction underway/complete for its street improvement project.
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2024-10-01 | 2025 Q1 | 2024 Q4 During the reporting period, the City of Groves had construction complete and the COCC underway for its street improvement project.
INF_HMID_LMI_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Groves completed construction and submitted the COCC for its street improvements project.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Woodloch executed the contract for its sewer facilities project.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Woodloch had environmental review underway for its sewer facilities project.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Woodloch had environmental review and engineering design underway for its Sewer Facilities Project.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2021-07-01 | 2021 Q4 | During the reporting?period,?the City of Woodloch had construction procurement underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Woodloch had construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Woodloch had construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Woodloch had grant closeout documents under review for its Sewer Facilities project.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Woodloch had 50% of construction complete for its Sewer project. A 4 month extension is pending to end contract 10/31/2023.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Woodloch had its Sewer project administratively closed.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2024-04-01 | 2024 Q3 | During the reporting period, the Town of Woodloch submitted grant closeout documents for its sewer facilities project.
INF_HMID_LMI_20-065-040-C121_Woodloch | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Woodloch | 2025-01-01 | 2025 Q2 | During the reporting period, the Town of Woodloch submitted grant closeout documents for its sewer facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Hitchcok had environmental review and engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Hitchcock completed environmental review for its flood and drainage facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Hitchcock had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Hitchcock had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Hitchcock had construction underway for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Hitchcock had 50% of construction complete for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Hitchcock had 50% of construction complete for its flood and drainage facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Hitchcock had 75% of construction complete for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Hitchcock had 75% of construction complete for its flood and drainage facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Hitchcock had grant closeout documents under review for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Hitchcock had grant closeout documents under review for its flood and drainage project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2023-10-01 | 2024 Q1 | During the quarter, the activity was completed and had all accomplishment data entered into DRGR. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-042-C128_Hitchcock_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hitchcock | 2024-01-01 | 2024 Q2 | During the reporting period, this activity was administratively closed, fully expended, all required closeout data was entered into DRGR and Activity Status changed to Completed.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Hitchcock completed environmental review for its sewer facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Hitchcock had construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Hitchcock had construction underway for its Sewer project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Hitchcock had construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Hitchcock had 50% of construction complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Hitchcock had 50% of construction complete for its sewer facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Hitchcock had 75% of construction complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Hitchcock had 75% of construction complete for its sewer facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Hitchcock had grant closeout documents under review for its Sewer Facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Hitchock had grant closeout documents under review for its sewer facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Hitchcock had grant closeout documents under review for its sewer facilities project.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-042-C128_Hitchcock_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hitchcock | 2024-01-01 | 2024 Q2 | During the reporting period, this activity was administratively closed, fully expended, all required closeout data was entered into DRGR and Activity Status changed to Completed.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Liverpool had environmental review and engineering design underway for it&apos;s street improvements project.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Liverpool completed Environmental Review and Engineering design for street improvements.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2021-04-01 | 2021 Q3 | During the reporting period the City of Liverpool had construction underway for its Street Improvement project.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Liverpool had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Liverpool completed construction and submitted grant closeout documents for its Street Improvements project.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Liverpool had grant closeout documents under review for its Sewer Facilities project.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2022-07-01 | 2022 Q4 | During the reporting period, City of Liverpool submitted grant closeout documents for its Street Improvement project. Closeout review underway.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2022-10-01 | 2023 Q1 | During the reporting period, the City completed construction payment and submitted COCCs and As-Builts. GCR is underway.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2023-01-01 | 2023 Q2 | Amendment increased performance measure for projected linear feet. Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-043-C129_Liverpool | Street Improvements | Construction/reconstruction of streets | Liverpool, city of | 2024-04-01 | 2024 Q3 | Final retainage draw has been released, GLO working on close out
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2019-10-01 | 2020 Q1
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2020-04-01 | 2020 Q3 | During the reporting period, the Town of Holiday Lakes had environmental review and engineering design underway for it&apos;s flood and drainage project.
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Holiday Lakes completed environmental review for its drainage project.
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2021-01-01 | 2021 Q2 | During the reporting period, the Town of Holiday Lakes had engineering design complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2021-04-01 | 2021 Q3 | During the reporting period the Town of Holiday Lakes had construction procurement underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Holiday Lakes had 70% of construction underway/complete for its flood and drainage improvements project.
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2022-07-01 | 2022 Q4 | During the reporting period, City of Holiday Lakes submitted grant closeout documents for its Flood and Drainage project. Closeout review underway.
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2022-10-01 | 2023 Q1 | During the reporting period, the City completed construction payment and submitted COCCs and As-Builts. GCR is underway.
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-045-C131_HolidayLakes | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Holiday Lake, Town of | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Holiday Lakes expended the final payment for grant administration and the grant is moving into closeout.
INF_HMID_LMI_20-065-046-C138_Rosenberg | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Rosenberg | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-046-C138_Rosenberg | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Rosenberg | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Rosenberg had environmental review underway for its sewer facilities project.
INF_HMID_LMI_20-065-046-C138_Rosenberg | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Rosenberg | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-046-C138_Rosenberg | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Rosenberg | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Rosenberg had environmental review and engineering design underway for its Sewer Facilities.
INF_HMID_LMI_20-065-046-C138_Rosenberg | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Rosenberg | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Rosenberg had engineering design complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-046-C138_Rosenberg | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Rosenberg | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Rosenberg completed construction and is pending submission of construction completion documentation for its sewer facilities project.
INF_HMID_LMI_20-065-046-C138_Rosenberg | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Rosenberg | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Rosenberg completed construction and submitted the COCC for its sewer facilities project.
INF_HMID_LMI_20-065-046-C138_Rosenberg | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Rosenberg | 2022-07-01 | 2022 Q4 | During the reporting, the City of Rosenberg had grant closeout documents under review for its flood and drainage facilities.
INF_HMID_LMI_20-065-046-C138_Rosenberg | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Rosenberg | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-046-C138_Rosenberg | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Rosenberg | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2020-07-01 | 2020 Q4 | During the reporting period, Bay City had environmental review and engineering design underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Bay City had environmental complete for its flood and drainage project.
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Bay City completed engineering design for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Bay City had construction procurement underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Bay City completed construction procurement for its flood and drainage project
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Bay City completed construction procurement for its Flood & Drainage project.
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Bay City submitted grant closeout documents for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2024-01-01 | 2024 Q2 | During the reporting period, budget lines for environmental reviews were added to the activity.
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Bay City had grant closeout documents under review for its Flood and Drainage project.
INF_HMID_LMI_20-065-048-C142_BayCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bay City | 2024-10-01 | 2025 Q1 | During the reporting period, a review was performed and this activity was correctly recategorized as an HMID activity. MID Expenditures were entered to equal the current expenditures.
INF_HMID_LMI_20-065-049-C156_China | Street Improvements | Construction/reconstruction of streets | China | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-049-C156_China | Street Improvements | Construction/reconstruction of streets | China | 2020-10-01 | 2021 Q1 | During the reporting period, the City of China completed engineering design for its street improvement project.
INF_HMID_LMI_20-065-049-C156_China | Street Improvements | Construction/reconstruction of streets | China | 2021-04-01 | 2021 Q3 | During the reporting period, the City of China had construction underway for its Street Improvement project.
INF_HMID_LMI_20-065-049-C156_China | Street Improvements | Construction/reconstruction of streets | China | 2021-10-01 | 2022 Q1 | During the reporting period, the City of China submitted grant closeout documents for its street improvement project.
INF_HMID_LMI_20-065-049-C156_China | Street Improvements | Construction/reconstruction of streets | China | 2022-07-01 | 2022 Q4 | During the reporting period, the City of China had grant closeout documents under review for its street improvements project.
INF_HMID_LMI_20-065-050-C158_Freeport | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Freeport | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-050-C158_Freeport | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Freeport | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Freeport had environmental review and engineering design underway for Sewer Facilities.
INF_HMID_LMI_20-065-050-C158_Freeport | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Freeport | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Freeport had construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-050-C158_Freeport | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Freeport | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Freeport had grant closeout documents under review for its Sewer Facilities project.
INF_HMID_LMI_20-065-050-C158_Freeport | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Freeport | 2022-10-01 | 2023 Q1 | During the reporting period, the City completed construction payment and submitted COCCs and As-Builts. GCR is underway.
INF_HMID_LMI_20-065-050-C158_Freeport | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Freeport | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-050-C158_Freeport | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Freeport | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-050-C158_Freeport | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Freeport | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Freeport had its Sewer Facility project administratively closed.
INF_HMID_LMI_20-065-050-C158_Freeport | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Freeport | 2025-01-01 | 2025 Q2 | Activity budget and obligation reduced according to closeout documentation, this activity is fully completed and administratively closed with all accomplishments and beneficiaries reported.
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2021-01-01 | 2021 Q2 | During the reporting period, City of Fulton had design underway for its Flood and Drainage Project.
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Fulton had engineering design underway for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2022-01-01 | 2022 Q2 | During the reporting period, the Town of Fulton had construction procurement underway for its flood and drainage project .
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained performance Statement Changes, added a new activity, and end date extension.
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2022-07-01 | 2022 Q4 | During the reporting period, the Town of Fulton had construction procurement underway for its flood and drainage project.
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Fulton had construction underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Fulton had construction underway for its drainage facilities project.
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2023-04-01 | 2023 Q3 | During the reporting period, the Town of Fulton had construction underway for its flood and drainage facilities project
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2023-07-01 | 2023 Q4 | ?During the reporting?period,?the Town of Fulton had 50% of construction?underway/complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2023-10-01 | 2024 Q1 | During the reporting period, Town of Fulton completed construction and is pending submission of construction completion documentation for its Flood and Drainage project.
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2024-01-01 | 2024 Q2 | During the reporting period, the Town of Fulton completed construction and is pending submission of construction completion documentation for its Flood and Drainage projects.
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2024-04-01 | 2024 Q3 | During the reporting period, the Town of Fulton completed construction and is pending submission of construction completion documentation for its Flood and Drainage projects.
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2024-07-01 | 2024 Q4 | During the reporting period, the Town of Fulton had construction complete and the COCC underway for its Flood & Drainage project.
INF_HMID_LMI_20-065-054-C164_Fulton_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fulton | 2024-10-01 | 2025 Q1 | During this reporting period, the Town of Fulton completed construction and submitted the COCC -and- its grant closeout documents for its Flood and Drainage project.
INF_HMID_LMI_20-065-054-C164_Fulton_SI | Street Improvements | Construction/reconstruction of streets | Fulton | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained performance Statement Changes, added a new activity, and end date extension.
INF_HMID_LMI_20-065-054-C164_Fulton_SI | Street Improvements | Construction/reconstruction of streets | Fulton | 2022-07-01 | 2022 Q4 | During the reporting period, the Town of Fulton had construction procurement underway for its Street Improvements project.
INF_HMID_LMI_20-065-054-C164_Fulton_SI | Street Improvements | Construction/reconstruction of streets | Fulton | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Futon had construction underway for its street improvement project.
INF_HMID_LMI_20-065-054-C164_Fulton_SI | Street Improvements | Construction/reconstruction of streets | Fulton | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Fulton had construction underway for its drainage facilities project.
INF_HMID_LMI_20-065-054-C164_Fulton_SI | Street Improvements | Construction/reconstruction of streets | Fulton | 2023-07-01 | 2023 Q4 | ?During the reporting?period,?the Town of Fulton had 50% of construction?underway/complete for its Street Improvements projects.
INF_HMID_LMI_20-065-054-C164_Fulton_SI | Street Improvements | Construction/reconstruction of streets | Fulton | 2023-10-01 | 2024 Q1 | During the reporting period, Town of Fulton completed construction and is pending submission of construction completion documentation for its Street Improvement project.
INF_HMID_LMI_20-065-054-C164_Fulton_SI | Street Improvements | Construction/reconstruction of streets | Fulton | 2024-04-01 | 2024 Q3 | During the reporting period, the Town of Fulton completed construction and is pending submission of construction completion documentation for its Street Improvements projects.
INF_HMID_LMI_20-065-054-C164_Fulton_SI | Street Improvements | Construction/reconstruction of streets | Fulton | 2024-07-01 | 2024 Q4 | During the reporting period, the Town of Fulton had construction complete and the COCC underway for its Street Improvement project.
INF_HMID_LMI_20-065-054-C164_Fulton_SI | Street Improvements | Construction/reconstruction of streets | Fulton | 2024-10-01 | 2025 Q1 | During this reporting period, the Town of Fulton completed construction and submitted the COCC -and- its grant closeout documents for its Street Improvement project.
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Victoria had environmental review and engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Victoria had construction procurement underway for its flood and drainage project.
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Victoria had construction procurement underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2022-10-01 | 2023 Q1 | During the reporting period, Victoria County had construction underway for its water facilities project.
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Victoria had construction underway for its Flood and drainage project.
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Victoria had 50% of construction underway/complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Victoria had 50% construction complete for its flood and drainage project.
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Victoria has 75% f of construction completed for its Flood and Drainage project.
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Victoria had more than 75% of construction complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Victoria submitted grant closeout documents for its Flood and Drainage project
INF_HMID_LMI_20-065-055-C165_Victoria | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria, City of (INC) | 2026-01-01 | 2026 Q2
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2020-04-01 | 2020 Q3 | During the reporting period, the Town of Refugio had engineering design underway for its Flood and Drainage projects.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2020-10-01 | 2021 Q1 | During the reporting period, the Town of Refugio completed environmental review for its flood and drainage facilities improvements project.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2021-04-01 | 2021 Q3 | During the reporting period, Refugio County had environmental review underway for its flood and drainage project. County expects to receive AUGF mid July.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2021-07-01 | 2021 Q4 | During the reporting period, the Town of Refugio had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2021-10-01 | 2022 Q1 | During the reporting period, the Town of Refugio had construction underway for its flood and drainage project.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2022-01-01 | 2022 Q2 | During the reporting period, Town of Refugio had 50% of construction complete for its flood and drainage project.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Refugio had 70% of construction underway/complete for its flood and drainage improvements project.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Refugio had 50% of construction underway/complete for its flood and drainage project.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Refugio completed construction and is pending submission of construction completion documentation for its flood and drainage project
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and increased funds.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2023-04-01 | 2023 Q3 | During the reporting period, the Town of Refugio completed construction and is pending submission of construction completion documentation for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2023-07-01 | 2023 Q4 | ?During the reporting?period,?the Town of Refugio had 50% of construction?underway/complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Refugio had grant closeout documents under review for its Flood and Drainage projects.
INF_HMID_LMI_20-065-057-C169_Refugio_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio, Town of | 2024-07-01 | 2024 Q4 | Activity completed during quarter.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2020-04-01 | 2020 Q3 | During the reporting period, the Town of Refugio had engineering design underway for its sewer project.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2020-10-01 | 2021 Q1 | During the reporting period, the Town of Refugio completed environmental review for its sewer facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2021-04-01 | 2021 Q3 | During the reporting period, Refugio County had engineering design is 98% complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2021-07-01 | 2021 Q4 | During the reporting period, the Town of Refugio had construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2021-10-01 | 2022 Q1 | During the reporting period, the Town of Refugio had construction underway for its flood and drainage project.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2022-01-01 | 2022 Q2 | During the reporting period, Town of Refugio had 50% of construction complete for its sewer facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Refugio had 60% of construction underway/complete for its sewer facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Refugio had 50% of construction underway/complete for its sewer facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Refugio completed construction and is pending submission of construction completion documentation for its sewer facilities project
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and increased funds.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2023-04-01 | 2023 Q3 | During the reporting period, the Town of Refugio completed construction and is pending submission of construction completion documentation for its Sewer and Facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2023-07-01 | 2023 Q4 | ?During the reporting?period,?the Town of Refugio had 50% of construction?underway/complete for its Sewer Facilities projects.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Refugio had grant closeout documents under review for its Sewer Facilities projects.
INF_HMID_LMI_20-065-057-C169_Refugio_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2024-07-01 | 2024 Q4 | Activity completed during quarter.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2020-04-01 | 2020 Q3 | During the reporting period, the Town of Refugio had engineering design underway for its Street Improvement projects.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2020-10-01 | 2021 Q1 | During the reporting period, the Town of Refugio completed environmental review for its street improvements project.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2021-04-01 | 2021 Q3 | During the reporting period, Refugio County completed environmental review for its street improvements project.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2021-07-01 | 2021 Q4 | During the reporting period, the Town of Refugio had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2021-10-01 | 2022 Q1 | During the reporting period, the Town of Refugio had construction underway for its flood and drainage project.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2022-01-01 | 2022 Q2 | During the reporting period, Town of Refugio had 50% of construction complete for its street improvements project.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Refugio had 60% of construction underway/complete for its street improvements project.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Refugio had 50% of construction underway/complete for its street improvements project.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Refugio completed construction and is pending submission of construction completion documentation for its street improvements project
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and increased funds.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2023-04-01 | 2023 Q3 | During the reporting period, the Town of Refugio completed construction and is pending submission of construction completion documentation for its Street Improvements project.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2023-07-01 | 2023 Q4 | During the reporting period, the Town of Refugio had construction complete and the COCC underway for its Street Improvements projects.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Refugio had grant closeout documents under review for its Street Improvements projects.
INF_HMID_LMI_20-065-057-C169_Refugio_SI | Street Improvements | Construction/reconstruction of streets | Refugio, Town of | 2024-07-01 | 2024 Q4 | Activity completed during quarter.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2020-04-01 | 2020 Q3 | During the reporting period, the Town of Refugio had engineering design underway for its Water facilities projects.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2020-10-01 | 2021 Q1 | During the reporting period, the Town of Refugio completed environmental review for its water facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2021-04-01 | 2021 Q3 | During the reporting period, Refugio County had engineering design is 99% complete for its Water Facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2021-07-01 | 2021 Q4 | During the reporting period, the Town of Refugio had construction underway for its Water Facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2021-10-01 | 2022 Q1 | During the reporting period, the Town of Refugio had construction underway for its flood and drainage project.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2022-01-01 | 2022 Q2 | During the reporting period, Town of Refugio had 50% of construction complete for its water facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Refugio had 30% of construction underway/complete for its water facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Refugio completed construction and is pending submission of construction completion documentation for its water facilities project
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2023-04-01 | 2023 Q3 | During the reporting period, the Town of Refugio completed construction and is pending submission of construction completion documentation for its Water Facilities project.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2023-07-01 | 2023 Q4 | During the reporting period, the Town of Refugio had construction complete and the COCC underway for its Water Facility projects.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Refugio had grant closeout documents under review for its Water Facilities projects.
INF_HMID_LMI_20-065-057-C169_Refugio_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio, Town of | 2024-07-01 | 2024 Q4 | Activity completed during quarter.
INF_HMID_LMI_20-065-060-C175_Alvin_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Alvin, City of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-060-C175_Alvin_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Alvin, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Alvin completed engineering design for its Public Facilities.
INF_HMID_LMI_20-065-060-C175_Alvin_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Alvin, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Alvin completed environmental review and engineering design for its Public Facilities project.
INF_HMID_LMI_20-065-060-C175_Alvin_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Alvin, City of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-060-C175_Alvin_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Alvin, City of | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained performance statement changes and end date extension. This activity will be cancelled.
INF_HMID_LMI_20-065-060-C175_Alvin_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Alvin, City of | 2022-07-01 | 2022 Q4 | During the reporting period, City of Alvin had construction underway for its Public Facilities project. Closeout is underway and documentation is forthcoming, once received actual accomplishments will be updated.
INF_HMID_LMI_20-065-060-C175_Alvin_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Alvin, City of | 2023-04-01 | 2023 Q3 | Activity pending cancellation.
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Alvin had environmental review and engineering design underway for its sewer facilities project.
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Alvin had environmental review underway and engineering design underway for its sewer facilities project.
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Alvin completed engineering design for its Sewer Facilities.
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Alvin completed environmental review and engineering design for its Sewer Facilities project.
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Alvin had 70% of construction underway/complete for its flood and drainage improvements project.
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2022-07-01 | 2022 Q4 | During the reporting period, City of Alvin had construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the city of Alvin had 75% of construction underway/complete for its sewer facilities project.
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2023-01-01 | 2023 Q2 | Area benefit changed to Survey and measures updated.
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2023-07-01 | 2023 Q4 | During the reporting period, construction complete and the COCC underway.
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2023-10-01 | 2024 Q1 | During this reporting period, the City of Alvin submitted grant close out documents Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-060-C175_Alvin_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2024-04-01 | 2024 Q3 | Final retainage draw has been released, GLO working on close out, DRGR is working closely to ensure the beneficiaries are addressed correctly
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Alvin had environmental review and engineering design underway for it&apos;s water facilities project.
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Alvin completed engineering design for its Water Facilities.
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Alvin completed environmental review and engineering design for its Water Facilities project. Negative balance for quarterly expenditure is a result of Clarification Form Adjustments.
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Alvin had 70% of construction underway/complete for its flood and drainage improvements project.
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2022-07-01 | 2022 Q4 | During the reporting period, City of Alvin had construction underway for its Water Facilities project.
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the city of Alvin had 75% of construction underway/complete for its water facilities project.
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2023-01-01 | 2023 Q2 | Area benefit changed to Survey and measures updated.
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2023-07-01 | 2023 Q4 | During the reporting period, construction complete and the COCC underway.
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2023-10-01 | 2024 Q1 | During this reporting period, the City of Alvin submitted grant close out documents Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-060-C175_Alvin_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Alvin, City of | 2024-04-01 | 2024 Q3 | Final retainage draw has been released, GLO working on close out, DRGR is working closely to ensure the beneficiaries are addressed correctly
INF_HMID_LMI_20-065-061-C176_WestColumbia | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | West Columbia | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-061-C176_WestColumbia | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | West Columbia | 2020-07-01 | 2020 Q4 | During the reporting period, the City of West Columbia had environmental review underway and engineering design underway for its sewer facilities project.
INF_HMID_LMI_20-065-061-C176_WestColumbia | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | West Columbia | 2020-10-01 | 2021 Q1 | During this reporting period, the City of West Columbia completed environmental review for its Sewer Facilities.
INF_HMID_LMI_20-065-061-C176_WestColumbia | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | West Columbia | 2021-10-01 | 2022 Q1 | During the reporting period, West Columbia had construction underway for its sewer facilities project.
INF_HMID_LMI_20-065-061-C176_WestColumbia | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | West Columbia | 2022-01-01 | 2022 Q2 | During the reporting period, the City of West Columbia completed construction and submitted the COCC for its sewer facilities project.
INF_HMID_LMI_20-065-061-C176_WestColumbia | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | West Columbia | 2022-04-01 | 2022 Q3 | During the reporting period, the City of West Columbia had grant closeout documents under review for its Sewer Facilities project.
INF_HMID_LMI_20-065-061-C176_WestColumbia | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | West Columbia | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2020-07-01 | 2020 Q4 | During the reporting period, Waller County had environmental review underway for its street improvement project.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2020-10-01 | 2021 Q1 | During the reporting period, Waller County had engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2021-01-01 | 2021 Q2 | During the reporting period, Waller County had preliminary engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2021-07-01 | 2021 Q4 | During the reporting period, Waller County had construction procurement and acquisition underway for its street improvements project.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2021-10-01 | 2022 Q1 | During the reporting period, Waller County had construction underway for its street improvements project.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2022-04-01 | 2022 Q3 | During the reporting period, Waller County had construction underway/complete for its street improvements project.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2022-07-01 | 2022 Q4 | During the reporting period, Waller County had engineering design and acquisition underway for its Street Improvements project.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2023-01-01 | 2023 Q2 | During the reporting period, Waller County had construction complete for one of its street improvements projects.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2023-10-01 | 2024 Q1 | During the reporting period, Waller County is currently a Harvey Reallocation Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2024-04-01 | 2024 Q3 | During the reporting period, Waller County has reconciled their budget information to include reallocation amount. The county has completed construction activities on Laneview project, and has begun activities on the Diemer project.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2024-07-01 | 2024 Q4 | During the reporting?period,?Waller County had 50% of construction?underway for its Deimer Rd. Street Improvement project.?
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2025-04-01 | 2025 Q3 | During the reporting period, Waller County had 95% of construction complete for its Street Improvements project.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2025-07-01 | 2025 Q4 | During the reporting period, Waller County completed construction and submitted the COCC for its Street Improvements project.
INF_HMID_LMI_20-065-062-C180_WallerCounty | Street Improvements | Construction/reconstruction of streets | Waller County | 2025-10-01 | 2026 Q1 | During the reporting period, Waller County submitted a refund and had grant closeout documents under review for its street improvements project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2020-07-01 | 2020 Q4 | During the reporting period, Calhoun County had environmental review underway and engineering design underway for it&apos;s flood and drainage project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2020-10-01 | 2021 Q1 | During this reporting period, Calhoun County had environmental review and engineering design underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2021-07-01 | 2021 Q4 | During the reporting period, Calhoun County had preliminary engineering design for its one of the flood and drainage projects.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2021-10-01 | 2022 Q1 | During the reporting period, Calhoun County had construction procurement underway for its Flood and Drainage project. Review of prior DRGR Vouchers resulted in revisions that lowered the total amount draw for this DRGR Activity.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2023-01-01 | 2023 Q2 | During the reporting period Calhoun County had construction complete its Flood and Drainage project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2023-04-01 | 2023 Q3 | During the reporting period, Calhoun County had 50% of construction complete for one of its Flood and Drainage projects (Alamo Drainage Project).
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2023-07-01 | 2023 Q4 | During the reporting period, Calhoun County had 50% of construction completed for its flood and drainage project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2023-10-01 | 2024 Q1 | During the reporting period, Calhoun County had 50% of construction completed for its flood and drainage project Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2024-01-01 | 2024 Q2 | During the reporting period, a contract amendment was executed that increased the amount of funding for the subrecipient and reallocated some of the funding amongst the activities of the contract.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2024-07-01 | 2024 Q4 | ?During the reporting?period,?the County had preliminary?engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2025-10-01 | 2026 Q1 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2026-01-01 | 2026 Q2
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2020-07-01 | 2020 Q4 | During the reporting period, Calhoun County had environmental review underway and engineering design underway for it&apos;s public facilities project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2020-10-01 | 2021 Q1 | During this reporting period, Calhoun County had environmental review and engineering design underway for its Public Facilities project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2021-07-01 | 2021 Q4 | During the reporting period, Calhoun County had preliminary engineering design for its one of the public facilities projects, and had construction procurement underway for another one of the public facilities projects.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2021-10-01 | 2022 Q1 | During the reporting period, Calhoun County had construction procurement underway for its Public Facilities project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2022-01-01 | 2022 Q2 | During the reporting period, Calhoun County had construction underway for its Public Facilities project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2022-04-01 | 2022 Q3 | During the reporting period, the County of Calhoun had construction procurement underway for is Public Facilities projects.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2022-07-01 | 2022 Q4 | During the reporting period, the County of Calhoun had construction underway for its Public Facilities project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2022-10-01 | 2023 Q1 | During the reporting period, Calhoun County had construction underway for its Public Facilities projects.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2023-01-01 | 2023 Q2 | During the reporting period Calhoun County had construction complete its Public Facilities project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2023-04-01 | 2023 Q3 | During the reporting period, the Calhoun County completed construction and submitted the COCC for one of its Public Facilities projects (Little Chocolate Bay Park Project).
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2023-07-01 | 2023 Q4 | During the reporting period, Calhoun County completed construction and submitted the COCC for its public facilities project.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2024-01-01 | 2024 Q2 | During the reporting period, a contract amendment was executed that increased the amount of funding for the subrecipient and reallocated some of the funding amongst the activities of the contract.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2025-04-01 | 2025 Q3 | During the reporting period, one bid complete and NTP was issued for one project, construction to begin.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2025-07-01 | 2025 Q4 | ?During the reporting?period, Calhoun County had 50% of construction?complete for its Public Facilities project. (i.e. Sewer facilities improvements,?etc.).?
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2025-10-01 | 2026 Q1 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
INF_HMID_LMI_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2026-01-01 | 2026 Q2
INF_HMID_LMI_20-065-066-C192_Robstown | Public Facilities | Rehabilitation/reconstruction of public facilities | Robstown, City of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-066-C192_Robstown | Public Facilities | Rehabilitation/reconstruction of public facilities | Robstown, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-066-C192_Robstown | Public Facilities | Rehabilitation/reconstruction of public facilities | Robstown, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the Town of Robstown had construction complete and the COCC underway for its Generator projects.
INF_HMID_LMI_20-065-066-C192_Robstown | Public Facilities | Rehabilitation/reconstruction of public facilities | Robstown, City of | 2023-10-01 | 2024 Q1 | During this reporting period, the City of Robstown submitted grant close out documents
INF_HMID_LMI_20-065-068-C194_Bayside | Street Improvements | Construction/reconstruction of streets | Bayside | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-068-C194_Bayside | Street Improvements | Construction/reconstruction of streets | Bayside | 2020-04-01 | 2020 Q3 | During the reporting period, the Town of Bayside had engineering design underway for its Street Improvement projects.
INF_HMID_LMI_20-065-068-C194_Bayside | Street Improvements | Construction/reconstruction of streets | Bayside | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Bayside completed engineering design for its street improvements project.
INF_HMID_LMI_20-065-068-C194_Bayside | Street Improvements | Construction/reconstruction of streets | Bayside | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Bayside had construction underway for its street improvements project.
INF_HMID_LMI_20-065-068-C194_Bayside | Street Improvements | Construction/reconstruction of streets | Bayside | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Bayside had construction complete for its street improvements project.
INF_HMID_LMI_20-065-068-C194_Bayside | Street Improvements | Construction/reconstruction of streets | Bayside | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Bayside has undergone environmental re-evaluation for amendment No 1 request to use remaining grant funds. Current grant scope has been completed and closeout documentation has been submitted.
INF_HMID_LMI_20-065-068-C194_Bayside | Street Improvements | Construction/reconstruction of streets | Bayside | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Bayside completed construction and is pending submission of construction completion documentation for its street improvements project.
INF_HMID_LMI_20-065-068-C194_Bayside | Street Improvements | Construction/reconstruction of streets | Bayside | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Bayside submitted grant closeout documents for its street improvements project.
INF_HMID_LMI_20-065-068-C194_Bayside | Street Improvements | Construction/reconstruction of streets | Bayside | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Bayside had grant closeout documents under review for its street improvements project
INF_HMID_LMI_20-065-068-C194_Bayside | Street Improvements | Construction/reconstruction of streets | Bayside | 2023-01-01 | 2023 Q2 | Activity created during quarter.
INF_HMID_LMI_20-065-068-C194_Bayside | Street Improvements | Construction/reconstruction of streets | Bayside | 2023-04-01 | 2023 Q3 | Per HUD recommendation, Expenditure amount adjusted to match Drawn amount due to DRGR system errors.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Lumberton had engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Lumberton completed engineering design for its flood and drainage facilities project.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Lumberton had engineering design complete for its flood and drainage project.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Lumberton had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Lumberton had construction underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Lumberton submitted grant closeout documents for its flood and drainage facility project.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Lumberton had construction activities underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Lumberton had construction activities underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Lumberton has completed construction is awaiting a budget change request to finalize closeout for its flood and drainage facilities project.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Lumberton completed construction and is awaiting a budget change request to complete grant closeout paperwork.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2023-01-01 | 2023 Q2 | Amendment moved funds from related activity.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Lumberton completed construction and is in the closeout process.
INF_HMID_LMI_20-065-069-C195_Lumberton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Lumberton | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Woodsboro had engineering design underway for its Street Improvement projects.
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Woodsboro had environmental underway for its street improvements project.
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Woodsboro had construction underway for its street improvements project.
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the Town of Woodsboro had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Woodsboro had 60% of construction underway/complete for its street improvements project
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2022-01-01 | 2022 Q2 | During the reporting period, City of Woodsboro had 90% of construction complete for its street improvements project.
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Woodsboro had 90% of construction underway/complete for its street improvements project.
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Woodsboro completed construction and is pending submission of construction completion documentation for its street improvements project.
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Woodsboro submitted grant closeout documents for its street improvements project.
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Woodsboro had its street improvements project administratively closed.
INF_HMID_LMI_20-065-070-C196_Woodsboro | Street Improvements | Construction/reconstruction of streets | Woodsboro, City of | 2023-07-01 | 2023 Q4 | Reduced funds expended to correct DRGR error due to parent/child grant rollup calculation.
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Port Lavaca had environmental review engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Port Lavaca had preliminary engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2021-04-01 | 2021 Q3 | During the reporting period, Port Lavaca had construction underway for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2021-07-01 | 2021 Q4 | Activity was adjusted from State MID to HUD MID, due to a misclassification of the MID designation. MID expenditures are updated to match expenditures to date.
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2021-10-01 | 2022 Q1 | During the reporting period Port Lavaca had construction underway for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Port Lavaca had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Port Lavaca had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2022-10-01 | 2023 Q1 | During the reporting period the City of Port Lavaca had construction underway for its Flood and Drainage project
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Port Lavaca had 50% of construction complete for its Flood and Drainage project. Contract Amendment to add additional local funding due to increased construction costs was approved during the reporting period.
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Port Lavaca had one project completed submitted for Relocation Assistance activity. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Port Lavaca completed construction has not sent in COCC docs
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2024-07-01 | 2024 Q4 | During the reporting period, corrections to admin fields in DRGR were made. No actual change during the quarter and this activity is still ongoing.
INF_HMID_LMI_20-065-071-C198_PortLavaca_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Port Lavaca | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Port Lavaca had grant closeout documents under review for its Flood and Drainage project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Port Lavaca had environmental review engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Port Lavaca had preliminary engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2021-04-01 | 2021 Q3 | During the reporting period, Port Lavaca had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2021-07-01 | 2021 Q4 | Activity was adjusted from State MID to HUD MID, due to a misclassification of the MID designation. MID expenditures are updated to match expenditures to date.
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2021-10-01 | 2022 Q1 | During the reporting period Port Lavaca had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Port Lavaca had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Port Lavaca had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2022-10-01 | 2023 Q1 | During the reporting period the City of Port Lavaca had construction underway for its Street Improvements project
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Port Lavaca had 50% of construction complete for its Street Improvements project. Contract Amendment to add additional local funding due to increased construction costs was approved during the reporting period.
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Port Lavaca had one project completed submitted for Relocation Assistance activity. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Port Lavaca completed construction has not sent in COCC docs
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2024-07-01 | 2024 Q4 | During the reporting period, corrections to admin fields in DRGR were made. No actual change during the quarter and this activity is still ongoing.
INF_HMID_LMI_20-065-071-C198_PortLavaca_SI | Street Improvements | Construction/reconstruction of streets | Port Lavaca | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Port Lavaca had grant closeout documents under review for its Street Improvement project.
INF_HMID_LMI_20-065-072-C199_VillageofJonesCreek | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jones Creek, Village of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-072-C199_VillageofJonesCreek | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jones Creek, Village of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Jones Creek Village had environmental review underway and engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-072-C199_VillageofJonesCreek | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jones Creek, Village of | 2020-10-01 | 2021 Q1 | During this reporting period, the City of Jones Creek had environmental review and engineering design underway for its Flood and Drainage Facilities.
INF_HMID_LMI_20-065-072-C199_VillageofJonesCreek | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jones Creek, Village of | 2021-04-01 | 2021 Q3 | During the reporting period, the Village of Jones Creek had construction procurement underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-072-C199_VillageofJonesCreek | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jones Creek, Village of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Jones Creek completed construction and submitted the COCC for its flood and drainage facilities project.
INF_HMID_LMI_20-065-072-C199_VillageofJonesCreek | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jones Creek, Village of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Jones Creek had grant closeout documents under review for its Sewer Facilities project.
INF_HMID_LMI_20-065-072-C199_VillageofJonesCreek | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jones Creek, Village of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-072-C199_VillageofJonesCreek | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jones Creek, Village of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-072-C199_VillageofJonesCreek | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jones Creek, Village of | 2025-07-01 | 2025 Q4 | During the reporting period, the Villages of Jones Creek had their GCR approved.
INF_HMID_LMI_20-065-073-C200_Kirbyville | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-073-C200_Kirbyville | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Kirbyville had engineering design underway for its sewer improvements project.
INF_HMID_LMI_20-065-073-C200_Kirbyville | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Kirbyville had environmental review underway for its sewer facilities project.
INF_HMID_LMI_20-065-073-C200_Kirbyville | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2021-01-01 | 2021 Q2 | During the reporting period, Kirbyville had advertising and bidding underway for its Sewer Facilities Improvement Project.
INF_HMID_LMI_20-065-073-C200_Kirbyville | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Kirbyville had construction procurement underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-073-C200_Kirbyville | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2021-07-01 | 2021 Q4 | During the reporting period, accepted applications for eligibility review for its infrastructure program.
INF_HMID_LMI_20-065-073-C200_Kirbyville | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Kirbyville submitted grant closeout documents for its sewer facilities project.
INF_HMID_LMI_20-065-073-C200_Kirbyville | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-073-C200_Kirbyville | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Kirbyville had grant closeout documents under review for its sewer facilities project
INF_HMID_LMI_20-065-073-C200_Kirbyville | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kirbyville | 2023-07-01 | 2023 Q4 | Activity completed.
INF_HMID_LMI_20-065-077-C219_MissouriCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Missouri City | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-077-C219_MissouriCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Missouri City | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Missouri City submitted grant closeout documents for its flood and drainage project.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2020-10-01 | 2021 Q1 | During the reporting period, San Patricio County had environmental review underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2021-01-01 | 2021 Q2 | During the reporting period, San Patricio County had preliminary engineering design underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2021-04-01 | 2021 Q3 | During the reporting period, San Patricio County completed construction procurement for its flood and drainage project.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2021-10-01 | 2022 Q1 | During the reporting period, San Patricio County completed engineering design for its Flood and Drainage project.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2022-04-01 | 2022 Q3 | During the reporting period, San Patricio County had 50% of construction underway/complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2022-07-01 | 2022 Q4 | During the reporting period, the County of San Patricio had 50% of construction underway/complete for its flood and drainage project.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2022-10-01 | 2023 Q1 | During the reporting period, San Patricio County had 50% of construction underway for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2023-04-01 | 2023 Q3 | During the reporting?period,?San Patricio County had 90% of construction?underway/complete for its flood and drainage facility project.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2023-07-01 | 2023 Q4 | During the Reporting Period, San Patricio County had 90% of construction Complete for its flood and drainage facility project.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2023-10-01 | 2024 Q1 | During the reporting period, San Patricio County has 100% of construction completed for its Flood and Drainage project.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2024-01-01 | 2024 Q2 | During the reporting period, San Patricio County has 100% of construction completed for its Flood and Drainage project.
INF_HMID_LMI_20-065-078-C221_SanPatricioCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | County of, San Patricio | 2025-10-01 | 2026 Q1 | During the reporting period, San Patricio County had grant closeout documents under review for its Flood and drainage project
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Richwood had environmental review and engineering design underway for it&apos;s sewer facillities project.
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Richwood completed environmental review and engineering design for Sewer Facilities.
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Richwood had engineering design complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2021-04-01 | 2021 Q3 | During the report period, the City of Richwood had construction procurement underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Richwood completed engineering design for its sewer facilities project.
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Richwood had grant closeout documents under review for its Sewer Facilities project.
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2022-10-01 | 2023 Q1 | During the reporting period, City of Richwood completed construction and is pending submission of construction completion documentation for its Sewer Facilities project.
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Richwood had close out underway.
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-080-C233_Richwood | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Richwood, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Richwood had grant closeout documents complete review. The final RFP was paid.
INF_HMID_LMI_20-065-081-C234_Wharton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-081-C234_Wharton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Wharton had environmental review and engineering design underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-081-C234_Wharton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Wharton had environmental review, acquisition and engineering design underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-081-C234_Wharton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-081-C234_Wharton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton | 2021-07-01 | 2021 Q4 | During the reporting?period,?the City of Wharton had preliminary?engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-081-C234_Wharton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Wharton had engineering design underway for its flood and drainage project
INF_HMID_LMI_20-065-081-C234_Wharton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Wharton had preliminary engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-082-C235_PattonVillage | Street Improvements | Construction/reconstruction of streets | Patton Village, City of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-082-C235_PattonVillage | Street Improvements | Construction/reconstruction of streets | Patton Village, City of | 2020-10-01 | 2021 Q1 | During the reporting period, City of Patton Village had environmental review underway for its street improvement project.
INF_HMID_LMI_20-065-082-C235_PattonVillage | Street Improvements | Construction/reconstruction of streets | Patton Village, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Patton Village had environmental review completed and the AUGF approved on 5/18/2021 for its Street Improvement project.
INF_HMID_LMI_20-065-082-C235_PattonVillage | Street Improvements | Construction/reconstruction of streets | Patton Village, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Patton Village had construction procurement underway for its street improvements project.
INF_HMID_LMI_20-065-082-C235_PattonVillage | Street Improvements | Construction/reconstruction of streets | Patton Village, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Patton Village had construction procurement underway for its Street Improvements project.
INF_HMID_LMI_20-065-082-C235_PattonVillage | Street Improvements | Construction/reconstruction of streets | Patton Village, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Patton Village had 50% of construction underway/complete for its Streets Improvement project.
INF_HMID_LMI_20-065-082-C235_PattonVillage | Street Improvements | Construction/reconstruction of streets | Patton Village, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Patton Village had 50% of construction underway/complete for its Street Improvements project.
INF_HMID_LMI_20-065-082-C235_PattonVillage | Street Improvements | Construction/reconstruction of streets | Patton Village, City of | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-082-C235_PattonVillage | Street Improvements | Construction/reconstruction of streets | Patton Village, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Patton Village had grant closeout documents under review for its Street Improvement project. The Closeout is on hold awaiting submission of their Single Audit (overdue)
INF_HMID_LMI_20-065-082-C235_PattonVillage | Street Improvements | Construction/reconstruction of streets | Patton Village, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Patton Village had grant closeout documents under review for its project
INF_HMID_LMI_20-065-082-C235_PattonVillage | Street Improvements | Construction/reconstruction of streets | Patton Village, City of | 2024-01-01 | 2024 Q2 | During the reporting period, this activity was administratively closed, fully expended, all required closeout data was entered into DRGR and Activity Status changed to Completed.
INF_HMID_LMI_20-065-083-C236_TexasCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Texas City | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-083-C236_TexasCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Texas City | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Texas City completed environmental review for its flood and drainage project.
INF_HMID_LMI_20-065-083-C236_TexasCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Texas City | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Texas City had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-083-C236_TexasCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Texas City | 2021-07-01 | 2021 Q4 | During the reporting period, the City Texas City had 50% of construction underway for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-083-C236_TexasCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Texas City | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Texas City had 50% of construction complete for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-083-C236_TexasCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Texas City | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Texas City completed construction and is pending submission of construction completion documentation.
INF_HMID_LMI_20-065-083-C236_TexasCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Texas City | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Texas City had grant closeout documents under review for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-083-C236_TexasCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Texas City | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Texas submitted grant closeout documents for its flood and drainage facilities project.
INF_HMID_LMI_20-065-083-C236_TexasCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Texas City | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-083-C236_TexasCity | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Texas City | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Port Neches had engineering design underway for its water facility project.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Port Neches completed engineering design for its water facilities project.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Port Neches had engineering design complete for its water facilities project.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Port Neches had construction procurement underway for its Water Facilities project.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Port Neches submitted grant closeout documents for its water facility project.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Port Neches had 50% of construction underway/complete for its water facilities project.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Port Neches had 50% of construction underway/complete for its water facilities project.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Port Neches completed construction and submitted the Certificate of Construction Completion for its water facilities project.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Port Neches completed construction and is pending submission of construction completion documentation for its water facilities project
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Port Neches completed construction and submitted the COCC for its water facilities project.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Port Neches completed construction and is pending submission of construction completion documentation for its water facility project.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2023-07-01 | 2023 Q4 | Amendment reallocated unspent funds to related activity.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-084-C243_PortNeches_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Port Neches submitted grant closeout documents for its water facilities project.
INF_HMID_LMI_20-065-086-C247_Ingleside | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Ingleside | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-086-C247_Ingleside | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Ingleside | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Ingleside had engineering design underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-086-C247_Ingleside | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Ingleside | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Ingleside had preliminary engineering design underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-086-C247_Ingleside | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Ingleside | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Ingleside had environmental review underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-086-C247_Ingleside | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Ingleside | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-086-C247_Ingleside | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Ingleside | 2023-04-01 | 2023 Q3 | Amendment increased projected performance measures. Area Benefit type corrected.
INF_HMID_LMI_20-065-086-C247_Ingleside | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Ingleside | 2023-07-01 | 2023 Q4 | During the Reporting Period, City of Ingleside had 25% of construction Complete for its current flood and drainage facility project.
INF_HMID_LMI_20-065-086-C247_Ingleside | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Ingleside | 2023-10-01 | 2024 Q1 | During the reporting period, City of Ingleside had 75% of construction completed for its Street Improvement project
INF_HMID_LMI_20-065-086-C247_Ingleside | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Ingleside | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Ingleside completed construction and is pending submission of construction completion documentation for its flood and drainage facilities project.
INF_HMID_LMI_20-065-086-C247_Ingleside | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Ingleside | 2024-07-01 | 2024 Q4 | During the reporting period, this contract is working through the closeout phase.
INF_HMID_LMI_20-065-087-C248_TylerCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-087-C248_TylerCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2020-10-01 | 2021 Q1 | During the reporting period, Tyler county had construction procurement underway for it&apos;s sewer facilities project.
INF_HMID_LMI_20-065-087-C248_TylerCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2021-01-01 | 2021 Q2 | During the reporting period, Tyler County had construction underway for it&apos;s Sewer Facilities project.
INF_HMID_LMI_20-065-087-C248_TylerCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2021-07-01 | 2021 Q4 | During the reporting period, Tyler County completed construction on its Sewer Facility project.
INF_HMID_LMI_20-065-087-C248_TylerCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2021-10-01 | 2022 Q1 | During the reporting period, Tyler County had construction complete and closeout documents underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-087-C248_TylerCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2022-04-01 | 2022 Q3 | During the reporting period, Tyler County billed for completion of Construction NTP milestone for GA only for it&apos;s SI project. Construction was completed and COCC submitted in 6/2021.
INF_HMID_LMI_20-065-087-C248_TylerCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-087-C248_TylerCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-087-C248_TylerCounty_SI | Street Improvements | Construction/reconstruction of streets | Tyler County | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-087-C248_TylerCounty_SI | Street Improvements | Construction/reconstruction of streets | Tyler County | 2020-10-01 | 2021 Q1 | During the reporting period, Tyler County completed it&apos;s street improvements project.
INF_HMID_LMI_20-065-087-C248_TylerCounty_SI | Street Improvements | Construction/reconstruction of streets | Tyler County | 2021-10-01 | 2022 Q1 | During the reporting period, Tyler County had construction complete and closeout documents underway for its Street Improvements project.
INF_HMID_LMI_20-065-087-C248_TylerCounty_SI | Street Improvements | Construction/reconstruction of streets | Tyler County | 2022-04-01 | 2022 Q3 | During the reporting period, Tyler County billed for completion of Construction NTP milestone for GA only for it&apos;s SI project. Construction was completed and COCC submitted in 9/2020.
INF_HMID_LMI_20-065-087-C248_TylerCounty_SI | Street Improvements | Construction/reconstruction of streets | Tyler County | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-087-C248_TylerCounty_SI | Street Improvements | Construction/reconstruction of streets | Tyler County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2020-07-01 | 2020 Q4 | During the reporting period, Tyler County had construction underway for its streets projects.
INF_HMID_LMI_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2020-10-01 | 2021 Q1 | During the reporting period, Tyler County had construction procurement underway for it&apos;s water facilities project.
INF_HMID_LMI_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2021-01-01 | 2021 Q2 | During the reporting period, Tyler County had construction underway for it&apos;s water facilities project.
INF_HMID_LMI_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2021-04-01 | 2021 Q3 | During the reporting period, Tyler County had construction underway for its water facilities improvement project.
INF_HMID_LMI_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2021-07-01 | 2021 Q4 | During the reporting period, Tyler County completed construction on its Water Facility project.
INF_HMID_LMI_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2021-10-01 | 2022 Q1 | During the reporting period, Tyler County had construction underway more than 50% complete for its Water Facilities Project. Review of prior DRGR Vouchers resulted in revisions that lowered the total amount draw for this DRGR Activity.
INF_HMID_LMI_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2022-04-01 | 2022 Q3 | During the reporting period, Tyler County billed for completion of Construction NTP milestone for GA only for it&apos;s WF project. Construction was completed and COCC submitted in 2/2022.
INF_HMID_LMI_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_LMI_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2023-04-01 | 2023 Q3 | During the reporting period, Tyler County had closeout preparation activities underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2023-10-01 | 2024 Q1 | During the reporting period Tyler County completed construction activities on its Water Facilities project. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-088-C249_SourLake_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Sour Lake | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-088-C249_SourLake_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Sour Lake | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Sour Lake had environmental review underway for its sewer facilities project.
INF_HMID_LMI_20-065-088-C249_SourLake_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Sour Lake | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Sour Lake had engineering design complete for its Sewer facilities project.
INF_HMID_LMI_20-065-088-C249_SourLake_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Sour Lake | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Sour Lake had environmental review underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-088-C249_SourLake_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Sour Lake | 2021-07-01 | 2021 Q4 | During the reporting period, the City Sour Lake had construction underway for its sewer facilities project. Negative balance for quarterly expenditure is a result of Clarification Form Adjustments.
INF_HMID_LMI_20-065-088-C249_SourLake_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Sour Lake | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Sour Lake had acquisition underway for its sewer facility project.
INF_HMID_LMI_20-065-088-C249_SourLake_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Sour Lake | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Sour Lake had construction activities underway for its sewer facilities project.
INF_HMID_LMI_20-065-088-C249_SourLake_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Sour Lake | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Sour Lake had construction activities underway for its sewer facilities project.
INF_HMID_LMI_20-065-088-C249_SourLake_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Sour Lake | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Sour Lake had construction underway for its Sewer Facilities project. Final work on the project is currently in progress.
INF_HMID_LMI_20-065-088-C249_SourLake_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Sour Lake | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Sour Lake completed construction and is in the process of completing closeout documentation to submit for its sewer facilities project.
INF_HMID_LMI_20-065-088-C249_SourLake_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Sour Lake | 2023-04-01 | 2023 Q3 | During the reporting period, Tyler County had closeout preparation activities underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-088-C249_SourLake_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Sour Lake | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Sour Lake had grant closeout documents under review Sewer Line project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Rockport had engineering design underway for its Flood and Drainage projects.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Rockport had engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Rockport had engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Rockport had engineering design underway for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Rockport had construction procurement underway for its Flood and Drainage project. Negative balance for quarterly expenditure is a result of Clarification Form Adjustments.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Rockport had construction underway for its Flood and Drainage Project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Rockport had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Rockport had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2022-07-01 | 2022 Q4 | Added a 0 to the elevated structures measure in the Action Plan module in order to be submitted.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Rockport had construction underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Rockport had preliminary engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Rockport had 50% of construction underway/complete for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Rockport had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2023-10-01 | 2024 Q1 | During the reporting?period,?the City of Rockport had 50% of construction?underway/complete for its Flood and Drainage project. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2024-01-01 | 2024 Q2 | During the reporting?period,?the City of Rockport had 50% of construction?underway/complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Rockport had 50% of construction underway/complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Rockport had 50.01% to 99% of construction underway/complete for its Flood and Drainage projects.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2025-04-01 | 2025 Q3 | During the reporting?period,?the City of Rockport had at least 50% of construction?underway/complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Rockport had at least 78.5% of construction underway/complete for its Flood and drainage project.
INF_HMID_LMI_20-065-091-C254_NuecesCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Nueces County | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-091-C254_NuecesCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Nueces County | 2021-10-01 | 2022 Q1 | During the reporting period, Nueces County completed construction and is pending submission of construction completion documentation for its Street Improvements project.
INF_HMID_LMI_20-065-091-C254_NuecesCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Nueces County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-091-C254_NuecesCounty_SI | Street Improvements | Construction/reconstruction of streets | Nueces County | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-091-C254_NuecesCounty_SI | Street Improvements | Construction/reconstruction of streets | Nueces County | 2020-10-01 | 2021 Q1 | During the reporting period, Nueces County had construction procurement underway for its street improvements project.
INF_HMID_LMI_20-065-091-C254_NuecesCounty_SI | Street Improvements | Construction/reconstruction of streets | Nueces County | 2021-04-01 | 2021 Q3 | During the reporting period, Nueces County completed construction and is pending submission of construction completion documentation for its Public Facility project. During the reporting period, Nueces County had construction underway for its Street Improvements project
INF_HMID_LMI_20-065-091-C254_NuecesCounty_SI | Street Improvements | Construction/reconstruction of streets | Nueces County | 2021-10-01 | 2022 Q1 | During the reporting period, Nueces County completed construction and is pending submission of construction completion documentation for its Public Facilities project.
INF_HMID_LMI_20-065-091-C254_NuecesCounty_SI | Street Improvements | Construction/reconstruction of streets | Nueces County | 2022-07-01 | 2022 Q4 | During the reporting period, Nueces County submitted the Certificate of Construction Completion for its street improvements project.
INF_HMID_LMI_20-065-091-C254_NuecesCounty_SI | Street Improvements | Construction/reconstruction of streets | Nueces County | 2023-04-01 | 2023 Q3 | During the reporting period, Nueces County had construction underway on the remaining street improvement projects.
INF_HMID_LMI_20-065-091-C254_NuecesCounty_SI | Street Improvements | Construction/reconstruction of streets | Nueces County | 2023-07-01 | 2023 Q4 | During the reporting period, Nueces County had grant closeout documents under review for its Street Improvements project.
INF_HMID_LMI_20-065-091-C254_NuecesCounty_SI | Street Improvements | Construction/reconstruction of streets | Nueces County | 2025-04-01 | 2025 Q3 | During the reporting period, Nueces County had grant closeout documents under review for its Street Improvements project.
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in End Date extended, Budget reallocated
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2023-01-01 | 2023 Q2 | During the reporting, Fort Bend County completed engineering design for its flood and drainage activities.
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2023-04-01 | 2023 Q3 | During the reporting period, Fort Bend County had 90% of engineering design complete.
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2023-07-01 | 2023 Q4 | During the reporting period, Fort Bend County had engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2023-10-01 | 2024 Q1 | During the reporting period, Fort Bend County had acquisition underway for its infrastructure project.
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2024-04-01 | 2024 Q3 | During the reporting period, the Fort Bend County had acquisition underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2024-07-01 | 2024 Q4 | During the reporting period, Fort Bend County had acquisition underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2024-10-01 | 2025 Q1 | During the reporting period, Fort Bend County had acquisition underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2025-01-01 | 2025 Q2 | During the reporting period, Fort Bend County had acquisition underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2025-04-01 | 2025 Q3 | During the reporting period, Fort Bend County had acquisition underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2025-07-01 | 2025 Q4 | During the reporting period, Fort Bend County had acquisition underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-092-C257_FortBendCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Fort Bend County | 2026-01-01 | 2026 Q2
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2020-04-01 | 2020 Q3 | During the reporting period, San Jacinto County had environmental review and engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2020-10-01 | 2021 Q1 | During the reporting period, San Jacinto County had engineering design underway for it&apos;s street improvements project.
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2021-01-01 | 2021 Q2 | During the reporting period, San Jacinto County had construction underway for it&apos;s Street Improvements project.
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2021-07-01 | 2021 Q4 | During the reporting period, San Jacinto County had construction underway for it&apos;s Street Improvements project.
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2021-10-01 | 2022 Q1 | During the reporting period, San Jacinto County had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2022-01-01 | 2022 Q2 | During the reporting period, San Jacinto County had construction underway and 1 CR approved for it&apos;s Street Improvements project.
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2022-04-01 | 2022 Q3 | During the reporting period, San Jacinto County completed construction and submitted the COCC for it&apos;s SI project.
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2022-07-01 | 2022 Q4 | During the reporting period, San Jacinto County completed construction of its Street Improvements project.
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2022-10-01 | 2023 Q1 | During the reporting period, preparation of the GCR was underway.
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2023-04-01 | 2023 Q3 | During the reporting period, San Jacinto County had closeout preparation activities underway for its Steet project.
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2024-01-01 | 2024 Q2 | During the reporting period, a contract amendment was executed that increased the budget for this activity
INF_HMID_LMI_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2024-07-01 | 2024 Q4 | During the reporting period, the additional funding allocated in the previous contract amendment was reimbursed to San Jacinto County for its street improvements project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2020-10-01 | 2021 Q1 | During the reporting period, Victoria County had environmental review and engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2021-04-01 | 2021 Q3 | During the reporting period, Victoria County completed environmental review and engineering design is underway at 75% complete for its Flood and Drainage project
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2021-07-01 | 2021 Q4 | During the reporting period, Victoria County had completed environmental review and engineering design for its flood and drainage project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2021-10-01 | 2022 Q1 | During the reporting period, Victoria County had construction procurement underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2022-01-01 | 2022 Q2 | During the reporting period, Victoria County completed engineering design for its Flood and Drainage project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in Performance Statement changed, Budget changed
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2023-01-01 | 2023 Q2 | During the reporting period, Victoria County had construction underway for its Flood and Drainage activities.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2023-04-01 | 2023 Q3 | During the reporting period, Victoria County had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2023-07-01 | 2023 Q4 | During the reporting period, Victoria County had 50% construction complete for its flood and drainage project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2023-10-01 | 2024 Q1 | During the reporting period, Victoria County has 75% of construction completed for its Flood and Drainage project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2024-04-01 | 2024 Q3 | During the reporting period, Victoria County had grant closeout documents under review for its Flood and Drainage project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2024-10-01 | 2025 Q1 | During the reporting period, Victoria County had grant closeout documents under review for its Flood and Drainage project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Victoria County | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Victoria County | 2020-10-01 | 2021 Q1 | During the reporting period, Victoria County had environmental review and engineering design underway for its street improvement project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Victoria County | 2021-04-01 | 2021 Q3 | During the reporting period, Victoria County completed environmental review and engineering design is underway at 75% complete for its Street Improvement project
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Victoria County | 2021-07-01 | 2021 Q4 | During the reporting period, Victoria County had construction procurement underway for its street improvement project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Victoria County | 2021-10-01 | 2022 Q1 | During the reporting period, Victoria County had construction underway for its Street Improvement project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Victoria County | 2022-01-01 | 2022 Q2 | During the reporting period, Victoria County had 50% of construction complete for its Street Improvement project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Victoria County | 2022-04-01 | 2022 Q3 | During the reporting period, Victoria County completed construction and submitted the COCC for its Street Improvement project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Victoria County | 2022-07-01 | 2022 Q4 | During the reporting period, Victoria County completed construction and is pending submission of the construction completion documents for its Street Improvement project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Victoria County | 2023-01-01 | 2023 Q2 | During the reporting period, Victoria County had completed construction for its Street Improvement project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Victoria County | 2023-04-01 | 2023 Q3 | During the reporting period, Victoria County completed construction and submitted the COCC for its Street Improvements project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Victoria County | 2024-04-01 | 2024 Q3 | During the reporting period, Victoria County had grant closeout documents under review for its Street Improvements project.
INF_HMID_LMI_20-065-094-C262_VictoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Victoria County | 2024-10-01 | 2025 Q1 | During the reporting period, Victoria County had grant closeout documents under review for its Street Improvement project.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2020-04-01 | 2020 Q3 | During the reporting period, the Liberty County had environmental review and engineering design underway for its sewer project.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Liberty County had construction procurement underway for its street improvements project.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2021-01-01 | 2021 Q2 | During the reporting period, Liberty County had construction procurement underway for its street improvements project. The 100% Design milestone achieved with the submission of a copy of their plans and specifications.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Liberty County had construction underway for its street improvements project. The Construction Notice-to-Proceed was issued in May 2021.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Liberty County had construction underway for its street improvements project.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Liberty County had construction underway for its street improvements project.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Liberty County had construction underway for its street improvements project.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2022-04-01 | 2022 Q3 | During the reporting period, Liberty County had construction underway for its street improvements project.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2022-07-01 | 2022 Q4 | During the reporting period, Liberty County submitted grant closeout documents for its street improvements project. Closeout review underway.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2023-01-01 | 2023 Q2 | During the reporting period, Liberty County had grant closeout documents under review for its street improvements project.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Liberty County had grant closeout documents under review for its street improvements project.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2025-01-01 | 2025 Q2 | During the reporting period, Liberty County processed a refund for ineligible CDBG funds as they complete close-out.
INF_HMID_LMI_20-065-097-C269_Taft | Street Improvements | Construction/reconstruction of streets | TAFT, CITY OF | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-097-C269_Taft | Street Improvements | Construction/reconstruction of streets | TAFT, CITY OF | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Taft had preliminary engineering design underway for its Street Improvement project.
INF_HMID_LMI_20-065-097-C269_Taft | Street Improvements | Construction/reconstruction of streets | TAFT, CITY OF | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Taft completed environmental review and engineering design for its street improvements project.
INF_HMID_LMI_20-065-097-C269_Taft | Street Improvements | Construction/reconstruction of streets | TAFT, CITY OF | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Taft had construction procurement underway for its Street Improvement project.
INF_HMID_LMI_20-065-097-C269_Taft | Street Improvements | Construction/reconstruction of streets | TAFT, CITY OF | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Taft completed construction procurement for its Street Improvement project.
INF_HMID_LMI_20-065-097-C269_Taft | Street Improvements | Construction/reconstruction of streets | TAFT, CITY OF | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Taft had 50% of construction underway/complete for its Streets Improvement project.
INF_HMID_LMI_20-065-097-C269_Taft | Street Improvements | Construction/reconstruction of streets | TAFT, CITY OF | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Taft had 50% of construction underway/complete for its Streets Improvement project.
INF_HMID_LMI_20-065-097-C269_Taft | Street Improvements | Construction/reconstruction of streets | TAFT, CITY OF | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2020-10-01 | 2021 Q1 | During the reporting period, Aransas County had engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2021-01-01 | 2021 Q2 | During the reporting period, Aransas County had design underway for its Flood and Drainage Project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2021-07-01 | 2021 Q4 | During the reporting period, Aransas County completed engineering design for its Flood and Drainage project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2021-10-01 | 2022 Q1 | During the reporting period, Aransas County had preliminary engineering design underway for its Flood and Drainage projects.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2022-04-01 | 2022 Q3 | During the reporting period, the County of Aransas completed environmental review for its Flood and Drainage projects.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2022-07-01 | 2022 Q4 | During the reporting period, the County of Aransas had construction procurement underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2022-10-01 | 2023 Q1 | During the reporting period, Aransas County had construction underway for its flood and drainage project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2023-01-01 | 2023 Q2 | During the reporting period, Aransas County had preliminary engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2023-04-01 | 2023 Q3 | During the reporting period, Aransas County had construction underway for its flood and drainage project
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2023-07-01 | 2023 Q4 | During the reporting period, Aransas County had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2023-10-01 | 2024 Q1 | During the reporting period, Aransas County had 50% of construction underway/complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2024-01-01 | 2024 Q2 | During the reporting?period,?the Aransas County had 50% of construction?underway/complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2024-04-01 | 2024 Q3 | During the reporting period, the Aransas County had 50% of construction underway/complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2024-07-01 | 2024 Q4 | During the reporting period, the Aransas County had construction underway for some of its Flood and Drainage projects and 50.01% of construction underway/complete for some of its Flood and Drainage projects.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2024-10-01 | 2025 Q1 | During the reporting period, Aransas County completed construction and is pending submission of construction completion documentation for its Flood and Drainage project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2025-01-01 | 2025 Q2 | During the reporting period, Aransas County had 50% of construction?underway/complete for their SW Flood & Drainage project. Additionally, they are still in the process of submitting construction completion documentation for the remaining Flood and Drainage projects.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2025-04-01 | 2025 Q3 | During the reporting¿period,¿Aransas County had preliminary as-builts underway for its Ruby Allen and SW F&D projects. During the reporting period, Aransas County completed engineering design for its SE F&D project. During the reporting period, Aransas County completed construction and submitted the COCC for its SE F&D project. During the reporting period, Aransas County completed construction and submitted the COCC for its Linden Street F&D project. During the reporting period, Aransas County had 95% of construction¿underway/complete for its SW F&D project. During the reporting period, Aransas County&apos;s Grant Administrator billed for construction closeout for SE and Linden Street F&D projects.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2025-07-01 | 2025 Q4 | The Aransas County had construction underway/complete and progress billed for administrative and engineering services related to the As-Builts/COCC/FWCR for its Flood and Drainage project for Ruby Allen.
INF_HMID_LMI_20-065-098-C270_AransasCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Aransas, County Of | 2025-10-01 | 2026 Q1 | During this reporting period, Aransas County billed for engineering services related to the As-Builts/COCC/FWCR for Linden Street, Ruby Allen/Traylor, SE Aransas Co., and SW Aransas Co. - F&D LMI, and Construction NTP for SE Aransas Co. - F&D LMI.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2020-10-01 | 2021 Q1 | During the reporting period, Aransas County had engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2021-01-01 | 2021 Q2 | During the reporting period, Aransas County had design underway for its Street Improvement Project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2021-04-01 | 2021 Q3 | During the reporting period, Aransas County completed environmental review for its Street Improvements project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2021-07-01 | 2021 Q4 | During the reporting period, Aransas County completed engineering design for its Flood and Drainage project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2021-10-01 | 2022 Q1 | During the reporting period, Aransas County had preliminary engineering design underway for its Street Improvement projects.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2022-04-01 | 2022 Q3 | During the reporting period, the County of Aransas completed environmental review for its Street Improvements projects.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2022-07-01 | 2022 Q4 | During the reporting period, the County of Aransas had construction procurement underway for its Street Improvements project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2022-10-01 | 2023 Q1 | During the reporting period, Aransas County had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2023-01-01 | 2023 Q2 | During the reporting period, Aransas County had construction underway for its street improvement project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2023-04-01 | 2023 Q3 | During the reporting period, Aransas County had construction underway for its street improvements project
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2023-07-01 | 2023 Q4 | During the reporting period, Aransas County had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2023-10-01 | 2024 Q1 | During the reporting period, Aransas County had 50% of construction underway/complete for its Street Improvement project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2024-01-01 | 2024 Q2 | During the reporting?period,?the Aransas County had 50% of construction?underway/complete for its Street Improvements project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2024-04-01 | 2024 Q3 | During the reporting period, the Aransas County had 50% of construction underway/complete for its Street Improvements project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2024-07-01 | 2024 Q4 | During the reporting period, the Aransas County had construction underway for some of its Street Improvements projects and 50.01% of construction underway/complete for some of its Street Improvements projects.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2024-10-01 | 2025 Q1 | During the reporting period, Aransas County completed construction and is pending submission of construction completion documentation for its Street Improvements project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2025-01-01 | 2025 Q2 | During the reporting period, Aransas County had 50% of construction?underway/complete for some of their Street Improvements project. Additionally, they are still in the process of submitting construction completion documentation for the remaining Street Improvements projects.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2025-04-01 | 2025 Q3 | During the reporting period, Aransas County completed engineering design for its Holiday Beach SI project. During the reporting period, Aransas County completed construction, but has not submitted the COCC for its Rattlesnake Point SI project. During the reporting period, Aransas County&apos;s Grant Administrator billed for construction closeout for Copano Heights SI project.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2025-07-01 | 2025 Q4 | During this reporting period, Aransas County completed construction and submitted the COCC and billed for administrative services related to the As-Builts/COCC/FWCR for Rattlesnake Point Road - SI LMI and Loop 1781 - SI LMI. During this reporting period, the Aransas County progress billed for engineering services related to the As-Builts/COCC/FWCR for Holiday Beach SI/LMI.
INF_HMID_LMI_20-065-098-C270_AransasCounty_SI | Street Improvements | Construction/reconstruction of streets | Aransas, County Of | 2025-10-01 | 2026 Q1 | During this reporting period, the Aransas County billed for engineering services related to the As-Builts/COCC/FWCR for Holiday Beach, Loop 1781, and Rattlesnake Point Road - SI LMI.
INF_HMID_LMI_20-065-101-C274_NewtonCounty | Street Improvements | Construction/reconstruction of streets | Newton County | 2020-01-01 | 2020 Q2
INF_HMID_LMI_20-065-101-C274_NewtonCounty | Street Improvements | Construction/reconstruction of streets | Newton County | 2020-10-01 | 2021 Q1 | During the reporting period, the Newton County had environmental review underway for its Street Improvements project.
INF_HMID_LMI_20-065-101-C274_NewtonCounty | Street Improvements | Construction/reconstruction of streets | Newton County | 2021-01-01 | 2021 Q2 | During the reporting period, Newton County had environmental and engineering underway for its Street Improvement Project.
INF_HMID_LMI_20-065-101-C274_NewtonCounty | Street Improvements | Construction/reconstruction of streets | Newton County | 2021-04-01 | 2021 Q3 | During the reporting period, Newton County had construction procurement underway for its Street Improvement project.
INF_HMID_LMI_20-065-101-C274_NewtonCounty | Street Improvements | Construction/reconstruction of streets | Newton County | 2021-10-01 | 2022 Q1 | During the reporting?period,?Newton County had construction?underway for its street improvements project.
INF_HMID_LMI_20-065-101-C274_NewtonCounty | Street Improvements | Construction/reconstruction of streets | Newton County | 2022-01-01 | 2022 Q2 | During the reporting period, the Newton County had construction underway for its street improvements project.
INF_HMID_LMI_20-065-101-C274_NewtonCounty | Street Improvements | Construction/reconstruction of streets | Newton County | 2022-04-01 | 2022 Q3 | During the reporting period, Newton County had 60% of construction underway/complete for its street improvements project.
INF_HMID_LMI_20-065-101-C274_NewtonCounty | Street Improvements | Construction/reconstruction of streets | Newton County | 2022-10-01 | 2023 Q1 | During the reporting period, the Newton County completed construction and is pending submission of construction completion documentation for its street improvements project.
INF_HMID_LMI_20-065-101-C274_NewtonCounty | Street Improvements | Construction/reconstruction of streets | Newton County | 2023-01-01 | 2023 Q2 | During the reporting period, Newton County completed construction and submitted the COCC for its street improvements project.
INF_HMID_LMI_20-065-101-C274_NewtonCounty | Street Improvements | Construction/reconstruction of streets | Newton County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-101-C274_NewtonCounty | Street Improvements | Construction/reconstruction of streets | Newton County | 2025-07-01 | 2025 Q4 | During the reporting period, the Newton County submitted their final PD request for payment. Closeout is in the final closeout stages.
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Silsbee had environmental review underway for its flood and drainage project.
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Silsbee had engineering design underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2021-01-01 | 2021 Q2 | Preliminary Design (30% Plan) - During the reporting period, the City of Silsbee had preliminary engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Silsbee had engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Silsbee had construction procurement underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Silsbee had construction underway for its Flood and Drainage facilities project.
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Silsbee had construction underway for its Flood and Drainage facilities project.
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Silsbee had construction underway for its Flood and Drainage facilities project.
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Silsbee had 50% of construction completed for its Flood and Drainage project.
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2024-01-01 | 2024 Q2 | During this reporting period, the city of Silsbee&apos;s construction on hold due to generators expected delivery time frame (50 weeks = 11 months).
INF_HMID_LMI_20-065-102-C275_Silsbee | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Silsbee | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Silsbee completed construction and the certificate of construction completion underway for its flood and drainage projects.
INF_HMID_LMI_20-065-102-C275_Silsbee_SI | Street Improvements | Construction/reconstruction of streets | Silsbee | 2023-07-01 | 2023 Q4 | Activity created.
INF_HMID_LMI_20-065-102-C275_Silsbee_SI | Street Improvements | Construction/reconstruction of streets | Silsbee | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Silsbee submitted grant closeout documents for its street improvements project.
INF_HMID_LMI_20-065-102-C275_Silsbee_SI | Street Improvements | Construction/reconstruction of streets | Silsbee | 2025-04-01 | 2025 Q3 | During the reporting period, The City of Silsbee had had grant closeout documents under review for its street improvements project
INF_HMID_LMI_20-065-105-C287_LaMarque | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | La Marque, City of | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-105-C287_LaMarque | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | La Marque, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of La Marque had engineering design complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-105-C287_LaMarque | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | La Marque, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of LaMarque had construction underway for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-105-C287_LaMarque | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | La Marque, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of La Marque had construction procurement underway for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-105-C287_LaMarque | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | La Marque, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the City of La had construction underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-105-C287_LaMarque | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | La Marque, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the City of La Marque had construction underway for its flood and drainage facilities project., and has not reached the 50% threshold.
INF_HMID_LMI_20-065-105-C287_LaMarque | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | La Marque, City of | 2024-07-01 | 2024 Q4 | During the reporting?period,?the City of La Marque had 50% of construction?underway/complete for its flood and drainage project.
INF_HMID_LMI_20-065-105-C287_LaMarque | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | La Marque, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the City of La Marque completed construction and is pending submission of construction completion documentation for its flood and drainage project.
INF_HMID_LMI_20-065-105-C287_LaMarque | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | La Marque, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the City of La Marque completed construction and submitted the COCC for its flood and drainage facilities project.
INF_HMID_LMI_20-065-106-C288_Pearland | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | PEARLAND, CITY OF | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-106-C288_Pearland | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | PEARLAND, CITY OF | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Pearland completed construction and is pending submission of construction completion documentation for its flood and drainage project.
INF_HMID_LMI_20-065-106-C288_Pearland | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | PEARLAND, CITY OF | 2026-01-01 | 2026 Q2
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2020-07-01 | 2020 Q4 | During the reporting period, Wharton County had acquisition, environmental review and engineering design underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Wharton County had environmental review underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Wharton County had engineering design underway for its flood and drainage project
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in Budget reallocated, Measures updated
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2022-10-01 | 2023 Q1 | During the reporting period, the County had engineering design underway for its flood and drainage project, however, these expenditures do not align with the reimbursement for the aforementioned professional services.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2023-01-01 | 2023 Q2 | During the reporting period, Wharton County had acquisition underway for its flood and drainage project.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2023-07-01 | 2023 Q4 | During the reporting period, the County completed acquisition for its flood and drainage project.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Wharton County had construction procurement underway for its infrastructure project. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2024-07-01 | 2024 Q4 | During the reporting period, Wharton County had construction procurement underway for its infrastructure project.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2025-01-01 | 2025 Q2 | During the reporting period , Wharton Cunty had construction procurement underway for its infrastructure project.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2025-04-01 | 2025 Q3 | During the reporting period, Wharton County had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2025-07-01 | 2025 Q4 | During the reporting period, a contract amendment was executed that reallocated funding from the Urgent Need Flood and Drainage activity to the LMI Flood and Drainage activity.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2025-10-01 | 2026 Q1 | During the reporting period Wharton County had 50% of construction complete for its flood and drainage project.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2020-07-01 | 2020 Q4 | During the reporting period, Wharton County had environmental review and engineering design underway for its sewer facilities project.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2021-07-01 | 2021 Q4 | During the reporting?period,?Wharton County had preliminary?engineering design underway for its Flood and Drainage Facilities projects.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Wharton County completed engineering design for its sewer facilities project.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Wharton County had construction procurement underway for its public facilities projects.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in Budget reallocated, Measures updated
INF_HMID_LMI_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2022-10-01 | 2023 Q1 | During the reporting period, the County had construction underway for its public facilities project, however, this expenditure was reimbursed in Q3 2022
INF_HMID_LMI_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2023-07-01 | 2023 Q4 | During the reporting period, the County did not have any activity for its sewer facility project.
INF_HMID_LMI_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2025-04-01 | 2025 Q3 | During the reporting period, Wharton County completed construction and is pending submission of construction completion documentation for its Sewer project.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Aransas Pass had engineering design complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Aransas Pass completed environmental review for its flood and drainage project.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2021-07-01 | 2021 Q4 | During the reporting period, Aransas Pass had completed environmental review and engineering design for its flood and drainage project.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Aransas Pass had construction underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Aransas Pass had 50% of construction underway/complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Aransas Pass had 50% of construction underway/complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Aransas Pass had 50% of construction underway/complete for its flood and drainage project.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Aransas Pass had 75% of construction underway for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Aransas Pass had 50% of construction complete for its water/sewer project.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2023-04-01 | 2023 Q3 | During the reporting?period,?the City of Aransas Pass had 90% of construction?underway/complete for its flood and drainage facility project.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2023-07-01 | 2023 Q4 | During the Reporting Period, City of Aransas Pass had 100% of construction Complete for its current flood and drainage facility project, submitted amendment request for additional projects to use cost savings.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2024-04-01 | 2024 Q3 | Activity budget and obligation adjusted due to a contract amendment.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Aransas Pass had construction underway for its flood and drainage project - N. McCambell-Stapp-King TA. Final payment affidavit submitted for N. McCambell-Stapp-King TA
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Aransas Pass completed construction and submitted the COCC for its flood and drainage project.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Aransas Pass completed construction and submitted the COCC for its flood and drainage project - FEMA pump stations.
INF_HMID_LMI_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Aransas Pass had construction procurement underway for its flood and drainage - Huff/Wheeler pump station.
INF_HMID_LMI_20-065-109-C303_AransasPass_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Aransas Pass | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-109-C303_AransasPass_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Aransas Pass | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Aransas Pass had engineering design complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-109-C303_AransasPass_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Aransas Pass | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Aransas Pass completed environmental review for its sewer project.
INF_HMID_LMI_20-065-109-C303_AransasPass_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Aransas Pass | 2021-07-01 | 2021 Q4 | During the reporting period, Aransas Pass accepted applications for eligibility review for its infrastructure program.
INF_HMID_LMI_20-065-109-C303_AransasPass_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Aransas Pass | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Aransas Pass completed construction and is pending submission of construction completion documentation for its Sewer project.
INF_HMID_LMI_20-065-109-C303_AransasPass_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Aransas Pass | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Aransas Pass had 50% of construction underway/complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-109-C303_AransasPass_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Aransas Pass | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-109-C303_AransasPass_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Aransas Pass | 2023-07-01 | 2023 Q4 | During the Reporting Period, City of Aransas Pass had 100% of construction Complete for its current flood and drainage facility project, submitted amendment request for additional projects to use cost savings.
INF_HMID_LMI_20-065-109-C303_AransasPass_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Aransas Pass | 2024-04-01 | 2024 Q3 | Activity budget and obligation adjusted due to a contract amendment.
INF_HMID_LMI_20-065-109-C303_AransasPass_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Aransas Pass | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Aransas Pass completed construction and submitted the COCC for its sewer facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio County | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-110-C306_RefugioCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio County | 2020-07-01 | 2020 Q4 | During the reporting period, the Refugio County had environmental review underway for its flood and drainage project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio County | 2020-10-01 | 2021 Q1 | During the reporting period, Refugio County had engineering design underway for its flood and drainage facilities improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio County | 2022-04-01 | 2022 Q3 | During the reporting period, Refugio County had construction underway for its flood and drainage improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio County | 2022-07-01 | 2022 Q4 | During the reporting period, Refugio County had construction underway for its flood and drainage project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio County | 2022-10-01 | 2023 Q1 | During the reporting period, Refugio County completed construction and is pending submission of construction completion documentation for its flood and drainage project
INF_HMID_LMI_20-065-110-C306_RefugioCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio County | 2023-10-01 | 2024 Q1 | During the reporting period, Refugio County completed construction and submitted the COCC for its Flood and Drainage project. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio County | 2024-04-01 | 2024 Q3 | During the reporting period, the Refugio County completed construction and is pending submission of construction completion documentation for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio County | 2024-10-01 | 2025 Q1 | During the reporting period, a contract amendment was executed to adjust project scope and budgets.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Refugio County | 2025-04-01 | 2025 Q3 | During the reporting period, the Refugio County completed construction and is pending submission of construction completion documentation for its flood and drainage.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2020-07-01 | 2020 Q4 | During the reporting period, Refugio County had environmental review underway for its public facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2020-10-01 | 2021 Q1 | During the reporting period, Refugio County had engineering design underway for its public facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2021-04-01 | 2021 Q3 | During the reporting period, Refugio County is preparing an amendment for budget change scope change for its public facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2021-10-01 | 2022 Q1 | During the reporting period, Refugio County had construction procurement underway for its public facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in End Date extended, Performance Statement changed, Budget changed
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2023-01-01 | 2023 Q2 | During the reporting period, the County of Refugio had construction underway for its Water Facilities projects.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2023-04-01 | 2023 Q3 | During the reporting period, the Refugio County completed construction and submitted the COCC for its Public Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2023-07-01 | 2023 Q4 | During the reporting?period,?Refugio County had 50% of construction?underway/complete for its Public Facility project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2023-10-01 | 2024 Q1 | During the reporting period, Refugio County completed construction and is pending submission of construction completion documentation for its Public Facility project. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2024-04-01 | 2024 Q3 | During the reporting period, the Refugio County completed construction and submitted the COCC for its Public Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2024-07-01 | 2024 Q4 | During the reporting period, the Refugio County completed construction and submitted the COCC for its two Public Facilities (Tivoli and Bayside) projects.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2025-01-01 | 2025 Q2 | During the reporting period, Refugio County had construction underway for its public facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2025-04-01 | 2025 Q3 | During the reporting period, the Refugio County completed construction and is pending submission of construction completion documentation for its Public Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2026-01-01 | 2026 Q2
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2020-07-01 | 2020 Q4 | During the reporting period, the Refugio County had environmental review underway for its sewer facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2020-10-01 | 2021 Q1 | During the reporting period, Refugio County had engineering design underway for its sewer facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2021-04-01 | 2021 Q3 | During the reporting period, Refugio County had engineering design is 98% complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in End Date extended, Performance Statement changed, Budget changed
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2022-10-01 | 2023 Q1 | During the reporting period, Refugio County had 50% of construction underway/complete for its sewer facilities project
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2023-01-01 | 2023 Q2 | During the reporting period, the County of Refugio had construction underway for its Water Facilities projects.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2023-04-01 | 2023 Q3 | During the reporting period, Refugio County had 50% of construction underway/complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2023-07-01 | 2023 Q4 | During the reporting?period,?Refugio County had 50% of construction?underway/complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2023-10-01 | 2024 Q1 | During the quarter, an amendment to this contract was executed, reducing the budget and obligation amounts. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2024-01-01 | 2024 Q2 | During the reporting period, the Refugio County completed construction and submitted the COCC for its Sewer Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2024-04-01 | 2024 Q3 | During the reporting period, the Refugio County completed construction and submitted the COCC for its Sewer Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2024-10-01 | 2025 Q1 | During the reporting period, a contract amendment was executed to adjust project scope and budgets.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2025-04-01 | 2025 Q3 | During the reporting period, the Refugio County completed construction and is pending submission of construction completion documentation for its sewer facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2020-07-01 | 2020 Q4 | During the reporting period, Refugio County had environmental review underway for its street improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2020-10-01 | 2021 Q1 | During the reporting period, Refugio County had engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2021-04-01 | 2021 Q3 | During the reporting period, Refugio County completed environmental review for its street improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2021-10-01 | 2022 Q1 | During the reporting period, Refugio County completed construction procurement for its street improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2022-04-01 | 2022 Q3 | During the reporting period, Refugio County had construction underway for its street improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2022-07-01 | 2022 Q4 | During the reporting period, Refugio County had 50% of construction underway/complete for its street improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2022-10-01 | 2023 Q1 | During the reporting period, Refugio County completed construction and is pending submission of construction completion documentation for its street improvements project
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2023-10-01 | 2024 Q1 | During the reporting period, Refugio County had construction complete and the COCC underway for its Street Improvement project. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2024-04-01 | 2024 Q3 | During the reporting period, the Refugio County completed construction and submitted the COCC for its Street Improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2024-10-01 | 2025 Q1 | During the reporting period, a contract amendment was executed to adjust project scope and budgets.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2025-01-01 | 2025 Q2 | During the reporting period, Refugio County completed environmental review for its street improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2025-04-01 | 2025 Q3 | During the reporting period, Refugio County had 50% of construction?underway/complete for its street improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2025-07-01 | 2025 Q4 | During the reporting period, Refugio County had 50% of construction underway/complete for its street improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2025-10-01 | 2026 Q1 | During the reporting period, Refugio County completed construction and is pending submission of construction completion documentation for its street improvements project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-110-C306_RefugioCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2020-07-01 | 2020 Q4 | During the reporting period, Refugio County had environmental review underway for its water facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2020-10-01 | 2021 Q1 | During the reporting period, Refugio County had engineering design underway for its water facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2021-04-01 | 2021 Q3 | During the reporting period, Refugio County had engineering design is 99% complete for its Water Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2022-10-01 | 2023 Q1 | During the reporting period, Refugio County had 50% of construction underway/complete for its water facilities project
INF_HMID_LMI_20-065-110-C306_RefugioCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2023-01-01 | 2023 Q2 | During the reporting period, the County of Refugio had construction underway for its Water Facilities projects.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2023-04-01 | 2023 Q3 | During the reporting period, Refugio County had 50% of construction underway/complete for its Sewer Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2023-07-01 | 2023 Q4 | During the reporting?period,?Refugio County had 50% of construction?underway/complete for its Water Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2023-10-01 | 2024 Q1 | During the reporting period, Refugio County completed construction and submitted the COCC for its Water Facility project. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2024-01-01 | 2024 Q2 | During the reporting period, the Refugio County completed construction and submitted the COCC for its Water Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2024-04-01 | 2024 Q3 | During the reporting period, the Refugio County completed construction and submitted the COCC for its Water Facilities project.
INF_HMID_LMI_20-065-110-C306_RefugioCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Refugio County | 2025-04-01 | 2025 Q3 | During the reporting period, the Refugio County completed construction and submitted the COCC for its Water Facilities project.
INF_HMID_LMI_20-065-113-C310_Baytown | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Baytown | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-113-C310_Baytown | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Baytown | 2020-10-01 | 2021 Q1 | During the Reporting Period, the City of Baytown completed environmental review for its Drainage Improvements project.
INF_HMID_LMI_20-065-113-C310_Baytown | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Baytown | 2022-10-01 | 2023 Q1 | During the reporting?period,?the City of Baytown had preliminary?engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-113-C310_Baytown | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Baytown | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Baytown completed construction and is pending submission of construction completion documentation for its flood and drainage project.
INF_HMID_LMI_20-065-113-C310_Baytown | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Baytown | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-113-C310_Baytown | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Baytown | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Baytown submitted grant closeout documents for its flood and drainage project.
INF_HMID_LMI_20-065-113-C310_Baytown | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | City of Baytown | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Baytown had grant closeout documents under review for its flood and drainage facilities project.
INF_HMID_LMI_20-065-114-C313_Gregory | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | GREGORY, CITY OF | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-114-C313_Gregory | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | GREGORY, CITY OF | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Gregory had environmental review underway for its Sewer project.
INF_HMID_LMI_20-065-114-C313_Gregory | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | GREGORY, CITY OF | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Gregory had construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-114-C313_Gregory | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | GREGORY, CITY OF | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Gregory had 50% of construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-114-C313_Gregory | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | GREGORY, CITY OF | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-114-C313_Gregory | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | GREGORY, CITY OF | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-114-C313_Gregory | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | GREGORY, CITY OF | 2023-07-01 | 2023 Q4 | During the Reporting Period, City of Gregory had 100% of construction Complete for its current flood and drainage facility project, COCC submitted.
INF_HMID_LMI_20-065-117-C378_PlumGrove | Street Improvements | Construction/reconstruction of streets | City of Plum Grove | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-117-C378_PlumGrove | Street Improvements | Construction/reconstruction of streets | City of Plum Grove | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Plum Grove had construction procurement underway for its street improvements project. The 100% Design milestone achieved with the submission of a copy of their plans and specifications.
INF_HMID_LMI_20-065-117-C378_PlumGrove | Street Improvements | Construction/reconstruction of streets | City of Plum Grove | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Plum Grove had construction underway for its street improvements project.
INF_HMID_LMI_20-065-117-C378_PlumGrove | Street Improvements | Construction/reconstruction of streets | City of Plum Grove | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Plum Grove submitted grant closeout documents for its street improvements project. The closeout documents are pending review.
INF_HMID_LMI_20-065-117-C378_PlumGrove | Street Improvements | Construction/reconstruction of streets | City of Plum Grove | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-117-C378_PlumGrove | Street Improvements | Construction/reconstruction of streets | City of Plum Grove | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Plum Grove had its grant closeout review underway for its street improvements project.
INF_HMID_LMI_20-065-117-C378_PlumGrove | Street Improvements | Construction/reconstruction of streets | City of Plum Grove | 2024-07-01 | 2024 Q4 | Activity completed during quarter.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2020-07-01 | 2020 Q4 | During the reporting period, Brazoria County had environmental review underway for its flood and drainage project.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2020-10-01 | 2021 Q1 | During the reporting period, Brazoria County had environmental review and engineering design underway.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2021-01-01 | 2021 Q2 | During the reporting period, the County had engineering design underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2021-04-01 | 2021 Q3 | During the reporting period, Brazoria County had environmental review underway for its Flood and Drainage Project. During the reporting period, Brazoria County had engineering design underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2022-01-01 | 2022 Q2 | During the reporting period, the Brazoria County had preliminary engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2022-07-01 | 2022 Q4 | During the reporting period, the County had preliminary engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2022-10-01 | 2023 Q1 | During the reporting period, the County had preliminary engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2023-01-01 | 2023 Q2 | During the reporting period, Brazoria County had engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2023-07-01 | 2023 Q4 | During the reporting period, the County completed partial designs for their flood and drainage project.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2023-10-01 | 2024 Q1 | During the reporting period, the County had engineering design underway for its flood and drainage projects Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2024-01-01 | 2024 Q2 | During the reporting period, the County had engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2024-04-01 | 2024 Q3 | During the reporting period, the County had environmental review underway for its flood and drainage project.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2025-07-01 | 2025 Q4 | During the reporting period, Brazoria County had acquisition underway for its flood and drainage project.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Brazoria County | 2025-10-01 | 2026 Q1 | During the reporting period, the Brazos County had construction procurement underway for its flood and drainage project.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty_SF | Sewer Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Brazoria County | 2025-07-01 | 2025 Q4 | During the reporting period, a contract amendment was executed and the activity was created and budgeted in DRGR.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty_SI | Street Improvements | Construction/reconstruction of streets | Brazoria County | 2025-07-01 | 2025 Q4 | During the reporting period, a contract amendment was executed and the activity was created and budgeted in DRGR.
INF_HMID_LMI_20-065-118-C388_BrazoriaCounty_WF | Water Facilities and Improvements | Construction/reconstruction of water/sewer lines or systems | Brazoria County | 2025-07-01 | 2025 Q4 | During the reporting period, a contract amendment was executed and the activity was created and budgeted in DRGR.
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2020-07-01 | 2020 Q4 | During the reporting period, the City of West Orange had environmental review and engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2020-10-01 | 2021 Q1 | During the reporting period, the City of West Orange had environmental review underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2021-01-01 | 2021 Q2 | During the reporting period, the City of West Orange had preliminary engineering design underway for its Flood and Drainage Facilities project.
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2021-04-01 | 2021 Q3 | During the reporting period, the City of West Orange completed environmental review for its Flood and Drainage project. During the reporting period, the City of West Orange had engineering design 48% complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2021-07-01 | 2021 Q4 | During the reporting period, the City of West Orange had construction underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2021-10-01 | 2022 Q1 | During the reporting period, the City of West Orange had construction underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2022-01-01 | 2022 Q2 | During the reporting period, the City of West Orange had construction underway for its flood and drainage project.
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2022-04-01 | 2022 Q3 | During the reporting period, the City of West Orange had construction completed and COCC underway on its Flood & Drainage project.
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2022-07-01 | 2022 Q4 | During the reporting period, the City of West Orange completed construction the Flood and Drainage project, but project closeout documents not yet submitted.
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2022-10-01 | 2023 Q1 | During the reporting period, construction was completed for flood and drainage
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2023-01-01 | 2023 Q2 | During the reporting period, the City of West Orange had construction complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2023-04-01 | 2023 Q3 | Amendment moved funds to related activity. Area Benefit type corrected.
INF_HMID_LMI_20-065-119-C390_WestOrange_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | CITY OF WEST ORANGE | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-119-C390_WestOrange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CITY OF WEST ORANGE | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-119-C390_WestOrange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CITY OF WEST ORANGE | 2020-07-01 | 2020 Q4 | During the reporting period, the City of West Orange had environmental review and engineering design underway for its public facilities project.
INF_HMID_LMI_20-065-119-C390_WestOrange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CITY OF WEST ORANGE | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-119-C390_WestOrange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CITY OF WEST ORANGE | 2021-01-01 | 2021 Q2 | During the reporting period, the City of West Orange had construction procurement underway for its Public Facilities project.
INF_HMID_LMI_20-065-119-C390_WestOrange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CITY OF WEST ORANGE | 2021-04-01 | 2021 Q3 | During the reporting period, the City of West Orange completed environmental review and procurement for its Public Facilities project. During the reporting period, the City of West Orange had construction underway for its Public Facilities project.
INF_HMID_LMI_20-065-119-C390_WestOrange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CITY OF WEST ORANGE | 2022-04-01 | 2022 Q3 | During the reporting period, 3% of project is completed, with one rescue boat delivered.
INF_HMID_LMI_20-065-119-C390_WestOrange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CITY OF WEST ORANGE | 2022-07-01 | 2022 Q4 | During the reporting period, the City of West Orange received a partial order of Fire Protection equipment.
INF_HMID_LMI_20-065-119-C390_WestOrange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CITY OF WEST ORANGE | 2022-10-01 | 2023 Q1 | During the reporting period, 85% of invoice for Fire Protection Facilities-Pumper Truck was paid. Awaiting title for retainage payment.
INF_HMID_LMI_20-065-119-C390_WestOrange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CITY OF WEST ORANGE | 2023-01-01 | 2023 Q2 | During the reporting period, the City of West Orange had construction complete for its Public Facilities project.
INF_HMID_LMI_20-065-119-C390_WestOrange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CITY OF WEST ORANGE | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity. Area Benefit type corrected.
INF_HMID_LMI_20-065-119-C390_WestOrange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CITY OF WEST ORANGE | 2023-07-01 | 2023 Q4 | During the reporting period, City of West Orange completed payments for Fire Protection Equipment purchases.
INF_HMID_LMI_20-065-119-C390_WestOrange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CITY OF WEST ORANGE | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-119-C390_WestOrange_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | CITY OF WEST ORANGE | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-119-C390_WestOrange_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | CITY OF WEST ORANGE | 2020-07-01 | 2020 Q4 | During the reporting period, the City of West Orange had environmental review and engineering design underway for its sewer facilities project.
INF_HMID_LMI_20-065-119-C390_WestOrange_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | CITY OF WEST ORANGE | 2020-10-01 | 2021 Q1
INF_HMID_LMI_20-065-119-C390_WestOrange_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | CITY OF WEST ORANGE | 2021-04-01 | 2021 Q3 | During the reporting period, the City of West Orange completed environmental review for its Sewer Facilities project.
INF_HMID_LMI_20-065-119-C390_WestOrange_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | CITY OF WEST ORANGE | 2021-10-01 | 2022 Q1 | During the reporting period, the City West Orange completed engineering design for its street improvements project.
INF_HMID_LMI_20-065-119-C390_WestOrange_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | CITY OF WEST ORANGE | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-119-C390_WestOrange_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | CITY OF WEST ORANGE | 2022-07-01 | 2022 Q4 | During the reporting period, the City of West Orange had engineering underway for the Sewer Facilities WWTP.
INF_HMID_LMI_20-065-119-C390_WestOrange_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | CITY OF WEST ORANGE | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity. Area Benefit type corrected.
INF_HMID_LMI_20-065-119-C390_WestOrange_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | CITY OF WEST ORANGE | 2024-07-01 | 2024 Q4 | During the reporting period, the City of West Orange had construction NTP issued and is now underway for its sewer facilities project
INF_HMID_LMI_20-065-119-C390_WestOrange_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | CITY OF WEST ORANGE | 2024-10-01 | 2025 Q1 | During the reporting?period,?the City of West Orange had all projects complete with the exception of the WWTP underway.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2020-07-01 | 2020 Q4 | During the reporting period, the City of West Orange had environmental review and engineering design underway for its street improvement project.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2020-10-01 | 2021 Q1 | During the reporting period, the City of West Orange had environmental review underway for its street improvements project.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2021-01-01 | 2021 Q2 | During the reporting period, the City of West Orange had preliminary engineering design underway for its Street Improvements project.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2021-07-01 | 2021 Q4 | During the reporting period, the City West Orange completed engineering design for its street improvements project.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2021-10-01 | 2022 Q1 | During the reporting period, the City West Orange completed engineering design for its sewer facilities project.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2022-01-01 | 2022 Q2 | During the reporting period, the City of West Orange had construction underway for its street improvement project.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2022-04-01 | 2022 Q3 | During the reporting period, 44% of construction has been completed for Street Improvement.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2022-07-01 | 2022 Q4 | During the reporting period, the City of West Orange completed 96% of construction for Street Improvements.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2022-10-01 | 2023 Q1 | During the reporting period, construction was completed for street improvements. A budget amendment must be executed to pay additional costs from change orders.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2023-01-01 | 2023 Q2 | During the reporting period, the City of West Orange had construction complete for its Street Improvements project.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity. Area Benefit type corrected.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2023-07-01 | 2023 Q4 | During the reporting period, City of West Orange completed construction closeout documents for its Street Improvements project.
INF_HMID_LMI_20-065-119-C390_WestOrange_SI | Street Improvements | Construction/reconstruction of streets | CITY OF WEST ORANGE | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Vidor had environmental review and engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Vidor had environmental review underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Vidor had engineering design 97% complete for its Flood and Drainage project.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Vidor had engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2021-10-01 | 2022 Q1 | During the reporting?period,?the City of Vidor had preliminary?engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Vidor had 90% completion of Engineering for Planning Study.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Vidor had engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2023-04-01 | 2023 Q3 | Amendment moved funds to related activity and decreased projected performance measures.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Vidor issued Construction NTP. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Vidor had 33% of F&D construction LMI underway.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Vidor awarded construction contracts for 3 project sites, Alamo, North Archie Street and Aery Road.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Vidor F&D project site Elgie Street & Tiger Creek construction underway with expected completion in September 2024.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2025-01-01 | 2025 Q2 | During the reporting?period,?the City of Vidor had 75% of construction?complete for its flood and drainage project.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2025-04-01 | 2025 Q3 | During the reporting?period,?the City of Vidor had 85% of construction?complete for its flood and drainage project
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Vidor completed construction and submitted the COCC for its Flood and Drainage.
INF_HMID_LMI_20-065-120-C407_Vidor_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Vidor | 2025-10-01 | 2026 Q1 | During the reporting period the City of Vidor was waiting for the GLO FIN to complete budget changes in TIGR in order to submit a final draw for their completed street improvements project.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Vidor had environmental review and engineering design underway for its street improvement project.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Vidor had environmental review underway for its street improvements project.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Vidor had engineering design 53% complete for its Street Improvement project.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Vidor had engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2021-10-01 | 2022 Q1 | During the reporting?period,?the City of Vidor had preliminary?engineering design underway for its street improvement project.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Vidor had engineering underway for its street improvements project.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Vidor had engineering design underway for LMI Street Improvements.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2022-10-01 | 2023 Q1 | During the reporting period, engineering design was underway for street improvements.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Vidor had engineering design underway for its street improvement project.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity and decreased projected performance measures.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Vidor reporting engineering design underway. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Vidor held Pre-Construction conference on 08/27/2024 for 2 SI project sites, Alamo and North Archie Street. NTP issued for 10/07/2024. Extension request submitted 09/24/24.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2024-10-01 | 2025 Q1 | During the reporting?period,?the City of Vidor had 60% of construction?underway for its SI project.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2025-01-01 | 2025 Q2 | During the reporting?period,?the City of Vidor had 75% of construction?complete for its street improvement project.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2025-04-01 | 2025 Q3 | During the reporting?period,?the City of Vidor had 85% of construction?complete for its street improvement project
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Vidor completed construction and submitted the COCC for its Street Improvements.
INF_HMID_LMI_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2025-10-01 | 2026 Q1 | During the reporting period the City of Vidor was waiting for the GLO FIN to complete budget changes in TIGR in order to submit a final draw for their completed street improvements project.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2020-10-01 | 2021 Q1 | During the reporting period, Jefferson County had engineering design underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2021-04-01 | 2021 Q3 | During the reporting period, the Jefferson County had environmental review underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2021-07-01 | 2021 Q4 | During the reporting?period,?Jefferson County had preliminary?engineering design underway for its flood and drainage facilities project. Negative balance for quarterly expenditure is a result of Clarification Form Adjustments.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2021-10-01 | 2022 Q1 | During the reporting period, Jefferson County had preliminary engineering design underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2022-01-01 | 2022 Q2 | During the reporting period, Jefferson County had engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2022-10-01 | 2023 Q1 | During the reporting period, Jefferson County had 50% of construction underway/complete for its flood and drainage project.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2023-01-01 | 2023 Q2 | During the reporting period, Jefferson County completed engineering design for its flood and drainage facilities project.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2023-07-01 | 2023 Q4 | During the reporting period, Jefferson County had construction underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2024-01-01 | 2024 Q2 | ?During the reporting?period,?the Jefferson County had 50% of construction?underway/complete for its flood and drainage project.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2024-10-01 | 2025 Q1 | During the reporting?period,?Jefferson County had 60% of construction?complete for its flood and drainage project.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2025-01-01 | 2025 Q2 | During the reporting?period,?Jefferson County had 75% of construction?underway/complete for its flood and drainage project.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2025-04-01 | 2025 Q3 | During the reporting?period,?Jefferson County had 90% of construction?underway for its flood and drainage project.
INF_HMID_LMI_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2026-01-01 | 2026 Q2
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Matagorda County had environmental review underway for its street improvements project.
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Matagorda County had engineering design underway for its Street Improvements project.
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Matagorda County completed engineering design for its Street Improvements project.
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2022-04-01 | 2022 Q3 | During the reporting period, the County of Matagorda had environmental review underway for its Street Improvements project.
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Matagorda County had construction procurement underway for its Street improvements project.
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Matagorda County had 50% of construction underway/complete for its Street Improvements (Marlin) project.
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Matagorda County completed construction and is pending submission of construction completion documentation for its Street Improvement project.
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2024-01-01 | 2024 Q2 | During the reporting?period,?the Matagorda County had 50% of construction?underway/complete for its Street Improvements project.
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2024-04-01 | 2024 Q3 | During the reporting period, the Matagorda County had 50% of construction underway/complete for its Street Improvements project.
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2025-01-01 | 2025 Q2 | Revised a portion of the activity budget and obligation from the UN Street Improvements activity.
INF_HMID_LMI_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2025-07-01 | 2025 Q4 | During the reporting period, the Matagorda County had 94.7% of construction underway/complete for its Sewer Facilities project (#10 Marlin Drive SI - LMI).
INF_HMID_LMI_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Danbury had environmental review underway for it Sewer Facilities project. During the reporting period, the City of Danbury had engineering design underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Danbury amended their contract to adjust projected beneficiaries and budgets.
INF_HMID_LMI_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_LMI_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Danbury had grant closeout documents under review for its Sewer Facilities project.
INF_HMID_LMI_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in End Date extended
INF_HMID_LMI_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2022-10-01 | 2023 Q1 | During the reporting period, City of Danbury completed construction and is pending submission of construction completion documentation for its Sewer Facilities project.
INF_HMID_LMI_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity. Area Benefit type corrected.
INF_HMID_LMI_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2023-07-01 | 2023 Q4 | Construction complete, COCC underway.
INF_HMID_LMI_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Danbury had close Out Underway
INF_HMID_LMI_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2024-01-01 | 2024 Q2 | During the reporting period, budget lines for environmental reviews were removed from the activity.
INF_HMID_LMI_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_HMID_LMI_20-065-135-C481_MontBelvieu | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | MONT BELVIEU, CITY OF | 2020-04-01 | 2020 Q3
INF_HMID_LMI_20-065-135-C481_MontBelvieu | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | MONT BELVIEU, CITY OF | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Mont Belvieu completed construction and submitted the COCC for its sewer facilities project.
INF_HMID_LMI_20-065-135-C481_MontBelvieu | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | MONT BELVIEU, CITY OF | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Mont Belvieu had its sewer facilities project administratively closed
INF_HMID_LMI_20-065-135-C481_MontBelvieu | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | MONT BELVIEU, CITY OF | 2023-07-01 | 2023 Q4 | Activity completed.
INF_HMID_LMI_20-065-136-C491_MontgomeryCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Montgomery County | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-136-C491_MontgomeryCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Montgomery County | 2023-01-01 | 2023 Q2 | During the reporting period, Montgomery County completed ENG, determining the project unfeasible and is researching and alternative project for a possible CR.
INF_HMID_LMI_20-065-136-C491_MontgomeryCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Montgomery County | 2023-07-01 | 2023 Q4 | Amendment reallocated funds from related activities.
INF_HMID_LMI_20-065-136-C491_MontgomeryCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Montgomery County | 2024-10-01 | 2025 Q1 | During the reporting period, Montgomery County completed construction and is pending submission of construction completion documentation for its flood and drainage project.
INF_HMID_LMI_20-065-136-C491_MontgomeryCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Montgomery County | 2025-01-01 | 2025 Q2 | During the reporting period, Montgomery County had construction complete and the COCC underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-136-C491_MontgomeryCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Montgomery County | 2025-07-01 | 2025 Q4 | There was no reportable change to this activity during the period.
INF_HMID_LMI_20-065-136-C491_MontgomeryCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Montgomery County | 2025-10-01 | 2026 Q1 | During the reporting period, Montgomery County had no reportable change to this activity.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2021-01-01 | 2021 Q2 | During the reporting period, the City Orange had preliminary engineering design underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Orange had construction underway for its flood and drainage project.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Orange had 90% construction completed on Coopers Gully Phase II.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Orange had 90% construction completed on a phase of the F&D project. Time extension and budget revision will allow additional phase to move forward.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2022-10-01 | 2023 Q1 | During the reporting period, the City completed one phase of the flood and drainage project Cooper&apos;s Gully construction (Phase 2). Phase 3 construction will be bid out in 2/2023.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Orange had engineering design and environmental activities underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Orange had 50% of construction complete for its flood and drainage project.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Orange had more than 50% of construction complete for one of its flood and drainage projects.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2024-04-01 | 2024 Q3 | During the reporting period, the city of Orange had 60% construction underway for its flood and drainage projects.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2024-07-01 | 2024 Q4 | During the reporting period, the city of Orange completed construction on Coopers Gully Phase 2 site of it s flood and drainage project.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2024-10-01 | 2025 Q1 | During the reporting period, the city of Orange prepared but has not submitted closeout docs and a final construction draw request for the completed Flood and Drainage project.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2025-07-01 | 2025 Q4 | During the reporting period, a contract amendment was executed that removed the Urgent Need Flood and Drainage project and redistributed the available budget to the still active activities in this contract.
INF_HMID_LMI_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2026-01-01 | 2026 Q2
INF_HMID_LMI_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2020-07-01 | 2020 Q4
INF_HMID_LMI_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Orange had construction underway for its Public Facilities project.
INF_HMID_LMI_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2022-04-01 | 2022 Q3 | During the reporting period, the city had HC SAR Vehicles purchased.
INF_HMID_LMI_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Orange completed construction on Fire Protection vehicles (Public Facilities projects).
INF_HMID_LMI_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Orange had closeout activities underway for its Public Facilities project.
INF_HMID_LMI_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2025-07-01 | 2025 Q4 | During the reporting period, a contract amendment was executed that removed the Urgent Need Flood and Drainage project and redistributed the available budget to the still active activities in this contract.
INF_HMID_LMI_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2026-01-01 | 2026 Q2
INF_HMID_LMI_20-065-142-C782_PortArthur_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Arthur | 2021-01-01 | 2021 Q2
INF_HMID_LMI_20-065-142-C782_PortArthur_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Arthur | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Port Arthur completed environmental review for its flood and drainage project.
INF_HMID_LMI_20-065-142-C782_PortArthur_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Arthur | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Port Arthur had preliminary engineering design underway for its flood and drainage project.
INF_HMID_LMI_20-065-142-C782_PortArthur_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Arthur | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Port Arthur completed engineering design for its flood and drainage project.
INF_HMID_LMI_20-065-142-C782_PortArthur_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Arthur | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Port Arthur had construction procurement underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-142-C782_PortArthur_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Arthur | 2024-04-01 | 2024 Q3 | During the reporting?period,?the City of Port Arthur had 50% of construction?underway/complete for its flood and drainage facilities project.
INF_HMID_LMI_20-065-142-C782_PortArthur_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Arthur | 2024-07-01 | 2024 Q4 | During the reporting period, corrections to admin fields in DRGR were made. No actual change during the quarter and this activity is still ongoing.
INF_HMID_LMI_20-065-142-C782_PortArthur_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Arthur | 2024-10-01 | 2025 Q1 | During the reporting?period,?the City of Port Arthur had 50% of construction?underway/complete for its flood and drainage project.
INF_HMID_LMI_20-065-142-C782_PortArthur_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Arthur | 2025-01-01 | 2025 Q2 | Updated the activity&apos;s projected number of beneficiaries to break out the low and moderate income individuals.
INF_HMID_LMI_20-065-142-C782_PortArthur_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Arthur | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Port Arthur had 50% of construction complete for its flood and drainage project.
INF_HMID_LMI_20-065-142-C782_PortArthur_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Arthur | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Port Arthur had 85% of construction complete for its flood and drainage project.
INF_HMID_LMI_20-065-142-C782_PortArthur_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Arthur | 2026-01-01 | 2026 Q2
INF_HMID_LMI_20-065-144-C843_Beaumont_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Beaumont | 2021-01-01 | 2021 Q2
INF_HMID_LMI_20-065-144-C843_Beaumont_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Beaumont | 2022-01-01 | 2022 Q2 | During the reporting period, the City of xx/Beaumont had engineering design underway for its water facilities project.
INF_HMID_LMI_20-065-144-C843_Beaumont_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Beaumont | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Beaumont completed engineering design for its water facilities project.
INF_HMID_LMI_20-065-144-C843_Beaumont_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Beaumont | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Beaumont completed engineering design for its water facilities project.
INF_HMID_LMI_20-065-144-C843_Beaumont_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Beaumont | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_LMI_20-065-144-C843_Beaumont_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Beaumont | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Beaumont had construction underway for its water facilities project.
INF_HMID_LMI_20-065-144-C843_Beaumont_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Beaumont | 2024-04-01 | 2024 Q3 | During the reporting?period,?the City of Beaumont had 50% of construction?underway/complete for its water facilities project.
INF_HMID_LMI_20-065-144-C843_Beaumont_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Beaumont | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Beaumont had 60% of construction complete for its water facilities project.
INF_HMID_LMI_20-065-144-C843_Beaumont_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Beaumont | 2026-01-01 | 2026 Q2
INF_HMID_LMI_20-065-145-C857_HardinCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Hardin, County of | 2021-01-01 | 2021 Q2
INF_HMID_LMI_20-065-145-C857_HardinCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Hardin, County of | 2021-07-01 | 2021 Q4 | During the reporting?period,?Hardin County had preliminary?engineering design underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Hardin, County of | 2023-01-01 | 2023 Q2 | During the reporting period, Hardin County had engineering design underway for its Flood and Drainage facilities project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Hardin, County of | 2023-07-01 | 2023 Q4 | Annual Section 3 Labor hours reported.
INF_HMID_LMI_20-065-145-C857_HardinCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Hardin, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Hardin County construction procurement underway for its Flood and Drainage (Saratoga) for Project Delivery.
INF_HMID_LMI_20-065-145-C857_HardinCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Hardin, County of | 2024-01-01 | 2024 Q2 | During the reporting period, Hardin County construction procurement underway for its Flood and Drainage facilities project
INF_HMID_LMI_20-065-145-C857_HardinCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Hardin, County of | 2024-10-01 | 2025 Q1 | During the reporting period, Hardin County completed construction and submitted the COCC for its flood and drainage project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Hardin, County of | 2025-01-01 | 2025 Q2 | During the reporting period, Hardin County had construction complete and construction closeout documents were finalized.
INF_HMID_LMI_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2021-01-01 | 2021 Q2
INF_HMID_LMI_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Hardin County had construction procurement underway for its public facilities project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Hardin County had 50% of construction underway/complete for its public facilities project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Hardin County had engineering design and environmental review underway for its public facilities project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2022-04-01 | 2022 Q3 | During the reporting period, Hardin County had procurement activities underway for its public facilities project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2023-01-01 | 2023 Q2 | During the reporting period, Hardin County had construction underway for its Public Facilities project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2023-07-01 | 2023 Q4 | Annual Section 3 Labor hours reported.
INF_HMID_LMI_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2024-01-01 | 2024 Q2 | During the reporting period, Hardin County had 50% of construction underway/complete for its public facilities project
INF_HMID_LMI_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2024-04-01 | 2024 Q3 | During this reporting period Hardin County PF Project: Hardin County ESD Radio Tower is at 3.96%expensed, Saratoga ESD LMI Fire Protection Facilities is at 92.14% expensed, Kountze ESD LMI Fire Protection Facilities is at 5.47% expensed, Silsbee ESD UN Fire Protection Facilities is at 93.36 % expensed
INF_HMID_LMI_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2024-07-01 | 2024 Q4 | There is a pending amendment for this contract. During this reporting period Hardin County had the Silsbee ESD UN Fire Protection Facilities is at 93.36 percent expensed, Saratoga ESD LMI Fire Protection Facilities is at 92.14 percent expensed, Kountze ESD LMI Fire Protection Facilities is at 5.47 percent expensed, Hardin County ESD Radio Tower is at 3.96 percent expensed.
INF_HMID_LMI_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2024-10-01 | 2025 Q1 | During the reporting period, Hardin County completed construction and submitted the COCC for its public facilities project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2025-01-01 | 2025 Q2 | During the reporting period, Hardin County had construction complete and construction closeout documents were finalized.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2021-01-01 | 2021 Q2
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2021-07-01 | 2021 Q4 | During the reporting?period,?Hardin County had preliminary?engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Hardin County had preliminary engineering design underway for its street improvement project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2022-04-01 | 2022 Q3 | During the reporting period, Hardin County had engineering and pre-construction activities underway for its street improvements project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Hardin County had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2023-01-01 | 2023 Q2 | During the reporting period, Hardin County had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Hardin County had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Hardin County had 50% of construction completed for its street improvement project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Hardin County completed construction procurement for its Street Improvements project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2024-01-01 | 2024 Q2 | During the reporting period, Hardin County had construction underway for its street improvements project
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2024-04-01 | 2024 Q3 | During this reporting period Hardin County SI Project Titles: Hardin County Saratoga Roads Project is at 27.36% expensed, and Hardin County Gore Store Road Project - Pct. 2 is at 99.63% expensed.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2024-07-01 | 2024 Q4 | During the reporting period, construction in ongoing and there is an amendment pending to correct project national objectives.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2024-10-01 | 2025 Q1 | During the reporting period, Hardin County completed construction and submitted the COCC for its street improvements project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2025-01-01 | 2025 Q2 | During the reporting period, Hardin County had construction complete and construction closeout documents were finalized.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2025-04-01 | 2025 Q3 | During the reporting period, Hardin County completed construction procurement for phase II of their street improvements project
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2025-07-01 | 2025 Q4 | During the reporting period, Hardin County had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-145-C857_HardinCounty_SI | Street Improvements | Construction/reconstruction of streets | Hardin, County of | 2025-10-01 | 2026 Q1 | During the reporting period, Hardin County completed construction and submitted the COCC for its street improvements project.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2021-01-01 | 2021 Q2
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Rose City had environmental review and engineering design underway for its Flood and Drainage project.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Rose City had engineering design underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Rose City had engineering design underway for its flood and drainage facilities project.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2022-04-01 | 2022 Q3 | During the reporting period, Rose City had engineering design underway for its Drainage Planning Study.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2022-10-01 | 2023 Q1 | During the reporting period, engineering design was underway for flood and drainage project.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Rose had engineering design underway and achieved AUGF for its flood and drainage project.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2023-10-01 | 2024 Q1 | During the reporting period, Rose City completed design plans and advertised for construction bids for its flood and drainage project.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2024-04-01 | 2024 Q3 | During the reporting period, Rose City completed environmental permitting and began construction for its flood and drainage project.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Rose City completed sole source procurement for its flood and drainage project.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Rose City completed construction procurement for its flood and drainage project.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2025-04-01 | 2025 Q3 | During the reporting?period,?the City of Rose City had 70% of construction?complete for its flood and drainage project
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Rose City completed construction and is pending submission of construction completion documentation for its flood and drainage project.
INF_HMID_LMI_20-065-146-C865_RoseCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Rose City | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Rose City completed construction and submitted the COCC for its flood and drainage project.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2021-01-01 | 2021 Q2
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Kountze had engineering design underway for its sewer facilities project.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Kountze had engineering design underway for its sewer facilities project.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Kountze completed engineering design for its sewer facilities project.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Kountze had bid advertisement underway for its Street Improvements project. Construction notice to proceed expected January 2023.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Kountze had construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Kountze had construction underway for its Sewer Facilities project.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Kountz had 50% of construction completed for its sewer facilities project.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Kountze completed construction and is pending submission of construction completion documentation for its Sewer Facilities project.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Kountze completed construction and submitted the COCC for its sewer facilities project
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Kountze submitted grant closeout documents for its sewer lines and lift station project.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Kountze had 95% of construction completed for its sewer facilities. Grant close-out will began when CDR Compliance monitoring closeout letter is issued to the city.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2025-01-01 | 2025 Q2 | During the quarter, there was no change to the activity. The contract closeout is still underway.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Kountze had grant closeout documents under review for its xx project
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_HMID_LMI_20-065-152-C921_Kountze_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Kountze | 2025-10-01 | 2026 Q1 | Activity was completed during the reporting period.
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2021-01-01 | 2021 Q2
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Kountze had engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Kountze had engineering design underway for its street improvements project.
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Kountze completed engineering design for its street improvements project.
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Kountze had bid advertisement underway for its Street Improvements project. Construction notice to proceed expected January 2023.
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Kountze had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Kountze had construction underway for its Street Improvements project.
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Kountz had 50% of construction completed for its street improvements project.
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Kountze completed construction and is pending submission of construction completion documentation for its Street Improvement project.
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Kountze completed construction and submitted the COCC for its streets improvements project
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2024-07-01 | 2024 Q4 | During the reporting period, the city of Kountze had 95% of construction completed for its street improvements. Grant closeout will began when CDR Compliance monitoring closeout letter is issued to the city.
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2025-01-01 | 2025 Q2 | During the quarter, there was no change to the activity. The contract closeout is still underway.
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Kountze had grant closeout documents under review for its xx project
INF_HMID_LMI_20-065-152-C921_Kountze_SI | Street Improvements | Construction/reconstruction of streets | Kountze | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_HMID_LMI_GranteeSupport[H5b]_ACQ | Infrastructure Grantee Support for Subrecipient HMID LMI Acquisition - General Activities | Acquisition - general | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_HMID_LMI_GranteeSupport[H5b]_ACQ | Infrastructure Grantee Support for Subrecipient HMID LMI Acquisition - General Activities | Acquisition - general | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 5028.2 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_ACQ | Infrastructure Grantee Support for Subrecipient HMID LMI Acquisition - General Activities | Acquisition - general | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 572.61 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_ACQ | Infrastructure Grantee Support for Subrecipient HMID LMI Acquisition - General Activities | Acquisition - general | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 742.24 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_ACQ | Infrastructure Grantee Support for Subrecipient HMID LMI Acquisition - General Activities | Acquisition - general | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 305.15 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_ACQ | Infrastructure Grantee Support for Subrecipient HMID LMI Acquisition - General Activities | Acquisition - general | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 128.13 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_ACQ | Infrastructure Grantee Support for Subrecipient HMID LMI Acquisition - General Activities | Acquisition - general | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, activity budget and obligation was revised.
INF_HMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_HMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 93784.82 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 36160.91 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 45429.27 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 19669.71 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 8712.72 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 20928.03 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_HMID_LMI_GranteeSupport[H5b]_HI | Infrastructure Grantee Support for Subrecipient HMID LMI Housing Incentives Activities | Housing incentives to encourage resettlement | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_HMID_LMI_GranteeSupport[H5b]_HI | Infrastructure Grantee Support for Subrecipient HMID LMI Housing Incentives Activities | Housing incentives to encourage resettlement | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 2622.3 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_HI | Infrastructure Grantee Support for Subrecipient HMID LMI Housing Incentives Activities | Housing incentives to encourage resettlement | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 572.61 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_HI | Infrastructure Grantee Support for Subrecipient HMID LMI Housing Incentives Activities | Housing incentives to encourage resettlement | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 742.24 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_HI | Infrastructure Grantee Support for Subrecipient HMID LMI Housing Incentives Activities | Housing incentives to encourage resettlement | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 305.15 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_HI | Infrastructure Grantee Support for Subrecipient HMID LMI Housing Incentives Activities | Housing incentives to encourage resettlement | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 128.13 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2023-07-01 | 2023 Q4 | Activity created.
INF_HMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_HMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 23686.13 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 8111.99 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 10338.98 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 4089.38 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 1641.08 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 4320.71 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_HMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_HMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 94354.94 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 34378.46 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 42827.39 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 18327.77 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 8087.14 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 18926.25 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_HMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_HMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 63067.17 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 22220.97 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 27332.19 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 12124.93 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 5558.98 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 11627.36 - State costs in support of activity delivery.
INF_HMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_HMID_NA_20-065-098-C270_AransasCounty_PLAN | Planning Study | Planning | Aransas, County Of | 2020-04-01 | 2020 Q3
INF_HMID_NA_20-065-098-C270_AransasCounty_PLAN | Planning Study | Planning | Aransas, County Of | 2020-10-01 | 2021 Q1 | During the reporting period, Aransas County continues to carry out administrative services for its planning study project.
INF_HMID_NA_20-065-098-C270_AransasCounty_PLAN | Planning Study | Planning | Aransas, County Of | 2021-01-01 | 2021 Q2 | During the reporting period, Aransas County had planning underway for its Planning Project.
INF_HMID_NA_20-065-098-C270_AransasCounty_PLAN | Planning Study | Planning | Aransas, County Of | 2021-04-01 | 2021 Q3 | During the reporting period, Aransas County had it&apos;s planning project underway.
INF_HMID_NA_20-065-098-C270_AransasCounty_PLAN | Planning Study | Planning | Aransas, County Of | 2021-07-01 | 2021 Q4 | During the reporting period, Aransas County completed the Planning Study for its Fiber Optics Loop project.
INF_HMID_NA_20-065-098-C270_AransasCounty_PLAN | Planning Study | Planning | Aransas, County Of | 2024-01-01 | 2024 Q2 | There were no changes to the budget, descriptions, or performance measures during the reporting period.
INF_HMID_NA_20-065-107-C294_WhartonCounty_PLAN | Planning Study | Planning | Wharton, County of | 2020-04-01 | 2020 Q3
INF_HMID_NA_20-065-107-C294_WhartonCounty_PLAN | Planning Study | Planning | Wharton, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Wharton County continues to carry out administrative services for its planning study project.
INF_HMID_NA_20-065-107-C294_WhartonCounty_PLAN | Planning Study | Planning | Wharton, County of | 2021-10-01 | 2022 Q1 | During the reporting period Wharton County completed 60% of their planning study.
INF_HMID_NA_20-065-107-C294_WhartonCounty_PLAN | Planning Study | Planning | Wharton, County of | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in Budget reallocated.
INF_HMID_NA_20-065-107-C294_WhartonCounty_PLAN | Planning Study | Planning | Wharton, County of | 2022-10-01 | 2023 Q1 | During the reporting period, the County had planning study development underway, however, these expenditures do not align with the expenditures reimbursed for professional services for the planning study during Q4 2022.
INF_HMID_NA_20-065-107-C294_WhartonCounty_PLAN | Planning Study | Planning | Wharton, County of | 2023-07-01 | 2023 Q4 | During the reporting period, the County completed its Planning Study.
INF_HMID_NA_20-065-120-C407_Vidor_PLAN | Planning Study | Planning | Vidor | 2020-04-01 | 2020 Q3
INF_HMID_NA_20-065-120-C407_Vidor_PLAN | Planning Study | Planning | Vidor | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Vidor continues to carry out administrative services for its planning study project.
INF_HMID_NA_20-065-120-C407_Vidor_PLAN | Planning Study | Planning | Vidor | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Vidor continues to carry out administrative services for its planning study project.
INF_HMID_NA_20-065-120-C407_Vidor_PLAN | Planning Study | Planning | Vidor | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Vidor had engineering services 17% complete for its Planning Study project.
INF_HMID_NA_20-065-120-C407_Vidor_PLAN | Planning Study | Planning | Vidor | 2021-07-01 | 2021 Q4 | During the reporting?period,?the City of Vidor had preliminary?engineering design underway for its planning study project.
INF_HMID_NA_20-065-120-C407_Vidor_PLAN | Planning Study | Planning | Vidor | 2021-10-01 | 2022 Q1 | During the reporting?period,?the City of Vidor had preliminary?engineering design underway for its planning study project.
INF_HMID_NA_20-065-120-C407_Vidor_PLAN | Planning Study | Planning | Vidor | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Vidor had engineering design underway for its planning project.
INF_HMID_NA_20-065-120-C407_Vidor_PLAN | Planning Study | Planning | Vidor | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Vidor had engineering design underway for its planning study.
INF_HMID_NA_20-065-120-C407_Vidor_PLAN | Planning Study | Planning | Vidor | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Vidor completed its design plan.
INF_HMID_NA_20-065-120-C407_Vidor_PLAN | Planning Study | Planning | Vidor | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_NA_20-065-121-C408_JeffersonCounty_PLAN | Planning Study | Planning | Jefferson County | 2020-10-01 | 2021 Q1
INF_HMID_NA_20-065-121-C408_JeffersonCounty_PLAN | Planning Study | Planning | Jefferson County | 2021-07-01 | 2021 Q4 | During the reporting?period,?Jefferson County had preliminary?engineering design underway for its planning study project.
INF_HMID_NA_20-065-121-C408_JeffersonCounty_PLAN | Planning Study | Planning | Jefferson County | 2022-01-01 | 2022 Q2 | During the reporting period, Jefferson County had engineering design underway for its planning study project. Correction to payments out of incorrect DRGR activities.
INF_HMID_NA_20-065-121-C408_JeffersonCounty_PLAN | Planning Study | Planning | Jefferson County | 2023-07-01 | 2023 Q4 | During the reporting period, Jefferson County completed construction and is pending submission of construction completion documentation for its planning study project.
INF_HMID_NA_20-065-121-C408_JeffersonCounty_PLAN | Planning Study | Planning | Jefferson County | 2023-10-01 | 2024 Q1 | During the reporting period, Jefferson County completed construction and is pending submission of construction completion documentation for its planning study project.
INF_HMID_NA_20-065-121-C408_JeffersonCounty_PLAN | Planning Study | Planning | Jefferson County | 2025-01-01 | 2025 Q2 | During the reporting period, Jefferson County completed construction and submitted the COCC for its planning study project.
INF_HMID_NA_20-065-121-C408_JeffersonCounty_PLAN | Planning Study | Planning | Jefferson County | 2026-01-01 | 2026 Q2
INF_HMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient HMID Planning Activities | Planning | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_HMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient HMID Planning Activities | Planning | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 5743.52 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient HMID Planning Activities | Planning | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 2319.54 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient HMID Planning Activities | Planning | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 2956.01 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient HMID Planning Activities | Planning | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 1209.31 - State costs in support of activity delivery.
INF_HMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient HMID Planning Activities | Planning | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 507.6 - State costs in support of activity delivery.
INF_HMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient HMID Planning Activities | Planning | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 1328.41 - State costs in support of activity delivery.
INF_HMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient HMID Planning Activities | Planning | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_HMID_SB_20-065-120-C407_Vidor_C&D | Clearance and Demolition | Clearance and Demolition | Vidor | 2020-04-01 | 2020 Q3
INF_HMID_SB_20-065-120-C407_Vidor_C&D | Clearance and Demolition | Clearance and Demolition | Vidor | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Vidor had environmental review underway for its clearance and demolition project.
INF_HMID_SB_20-065-120-C407_Vidor_C&D | Clearance and Demolition | Clearance and Demolition | Vidor | 2020-10-01 | 2021 Q1
INF_HMID_SB_20-065-120-C407_Vidor_C&D | Clearance and Demolition | Clearance and Demolition | Vidor | 2021-10-01 | 2022 Q1 | During the reporting?period,?the City of Vidor had preliminary?engineering design underway for its clearance and demolition project. Review of prior DRGR Vouchers resulted in revisions that lowered the total amount draw for this DRGR Activity.
INF_HMID_SB_20-065-120-C407_Vidor_C&D | Clearance and Demolition | Clearance and Demolition | Vidor | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Vidor had the construction phase (demolition) underway.
INF_HMID_SB_20-065-120-C407_Vidor_C&D | Clearance and Demolition | Clearance and Demolition | Vidor | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Vidor achieved AUGF for its Clearance and Demolition project.
INF_HMID_SB_20-065-120-C407_Vidor_C&D | Clearance and Demolition | Clearance and Demolition | Vidor | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Vidor had demolition underway for its clearance and demolition project.
INF_HMID_SB_20-065-120-C407_Vidor_C&D | Clearance and Demolition | Clearance and Demolition | Vidor | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Vidor demo and cleared 11 homes.
INF_HMID_SB_20-065-120-C407_Vidor_C&D | Clearance and Demolition | Clearance and Demolition | Vidor | 2025-07-01 | 2025 Q4 | During the reporting period, a contract amendment was executed that reallocated the budget after cancelling the Urgent Need Street Improvements project.
INF_HMID_SB_GranteeSupport[H5b]_C&D | Infrastructure Grantee Support for Subrecipient HMID SB Clearance and Demolition Activities | Clearance and Demolition | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_HMID_SB_GranteeSupport[H5b]_C&D | Infrastructure Grantee Support for Subrecipient HMID SB Clearance and Demolition Activities | Clearance and Demolition | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 1202.95 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_SB_GranteeSupport[H5b]_C&D | Infrastructure Grantee Support for Subrecipient HMID SB Clearance and Demolition Activities | Clearance and Demolition | Texas General Land Office | 2025-01-01 | 2025 Q2 | Increased the activity budget and obligation as additional funds for state costs in support of activity delivery was allocated to the Local Infrastructure Program.
INF_HMID_SB_GranteeSupport[H5b]_C&D | Infrastructure Grantee Support for Subrecipient HMID SB Clearance and Demolition Activities | Clearance and Demolition | Texas General Land Office | 2025-07-01 | 2025 Q4 | Reduced the activity budget and obligation to increase the other Grantee Support activities that had a higher percentage of total projects.
INF_HMID_SB_GranteeSupport[H5b]_C&D | Infrastructure Grantee Support for Subrecipient HMID SB Clearance and Demolition Activities | Clearance and Demolition | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. State costs in support of activity delivery.
INF_HMID_UN_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2019-10-01 | 2020 Q1
INF_HMID_UN_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2020-07-01 | 2020 Q4 | During the reporting period, the Jasper County had engineering design underway for its street improvements project.
INF_HMID_UN_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2020-10-01 | 2021 Q1
INF_HMID_UN_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2021-01-01 | 2021 Q2 | During the reporting period, Jasper County had construction underway for its Street Improvement Project.
INF_HMID_UN_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2021-04-01 | 2021 Q3 | During the reporting period, Jasper County had construction procurement underway for its Street Improvement project.
INF_HMID_UN_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2021-10-01 | 2022 Q1 | During the reporting?period,?Jasper County had 59% of construction?complete for its street improvement project.
INF_HMID_UN_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2022-01-01 | 2022 Q2 | During the reporting period, Jasper County completed construction and submitted the COCC for its street improvement project.
INF_HMID_UN_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2022-04-01 | 2022 Q3 | During the reporting period, construction was underway for Jasper County&apos;s street improvement project.
INF_HMID_UN_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2022-07-01 | 2022 Q4 | During the reporting period, amendment was completed to process final payments.
INF_HMID_UN_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2022-10-01 | 2023 Q1 | During the reporting period, the County completed construction payment and submitted COCCs and As-Builts
INF_HMID_UN_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-013-C049_JasperCounty | Street Improvements | Construction/reconstruction of streets | Jasper County | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_UN_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2019-10-01 | 2020 Q1
INF_HMID_UN_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Nome completed engineering design for its street improvement project.
INF_HMID_UN_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Nome had 50% of construction underway for its street improvement project.
INF_HMID_UN_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Nome had construction underway for its Street Improvement project.
INF_HMID_UN_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Nome submitted grant closeout documents for its street improvement project.
INF_HMID_UN_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_HMID_UN_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Nome had grant closeout documents approved for its street improvements project.
INF_HMID_UN_20-065-027-C092_Nome | Street Improvements | Construction/reconstruction of streets | Nome | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Nome had grant closeout documents approved for its street improvement project.
INF_HMID_UN_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2019-10-01 | 2020 Q1
INF_HMID_UN_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Dickinson had construction procurement underway for its flood and drainage facilities project.
INF_HMID_UN_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Dickinson had construction underway for its Flood and Drainage project.
INF_HMID_UN_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Dickinson had construction underway for its Flood and Drainage project.
INF_HMID_UN_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Dickinson had 50% of construction complete for its Flood and Drainage Facilities project.
INF_HMID_UN_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2022-01-01 | 2022 Q2 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
INF_HMID_UN_20-065-029-C096_Dickinson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dickinson | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Dickinson had 70% of construction complete for its Flood and Drainage Facilities Project.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2020-01-01 | 2020 Q2
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Groves completed environmental review for its sewer facilities project.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Groves completed engineering design for its sewer facilities project.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Groves had engineering design complete for its sewer facilities project.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Groves had construction procurement underway for its Sewer Facilities project.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2021-07-01 | 2021 Q4 | ?During the reporting?period,?the City of Groves had 50% of construction?underway/complete for its sewer facilities project.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Groves had 50% of construction underway/complete for its sewer facilities project.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Groves completed construction and is pending submission of construction completion documentation for its sewer facilities project.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Groves had construction complete and the COCC underway for its sewer facilities project.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Groves completed construction and submitted the Certificate of Construction Completion for its sewer facilities project.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Aransas Pass had 75% of construction underway for its Flood and Drainage Facilities project.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_UN_20-065-039-C120_Groves_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Groves | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Groves completed construction and submitted the COCC for its sewer facilities project.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2020-01-01 | 2020 Q2
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Groves completed environmental review for its street improvement project.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Groves completed engineering design for its street improvement project.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Groves had engineering design complete for its street improvement project.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2021-07-01 | 2021 Q4 | ?During the reporting?period,?the City of Groves had 50% of construction?underway/complete for its street improvements project.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Groves had 50% of construction underway/complete for its street improvement project.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2022-01-01 | 2022 Q2 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Groves had construction complete and the COCC underway for its street improvement project.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Groves had construction complete and the Certificate of Construction Completion underway for its street improvements project.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Groves completed engineering design for its street improvements project.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2023-04-01 | 2023 Q3 | During the reporting?period,?the City of Groves had 50% of construction?underway/complete for its street improvement project.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Groves completed construction and is pending submission of construction completion documentation for its street improvement project. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Groves completed construction and submitted the COCC for its street improvement project.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Groves completed construction and ending submission of construction completion documentation for its street improvements project.
INF_HMID_UN_20-065-039-C120_Groves_SI | Street Improvements | Construction/reconstruction of streets | Groves | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Groves completed construction and submitted the COCC for its street improvements project.
INF_HMID_UN_20-065-049-C156_China | Street Improvements | Construction/reconstruction of streets | China | 2020-01-01 | 2020 Q2
INF_HMID_UN_20-065-049-C156_China | Street Improvements | Construction/reconstruction of streets | China | 2020-10-01 | 2021 Q1 | During the reporting period, the City of China completed engineering design for its street improvement project.
INF_HMID_UN_20-065-049-C156_China | Street Improvements | Construction/reconstruction of streets | China | 2021-04-01 | 2021 Q3 | During the reporting period, the City of China had construction underway for its Street Improvement project.
INF_HMID_UN_20-065-049-C156_China | Street Improvements | Construction/reconstruction of streets | China | 2021-10-01 | 2022 Q1 | During the reporting period, the City of China submitted grant closeout documents for its street improvement project.
INF_HMID_UN_20-065-049-C156_China | Street Improvements | Construction/reconstruction of streets | China | 2022-07-01 | 2022 Q4 | During the reporting period, the City of China had grant closeout documents under review for its street improvements project.
INF_HMID_UN_20-065-049-C156_China | Street Improvements | Construction/reconstruction of streets | China | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2020-01-01 | 2020 Q2
INF_HMID_UN_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2020-07-01 | 2020 Q4 | During the reporting period, Calhoun County had environmental review underway and engineering design underway for it&apos;s public facilities project.
INF_HMID_UN_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2020-10-01 | 2021 Q1 | During the reporting period, Calhoun County had construction underway for its Public Facilities project.
INF_HMID_UN_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2021-07-01 | 2021 Q4 | During the reporting period, Calhoun County had construction underway for its public facilities project.
INF_HMID_UN_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2021-10-01 | 2022 Q1 | During the reporting period, Calhoun County had construction procurement underway for its Public Facilities project.
INF_HMID_UN_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2022-01-01 | 2022 Q2 | During the reporting period, Calhoun County had construction complete and the CoCC underway for its Public Facilities project.
INF_HMID_UN_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2022-07-01 | 2022 Q4 | During the reporting period, the County Calhoun completed construction and submitted the Certificate of Construction Completion for its Public Facilities project.
INF_HMID_UN_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2023-04-01 | 2023 Q3 | Area Benefit type corrected. Activty is in HUD most impacted and distressed zip code, and was appropriately added a MID budget. MID expenditures caught up in quarter.
INF_HMID_UN_20-065-064-C182_CalhounCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | CALHOUN COUNTY | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_UN_20-065-069-C195_Lumberton | Street Improvements | Construction/reconstruction of streets | Lumberton | 2020-01-01 | 2020 Q2
INF_HMID_UN_20-065-069-C195_Lumberton | Street Improvements | Construction/reconstruction of streets | Lumberton | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Lumberton completed engineering design for its street improvement project.
INF_HMID_UN_20-065-069-C195_Lumberton | Street Improvements | Construction/reconstruction of streets | Lumberton | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Lumberton had engineering design complete for its street improvement project.
INF_HMID_UN_20-065-069-C195_Lumberton | Street Improvements | Construction/reconstruction of streets | Lumberton | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Lumberton had construction underway for its Street Improvement project.
INF_HMID_UN_20-065-069-C195_Lumberton | Street Improvements | Construction/reconstruction of streets | Lumberton | 2021-07-01 | 2021 Q4 | ?During the reporting?period,?the City of Lumberton had 50% of construction?underway/complete for its street improvements project.
INF_HMID_UN_20-065-069-C195_Lumberton | Street Improvements | Construction/reconstruction of streets | Lumberton | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Lumberton had 50% of construction underway/complete for its street improvement project.
INF_HMID_UN_20-065-069-C195_Lumberton | Street Improvements | Construction/reconstruction of streets | Lumberton | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Lumberton had construction activities underway for its street improvements project.
INF_HMID_UN_20-065-069-C195_Lumberton | Street Improvements | Construction/reconstruction of streets | Lumberton | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Lumberton had construction activities underway for its street improvements project.
INF_HMID_UN_20-065-069-C195_Lumberton | Street Improvements | Construction/reconstruction of streets | Lumberton | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Lumberton has completed construction is awaiting a budget change request to finalize closeout for its street improvements project.
INF_HMID_UN_20-065-069-C195_Lumberton | Street Improvements | Construction/reconstruction of streets | Lumberton | 2023-01-01 | 2023 Q2 | Amendment moved funds to related activity.
INF_HMID_UN_20-065-069-C195_Lumberton | Street Improvements | Construction/reconstruction of streets | Lumberton | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Lumberton has completed construction and is in the closeout process.
INF_HMID_UN_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2020-01-01 | 2020 Q2
INF_HMID_UN_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Colorado County had environmental review and engineering design underway for its water facilities project.
INF_HMID_UN_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Colorado County had 50% of construction underway for its flood and drainage facilities project.
INF_HMID_UN_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Colorado County had 50% of construction underway/complete for its Flood and Drainage Facilities project.
INF_HMID_UN_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2022-01-01 | 2022 Q2 | During the reporting period, the Colorado County submitted grant closeout documents for its Flood Drainage Facilities project.
INF_HMID_UN_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2022-04-01 | 2022 Q3 | During the reporting period, the Colorado County had 50% of construction underway/complete for its Flood and Drainage Facilities project.
INF_HMID_UN_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2023-07-01 | 2023 Q4 | During the reporting period, the Colorado County had grant closeout documents under review for its F&D project.
INF_HMID_UN_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2023-10-01 | 2024 Q1 | During the reporting period, the Colorado County had grant closeout documents under review for its F&D project - pending correction by Finance/BSO of it&apos;s Budget/DRGR activity amounts
INF_HMID_UN_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2024-04-01 | 2024 Q3 | Activity has been administratively closed during the quarter. All payments have been completed and all accomplishments were entered. Activity status has been updated to Completed.
INF_HMID_UN_20-065-084-C243_PortNeches_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2022-07-01 | 2022 Q4 | Activity created during the quarter.
INF_HMID_UN_20-065-084-C243_PortNeches_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-084-C243_PortNeches_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2023-07-01 | 2023 Q4 | Amendment reallocated unspent funds from related activity.
INF_HMID_UN_20-065-084-C243_PortNeches_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2024-04-01 | 2024 Q3 | During the reporting?period,?the City of Port Neches had 50% of construction?underway/complete for its Sewer facilities project.
INF_HMID_UN_20-065-084-C243_PortNeches_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Port Neches had 75% of construction complete for its sewer facilities project.
INF_HMID_UN_20-065-084-C243_PortNeches_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Port Neches completed construction and is pending submission of construction completion documentation for its sewer facilities project.
INF_HMID_UN_20-065-084-C243_PortNeches_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Port Neches completed construction and submitted the COCC for its sewer facilities project.
INF_HMID_UN_20-065-084-C243_PortNeches_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Port Neches | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Port Neches submitted grant closeout documents for its sewer facilities project.
INF_HMID_UN_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2020-01-01 | 2020 Q2
INF_HMID_UN_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2020-10-01 | 2021 Q1 | During the reporting period, Tyler County had construction procurement underway for it&apos;s water facilities project.
INF_HMID_UN_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2021-01-01 | 2021 Q2 | During the reporting period, Tyler County had construction underway for it&apos;s Water Facilities project.
INF_HMID_UN_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2021-04-01 | 2021 Q3 | During the reporting period, Tyler County had construction underway for its water facilities improvement project.
INF_HMID_UN_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2021-10-01 | 2022 Q1 | During the reporting period, Tyler County had construction underway more than 50% complete for its Water Facilities project.
INF_HMID_UN_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2022-04-01 | 2022 Q3 | During the reporting period, Tyler County billed for completion of Construction NTP milestone for GA only for it&apos;s WF project. Construction was completed and COCC submitted in 2/2022.
INF_HMID_UN_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2022-07-01 | 2022 Q4 | During the reporting period, Tyler County had 95% construction complete on its Water Facilities project. Construction expected to be completed within next quarter.
INF_HMID_UN_20-065-087-C248_TylerCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Tyler County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2020-01-01 | 2020 Q2
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Rockport had engineering design underway for its Flood and Drainage Facilities project.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Rockport had engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Rockport had engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2021-01-01 | 2021 Q2
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Rockport had engineering design underway for its Flood and Drainage Facilities project.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Rockport had construction procurement underway for its Flood and Drainage project.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Rockport completed environmental review for its Flood and Drainage projects.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Rockport had engineering design underway for its Flood and Drainage project.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Rockport completed engineering design for its Flood and Drainage projects.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Rockport had construction underway for its Flood and Drainage project.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Rockport had construction underway for its food and drainage faculties project.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Rockport had preliminary engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Rockport had 50% of construction underway/complete for its Flood and Drainage Facilities project.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2023-07-01 | 2023 Q4 | During the reporting?period,?the City of Rockport had 50% of construction?underway/complete for its Flood and Drainage project.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Rockport completed construction and is pending submission of construction completion documentation for its Flood and Drainage project. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2025-04-01 | 2025 Q3 | During the reporting?period,?the City of Rockport had at least 50% of construction?underway/complete for its Flood and Drainage project.
INF_HMID_UN_20-065-090-C252_Rockport | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Rockport | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Rockport had at least 87% of construction underway/complete for its Flood and drainage project.
INF_HMID_UN_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2020-01-01 | 2020 Q2
INF_HMID_UN_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2020-10-01 | 2021 Q1 | During the reporting period, San Jacinto County had engineering design underway for it&apos;s street improvements project.
INF_HMID_UN_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2021-01-01 | 2021 Q2 | During the reporting period, San Jacinto County had construction underway for it&apos;s Street Improvements project.
INF_HMID_UN_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2021-07-01 | 2021 Q4 | During the reporting period, San Jacinto County had construction underway for it&apos;s Street Improvements project.
INF_HMID_UN_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2021-10-01 | 2022 Q1 | During the reporting period, San Jacinto County had construction underway for its Street Improvements project.
INF_HMID_UN_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2022-01-01 | 2022 Q2 | During the reporting period, San Jacinto County had construction underway and 1 CR approved for it&apos;s Street Improvements project.
INF_HMID_UN_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2022-04-01 | 2022 Q3 | During the reporting period, San Jacinto County completed construction and submitted the COCC for it&apos;s SI project.
INF_HMID_UN_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2022-07-01 | 2022 Q4 | During the reporting period, San Jacinto County completed construction of its Street Improvements project.
INF_HMID_UN_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2023-04-01 | 2023 Q3 | During the reporting period, San Jacinto County had closeout preparation activities underway for its Steet project.
INF_HMID_UN_20-065-093-C261_SanJacintoCounty | Street Improvements | Construction/reconstruction of streets | San Jacinto County | 2023-07-01 | 2023 Q4 | During the reporting period, San Jacinto County had CR2 underway to add DETBOG reallocation funding to it&apos;s already expired contract for Street Improvements activity.
INF_HMID_UN_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2020-01-01 | 2020 Q2
INF_HMID_UN_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2020-10-01 | 2021 Q1 | During the reporting period, Victoria County had environmental review and engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2021-04-01 | 2021 Q3 | During the reporting period, Victoria County completed environmental review and engineering design is underway at 75% complete for its Flood and Drainage project.
INF_HMID_UN_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2021-07-01 | 2021 Q4 | During the reporting period, Victoria County had completed environmental review and engineering design for its flood and drainage project.
INF_HMID_UN_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2021-10-01 | 2022 Q1 | During the reporting period, Victoria County had construction procurement underway for its Flood and Drainage project.
INF_HMID_UN_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2022-01-01 | 2022 Q2 | During the reporting period, Victoria County completed engineering design for its Flood and Drainage project.
INF_HMID_UN_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2022-07-01 | 2022 Q4 | During the reporting period, Victoria County completed construction procurement for its Flood and Drainage project.
INF_HMID_UN_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2023-01-01 | 2023 Q2 | During the reporting period, Victoria County had completed construction for its Flood and Drainage activity.
INF_HMID_UN_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2023-04-01 | 2023 Q3 | During the reporting period, Victoria County completed construction and submitted the COCC for its Flood and Drainage project.
INF_HMID_UN_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2023-07-01 | 2023 Q4 | During the reporting period, Victoria County had completed construction and submitted the COCC its flood and drainage project.
INF_HMID_UN_20-065-094-C262_VictoriaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Victoria County | 2024-10-01 | 2025 Q1 | During the reporting period, Victoria County had grant closeout documents under review for its Flood and Drainage project.
INF_HMID_UN_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2020-01-01 | 2020 Q2
INF_HMID_UN_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Liberty County had construction procurement underway for its street improvements project.
INF_HMID_UN_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2021-01-01 | 2021 Q2 | During the reporting period, Liberty County had construction procurement underway for its street improvements project. The 100% Design milestone achieved with the submission of a copy of their plans and specifications.
INF_HMID_UN_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Liberty County had construction underway for its street improvements project. The Construction Notice-to-Proceed was issued in May 2021.
INF_HMID_UN_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Liberty County had construction underway for its street improvements project.
INF_HMID_UN_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Liberty County had construction underway for its street improvements project. Review of prior DRGR Vouchers resulted in revisions that lowered the total amount draw for this DRGR Activity.
INF_HMID_UN_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Liberty County had construction underway for its street improvements project.
INF_HMID_UN_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2022-04-01 | 2022 Q3 | During the reporting period, Liberty County had construction underway for its street improvements project.
INF_HMID_UN_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2022-07-01 | 2022 Q4 | During the reporting period, Liberty County submitted grant closeout documents for its street improvements project. Closeout review underway.
INF_HMID_UN_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2023-01-01 | 2023 Q2 | During the reporting period, Liberty County had grant closeout documents under review for its street improvements project.
INF_HMID_UN_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-095-C264_LibertyCounty | Street Improvements | Construction/reconstruction of streets | Liberty, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Liberty County had grant closeout documents under review for its street improvements project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2020-10-01 | 2021 Q1 | During the reporting period, Aransas County had engineering design underway for its public facilities project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2021-01-01 | 2021 Q2 | During the reporting period, Aransas County had design underway for its Public Facilities Project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2021-04-01 | 2021 Q3 | During the reporting period, Aransas County completed environmental review for its Public Facilities project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2021-07-01 | 2021 Q4 | During the reporting period, Aransas County completed engineering design for its Public Facilities project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2021-10-01 | 2022 Q1 | During the reporting period, Aransas County had construction procurement underway for its Public Facilities projects.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2022-01-01 | 2022 Q2 | During the reporting period, Aransas County had construction underway for its Public Facilities project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2022-04-01 | 2022 Q3 | During the reporting period, the County of Aransas had construction underway for its Public Facilities projects.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2022-07-01 | 2022 Q4 | During the reporting period, the County of Aransas had construction underway for its Public Facilities projects.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2022-10-01 | 2023 Q1 | During the reporting period, Aransas County had 50% of construction underway/complete for its public facilities project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2023-01-01 | 2023 Q2 | During the reporting period, Aransas County had construction underway for its public facilities.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2023-04-01 | 2023 Q3 | During the reporting period, the Aransas County completed construction and submitted the COCC for its public facilities project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2023-07-01 | 2023 Q4 | During the reporting period, Aransas County had construction underway for its Public Facilities project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2023-10-01 | 2024 Q1 | During the reporting period, Aransas County had 50% of construction underway/complete for its Public Facility project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2024-01-01 | 2024 Q2 | During the reporting?period,?the Aransas County had 50% of construction?underway/complete for its Public Facilities project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2024-04-01 | 2024 Q3 | During the reporting period, the Aransas County had 50% of construction underway/complete for its Public Facilities project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2024-07-01 | 2024 Q4 | During the reporting period, the Aransas County had 50.01% of construction underway/complete for its Public Facilities project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2024-10-01 | 2025 Q1 | During the reporting?period,?Aransas County had 80% of construction?underway/complete for its Public Facilities project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2025-01-01 | 2025 Q2 | During this reporting period, the Grant Administrator billed for the following items related to the Public Facilities projects: KOW, Startups, Environmental NTP, Environmental ERR, Bid Ad, Construction NTP.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2025-04-01 | 2025 Q3 | During the reporting period, Aransas County had construction?underway at over 50% completion for its Downtown Anchor Building PF project.
INF_HMID_UN_20-065-098-C270_AransasCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Aransas, County Of | 2025-07-01 | 2025 Q4 | During the reporting?period,?the Aransas County had 82% of construction?underway/complete for its Public Facilities project (DTA).
INF_HMID_UN_20-065-106-C288_Pearland | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | PEARLAND, CITY OF | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-106-C288_Pearland | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | PEARLAND, CITY OF | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Pearland completed construction and is pending submission of construction completion documentation for its flood and drainage project.
INF_HMID_UN_20-065-106-C288_Pearland | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | PEARLAND, CITY OF | 2026-01-01 | 2026 Q2
INF_HMID_UN_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2020-07-01 | 2020 Q4 | During the reporting period, Wharton County had acquisition, environmental review and engineering design underway for its flood and drainage facilities project.
INF_HMID_UN_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Wharton County had environmental review underway for its flood and drainage facilities project.
INF_HMID_UN_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Wharton County had engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in Budget reallocated, Measures updated
INF_HMID_UN_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2022-10-01 | 2023 Q1 | During the reporting period, the County had engineering design underway for its flood and drainage project, however, these expenditures do not align with the reimbursement for the aforementioned professional services.
INF_HMID_UN_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2023-07-01 | 2023 Q4 | During the reporting period, the County completed acquisition for its flood and drainage project.
INF_HMID_UN_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_UN_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2025-01-01 | 2025 Q2 | During the reporting period, Wharton County completed construction for its Flood and Drainage projects.
INF_HMID_UN_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2025-04-01 | 2025 Q3 | During the reporting period, Wharton County had construction underway for its Flood and Drainage project.
INF_HMID_UN_20-065-107-C294_WhartonCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Wharton, County of | 2025-07-01 | 2025 Q4 | During the reporting period, a contract amendment was executed that reallocated funding from the Urgent Need Flood and Drainage activity to the LMI Flood and Drainage activity.
INF_HMID_UN_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2020-07-01 | 2020 Q4 | During the reporting period, Wharton County had environmental review and engineering design underway for its sewer facilities project.
INF_HMID_UN_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2020-10-01 | 2021 Q1
INF_HMID_UN_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Wharton County completed the environmental review for their sewer facilities projects.
INF_HMID_UN_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Wharton County completed engineering design for its sewer facilities project.
INF_HMID_UN_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Wharton County had construction procurement underway for its public facilities projects .
INF_HMID_UN_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in Activity cancelled. Activity will be cancelled, voucher reconciliation is ongoing and once completed activity will be removed and actual accomplishments updated.
INF_HMID_UN_20-065-107-C294_WhartonCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2023-04-01 | 2023 Q3 | Projected beneficiaries reduced due to pending cancellation.
INF_HMID_UN_20-065-107-C294_WhartonCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-107-C294_WhartonCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2020-07-01 | 2020 Q4 | During the reporting period, Wharton County had environmental review and engineering design underway for its water facilities project.
INF_HMID_UN_20-065-107-C294_WhartonCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2020-10-01 | 2021 Q1
INF_HMID_UN_20-065-107-C294_WhartonCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Wharton County completed the environmental review for their water facilities projects.
INF_HMID_UN_20-065-107-C294_WhartonCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Wharton County completed engineering design for its sewer facilities project.
INF_HMID_UN_20-065-107-C294_WhartonCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Wharton County had construction procurement underway for its public facilities projects.
INF_HMID_UN_20-065-107-C294_WhartonCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in Budget reallocated, Measures updated
INF_HMID_UN_20-065-107-C294_WhartonCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2022-10-01 | 2023 Q1 | During the reporting period, the County had construction underway for its public facilities project, however, this expenditure was reimbursed in Q3 2022
INF_HMID_UN_20-065-107-C294_WhartonCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-107-C294_WhartonCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2023-07-01 | 2023 Q4 | During the reporting period, the County did not have any activity for its water facility project.
INF_HMID_UN_20-065-107-C294_WhartonCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Wharton, County of | 2025-04-01 | 2025 Q3 | During the reporting period, Wharton County completed construction and is pending submission of construction completion documentation for its Sewer project.
INF_HMID_UN_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Aransas Pass had engineering design complete for its Flood and Drainage project.
INF_HMID_UN_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2021-07-01 | 2021 Q4 | During the reporting period, Aransas Pass had completed environmental review and engineering design for its flood and drainage project.
INF_HMID_UN_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Aransas Pass had construction underway for its Flood and Drainage project.
INF_HMID_UN_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Aransas Pass had 50% of construction underway/complete for its Flood and Drainage project.
INF_HMID_UN_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Aransas Pass had 50% of construction underway/complete for its Flood and Drainage project.
INF_HMID_UN_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Aransas Pass had 75% of construction underway for its Flood and Drainage Facilities project.
INF_HMID_UN_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Aransas Pass had 50% of construction complete for its flood and drainage project.
INF_HMID_UN_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2023-04-01 | 2023 Q3 | During the reporting?period,?the City of Aransas Pass had 90% of construction?underway/complete for its flood and drainage facility project.
INF_HMID_UN_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2023-07-01 | 2023 Q4 | During the Reporting Period, City of Aransas Pass had 100% of construction Complete for its current flood and drainage facility project, submitted amendment request for additional projects to use cost savings.
INF_HMID_UN_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2024-04-01 | 2024 Q3 | Activity budget and obligation adjusted due to a contract amendment.
INF_HMID_UN_20-065-109-C303_AransasPass_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Aransas Pass | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Aransas Pass completed construction and submitted the COCC for its flood and drainage project.
INF_HMID_UN_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2022-07-01 | 2022 Q4 | Activity created during the quarter.
INF_HMID_UN_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2024-10-01 | 2025 Q1 | During the reporting?period,?Refugio County had 95% of construction?underway/complete for its Public Facilities project.
INF_HMID_UN_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2025-01-01 | 2025 Q2 | During the reporting period, Refugio County completed construction and submitted the COCC for its public facilities project.
INF_HMID_UN_20-065-110-C306_RefugioCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Refugio County | 2026-01-01 | 2026 Q2
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2020-07-01 | 2020 Q4 | During the reporting period, Refugio County had environmental review underway for its street improvements project.
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2020-10-01 | 2021 Q1 | During the reporting period, Refugio County had engineering design underway for its street improvements project.
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2021-04-01 | 2021 Q3 | During the reporting period, Refugio County completed environmental review for its street improvements project.
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2021-10-01 | 2022 Q1 | During the reporting period, Refugio County completed construction procurement for its street improvements project.
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2022-04-01 | 2022 Q3 | During the reporting period, Refugio County had construction underway for its street improvements project.
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2022-07-01 | 2022 Q4 | During the reporting period, Refugio County had 50% of construction underway/complete for its street improvements project.
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2022-10-01 | 2023 Q1 | During the reporting period, Refugio County completed construction and is pending submission of construction completion documentation for its street improvements project
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2023-10-01 | 2024 Q1 | During the reporting period, Refugio County completed construction and submitted the COCC for its Street Improvement project. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2024-10-01 | 2025 Q1 | During the reporting period, a contract amendment was executed to adjust project scope and budgets.
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2025-01-01 | 2025 Q2 | During the reporting period, Refugio County completed construction and submitted the COCC for its street improvements project.
INF_HMID_UN_20-065-110-C306_RefugioCounty_SI | Street Improvements | Construction/reconstruction of streets | Refugio County | 2025-04-01 | 2025 Q3 | During the reporting period, Refugio County completed construction and submitted the COCC for its street improvements project.
INF_HMID_UN_20-065-114-C313_Gregory | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | GREGORY, CITY OF | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-114-C313_Gregory | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | GREGORY, CITY OF | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Gregory had environmental review underway for its Sewer project.
INF_HMID_UN_20-065-114-C313_Gregory | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | GREGORY, CITY OF | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Gregory had procurement activities underway for its sewer facilities project.
INF_HMID_UN_20-065-114-C313_Gregory | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | GREGORY, CITY OF | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-114-C313_Gregory | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | GREGORY, CITY OF | 2023-07-01 | 2023 Q4 | During the Reporting Period, City of Gregory had 100% of construction Complete for its current flood and drainage facility project, COCC submitted.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Vidor had environmental review and engineering design underway for its street improvement project.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Vidor had environmental review underway for its street improvements project.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Vidor had engineering design 53% complete for its Street Improvement project.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Vidor had engineering design underway for its street improvements project.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2021-10-01 | 2022 Q1 | During the reporting?period,?the City of Vidor had preliminary?engineering design underway for its street improvement project.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Vidor had engineering underway for its street improvements project.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Vidor had engineering design underway for LMI Street Improvements. Correction to allocation.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2022-10-01 | 2023 Q1 | During the reporting period, engineering design was underway for street improvements.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Vidor had engineering design 94% complete for its street improvement project.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2023-04-01 | 2023 Q3 | Amendment moved funds to related activity and decreased projected performance measures.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Vidor reporting engineering design underway. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Vidor held Pre-Construction conference on 08/27/2024 for 1 UN SI project site, Aery Road. NTP issued for 10/07/2024. Extension request submitted 09/24/24.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2024-10-01 | 2025 Q1 | During the reporting?period,?the City of Vidor had 60% of construction?underway for its SI project.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2025-01-01 | 2025 Q2 | During the reporting?period,?the City of Vidor had 85% of construction?complete for its street improvement project.
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2025-04-01 | 2025 Q3 | During the reporting?period,?the City of Vidor had 85% of construction?complete for its street improvement project
INF_HMID_UN_20-065-120-C407_Vidor_SI | Street Improvements | Construction/reconstruction of streets | Vidor | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Vidor completed construction and submitted the COCC for its Street Improvements.
INF_HMID_UN_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2020-10-01 | 2021 Q1
INF_HMID_UN_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2022-01-01 | 2022 Q2 | During the reporting period, Jefferson County had engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2023-01-01 | 2023 Q2 | During the reporting period, Jefferson County completed engineering design for its flood and drainage project.
INF_HMID_UN_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2023-10-01 | 2024 Q1 | During the reporting period, Jefferson County had preliminary engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2024-07-01 | 2024 Q4 | During the reporting period, Jefferson County had construction underway for its flood and drainage project.
INF_HMID_UN_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2025-01-01 | 2025 Q2 | During the reporting?period,?Jefferson County had 65% of construction?underway/complete for its flood and drainage project.
INF_HMID_UN_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2025-04-01 | 2025 Q3 | During the reporting?period,?Jefferson County had 95% of construction?complete for its flood and drainage project.
INF_HMID_UN_20-065-121-C408_JeffersonCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Jefferson County | 2026-01-01 | 2026 Q2
INF_HMID_UN_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Matagorda County had environmental review underway for its street improvements project.
INF_HMID_UN_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Matagorda County had engineering design underway for its Street Improvements project.
INF_HMID_UN_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Matagorda County completed engineering design for its Street Improvements project.
INF_HMID_UN_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2022-04-01 | 2022 Q3 | During the reporting period, the County of Matagorda had environmental review underway for its Streets Improvements project.
INF_HMID_UN_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Matagorda County had construction procurement underway for its Street improvements project.
INF_HMID_UN_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_UN_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Matagorda County had construction underway for its Street Improvements (Carancahua Street Bridge) project.
INF_HMID_UN_20-065-123-C430_MatagordaCounty_SI | Street Improvements | Construction/reconstruction of streets | Matagorda, County of | 2025-01-01 | 2025 Q2 | Revised a portion of the activity budget and obligation to the LMI Street Improvements activity.
INF_HMID_UN_20-065-125-C436_WoodbranchVillage | Water Facilities | Construction/reconstruction of water/sewer lines or systems | WOODBRANCH VILLAGE, CITY HALL | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-125-C436_WoodbranchVillage | Water Facilities | Construction/reconstruction of water/sewer lines or systems | WOODBRANCH VILLAGE, CITY HALL | 2021-04-01 | 2021 Q3 | During the report period, the City of Woodbranch village had completed construction at 99% and is pending submission of construction completion documentation for its Water Facilities project.
INF_HMID_UN_20-065-125-C436_WoodbranchVillage | Water Facilities | Construction/reconstruction of water/sewer lines or systems | WOODBRANCH VILLAGE, CITY HALL | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Woodbranch Village had construction procurement underway for its Water Facilities project.
INF_HMID_UN_20-065-125-C436_WoodbranchVillage | Water Facilities | Construction/reconstruction of water/sewer lines or systems | WOODBRANCH VILLAGE, CITY HALL | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Woodbranch Village completed construction procurement for its Water Facilities project. The NTOP is expected to be issued 7/13/22.
INF_HMID_UN_20-065-125-C436_WoodbranchVillage | Water Facilities | Construction/reconstruction of water/sewer lines or systems | WOODBRANCH VILLAGE, CITY HALL | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Woodbranch Village had 50% of construction underway/complete for its Water Facilities project.
INF_HMID_UN_20-065-125-C436_WoodbranchVillage | Water Facilities | Construction/reconstruction of water/sewer lines or systems | WOODBRANCH VILLAGE, CITY HALL | 2023-01-01 | 2023 Q2 | o During the reporting period, the City of Woodbranch Village had construction procurement underway for its Water project.
INF_HMID_UN_20-065-125-C436_WoodbranchVillage | Water Facilities | Construction/reconstruction of water/sewer lines or systems | WOODBRANCH VILLAGE, CITY HALL | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Woodbranch Village had construction underway for its Water Facilities project.
INF_HMID_UN_20-065-125-C436_WoodbranchVillage | Water Facilities | Construction/reconstruction of water/sewer lines or systems | WOODBRANCH VILLAGE, CITY HALL | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Woodbranch Village completed construction and is pending submission of construction completion documentation for its Water Facilities project.
INF_HMID_UN_20-065-125-C436_WoodbranchVillage | Water Facilities | Construction/reconstruction of water/sewer lines or systems | WOODBRANCH VILLAGE, CITY HALL | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Woodbranch Village had grant closeout documents under review for its water facilities project.
INF_HMID_UN_20-065-126-C437_Dayton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dayton | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-126-C437_Dayton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dayton | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Dayton had environmental review underway for its flood and drainage facilities improvements project.
INF_HMID_UN_20-065-126-C437_Dayton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dayton | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Dayton had construction procurement underway for its flood and drainage facilities improvements project. The bid was awarded but the contract has not been executed.
INF_HMID_UN_20-065-126-C437_Dayton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dayton | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Dayton had engineering re-design underway for its flood and drainage facilities improvements project.
INF_HMID_UN_20-065-126-C437_Dayton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dayton | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_UN_20-065-126-C437_Dayton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dayton | 2023-10-01 | 2024 Q1 | During the reporting the City of Dayton completed construction and is pending submission of construction completion documentation for its flood and drainage project.
INF_HMID_UN_20-065-126-C437_Dayton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dayton | 2024-04-01 | 2024 Q3 | During the reporting period, the City Dayton submitted grant closeout documents for its flood and drainage project.
INF_HMID_UN_20-065-126-C437_Dayton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Dayton | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Dayton had grant closeout documents under review for its flood and drainage project.
INF_HMID_UN_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2020-07-01 | 2020 Q4
INF_HMID_UN_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Danbury had environmental review underway for it Sewer Facilities project. During the reporting period, the City of Danbury had engineering design underway for its Sewer Facilities project.
INF_HMID_UN_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Danbury amended their contract to adjust projected beneficiaries and budgets.
INF_HMID_UN_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Danbury had grant closeout documents under review for its Sewer Facilities project.
INF_HMID_UN_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in End Date extended
INF_HMID_UN_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2022-10-01 | 2023 Q1 | During the reporting period, City of Danbury completed construction and is pending submission of construction completion documentation for its Sewer Facilities project.
INF_HMID_UN_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2023-04-01 | 2023 Q3 | Amendment moved funds to related activity. Area Benefit type corrected.
INF_HMID_UN_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2023-07-01 | 2023 Q4 | During the reporting period, the City Danbury had grant closeout documents under review for its sewer improvements project.
INF_HMID_UN_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Danbury had Close Out Underway
INF_HMID_UN_20-065-127-C438_Danbury | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | DANBURY, CITY OF | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_HMID_UN_20-065-129-C440_Portland | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | PORTLAND, CITY OF | 2020-07-01 | 2020 Q4
INF_HMID_UN_20-065-129-C440_Portland | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | PORTLAND, CITY OF | 2021-07-01 | 2021 Q4 | During the reporting period, the CITY Portland had construction procurement underway for its flood and project.
INF_HMID_UN_20-065-129-C440_Portland | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | PORTLAND, CITY OF | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Portland completed environmental review for its flood and drainage project.
INF_HMID_UN_20-065-129-C440_Portland | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | PORTLAND, CITY OF | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Portland is obtaining construction bids for its flood and drainage project.
INF_HMID_UN_20-065-129-C440_Portland | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | PORTLAND, CITY OF | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Portland completed engineering design for its flood and drainage project. During the reporting period, the City of Portland had construction procurement underway for its flood and drainage project.
INF_HMID_UN_20-065-129-C440_Portland | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | PORTLAND, CITY OF | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Portland had construction underway for its flood and drainage project.
INF_HMID_UN_20-065-129-C440_Portland | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | PORTLAND, CITY OF | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Portland had construction underway for its flood and drainage project.
INF_HMID_UN_20-065-129-C440_Portland | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | PORTLAND, CITY OF | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Portland completed construction and is pending submission of construction completion documentation
INF_HMID_UN_20-065-129-C440_Portland | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | PORTLAND, CITY OF | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Portland completed construction and submitted the COCC for its Flood and Drainage Facilities project.
INF_HMID_UN_20-065-129-C440_Portland | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | PORTLAND, CITY OF | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Portland had grant closeout documents under review for its flood and drainage project.
INF_HMID_UN_20-065-131-C442_Simonton | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Simonton, City of | 2020-07-01 | 2020 Q4
INF_HMID_UN_20-065-131-C442_Simonton | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Simonton, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Simonton had engineering design underway for its flood and drainage facilities project.
INF_HMID_UN_20-065-131-C442_Simonton | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Simonton, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Simonton had preliminary engineering design under for its flood and drainage project.
INF_HMID_UN_20-065-131-C442_Simonton | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Simonton, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Simonton had construction underway for its flood and drainage facilities project.
INF_HMID_UN_20-065-131-C442_Simonton | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Simonton, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Simonton had construction underway for its flood and drainage facility project.
INF_HMID_UN_20-065-131-C442_Simonton | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Simonton, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Simonton had 50% of construction complete for its flood and drainage project.
INF_HMID_UN_20-065-131-C442_Simonton | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Simonton, City of | 2022-07-01 | 2022 Q4 | During the reporting period the City of Simonton had construction complete and is pending submission of construction completion documentation for its flood and drainage facilities.
INF_HMID_UN_20-065-131-C442_Simonton | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Simonton, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Simonton completed construction and submitted the COCC for its flood and drainage project.
INF_HMID_UN_20-065-131-C442_Simonton | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Simonton, City of | 2024-01-01 | 2024 Q2 | During the reporting period, this activity was administratively closed, fully expended, all required closeout data was entered into DRGR and Activity Status changed to Completed.
INF_HMID_UN_20-065-131-C442_Simonton | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Simonton, City of | 2024-04-01 | 2024 Q3 | Activity budget and obligation reduced for closeout. This activity has been fully closed, all accomplishments entered, and activity status updated to Completed.
INF_HMID_UN_20-065-133-C445_CorpusChristi | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CORPUS CHRISTI, CITY OF | 2020-07-01 | 2020 Q4
INF_HMID_UN_20-065-133-C445_CorpusChristi | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CORPUS CHRISTI, CITY OF | 2023-01-01 | 2023 Q2 | During the reporting period, Corpus Christi had engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-133-C445_CorpusChristi | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CORPUS CHRISTI, CITY OF | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-133-C445_CorpusChristi | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CORPUS CHRISTI, CITY OF | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
INF_HMID_UN_20-065-133-C445_CorpusChristi | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CORPUS CHRISTI, CITY OF | 2025-07-01 | 2025 Q4 | During the reporting period, The city of corpus Christi is still in construction phase for its Flood and Drainage Project
INF_HMID_UN_20-065-134-C451_Friendswood | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | City of Friendswood | 2020-04-01 | 2020 Q3
INF_HMID_UN_20-065-134-C451_Friendswood | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | City of Friendswood | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Friendswood had construction procurement underway for its Flood and Drainage Facilities project.
INF_HMID_UN_20-065-134-C451_Friendswood | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | City of Friendswood | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Friendswood had environmental review underway for its flood and drainage project.
INF_HMID_UN_20-065-134-C451_Friendswood | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | City of Friendswood | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Friendswood had environmental review underway for its flood and drainage project.
INF_HMID_UN_20-065-134-C451_Friendswood | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | City of Friendswood | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Friendswood had completed engineering design and had construction procurement underway for its Flood and Drainage project.
INF_HMID_UN_20-065-134-C451_Friendswood | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | City of Friendswood | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Friendswood had construction underway for its Flood and Drainage project.
INF_HMID_UN_20-065-134-C451_Friendswood | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | City of Friendswood | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Friendswood completed construction and is pending submission of construction completion documentation for its Flood and Drainage project.
INF_HMID_UN_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2020-07-01 | 2020 Q4
INF_HMID_UN_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Orange had preliminary engineering design underway for its Flood and Drainage project.
INF_HMID_UN_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
INF_HMID_UN_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Orange had environmental clearance underway for its Flood and Drainage project.
INF_HMID_UN_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2025-04-01 | 2025 Q3 | Amendment was executed during the quarter, that reallocated funding amongst activities resulting in a decrease to the budget and obligation of this activity.
INF_HMID_UN_20-065-140-C594_Orange_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Orange | 2026-01-01 | 2026 Q2
INF_HMID_UN_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
INF_HMID_UN_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2022-04-01 | 2022 Q3 | During the reporting period, the city had HC SAR Vehicles purchased.
INF_HMID_UN_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2022-10-01 | 2023 Q1 | During the reporting period, high clearance search and rescue vehicles (public facilities) were purchased.
INF_HMID_UN_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Orange construction was underway (95% complete) for Regional Radio Tower (Public Facilities project).
INF_HMID_UN_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Orange had construction closeout activities underway for its Public Facilities project.
INF_HMID_UN_20-065-140-C594_Orange_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Orange | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Orange completed construction and submitted the COCC for its Public Facilities project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2021-01-01 | 2021 Q2
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2021-07-01 | 2021 Q4 | During the reporting period, the City of League City had environmental review underway for its Flood and Drainage Facilities project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2021-10-01 | 2022 Q1 | During the reporting period, the City of League City had 50% of construction complete for its Flood Drainage Facilities project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2022-01-01 | 2022 Q2 | During the reporting period, the City of League City had environmental review underway for its flood and drainage project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2022-04-01 | 2022 Q3 | During the reporting period, the City of League City had environmental review underway for its Flood and Drainage Facilities project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2022-07-01 | 2022 Q4 | During the reporting period, the City of League City had environmental review underway for its Flood and Drainage project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2022-10-01 | 2023 Q1 | During the reporting period, the City of League City completed environmental review for its flood and drainage facilities project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2023-01-01 | 2023 Q2 | During the reporting period, the City of League City had environmental review underway for its Flood and Drainage project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2023-04-01 | 2023 Q3 | During the reporting period, the City of League City had environmental complete for its flood and drainage project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2024-01-01 | 2024 Q2 | During the reporting period, the City of League City completed environmental review for its flood and drainage project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2024-04-01 | 2024 Q3 | During the reporting period, the City of League City completed engineering design for its flood and drainage project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2024-07-01 | 2024 Q4
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2024-10-01 | 2025 Q1 | During the reporting period, the City of League City had construction procurement underway for its flood and drainage project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2025-01-01 | 2025 Q2 | During the reporting period, the City of League City had construction procurement underway for its flood and drainage project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2025-04-01 | 2025 Q3 | During the reporting period, the City of League City continued construction procurement for its flood and drainage project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2025-07-01 | 2025 Q4 | During the reporting period, the City of League City had construction procurement underway for its flood and drainage project.
INF_HMID_UN_20-065-141-C780_LeagueCity_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | League City | 2025-10-01 | 2026 Q1 | During the reporting period, the City of League City had bid opening as part of construction procurement for its Flood and drainage project.
INF_HMID_UN_20-065-143-C811_PortAransas_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Aransas | 2021-01-01 | 2021 Q2
INF_HMID_UN_20-065-143-C811_PortAransas_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Aransas | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Port Aransas had engineering design and environmental review underway for its flood and drainage project.
INF_HMID_UN_20-065-143-C811_PortAransas_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Aransas | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Port Aransas had engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-143-C811_PortAransas_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Aransas | 2023-04-01 | 2023 Q3 | Amendment reduced projected performance measures. Area Benefit type corrected.
INF_HMID_UN_20-065-143-C811_PortAransas_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Aransas | 2023-10-01 | 2024 Q1 | During the reporting period, Port Aransas had construction underway for its flood and drainage project.
INF_HMID_UN_20-065-143-C811_PortAransas_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Aransas | 2024-01-01 | 2024 Q2 | During the reporting period, Port Aransas had construction underway for its flood and drainage project and waiting on environmental for phase 2 project.
INF_HMID_UN_20-065-143-C811_PortAransas_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Aransas | 2024-04-01 | 2024 Q3 | During the reporting period, Port Aransas had construction underway for its flood and drainage project and currently waiting on environmental for phase 2 project.
INF_HMID_UN_20-065-143-C811_PortAransas_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Aransas | 2024-07-01 | 2024 Q4 | During the reporting period Port Aransas is sending documents in for time extension .
INF_HMID_UN_20-065-143-C811_PortAransas_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Aransas | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Port Aransas had 50% of construction underway/complete for its Flood and Drainage project.
INF_HMID_UN_20-065-143-C811_PortAransas_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Aransas | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Port Aransas had 85% of construction underway/complete for its Flood and Drainage project.
INF_HMID_UN_20-065-143-C811_PortAransas_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Aransas | 2025-04-01 | 2025 Q3 | During reporting period, the City of Port Aransas had 90% of construction underway/complete for its Flood and Drainage project.
INF_HMID_UN_20-065-143-C811_PortAransas_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Port Aransas | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Port Aransas has completed project and is closeout for its Flood and drainage project.
INF_HMID_UN_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2021-01-01 | 2021 Q2
INF_HMID_UN_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Hardin County had construction procurement underway for its public facilities project.
INF_HMID_UN_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2022-04-01 | 2022 Q3 | During the reporting period, Hardin County had procurement activities underway for its public facilities project.
INF_HMID_UN_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Hardin County was awaiting approval of a scope of work change request for its Public Facilities project.
INF_HMID_UN_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2023-01-01 | 2023 Q2 | Amendment changed performance measures.
INF_HMID_UN_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_HMID_UN_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2023-07-01 | 2023 Q4 | Annual Section 3 Labor hours reported.
INF_HMID_UN_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Hardin County completed construction procurement for its Public Facilities project.
INF_HMID_UN_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2024-01-01 | 2024 Q2 | During the reporting period, Hardin County had construction underway for its public facilities project
INF_HMID_UN_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2024-10-01 | 2025 Q1 | During the reporting period, Hardin County completed construction and submitted the COCC for its public facilities project.
INF_HMID_UN_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2025-01-01 | 2025 Q2 | During the reporting period, Hardin County had construction complete and construction closeout documents were finalized.
INF_HMID_UN_20-065-145-C857_HardinCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Hardin, County of | 2025-04-01 | 2025 Q3 | During the reporting period, Hardin County submitted the COCC for its fire protection facilities project
INF_HMID_UN_20-065-147-C902_BevilOaks_SI | Street Improvements | Construction/reconstruction of streets | Bevil Oaks | 2021-01-01 | 2021 Q2
INF_HMID_UN_20-065-147-C902_BevilOaks_SI | Street Improvements | Construction/reconstruction of streets | Bevil Oaks | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Bevil Oaks completed engineering design for its street improvement project.
INF_HMID_UN_20-065-147-C902_BevilOaks_SI | Street Improvements | Construction/reconstruction of streets | Bevil Oaks | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Bevil Oaks completed engineering design for its street improvements project.
INF_HMID_UN_20-065-147-C902_BevilOaks_SI | Street Improvements | Construction/reconstruction of streets | Bevil Oaks | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Bevil Oaks had construction procurement underway for its street improvement project.
INF_HMID_UN_20-065-147-C902_BevilOaks_SI | Street Improvements | Construction/reconstruction of streets | Bevil Oaks | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Bevil Oaks had construction underway for its street improvements project.
INF_HMID_UN_20-065-147-C902_BevilOaks_SI | Street Improvements | Construction/reconstruction of streets | Bevil Oaks | 2023-04-01 | 2023 Q3 | During the reporting?period,?the City of Bevil Oaks had 50% of construction?underway/complete for its street improvements project.
INF_HMID_UN_20-065-147-C902_BevilOaks_SI | Street Improvements | Construction/reconstruction of streets | Bevil Oaks | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Bevil Oaks completed construction and submitted the COCC for its street improvements project.
INF_HMID_UN_20-065-147-C902_BevilOaks_SI | Street Improvements | Construction/reconstruction of streets | Bevil Oaks | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Bevil Oaks had grant closeout documents under review for its street improvements project.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2021-01-01 | 2021 Q2
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Rose Hill Acres had environmental review underway for its Street Improvement project.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2021-07-01 | 2021 Q4 | During the reporting?period,?the City of Rose Hill Acres had preliminary?engineering design underway for its street improvements project.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Rose Hill Acres had preliminary engineering design underway for its street improvement project.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2022-04-01 | 2022 Q3 | No changes took place during the reporting period.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Rose Hill Acres completed environmental review for its street improvements project.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Rose Hill Acres submitted a RROF and is awaiting AUGF.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Rose Hill Acres had bid advertisement underway for its street improvements project.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Rose Hill Acres had bid advertisement completed for its street improvements project.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2023-07-01 | 2023 Q4 | Annual Section 3 Labor hours reported.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Rose Hill Acres had construction procurement underway for its Street Improvements project
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2024-07-01 | 2024 Q4 | Annual Section 3 measures reported.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2025-07-01 | 2025 Q4 | During the reporting?period,?the City of Rose Hill Acres had 50% of construction?complete for its street improvement project.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Rose Hill Acres completed construction and is pending submission of construction completion documentation for its street improvement project.
INF_HMID_UN_20-065-148-C903_RoseHillAcres_SI | Street Improvements | Construction/reconstruction of streets | Rose Hill Acres, City of | 2026-01-01 | 2026 Q2
INF_HMID_UN_20-065-149-C905_Nederland_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Nederland, City of | 2021-01-01 | 2021 Q2
INF_HMID_UN_20-065-149-C905_Nederland_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Nederland, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Nederland had engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-149-C905_Nederland_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Nederland, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Nederland had preliminary engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-149-C905_Nederland_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Nederland, City of | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_HMID_UN_20-065-149-C905_Nederland_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Nederland, City of | 2023-07-01 | 2023 Q4 | Annual Section 3 Labor hours reported.
INF_HMID_UN_20-065-149-C905_Nederland_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Nederland, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Nederland completed construction and is pending submission of construction completion documentation for its flood and drainage project.
INF_HMID_UN_20-065-149-C905_Nederland_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Nederland, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Nederland had construction complete and the COCC underway for its flood and drainage project.
INF_HMID_UN_20-065-149-C905_Nederland_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Nederland, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Nederland completed construction and submitted the COCC for its flood and drainage project.
INF_HMID_UN_20-065-149-C905_Nederland_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Nederland, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Nederland completed construction and submitted the COCC, FWCR and As-builts for its flood and drainage project.
INF_HMID_UN_20-065-149-C905_Nederland_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Nederland, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Nederland completed construction and submitted the COCC for its flood and drainage project.
INF_HMID_UN_20-065-149-C905_Nederland_SI | Street Improvements | Construction/reconstruction of streets | Nederland, City of | 2024-04-01 | 2024 Q3 | Activity budget and obligation adjusted due to a contract amendment.
INF_HMID_UN_20-065-149-C905_Nederland_SI | Street Improvements | Construction/reconstruction of streets | Nederland, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Nederland completed construction and submitted the COCC for its street improvement project.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2021-01-01 | 2021 Q2
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Orange County had engineering design underway for its flood and drainage facilities project.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Orange County had engineering design underway for its flood and drainage facilities project.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Orange County had engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2022-04-01 | 2022 Q3 | During the reporting period, Orange County had engineering design underway for all 4 F&D projects.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2022-07-01 | 2022 Q4 | During the reporting period, Orange County had AUGFs issued for all 4 F&D projects, and Engineering Design was underway.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2022-10-01 | 2023 Q1 | During the reporting period, engineering design was underway for flood and drainage projects.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Orange County completed construction procurement for its flood and drainage facilities project.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Orange County had construction underway for its flood and drainage project.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Orange County had construction underway for its flood and drainage project.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2024-01-01 | 2024 Q2 | During the reporting period, Orange County had 50% of construction complete for its flood and drainage project.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2024-04-01 | 2024 Q3 | During the reporting?period,?Orange County had 50% of construction?underway/complete for its flood and drainage facilities project.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2024-07-01 | 2024 Q4 | During the reporting period, Orange County had 75% of construction complete for its flood and drainage project.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2024-10-01 | 2025 Q1 | During the reporting?period,?Orange County had 80% of construction?complete for its flood and drainage project.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2025-04-01 | 2025 Q3 | Amendment was executed during the quarter, that reduced the scope of the projects.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2025-07-01 | 2025 Q4 | During the reporting period, Orange County has construction underway for its flood and drainage project.
INF_HMID_UN_20-065-150-C911_OrangeCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Orange, County of | 2025-10-01 | 2026 Q1 | During the reporting period, Orange County had construction complete and the COCC underway for its flood and drainage project
INF_HMID_UN_20-065-151-C916_TaylorLanding_SI | Street Improvements | Construction/reconstruction of streets | Taylor Landing, City of | 2021-01-01 | 2021 Q2
INF_HMID_UN_20-065-151-C916_TaylorLanding_SI | Street Improvements | Construction/reconstruction of streets | Taylor Landing, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Taylor Landing had engineering design underway for its street improvement project
INF_HMID_UN_20-065-151-C916_TaylorLanding_SI | Street Improvements | Construction/reconstruction of streets | Taylor Landing, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Taylor Landing completed environmental review for its street improvements project.
INF_HMID_UN_20-065-151-C916_TaylorLanding_SI | Street Improvements | Construction/reconstruction of streets | Taylor Landing, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Taylor Landing completed engineering design for its street improvements project.
INF_HMID_UN_20-065-151-C916_TaylorLanding_SI | Street Improvements | Construction/reconstruction of streets | Taylor Landing, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Taylor Landing completed engineering design for its street improvements project.
INF_HMID_UN_20-065-151-C916_TaylorLanding_SI | Street Improvements | Construction/reconstruction of streets | Taylor Landing, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Taylor Landing had construction procurement underway for its street improvement project.
INF_HMID_UN_20-065-151-C916_TaylorLanding_SI | Street Improvements | Construction/reconstruction of streets | Taylor Landing, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Taylor Landing had construction underway for its street improvements project.
INF_HMID_UN_20-065-151-C916_TaylorLanding_SI | Street Improvements | Construction/reconstruction of streets | Taylor Landing, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Taylor Landing submitted grant closeout documents for its street improvements project.
INF_HMID_UN_20-065-151-C916_TaylorLanding_SI | Street Improvements | Construction/reconstruction of streets | Taylor Landing, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Taylor Landing had grant closeout documents under review for its street improvements project.
INF_HMID_UN_20-065-151-C916_TaylorLanding_SI | Street Improvements | Construction/reconstruction of streets | Taylor Landing, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Taylor Landing had grant closeout documents under review for its street improvement project.
INF_HMID_UN_20-065-153-C929_BridgeCity_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bridge City | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
INF_HMID_UN_20-065-153-C929_BridgeCity_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bridge City | 2022-04-01 | 2022 Q3 | No changes took place during the reporting period.
INF_HMID_UN_20-065-153-C929_BridgeCity_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bridge City | 2022-07-01 | 2022 Q4 | During the reporting period, Bridge City had Environmental Notice to Proceed underway.
INF_HMID_UN_20-065-153-C929_BridgeCity_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bridge City | 2023-01-01 | 2023 Q2 | During the reporting period, Bridge City had engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-153-C929_BridgeCity_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bridge City | 2023-04-01 | 2023 Q3 | During the reporting period, Bridge City had engineering underway for its flood and drainage project.
INF_HMID_UN_20-065-153-C929_BridgeCity_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bridge City | 2023-07-01 | 2023 Q4 | During the reporting period, Bridge City had engineering design underway for its Flood and Drainage project.
INF_HMID_UN_20-065-153-C929_BridgeCity_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bridge City | 2023-10-01 | 2024 Q1 | During the reporting period, Bridge City had engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-153-C929_BridgeCity_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bridge City | 2024-07-01 | 2024 Q4 | Annual Section 3 measures reported.
INF_HMID_UN_20-065-153-C929_BridgeCity_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bridge City | 2024-10-01 | 2025 Q1 | During the reporting period, a contract amendment was executed to adjust project scope and budgets.
INF_HMID_UN_20-065-153-C929_BridgeCity_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bridge City | 2025-07-01 | 2025 Q4 | Activity reported Section 3 measures.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2021-07-01 | 2021 Q4 | New contract executed and entered into DRGR adding and/or adjusting budgets for new and exisiting activities within the contract in Q3 2021.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2022-04-01 | 2022 Q3 | No changes took place during the reporting period.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2022-07-01 | 2022 Q4 | During the reporting period, Bridge City had Engineering Design underway for Flood and Drainage.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2022-10-01 | 2023 Q1 | During the reporting period, construction was underway for Sunnyside Well, however this billing may be for engineering and project delivery.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2023-01-01 | 2023 Q2 | During the reporting period, Bridge City had construction underway for its water facilities project.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2023-04-01 | 2023 Q3 | During the reporting period, Bridge City had construction underway for its water facilities project.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2023-07-01 | 2023 Q4 | During the reporting period, Bridge City had engineering design completed and construction underway for its Water Facilities project.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2023-10-01 | 2024 Q1 | During the reporting period, Bridge City had construction underway for its water facilities project.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2024-01-01 | 2024 Q2 | During the reporting period, Bridge City had construction underway and 30% complete for its water facilities project.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2024-04-01 | 2024 Q3 | During the reporting period, Bridge City had construction underway for its water facilities project.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2024-07-01 | 2024 Q4 | Annual Section 3 measures reported.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2024-10-01 | 2025 Q1 | During the reporting?period,?the City of Bridge City had 90% of construction?complete for its water facilities project.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Bridge City had construction complete and the COCC submitted for its water facilities project.
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Bridge City completed construction and submitted the COCC for its water facilities project
INF_HMID_UN_20-065-153-C929_BridgeCity_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bridge City | 2025-07-01 | 2025 Q4 | Activity reported Section 3 measures.
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2021-04-01 | 2021 Q3
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Pine Forest had engineering design underway for its flood and drainage project.
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2022-04-01 | 2022 Q3 | During the reporting period, Pine Forest had environmental and engineering design underway.
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Pinehurst completed Engineering Design for Flood and Drainage.
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2022-10-01 | 2023 Q1 | During the reporting period, engineering design was underway. This invoice was for project delivery.
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Pine Forest completed a cultural resource dig required for environmental clearance on its flood and drainage project.
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2023-07-01 | 2023 Q4 | Section 3 reported actuals revised.
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Pine Forest issued construction notice to proceed for its flood and drainage project.
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Pine Forest had construction underway for its flood and drainage project
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Pine Forest had construction underway for its flood and drainage project
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Bridge City has construction underway (60% complete) for its flood and drainage project.
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Pine Forest County completed construction and submitted the COCC for its Flood and Drainage project.
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Pine Forest had grant closeout documents under review for its Flood and Drainage project
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_HMID_UN_20-065-154-C933_PineForest_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Pine Forest | 2025-10-01 | 2026 Q1 | Activity was completed during the reporting period.
INF_HMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_HMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 42061.45 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 15049.3 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 19193.45 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 8121.22 - State costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 3538.43 - State costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 7973.33 - State costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient HMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_HMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_HMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 12639.87 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 4632.66 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 5898.47 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 2551.47 - State costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 1138.41 - State costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 2985.94 - State costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient HMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_HMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_HMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 25546.25 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 9844.36 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 12552.74 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 5131.73 - State costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 2148.68 - State costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 5649.13 - State costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient HMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_HMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 15312.3 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 5205.27 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 6640.71 - Quarterly expenditure for state costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 2718.43 - State costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 1138.41 - State costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 2985.94 - State costs in support of activity delivery.
INF_HMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient HMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_SMID_LMI_20-065-002-B964_Moulton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Moulton, City of | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-002-B964_Moulton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Moulton, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Moulton had construction underway for its Flood and Drainage Facilities Improvements project.
INF_SMID_LMI_20-065-002-B964_Moulton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Moulton, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Moulton submitted closeout documents for its flood and drainage project. The issuance of the administratively complete letter is pending.
INF_SMID_LMI_20-065-002-B964_Moulton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Moulton, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Moulton is pending administrative closeout.
INF_SMID_LMI_20-065-002-B964_Moulton | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Moulton, City of | 2023-01-01 | 2023 Q2 | Activity completed.
INF_SMID_LMI_20-065-011-C032_EagleLake | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Eagle Lake, City of | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-011-C032_EagleLake | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Eagle Lake, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Eagle Lake completed engineering design for its sewer facilities project.
INF_SMID_LMI_20-065-011-C032_EagleLake | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Eagle Lake, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Eagle Lake had construction underway for its sewer facilities project.
INF_SMID_LMI_20-065-011-C032_EagleLake | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Eagle Lake, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Eagle Lake had 80% of construction underway for its sewer facilities project.
INF_SMID_LMI_20-065-011-C032_EagleLake | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Eagle Lake, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Eagle Lake completed construction and is pending submission of construction completion documentation for its sewer facilities project.
INF_SMID_LMI_20-065-011-C032_EagleLake | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Eagle Lake, City of | 2021-07-01 | 2021 Q4 | Activity is close to completion.
INF_SMID_LMI_20-065-011-C032_EagleLake | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Eagle Lake, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Eagle Lake had grant closeout documents under review for its sewer facilities project.
INF_SMID_LMI_20-065-011-C032_EagleLake | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Eagle Lake, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-011-C032_EagleLake | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Eagle Lake, City of | 2023-07-01 | 2023 Q4 | Activity completed.
INF_SMID_LMI_20-065-012-C039_Goliad | Street Improvements | Construction/reconstruction of streets | Goliad, City Of | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-012-C039_Goliad | Street Improvements | Construction/reconstruction of streets | Goliad, City Of | 2020-01-01 | 2020 Q2 | During the reporting period, the City of Goliad had engineering design underway for its street improvement project.
INF_SMID_LMI_20-065-012-C039_Goliad | Street Improvements | Construction/reconstruction of streets | Goliad, City Of | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-012-C039_Goliad | Street Improvements | Construction/reconstruction of streets | Goliad, City Of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Goliad had completed environmental review and completed engineering design for its street improvement project.
INF_SMID_LMI_20-065-012-C039_Goliad | Street Improvements | Construction/reconstruction of streets | Goliad, City Of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Goliad had completed construction procurement for its street improvements project.
INF_SMID_LMI_20-065-012-C039_Goliad | Street Improvements | Construction/reconstruction of streets | Goliad, City Of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Goliad had 50% of construction underway for its street improvement project.
INF_SMID_LMI_20-065-012-C039_Goliad | Street Improvements | Construction/reconstruction of streets | Goliad, City Of | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Goliad completed construction and submitted the COCC for its Street Improvement project.
INF_SMID_LMI_20-065-012-C039_Goliad | Street Improvements | Construction/reconstruction of streets | Goliad, City Of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Goliad submitted grant closeout documents for its street improvements project.
INF_SMID_LMI_20-065-012-C039_Goliad | Street Improvements | Construction/reconstruction of streets | Goliad, City Of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Goliad had grant closeout under review for its Street Improvement project.
INF_SMID_LMI_20-065-012-C039_Goliad | Street Improvements | Construction/reconstruction of streets | Goliad, City Of | 2023-01-01 | 2023 Q2 | Activity completed.
INF_SMID_LMI_20-065-012-C039_Goliad | Street Improvements | Construction/reconstruction of streets | Goliad, City Of | 2023-04-01 | 2023 Q3 | Per HUD recommendation, Expenditure amount adjusted to match Drawn amount due to DRGR system errors.
INF_SMID_LMI_20-065-015-C054_NewWaverly | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | New Waverly | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-015-C054_NewWaverly | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | New Waverly | 2020-10-01 | 2021 Q1 | During the reporting period the City of New Waverly had finalized acquisition for its flood and drainage facilities project.
INF_SMID_LMI_20-065-015-C054_NewWaverly | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | New Waverly | 2021-04-01 | 2021 Q3 | During the reporting period, the City of New Waverly had construction underway for its Flood and Drainage Facilities project. The Construction Notice to Proceed was issued on April 14, 2021 and construction began on April 26, 2021.
INF_SMID_LMI_20-065-015-C054_NewWaverly | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | New Waverly | 2022-04-01 | 2022 Q3 | During the reporting period, the City of New Waverly completed construction and submitted closeout documents for review.
INF_SMID_LMI_20-065-015-C054_NewWaverly | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | New Waverly | 2022-07-01 | 2022 Q4 | During the reporting period, the City of New Waverly completed construction on its Flood and Drainage facilities project. Review of closeout documents underway.
INF_SMID_LMI_20-065-015-C054_NewWaverly | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | New Waverly | 2022-10-01 | 2023 Q1 | During the reporting period, the City of New Waverly submitted grant completion documentation is awaiting finalization of review of closeout documents.
INF_SMID_LMI_20-065-015-C054_NewWaverly | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | New Waverly | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-015-C054_NewWaverly | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | New Waverly | 2025-04-01 | 2025 Q3 | During the reporting period, the City of New Waverly had grant closeout documents under review for its flood & drainage project
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2020-04-01 | 2020 Q3 | During the reporting period, the Bee County had environmental review and engineering design underway for its sewer facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2020-07-01 | 2020 Q4 | During the reporting period, Bee County had completed environmental review and completed engineering design for its sewer facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2020-10-01 | 2021 Q1
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2021-01-01 | 2021 Q2 | During the reporting period, Bee County had engineering design and environmental complete for its sewer facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Bee County had construction underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Bee County had construction procurement underway for its Water project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in End Date extended, Performance Statement changed
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Bee County had 50% of construction underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2023-01-01 | 2023 Q2 | Amendment moved funds to related activity.
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2024-01-01 | 2024 Q2 | During the reporting period, Bee County completed construction and submitted the COCC for its sewer facilities project
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2025-07-01 | 2025 Q4 | During the reporting period, Bee County completed construction and submitted the COCC for its sewer facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2025-10-01 | 2026 Q1 | During the reporting period, Bee County had grant closeout documents under review for its sewer facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2020-04-01 | 2020 Q3 | During the reporting period, the Bee County had environmental review and engineering design underway for its water facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2020-07-01 | 2020 Q4 | During the reporting period, Bee County had completed environmental review and completed engineering design for its water facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2020-10-01 | 2021 Q1
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2021-01-01 | 2021 Q2 | During the reporting period, Bee County had engineering design and environmental complete for its water facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Bee County had construction underway for its Water Facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Bee County had construction procurement underway for its Sewer project. Review of prior DRGR Vouchers resulted in revisions that lowered the total amount draw for this DRGR Activity.
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in End Date extended, Performance Statement changed
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Bee County had 50% of construction underway for its Water Facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2023-01-01 | 2023 Q2 | Amendment moved funds from related activity
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Bee County completed construction and is pending submission of construction completion documentation for its water facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2025-07-01 | 2025 Q4 | During the reporting period, Bee County completed construction and submitted the COCC for its water facilities project.
INF_SMID_LMI_20-065-016-C056_BeeCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Bee, County of | 2025-10-01 | 2026 Q1 | During the reporting period, Bee County had grant closeout documents under review for its water facilities project.
INF_SMID_LMI_20-065-019-C065_PrairieView | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Prairie View | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-019-C065_PrairieView | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Prairie View | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Prairie View had engineering design underway for its sewer facilities project.
INF_SMID_LMI_20-065-019-C065_PrairieView | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Prairie View | 2021-04-01 | 2021 Q3 | During the reporting period, Prairie View had construction underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-019-C065_PrairieView | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Prairie View | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Prairie View had construction underway for its sewer facilities project.
INF_SMID_LMI_20-065-019-C065_PrairieView | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Prairie View | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Prairie View had construction underway for its sewer facilities project.
INF_SMID_LMI_20-065-019-C065_PrairieView | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Prairie View | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Prairie View submitted grant closeout documents for its sewer facilities project. The closeout documents are pending review.
INF_SMID_LMI_20-065-019-C065_PrairieView | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Prairie View | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Prairie View submitted grant closeout documents for its sewer facilities project. The issuance of the administratively complete letter is pending.
INF_SMID_LMI_20-065-019-C065_PrairieView | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Prairie View | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Prairie View submitted grant closeout documents for its sewer facilities project. Closeout review underway.
INF_SMID_LMI_20-065-019-C065_PrairieView | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Prairie View | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2020-04-01 | 2020 Q3 | During the reporting period, the Caldwell County had environmental review and engineering design underway for its flood and drainage facilities project.
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2020-07-01 | 2020 Q4
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2021-01-01 | 2021 Q2 | During the reporting period, Caldwell County had construction procurement underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Caldwell had acquisition underway for its Flood and Drainage Facilities project with one parcel pending.
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Caldwell County had construction procurement underway for its flood and drainage project.
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2022-04-01 | 2022 Q3 | During the reporting period, Caldwell County had construction underway for its flood and drainage facilities project.
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2022-07-01 | 2022 Q4 | During the reporting period, Caldwell County continued construction on 3 out of 4 sites, completion at 95%.
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2022-10-01 | 2023 Q1 | During the reporting period, the County completed construction on 3 out of 4 sites
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2023-01-01 | 2023 Q2 | During the reporting period, Caldwell County had completed construction for its Flood and Drainage project.
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Caldwell County submitted grant closeout documents for its Flood and Drainage project. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2025-01-01 | 2025 Q2 | During the reporting period, Caldwell County had its flood and drainage project administratively closed.
INF_SMID_LMI_20-065-020-C066_CaldwellCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Caldwell, County of | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Ganado had engineering design underway for its sewer facilities project.
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2020-10-01 | 2021 Q1
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Ganado had engineering design complete for its sewer facilities project.
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2021-04-01 | 2021 Q3 | During the reporting period, Ganado had construction underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Ganado had construction underway for its sewer facility projects.
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2022-04-01 | 2022 Q3 | During the reporting period, the City had construction underway for its sewer facility projects.
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Ganado had 50% of construction underway/complete for its sewer facilities projects.
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Ganado had 50% of construction underway/complete for its public facility project, however, no expenditures were reimbursed in Q4 2022.
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Ganado completed construction and submitted the COCC for its sewer facilities project.
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Ganado had grant closeout documents under review for its infrastructure projects.
INF_SMID_LMI_20-065-023-C082_Ganado | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | City of Ganado Inc | 2024-04-01 | 2024 Q3 | Activity has been administratively closed during the quarter. All payments have been completed and all accomplishments were entered. Activity status has been updated to Completed.
INF_SMID_LMI_20-065-032-C109_Edna | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-032-C109_Edna | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Edna completed engineering design for its sewer facilities project.
INF_SMID_LMI_20-065-032-C109_Edna | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Edna completed construction procurement for its sewer facilities project.
INF_SMID_LMI_20-065-032-C109_Edna | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Edna had construction underway for its sewer facilities project.
INF_SMID_LMI_20-065-032-C109_Edna | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2021-04-01 | 2021 Q3 | During the reporting period, Edna had construction underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-032-C109_Edna | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2021-07-01 | 2021 Q4 | During the reporting?period,?the City of Edna had 50% of construction?underway/complete for its sewer project.
INF_SMID_LMI_20-065-032-C109_Edna | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Edna completed construction and is pending submission of a change request to add an additional activity.
INF_SMID_LMI_20-065-032-C109_Edna | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Edna completed construction and is submitted an amendment request to add additional sewer projects.
INF_SMID_LMI_20-065-032-C109_Edna | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_SMID_LMI_20-065-032-C109_Edna | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Edna had grant closeout documents under review for its infrastructure program.
INF_SMID_LMI_20-065-032-C109_Edna | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-032-C109_Edna | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Edna had grant closeout documents under review for its Sewer project.
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of La Ward had environmental review and engineering design underway for its sewer facilities project.
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2020-07-01 | 2020 Q4
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the city of Laward had construction procurement underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of La Ward completed bid advertisement for their sewer facilities project.
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of La Ward had construction underway for its sewer facility project.
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City had construction underway for its water facility project.
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in Budget changed
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of La Ward had 50% of construction underway/complete for its sewer facility project
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of LaWard had construction underway for its sewer facility project.
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the City of La Ward submitted grant closeout documents for its Sewer Facility project.
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the City of La Ward had grant closeout documents under review for its infrastructure projects.
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the City of La Ward had grant closeout documents under review for its Flood and Drainage project.
INF_SMID_LMI_20-065-033-C111_LaWard_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of La Ward had environmental review and engineering design underway for its water facilities project.
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2020-07-01 | 2020 Q4
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2021-04-01 | 2021 Q3 | During the reporting period, the city of Laward had construction procurement underway for its Water Facilities project.
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of La Ward completed bid advertisement for its water facility project.
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of La Ward completed construction procurement for its water facility project.
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City had construction underway for its sewer project.
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in Budget changed
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the City of La Ward submitted grant closeout documents for its Water Facility project.
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2024-01-01 | 2024 Q2 | During the reporting period, the City of La Ward had grant closeout documents under review for its infrastructure projects.
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the City of La Ward had grant closeout documents under review for its Flood and Drainage project.
INF_SMID_LMI_20-065-033-C111_LaWard_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Laward, City of | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_SMID_LMI_20-065-035-C115_Wallis_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Wallis | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-035-C115_Wallis_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Wallis | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Wallis had environmental review underway for its public facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Wallis | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Wallis had engineering design underway for its public facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Wallis | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Wallis had preliminary engineering design underway for its public facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Wallis | 2021-04-01 | 2021 Q3 | During the reporting period, Wallis completed environmental review for its Public Facilities project. Correction on an incorrect invoice split
INF_SMID_LMI_20-065-035-C115_Wallis_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Wallis | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Wallis had construction underway for its public facilities project. Review of prior DRGR Vouchers resulted in revisions that lowered the total amount draw for this DRGR Activity.
INF_SMID_LMI_20-065-035-C115_Wallis_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Wallis | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Wallis had construction underway for its public facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Wallis | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Wallis completed construction and submitted the COCC for its public facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Wallis | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-035-C115_Wallis_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Wallis | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Wallis had grant closeout documents under review for its Public Facilities project. Final payments were processed.
INF_SMID_LMI_20-065-035-C115_Wallis_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wallis | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-035-C115_Wallis_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wallis | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Wallis had environmental review underway for its public facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wallis | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Wallis had engineering design underway for its sewer facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wallis | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Wallis had preliminary engineering design underway for its sewer facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wallis | 2021-04-01 | 2021 Q3 | During the reporting period, Wallis had construction underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wallis | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Wallis had construction underway for its sewer facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wallis | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Wallis had 50% of construction underway/complete for its sewer facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wallis | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Wallis had construction underway for its sewer facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wallis | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Wallis completed construction and submitted the COCC for its sewer facilities project.
INF_SMID_LMI_20-065-035-C115_Wallis_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wallis | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-035-C115_Wallis_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Wallis | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Wallis had grant closeout documents under review for its Sewer Facilities project. Final payments were processed.
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Hallettsville had environmental review and engineering design underway for its flood and drainage facilities project.
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2020-10-01 | 2021 Q1
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2021-04-01 | 2021 Q3 | During this reporting period, the City of Hallettsville awarded a construction contract.
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Hallettsville completed construction procurement for its flood and drainage project.
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Hallettsville had construction underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Hallettsville had 50% of construction underway/complete for its Flood and Drainage project.
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Hallettsville had 70% of construction underway/complete for its flood and drainage project.
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Hallettsville had grant closeout documents under review for its Flood and Drainage project.
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Hallettsville had grant closeout documents under review for its drainage improvement project.
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2024-01-01 | 2024 Q2 | During the reporting period, this activity was administratively closed, fully expended, all required closeout data was entered into DRGR and Activity Status changed to Completed.
INF_SMID_LMI_20-065-036-C116_Hallettsville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Hallettsville, City of | 2024-04-01 | 2024 Q3 | Activity budget and obligation reduced for closeout. This activity has been fully closed, all accomplishments entered, and activity status updated to Completed.
INF_SMID_LMI_20-065-041-C122_KarnesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Karnes, County of | 2019-10-01 | 2020 Q1
INF_SMID_LMI_20-065-041-C122_KarnesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Karnes, County of | 2020-04-01 | 2020 Q3 | During the reporting period, the Karnes County had environmental review and engineering design underway for its flood and drainage facilities project.
INF_SMID_LMI_20-065-041-C122_KarnesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Karnes, County of | 2020-07-01 | 2020 Q4 | During the reporting period, Karnes County had environmental review and engineering design underway for its flood and drainage project.
INF_SMID_LMI_20-065-041-C122_KarnesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Karnes, County of | 2020-10-01 | 2021 Q1
INF_SMID_LMI_20-065-041-C122_KarnesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Karnes, County of | 2021-01-01 | 2021 Q2 | During the reporting period, Karnes County had engineering design and environmental complete for its flood and drainage project.
INF_SMID_LMI_20-065-041-C122_KarnesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Karnes, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Karnes County had completed environmental and engineering design for its Flood and Drainage Facilities project.
INF_SMID_LMI_20-065-041-C122_KarnesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Karnes, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Karnes County completed construction and submitted the COCC for its flood and drainage project.
INF_SMID_LMI_20-065-041-C122_KarnesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Karnes, County of | 2022-07-01 | 2022 Q4 | Added a 0 to the elevated structures measure in the Action Plan module in order to be submitted.
INF_SMID_LMI_20-065-041-C122_KarnesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Karnes, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Karnes County had closeout documents under review for its Flood and Drainage project.
INF_SMID_LMI_20-065-041-C122_KarnesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Karnes, County of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-041-C122_KarnesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Karnes, County of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Smiley had environmental review and engineering design underway for its street improvement project.
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Smiley completed environmental review and had engineering design is underway for its street improvement project.
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Smiley had engineering design underway and environmental complete for its street improvement project.
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2021-04-01 | 2021 Q3 | During the reporting period, Smiley had construction underway for its Street Improvements project.
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Smiley completed construction and is pending submission of construction completion documentation for its street improvements project.
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Smiley had completed construction and is pending submission of construction completion documentation for its Street Improvement project.
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Smiley completed construction and submitted grant closeout documents for its Street Improvement project.
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Smiley had grant closeout documents under review for its Street Improvement project.
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2025-04-01 | 2025 Q3 | Activity budget and obligation were reduced during the quarter as part of the closeout process.
INF_SMID_LMI_20-065-044-C130_Smiley | Street Improvements | Construction/reconstruction of streets | Smiley, City of | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2020-04-01 | 2020 Q3 | During the reporting period, Gonzales County had environmental review and engineering design underway for its Public Facilities project.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2020-07-01 | 2020 Q4
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2020-10-01 | 2021 Q1 | During the reporting period, Gonzales County had environmental review and engineering design underway for its public facilities project.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2021-01-01 | 2021 Q2 | During the reporting period, Gonzales County had engineering design underway and environmental complete for its public facilities project.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2021-04-01 | 2021 Q3 | During the reporting period, Gonzales County had completed environmental and engineering design is underway for its Public Facilities project.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2021-10-01 | 2022 Q1 | During the reporting period, Gonzales County had construction procurement underway for its Public Facilities project. Review of prior DRGR Vouchers resulted in revisions that lowered the total amount draw for this DRGR Activity.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2022-01-01 | 2022 Q2 | During the reporting period, Gonzales County had construction procurement underway for its Public Facilities project.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2022-07-01 | 2022 Q4 | During the reporting period, Gonzales County had 50% complete for its Public Facilities project.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2022-10-01 | 2023 Q1 | During the reporting period, Gonzales County had 50% of construction complete for its Public Facilities project.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2023-04-01 | 2023 Q3 | During the reporting period, Gonzales County completed construction and submitted the COCC for its Public Facilities project.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2023-07-01 | 2023 Q4 | During the reporting period, Gonzales County submitted closeout documents for its public facilities project.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Gonzales had expenditures related to the administration of the project.
INF_SMID_LMI_20-065-047-C139_Gonzales | Public Facilities | Rehabilitation/reconstruction of public facilities | Gonzales County | 2025-01-01 | 2025 Q2 | Updated the activity&apos;s projected number of beneficiaries to break out the low and moderate income individuals.
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Nixon had environmental review and engineering design underway for its flood and drainage project.
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2020-10-01 | 2021 Q1
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Nixon had acquisition underway for its flood and drainage project.
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Nixon had acquisition underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Nixon had acquisition underway for its flood and drainage facilities project.
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Nixon executed a contract change request to include adding a $100,000 Harvey Reallocation from the Golden Crescent Regional Planning Commission and term extension through 8/31/2025, as well as awarded their construction contract with work to begin in Q4 2024.
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Nixon received payment for the Notice to Proceed with Construction for their flood and drainage project.
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Nixon had construction underway for its flood and drainage project.
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Nixon continued construction for their Flood and Drainage project.
INF_SMID_LMI_20-065-051-C160_Nixon | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Nixon, City of | 2025-07-01 | 2025 Q4 | During the reporting period, construction is underway for the City of Nixon&apos;s Flood and Drainage project.
INF_SMID_LMI_20-065-052-C162_Iola | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-052-C162_Iola | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2020-04-01 | 2020 Q3 | During the reporting period , the City of Iola had environmental review underway for it&apos;s flood and drainage facilities project.
INF_SMID_LMI_20-065-052-C162_Iola | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2020-07-01 | 2020 Q4
INF_SMID_LMI_20-065-052-C162_Iola | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Iola had engineering design complete for its flood and drainage project.
INF_SMID_LMI_20-065-052-C162_Iola | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2021-04-01 | 2021 Q3 | During the reporting period, the city of Iola had construction underway for its Flood and Drainage Facilities project.
INF_SMID_LMI_20-065-052-C162_Iola | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_SMID_LMI_20-065-052-C162_Iola | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Iola completed construction and is pending submission of construction completion documentation for its flood and drainage facilities project.
INF_SMID_LMI_20-065-052-C162_Iola | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Iola had 95% of construction underway for its flood and drainage project.
INF_SMID_LMI_20-065-052-C162_Iola | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-052-C162_Iola | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-052-C162_Iola | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2025-04-01 | 2025 Q3 | During the reporting period the City of Iola had grant closeout documents under review for its flood and drainage facilities project.
INF_SMID_LMI_20-065-053-C163_Shiner | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Shiner, City of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-053-C163_Shiner | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Shiner, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Shiner had environmental review and engineering design underway for its flood and drainage facilities project.
INF_SMID_LMI_20-065-053-C163_Shiner | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Shiner, City of | 2020-10-01 | 2021 Q1
INF_SMID_LMI_20-065-053-C163_Shiner | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Shiner, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Shiner had engineering design underway and environmental complete for its flood and drainage project.
INF_SMID_LMI_20-065-053-C163_Shiner | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Shiner, City of | 2021-04-01 | 2021 Q3 | During this reporting period, the City of Shiner has construction underway for its flood and drainage project.
INF_SMID_LMI_20-065-053-C163_Shiner | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Shiner, City of | 2021-07-01 | 2021 Q4 | During the reporting?period,?the City of Shiner had 50% of construction?underway/complete for its Flood and Drainage project.
INF_SMID_LMI_20-065-053-C163_Shiner | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Shiner, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Shiner had construction underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-053-C163_Shiner | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Shiner, City of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-053-C163_Shiner | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Shiner, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the city of Shiner has grant closeout documents submitted for its Sewer facilities project.
INF_SMID_LMI_20-065-053-C163_Shiner | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Shiner, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-053-C163_Shiner | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Shiner, City of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-053-C163_Shiner | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Shiner, City of | 2024-04-01 | 2024 Q3 | Activity has been administratively closed during the quarter. All payments have been completed and all accomplishments were entered. Activity status has been updated to Completed.
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2020-04-01 | 2020 Q3 | During the reporting period , the City of Bedias had environmental review underway for it&apos;s flood and drainage facilities project.
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2020-07-01 | 2020 Q4
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Bedias completed environmental review for its flood and drainage project.
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Bedias had construction underway for its flood and drainage project.
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2022-07-01 | 2022 Q4 | Added a 0 to the elevated structures measure in the Action Plan module in order to be submitted.
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Bedias completed construction and is pending submission of construction completion documentation for its flood and drainage facilities project.
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Bedias completed construction and submitted the COCC for its flood and drainage facilities project
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2024-07-01 | 2024 Q4 | During the reporting period, the city of Bedias had grant closeout report approved.
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2024-10-01 | 2025 Q1 | During the reporting period, this contract was administratively closed in DRGR. All funds have been drawn, and accomplishment and beneficiaries were entered.
INF_SMID_LMI_20-065-056-C167_Bedias | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Bedias, City of | 2025-01-01 | 2025 Q2 | Activity budget and obligation reduced according to closeout documentation, this activity is fully completed and administratively closed.
INF_SMID_LMI_20-065-058-C170_Somerville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Somerville | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-058-C170_Somerville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Somerville | 2021-01-01 | 2021 Q2 | During the reporting period, Somerville had engineering design underway and environmental complete for its flood and drainage facilities project.
INF_SMID_LMI_20-065-058-C170_Somerville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Somerville | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Somerville had preliminary engineering design underway for its flood and drainage project.
INF_SMID_LMI_20-065-058-C170_Somerville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Somerville | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-058-C170_Somerville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Somerville | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-058-C170_Somerville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Somerville | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Somerville submitted grant closeout documents for its flood and drainage project.
INF_SMID_LMI_20-065-058-C170_Somerville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Somerville | 2024-01-01 | 2024 Q2 | During this reporting period the City of Somerville was closed for its Flood and Drainage project.
INF_SMID_LMI_20-065-058-C170_Somerville | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Somerville | 2024-04-01 | 2024 Q3 | Activity budget and obligation reduced for closeout. This activity has been fully closed, all accomplishments entered, and activity status updated to Completed.
INF_SMID_LMI_20-065-059-C171_ToddMission_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-059-C171_ToddMission_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Todd Mission had environmental review underway for it&apos;s flood and drainage project.
INF_SMID_LMI_20-065-059-C171_ToddMission_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2020-10-01 | 2021 Q1
INF_SMID_LMI_20-065-059-C171_ToddMission_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Todd Mission had 50% of construction complete for its Flood and Drainage project. Review of prior DRGR Vouchers resulted in revisions that lowered the total amount draw for this DRGR Activity.
INF_SMID_LMI_20-065-059-C171_ToddMission_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-059-C171_ToddMission_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Todd Mission had 70% of construction underway/complete for its flood and drainage project.
INF_SMID_LMI_20-065-059-C171_ToddMission_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Todd Mission had grant closeout documents under review for its flood and drainage facilities project.
INF_SMID_LMI_20-065-059-C171_ToddMission_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-059-C171_ToddMission_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2025-04-01 | 2025 Q3 | During the reporting period the City of Todd Mission had final payment processed and paid. Closeout underway for its flood and drainage facility project.
INF_SMID_LMI_20-065-059-C171_ToddMission_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_SMID_LMI_20-065-059-C171_ToddMission_SI | Street Improvements | Construction/reconstruction of streets | Todd Mission, City of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-059-C171_ToddMission_SI | Street Improvements | Construction/reconstruction of streets | Todd Mission, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Todd Mission had environmental review underway for it&apos;s street improvement project.
INF_SMID_LMI_20-065-059-C171_ToddMission_SI | Street Improvements | Construction/reconstruction of streets | Todd Mission, City of | 2020-10-01 | 2021 Q1
INF_SMID_LMI_20-065-059-C171_ToddMission_SI | Street Improvements | Construction/reconstruction of streets | Todd Mission, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Todd Mission had 50% of construction complete for its Street Improvement project.
INF_SMID_LMI_20-065-059-C171_ToddMission_SI | Street Improvements | Construction/reconstruction of streets | Todd Mission, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Todd Mission had 50% of construction underway/complete for its street improvements project.
INF_SMID_LMI_20-065-059-C171_ToddMission_SI | Street Improvements | Construction/reconstruction of streets | Todd Mission, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Todd Mission had grant closeout documents under review for its street improvements project.
INF_SMID_LMI_20-065-059-C171_ToddMission_SI | Street Improvements | Construction/reconstruction of streets | Todd Mission, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-059-C171_ToddMission_SI | Street Improvements | Construction/reconstruction of streets | Todd Mission, City of | 2025-04-01 | 2025 Q3 | During the reporting period the City of Todd Mission had final payment processed and paid. Closeout underway for its street improvements project.
INF_SMID_LMI_20-065-059-C171_ToddMission_SI | Street Improvements | Construction/reconstruction of streets | Todd Mission, City of | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_SMID_LMI_20-065-063-C181_Cuero_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cuero, City of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-063-C181_Cuero_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cuero, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Cuero had engineering design and environmental complete for its flood and drainage project.
INF_SMID_LMI_20-065-063-C181_Cuero_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cuero, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Cuero had completed construction procurement for its Flood and Drainage project.
INF_SMID_LMI_20-065-063-C181_Cuero_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cuero, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Cuero has 50% of construction complete for its Flood and Drainage project.
INF_SMID_LMI_20-065-063-C181_Cuero_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cuero, City of | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained budget changes and end date extension.
INF_SMID_LMI_20-065-063-C181_Cuero_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cuero, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Cuero completed construction and is pending submission of construction completion documentation for its Flood and Drainage project.
INF_SMID_LMI_20-065-063-C181_Cuero_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cuero, City of | 2023-07-01 | 2023 Q4 | Amendment reduced scope and reallocated funds to related activities.
INF_SMID_LMI_20-065-063-C181_Cuero_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Cuero, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Cuero completed construction and submitted the COCC for its flood and drainage project.
INF_SMID_LMI_20-065-063-C181_Cuero_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-063-C181_Cuero_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Cuero had engineering design and environmental complete for its sewer facilities project.
INF_SMID_LMI_20-065-063-C181_Cuero_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Cuero had completed construction procurement for its Sewer Facilities project.
INF_SMID_LMI_20-065-063-C181_Cuero_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Cuero had 50% of construction complete for its Sewer Facilities project.
INF_SMID_LMI_20-065-063-C181_Cuero_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained budget changes and end date extension.
INF_SMID_LMI_20-065-063-C181_Cuero_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Cuero completed construction and is pending submission of construction completion documentation for its Sewer Facilities project.
INF_SMID_LMI_20-065-063-C181_Cuero_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Cuero completed construction and submitted the COCC for its Sewer Facilities project.
INF_SMID_LMI_20-065-063-C181_Cuero_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2023-07-01 | 2023 Q4 | Amendment reduced scope and reallocated funds to related activities.
INF_SMID_LMI_20-065-063-C181_Cuero_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Cuero had construction complete for its sewer project.
INF_SMID_LMI_20-065-063-C181_Cuero_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Cuero completed construction and submitted the COCC for its sewer facilities project.
INF_SMID_LMI_20-065-063-C181_Cuero_SI | Street Improvements | Construction/reconstruction of streets | Cuero, City of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-063-C181_Cuero_SI | Street Improvements | Construction/reconstruction of streets | Cuero, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Cuero had engineering design and environmental complete for its street improvement project.
INF_SMID_LMI_20-065-063-C181_Cuero_SI | Street Improvements | Construction/reconstruction of streets | Cuero, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Cuero had completed construction procurement for its Street Improvements project.
INF_SMID_LMI_20-065-063-C181_Cuero_SI | Street Improvements | Construction/reconstruction of streets | Cuero, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Cuero had 50% of construction complete for its Street Improvement project.
INF_SMID_LMI_20-065-063-C181_Cuero_SI | Street Improvements | Construction/reconstruction of streets | Cuero, City of | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained budget changes and end date extension.
INF_SMID_LMI_20-065-063-C181_Cuero_SI | Street Improvements | Construction/reconstruction of streets | Cuero, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Cuero completed construction and is pending submission of construction completion documentation for its Street Improvement project.
INF_SMID_LMI_20-065-063-C181_Cuero_SI | Street Improvements | Construction/reconstruction of streets | Cuero, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Cuero completed construction and submitted the COCC for its Street Improvement project.
INF_SMID_LMI_20-065-063-C181_Cuero_SI | Street Improvements | Construction/reconstruction of streets | Cuero, City of | 2023-07-01 | 2023 Q4 | Amendment increased scope and reallocated funds from related activity.
INF_SMID_LMI_20-065-063-C181_Cuero_SI | Street Improvements | Construction/reconstruction of streets | Cuero, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Cuero had construction complete for its Street Improvement project.
INF_SMID_LMI_20-065-063-C181_Cuero_SI | Street Improvements | Construction/reconstruction of streets | Cuero, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Cuero completed construction and submitted the COCC for its street improvements projects.
INF_SMID_LMI_20-065-063-C181_Cuero_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-063-C181_Cuero_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Cuero had engineering design and environmental complete for its water facilities project.
INF_SMID_LMI_20-065-063-C181_Cuero_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Cuero had completed construction procurement for its Water Facilities project.
INF_SMID_LMI_20-065-063-C181_Cuero_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Cuero had 50% of construction complete for its water facilities project.
INF_SMID_LMI_20-065-063-C181_Cuero_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained budget changes and end date extension.
INF_SMID_LMI_20-065-063-C181_Cuero_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Cuero completed construction and is pending submission of construction completion documentation for its Water Facilities project.
INF_SMID_LMI_20-065-063-C181_Cuero_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Cuero completed construction and submitted the COCC for its Water Facilities project.
INF_SMID_LMI_20-065-063-C181_Cuero_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2023-07-01 | 2023 Q4 | Amendment increased scope and reallocated funds from related activity.
INF_SMID_LMI_20-065-063-C181_Cuero_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Cuero had construction complete for its water facilities project.
INF_SMID_LMI_20-065-063-C181_Cuero_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Cuero, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Cuero completed construction and submitted the COCC for its water facilities project.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2021-10-01 | 2022 Q1 | Activity was revised from benefitting HUD designated most impacted and distressed areas to the State designated most impact and distressed areas.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2022-01-01 | 2022 Q2 | During the reporting period, Calhoun County had construction procurement underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2022-07-01 | 2022 Q4 | During the reporting period, the County of Calhoun had construction underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2022-10-01 | 2023 Q1 | During the reporting period, Calhoun County had construction underway for its Flood and Drainage projects.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2023-01-01 | 2023 Q2 | During the reporting period, Calhoun County had construction underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2023-04-01 | 2023 Q3 | During the reporting period, the Calhoun County had construction underway for its Flood and Drainage project (Lane Road Drainage). The negative amount in the Q2 expenditure column is due to an update to the contract in TIGR.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2023-07-01 | 2023 Q4 | During the reporting period, Calhoun County had construction underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2023-10-01 | 2024 Q1 | During the reporting period, Calhoun County had 50% of construction completed for its flood and drainage project
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2024-01-01 | 2024 Q2 | During the reporting period, a contract amendment was executed that increased the amount of funding for the subrecipient and reallocated some of the funding amongst the activities of the contract.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2024-04-01 | 2024 Q3 | During the reporting period, Calhoun County had construction underway for its Lane Road project. Rebid was necessary for LCB. Construction complete on its Communication Systems Improvements project.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2024-07-01 | 2024 Q4 | During the reporting period, the County had construction underway for its flood and drainage project.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2024-10-01 | 2025 Q1 | During the reporting period, the County had construction underway for its flood and drainage project. Phase 1 has been completed for Lane Road Drainage, Phase 2 is pending.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2025-01-01 | 2025 Q2 | During the reporting period, the County had construction underway for its Public Facilities project. Phase 1 has been completed for Lane Road Drainage, Phase 2 is pending its bid phase.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2025-04-01 | 2025 Q3 | Phase 1 has been completed for Lane Road Drainage, Phase 2 construction is underway.
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2025-07-01 | 2025 Q4 | During the reporting period, Calhoun County had construction underway for its flood and drainage facilities. (e.g. sewer facilities, street improvements, etc.)
INF_SMID_LMI_20-065-064-C182_CalhounCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | CALHOUN COUNTY | 2025-10-01 | 2026 Q1 | During the reporting period, Calhoun County had construction underway for its flood and drainage facilities.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2020-07-01 | 2020 Q4 | During the reporting period, Austin County had environmental review underway for its street improvement project.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2020-10-01 | 2021 Q1 | During the reporting period, Austin County had engineering design underway for its street improvements project.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2021-04-01 | 2021 Q3 | During the reporting period, Austin County had engineering design underway for its Street Improvements project.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2021-10-01 | 2022 Q1 | During the reporting period, Austin County had preliminary engineering design underway for its street improvements project. Review of prior DRGR Vouchers resulted in revisions that lowered the total amount draw for this DRGR Activity.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2022-04-01 | 2022 Q3 | During the reporting period, Austin County had construction procurement underway for its street improvement project.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2022-07-01 | 2022 Q4 | During the reporting period, Austin County had construction procurement underway for its street improvements project. Costs reallocated to UN activity.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2023-04-01 | 2023 Q3 | During the reporting period, Austin County completed construction procurement for its street improvement project
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2024-01-01 | 2024 Q2 | During the reporting period, Austin County completed activities for Stockhold Road.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2024-04-01 | 2024 Q3 | During the reporting period, Austin County completed activities for New Bremen Road.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2024-07-01 | 2024 Q4 | During the reporting?period,?Austin County had 50% of construction?sites completed for its Street Improvements project. ?
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2024-10-01 | 2025 Q1 | During the reporting period, Austin County had 75% of construction complete for its street improvements project.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2025-01-01 | 2025 Q2 | During the reporting period, Austin County had 85% of construction complete for its Street Improvements project.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2025-04-01 | 2025 Q3 | During the reporting period, Austin County had 90% of construction completed for its Street Improvements project.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2025-07-01 | 2025 Q4 | During the reporting period, Austin County had construction underway for its Street Improvements project.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2025-10-01 | 2026 Q1 | During the reporting period Austin County had construction underway and 75% complete for its street improvements project.
INF_SMID_LMI_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2026-01-01 | 2026 Q2
INF_SMID_LMI_20-065-067-C193_Hempstead_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-067-C193_Hempstead_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Hempstead had environmental review underway for its sewer facilities project.
INF_SMID_LMI_20-065-067-C193_Hempstead_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Hempstead had engineering design underway for its sewer facilities project.
INF_SMID_LMI_20-065-067-C193_Hempstead_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2021-01-01 | 2021 Q2 | During the reporting period, Hempstead had engineering design underway and environmental complete for its sewer facilities project.
INF_SMID_LMI_20-065-067-C193_Hempstead_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Hempstead had construction underway for its sewer facilities project. Construction is 90% complete.
INF_SMID_LMI_20-065-067-C193_Hempstead_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Hempstead had 50% of construction complete for its sewer facilities project. Correction to payments out of incorrect DRGR activities.
INF_SMID_LMI_20-065-067-C193_Hempstead_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-067-C193_Hempstead_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-067-C193_Hempstead_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2024-01-01 | 2024 Q2 | During the reporting period, City of Hempstead had Closeout Documents under review for its Sewer Project
INF_SMID_LMI_20-065-067-C193_Hempstead_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2020-07-01 | 2020 Q4
INF_SMID_LMI_20-065-067-C193_Hempstead_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Hempstead had engineering design underway for its water facilities project.
INF_SMID_LMI_20-065-067-C193_Hempstead_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2021-01-01 | 2021 Q2 | During the reporting period, Hempstead had engineering design underway and environmental complete for its water facilities project.
INF_SMID_LMI_20-065-067-C193_Hempstead_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Hempstead had construction underway for its sewer facilities project. Construction is 90% complete.
INF_SMID_LMI_20-065-067-C193_Hempstead_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Hempstead had 50% of construction complete for its water facilities project.
INF_SMID_LMI_20-065-067-C193_Hempstead_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-067-C193_Hempstead_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Hempstead | 2024-01-01 | 2024 Q2 | During the reporting period, City of Hempstead had Closeout Documents under review for its Water Project
INF_SMID_LMI_20-065-074-C201_Yorktown | Street Improvements | Construction/reconstruction of streets | Yorktown, City of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-074-C201_Yorktown | Street Improvements | Construction/reconstruction of streets | Yorktown, City of | 2020-04-01 | 2020 Q3 | During the reporting period, the City of Yorktown had environmental review and engineering design underway for its Street Improvements project.
INF_SMID_LMI_20-065-074-C201_Yorktown | Street Improvements | Construction/reconstruction of streets | Yorktown, City of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Yorktown completed environmental review and engineering design is underway for its street improvement project.
INF_SMID_LMI_20-065-074-C201_Yorktown | Street Improvements | Construction/reconstruction of streets | Yorktown, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Yorktown completed environmental review and had engineering design underway for its street improvements.
INF_SMID_LMI_20-065-074-C201_Yorktown | Street Improvements | Construction/reconstruction of streets | Yorktown, City of | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Yorktown had engineering design underway and environmental complete for its street improvement project.
INF_SMID_LMI_20-065-074-C201_Yorktown | Street Improvements | Construction/reconstruction of streets | Yorktown, City of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Yorktown had construction underway for its street improvements project.
INF_SMID_LMI_20-065-074-C201_Yorktown | Street Improvements | Construction/reconstruction of streets | Yorktown, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Yorktown had 50% of construction underway/complete for its Street Improvement project.
INF_SMID_LMI_20-065-074-C201_Yorktown | Street Improvements | Construction/reconstruction of streets | Yorktown, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Yorktown completed construction and submitted grant closeout documents for its Street Improvement project.
INF_SMID_LMI_20-065-074-C201_Yorktown | Street Improvements | Construction/reconstruction of streets | Yorktown, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Yorktown had grant closeout documents under review for its Street Improvement project.
INF_SMID_LMI_20-065-074-C201_Yorktown | Street Improvements | Construction/reconstruction of streets | Yorktown, City of | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Yorktown had grant closeout documents under review for its Street Improvement project.
INF_SMID_LMI_20-065-074-C201_Yorktown | Street Improvements | Construction/reconstruction of streets | Yorktown, City of | 2023-07-01 | 2023 Q4 | Reduced funds expended to correct DRGR error due to parent/child grant rollup calculation.
INF_SMID_LMI_20-065-075-C203_Gonzales_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales, City Of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-075-C203_Gonzales_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales, City Of | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Gonzales had engineering design underway for its sewer facilities project.
INF_SMID_LMI_20-065-075-C203_Gonzales_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales, City Of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Gonzales had environmental review and engineering design underway for its sewer project.
INF_SMID_LMI_20-065-075-C203_Gonzales_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales, City Of | 2021-01-01 | 2021 Q2 | During the reporting period, the City Of Gonzales had engineering design complete and environmental underway for its sewer facilities project.
INF_SMID_LMI_20-065-075-C203_Gonzales_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales, City Of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Gonzales completed construction procurement for its Sewer Facilities project.
INF_SMID_LMI_20-065-075-C203_Gonzales_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales, City Of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Gonzales had construction underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-075-C203_Gonzales_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales, City Of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Gonzales has construction underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-075-C203_Gonzales_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales, City Of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Gonzales completed construction and is pending submission of the construction completion documents for its flood and drainage facilities project.
INF_SMID_LMI_20-065-075-C203_Gonzales_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales, City Of | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_SMID_LMI_20-065-075-C203_Gonzales_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales, City Of | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Gonzales had grant closeout documents under review for its Sewer Facilities project.
INF_SMID_LMI_20-065-075-C203_Gonzales_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales, City Of | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Gonzales submitted closeout documents for its sewer facilities project.
INF_SMID_LMI_20-065-075-C203_Gonzales_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales, City Of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Point Comfort had environmental review underway for it&apos;s flood and drainage project.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2020-10-01 | 2021 Q1 | During this reporting period, the City of Point Comfort had environmental review and engineering design underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2021-07-01 | 2021 Q4 | During the reporting period, Point Comfort had completed engineering design and had construction procurement underway for its flood and drainage project.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Point Comfort had construction procurement underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Point Comfort had construction procurement underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Point Comfort had construction underway for its flood and drainage facilities project.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2023-04-01 | 2023 Q3 | Amendment moved budget to related activity and increased projected performance measures. Area Benefit type corrected.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2023-10-01 | 2024 Q1 | During the reporting period, Point Comfort construction completed for its flood and drainage project amending budget Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2024-01-01 | 2024 Q2 | During the reporting period, Point Comfort completed construction for its Flood and Drainage Facilities project.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2024-04-01 | 2024 Q3 | During the reporting period, Point Comfort completed construction for its Flood and Drainage Facilities project.
INF_SMID_LMI_20-065-076-C218_PointComfort_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Point Comfort City Hall | 2024-07-01 | 2024 Q4 | During the reporting period, Point Comfort submitted grant closeout documents for its Flood and Drainage project.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Point Comfort had environmental review underway for it&apos;s street improvements project.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2020-10-01 | 2021 Q1 | During this reporting period, the City of Point Comfort had environmental review and engineering design underway for its Street Improvements project.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2021-07-01 | 2021 Q4 | During the reporting period, Point Comfort had completed engineering design and had construction procurement underway for its street improvements project.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Point Comfort had construction procurement underway for its Street Improvements project.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Point Comfort had construction procurement underway for its Street Improvements project.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Point Comfort had construction underway for its Street Improvements project.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Point Comfort had 50% of construction complete for its Street Improvements project.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2023-04-01 | 2023 Q3 | Amendment moved funds to related activity. Area Benefit type corrected.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2023-10-01 | 2024 Q1 | During the reporting period, Point Comfort construction completed for its street improvement project amending budget Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2024-01-01 | 2024 Q2 | During the reporting period, Point Comfort completed construction for its Street Improvement project.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2024-04-01 | 2024 Q3 | During the reporting period, Point Comfort completed construction for its Street Improvement project.
INF_SMID_LMI_20-065-076-C218_PointComfort_SI | Street Improvements | Construction/reconstruction of streets | Point Comfort City Hall | 2024-07-01 | 2024 Q4 | During the reporting period, Point Comfort submitted grant closeout documents for its Street Improvements project.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Point Comfort had environmental review underway for it&apos;s water facilities project.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2020-10-01 | 2021 Q1 | During this reporting period, the City of Point Comfort had environmental review and engineering design underway for its Water Facilities project.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2021-07-01 | 2021 Q4 | During the reporting period, Point Comfort had completed engineering design and had construction procurement underway for its water facilities project.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Point Comfort had construction underway for its Water Facilities project.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Point Comfort had 50% of construction complete for its Water Facilities project.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2022-10-01 | 2023 Q1 | During the reporting period the City of Point Comfort completed construction and is pending submission of construction closeout documentation for its Water Facilities project.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Point Comfort had 50% of construction complete for its Water Facilities project.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity. Area Benefit type corrected.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2023-10-01 | 2024 Q1 | During the reporting period, Point Comfort construction 75% completed for its WI Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2024-01-01 | 2024 Q2 | During the reporting period, Point Comfort completed construction for its Water Facilities project.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2024-04-01 | 2024 Q3 | During the reporting period, Point Comfort completed construction for its Water Facilities project.
INF_SMID_LMI_20-065-076-C218_PointComfort_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Point Comfort City Hall | 2024-07-01 | 2024 Q4 | During the reporting period, corrections to admin fields in DRGR were made. No actual change during the quarter and this activity is still ongoing.
INF_SMID_LMI_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2020-04-01 | 2020 Q3 | During the reporting period, Colorado County had environmental review and engineering design underway for its flood and drainage facilities project.
INF_SMID_LMI_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2020-07-01 | 2020 Q4
INF_SMID_LMI_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2020-10-01 | 2021 Q1 | During this reporting period, Colorado County had environmental and engineering design underway for its flood and drainage project.
INF_SMID_LMI_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Colorado County had 50% of construction underway for its flood and drainage facilities project.
INF_SMID_LMI_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Colorado County had 50% of construction underway/complete for its Flood and Drainage Facilities project.
INF_SMID_LMI_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2022-01-01 | 2022 Q2 | During the reporting period, the Colorado County completed construction and is pending submission of construction completion documentation for it&apos;s Flood & Drainage project.
INF_SMID_LMI_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2022-04-01 | 2022 Q3 | During the reporting period, the Colorado County had 50% of construction underway/complete for its Flood and Drainage Facilities project Correction to drawn amount.
INF_SMID_LMI_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2023-07-01 | 2023 Q4 | During the reporting period, the Colorado County had grant closeout documents under review for its F&D project.
INF_SMID_LMI_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2023-10-01 | 2024 Q1 | During the reporting period, the Colorado County had grant closeout documents under review for its F&D project
INF_SMID_LMI_20-065-079-C231_ColoradoCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Colorado, County of | 2024-04-01 | 2024 Q3 | Activity has been administratively closed during the quarter. All payments have been completed and all accomplishments were entered. Activity status has been updated to Completed.
INF_SMID_LMI_20-065-085-C246_Yoakum_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | YOAKUM, CITY OF | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-085-C246_Yoakum_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | YOAKUM, CITY OF | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Yoakum had environmental review and engineering design underway for its flood and drainage project.
INF_SMID_LMI_20-065-085-C246_Yoakum_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | YOAKUM, CITY OF | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained performance statement changes, budget changes, and end date extension.
INF_SMID_LMI_20-065-085-C246_Yoakum_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | YOAKUM, CITY OF | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Yoakum had 50% of construction complete for its Flood and Drainage project.
INF_SMID_LMI_20-065-085-C246_Yoakum_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | YOAKUM, CITY OF | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-085-C246_Yoakum_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | YOAKUM, CITY OF | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Yoakum had 50% of construction complete for its flood and drainage project.
INF_SMID_LMI_20-065-085-C246_Yoakum_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | YOAKUM, CITY OF | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Yoakum completed construction for its Flood and Drainage project.
INF_SMID_LMI_20-065-085-C246_Yoakum_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | YOAKUM, CITY OF | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Yoakum had completed construction and submitted the COCC for its Flood and Drainage project
INF_SMID_LMI_20-065-085-C246_Yoakum_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | YOAKUM, CITY OF | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Yoakum submitted grant closeout documents for its flood and drainage project.
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Yoakum had environmental review and engineering design underway for its public facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Yoakum completed environmental review and engineering design for its public facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Yoakum had completed construction procurement for its Public Facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Yoakum had construction underway for one of its Public Facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Yoakum completed construction procurement for its Public Facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Yoakum had construction underway for its Public Facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Yoakum had construction underway for its Public Facility project.
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Yoakum had completed construction and submitted the COCC for its public facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Yoakum completed construction for its Public Facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Yoakum had completed construction and submitted the COCC for its Public Facilities project
INF_SMID_LMI_20-065-085-C246_Yoakum_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | YOAKUM, CITY OF | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Yoakum submitted grant closeout documents for its public facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-085-C246_Yoakum_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Yoakum had environmental review and engineering design underway for its sewer project.
INF_SMID_LMI_20-065-085-C246_Yoakum_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Yoakum had construction underway for its sewer facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Yoakum had completed construction procurement for its Sewer Facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-085-C246_Yoakum_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained performance statement changes, budget changes, and end date extension.
INF_SMID_LMI_20-065-085-C246_Yoakum_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_SMID_LMI_20-065-085-C246_Yoakum_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-085-C246_Yoakum_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Yoakum, had 50% of construction complete for its sewer facilities project .
INF_SMID_LMI_20-065-085-C246_Yoakum_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Yoakum had completed construction and submitted the COCC for its Sewer Facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Yoakum submitted grant closeout documents for its sewer facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_SI | Street Improvements | Construction/reconstruction of streets | YOAKUM, CITY OF | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-085-C246_Yoakum_SI | Street Improvements | Construction/reconstruction of streets | YOAKUM, CITY OF | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Yoakum had environmental review and engineering design underway for its street improvement project.
INF_SMID_LMI_20-065-085-C246_Yoakum_SI | Street Improvements | Construction/reconstruction of streets | YOAKUM, CITY OF | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Yoakum had construction underway for its street improvements project.
INF_SMID_LMI_20-065-085-C246_Yoakum_SI | Street Improvements | Construction/reconstruction of streets | YOAKUM, CITY OF | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Yoakum had construction underway for its Street Improvements project.
INF_SMID_LMI_20-065-085-C246_Yoakum_SI | Street Improvements | Construction/reconstruction of streets | YOAKUM, CITY OF | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Yoakum had 50% of construction underway for its Street Improvement project.
INF_SMID_LMI_20-065-085-C246_Yoakum_SI | Street Improvements | Construction/reconstruction of streets | YOAKUM, CITY OF | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Yoakum had construction underway for its Street Improvement project.
INF_SMID_LMI_20-065-085-C246_Yoakum_SI | Street Improvements | Construction/reconstruction of streets | YOAKUM, CITY OF | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_SMID_LMI_20-065-085-C246_Yoakum_SI | Street Improvements | Construction/reconstruction of streets | YOAKUM, CITY OF | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-085-C246_Yoakum_SI | Street Improvements | Construction/reconstruction of streets | YOAKUM, CITY OF | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Yoakum had completed construction and submitted the COCC for its Street Improvements project.
INF_SMID_LMI_20-065-085-C246_Yoakum_SI | Street Improvements | Construction/reconstruction of streets | YOAKUM, CITY OF | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Yoakum submitted grant closeout documents for its street improvements project.
INF_SMID_LMI_20-065-085-C246_Yoakum_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-085-C246_Yoakum_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Yoakum had environmental review and engineering design underway for its water facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Yoakum had construction underway for its water facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Yoakum had completed construction procurement for its Water Facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-085-C246_Yoakum_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2022-04-01 | 2022 Q3 | Amendment took effect during the quarter and contained performance statement changes, budget changes, and end date extension.
INF_SMID_LMI_20-065-085-C246_Yoakum_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_SMID_LMI_20-065-085-C246_Yoakum_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-085-C246_Yoakum_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Yoakum had 50% of construction complete for its water facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Yoakum had completed construction and submitted the COCC for its Water Facilities project.
INF_SMID_LMI_20-065-085-C246_Yoakum_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | YOAKUM, CITY OF | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Yoakum submitted grant closeout documents for its water facilities project.
INF_SMID_LMI_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Jackson County had engineering design underway for its street improvements project.
INF_SMID_LMI_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2021-01-01 | 2021 Q2 | During the reporting period, Jackson County had engineering design underway and environmental complete for its street improvement project.
INF_SMID_LMI_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Jackson County completed engineering design for its street improvements project.
INF_SMID_LMI_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Jackson County had construction underway for its street improvement project.
INF_SMID_LMI_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Jackson County had construction underway for its street improvement project.
INF_SMID_LMI_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2022-07-01 | 2022 Q4 | During the reporting period, Jackson County had construction complete and the Certificate of Construction Completion underway for its street improvement projects.
INF_SMID_LMI_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Jackson County has completed construction and is in the closeout process.
INF_SMID_LMI_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2025-07-01 | 2025 Q4 | During the reporting period, Jackson County has completed construction and is in its closeout period.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_SI | Street Improvements | Construction/reconstruction of streets | Goliad, County of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-099-C271_GoliadCounty_SI | Street Improvements | Construction/reconstruction of streets | Goliad, County of | 2020-07-01 | 2020 Q4 | During the reporting period, Goliad County had environmental review and engineering design underway for its street improvement project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_SI | Street Improvements | Construction/reconstruction of streets | Goliad, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Goliad County had environmental review and engineering design underway for its street improvement project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_SI | Street Improvements | Construction/reconstruction of streets | Goliad, County of | 2021-01-01 | 2021 Q2 | During the reporting period, Goliad County had engineering design underway and environmental complete for its street improvement project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_SI | Street Improvements | Construction/reconstruction of streets | Goliad, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Goliad County had completed environmental and engineering design underway for its Street Improvements project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_SI | Street Improvements | Construction/reconstruction of streets | Goliad, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Goliad County had construction underway for its Street Improvement project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_SI | Street Improvements | Construction/reconstruction of streets | Goliad, County of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_SI | Street Improvements | Construction/reconstruction of streets | Goliad, County of | 2022-04-01 | 2022 Q3 | During the reporting period, Goliad County had construction underway for its street improvement project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_SI | Street Improvements | Construction/reconstruction of streets | Goliad, County of | 2022-07-01 | 2022 Q4 | During the reporting period, Goliad County completed construction and is pending submission of construction completion documents for its Street Improvements project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_SI | Street Improvements | Construction/reconstruction of streets | Goliad, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Goliad County had construction complete and the COCC underway for its Street Improvements project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_SI | Street Improvements | Construction/reconstruction of streets | Goliad, County of | 2023-01-01 | 2023 Q2 | During the reporting period, Goliad County had construction complete and submitted the COCC for its Street Improvement project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_SI | Street Improvements | Construction/reconstruction of streets | Goliad, County of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, County of | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-099-C271_GoliadCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, County of | 2020-07-01 | 2020 Q4 | During the reporting period, Goliad County had environmental review and engineering design underway for its water facilities project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Goliad County had environmental review and engineering design underway for its water facilities project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Goliad County had completed environmental and engineering design underway for its Water Facilities project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Goliad County had construction underway for its Water Facilities project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, County of | 2022-04-01 | 2022 Q3 | During the reporting period, Goliad County had construction underway for its Water Facilities project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, County of | 2022-07-01 | 2022 Q4 | During the reporting period, Goliad County completed construction and is pending submission of construction completion documents for its Water Facilities project. Costs moved to UN activity.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Goliad County had construction complete and the COCC underway for its Water Facilities project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, County of | 2023-01-01 | 2023 Q2 | During the reporting period, Goliad County has construction complete and submitted the COCC for its Water Facilities project.
INF_SMID_LMI_20-065-099-C271_GoliadCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, County of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-100-C273_GrimesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Grimes County | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-100-C273_GrimesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Grimes County | 2021-01-01 | 2021 Q2 | During the reporting period, Grimes County had engineering design complete for its flood and drainage project.
INF_SMID_LMI_20-065-100-C273_GrimesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Grimes County | 2021-04-01 | 2021 Q3 | During the reporting period, Grimes had construction underway for its Flood and Drainage Facilities project.
INF_SMID_LMI_20-065-100-C273_GrimesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Grimes County | 2021-10-01 | 2022 Q1 | During the reporting period, Grimes County had 50% of construction complete for its Flood and Drainage project.
INF_SMID_LMI_20-065-100-C273_GrimesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Grimes County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_LMI_20-065-100-C273_GrimesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Grimes County | 2022-07-01 | 2022 Q4 | During the reporting period, Grimes County completed construction and is pending submission of construction completion documents for its Flood and Drainage project.
INF_SMID_LMI_20-065-100-C273_GrimesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Grimes County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-100-C273_GrimesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Grimes County | 2025-04-01 | 2025 Q3 | During the reporting period, Grimes County&apos;s final PD draw was pad.
INF_SMID_LMI_20-065-100-C273_GrimesCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Grimes County | 2025-07-01 | 2025 Q4 | During the reporting period, the Grimes County had no activity. Closeout is in the final closeout stages.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Seadrift had environmental review underway for it&apos;s public facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2020-10-01 | 2021 Q1 | During this reporting period, the City of Seadrift had environmental review and engineering design underway for its Public Facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2021-04-01 | 2021 Q3 | During the reporting period, Seadrift had construction underway for its Public Facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Seadrift had completed environmental review and had engineering design underway for its public facilities projects.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Seadrift had construction underway for its Public Facilities projects.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Seadrift had construction complete and CoCC underway for its Public Facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Seadrift had completed construction and submitted the CoCC for its Public Facilities projects.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Seadrift had completed construction and submitted the Certificate of Construction Completion for its Public Facilities projects.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Seadrift had construction underway for its Public Facilities projects.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Seadrift completed construction and submitted the COCC for two of its Public Facilities Projects (Bayside Park Erosion 12-15th St. and Fire Station Generator Projects).
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2023-07-01 | 2023 Q4 | During the Reporting Period, City of Seadrift had 100% of construction Complete for its current flood and drainage facility project, COCC for current projects submitted, amendment request submitted for additional project to utilize cost savings.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2024-07-01 | 2024 Q4 | ?During the reporting?period,?the City of Seadrift had construction?underway for its Public Facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Seadrift | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Seadrift completed construction and submitted the COCC for its Public Facilities Bayfront Seawall project and had preliminary¿engineering design underway for its Water Facilities Water Tank II project.
INF_SMID_LMI_20-065-103-C278_Seadrift_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-103-C278_Seadrift_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Seadrift had environmental review underway for it&apos;s sewer facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2020-10-01 | 2021 Q1
INF_SMID_LMI_20-065-103-C278_Seadrift_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Seadrift had completed environmental review and had preliminary engineering design underway for its sewer facilities projects.
INF_SMID_LMI_20-065-103-C278_Seadrift_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Seadrift had construction underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Seadrift had construction complete and CoCC underway for its Public Facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Seadrift completed construction and submitted the COCC for its Sewer Facilities project
INF_SMID_LMI_20-065-103-C278_Seadrift_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2024-07-01 | 2024 Q4 | Budget reduced and reallocated to associated Water Facilities activity.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2020-01-01 | 2020 Q2
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Seadrift had environmental review underway for it&apos;s water facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2020-10-01 | 2021 Q1 | During this reporting period, the City of Seadrift had environmental review and engineering design underway for its Water Facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2021-04-01 | 2021 Q3 | During the reporting period, Seadrift had construction underway for its Water Facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Seadrift had completed environmental review and had engineering design underway for its water facilities projects.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Seadrift had construction underway for its Water Facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Seadrift had construction complete and CoCC underway for its Public Facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Seadrift had construction complete and CoCC underway for its Water Facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Seadrift completed construction and submitted the COCC for its Water Facilities project.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2024-10-01 | 2025 Q1 | During the reporting period, the activity obligation was increased to match the contractual budget.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Seadrift had 75% of construction completed.
INF_SMID_LMI_20-065-103-C278_Seadrift_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Seadrift | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Seadrift had 80% of construction completed.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2020-07-01 | 2020 Q4 | During the reporting period, Walker County had environmental review underway for its street improvement project.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2020-10-01 | 2021 Q1 | During the reporting period, the Walker County had environmental review underway for its Street Improvements project.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2021-01-01 | 2021 Q2 | During the reporting period, Walker County had environmental review and engineering design underway for its Street Improvement Project.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2021-04-01 | 2021 Q3 | During the reporting period, Walker County had environmental review underway for its Street Improvements project. It is anticipated that the AUGF will be issued in July 2021.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2021-07-01 | 2021 Q4 | During the reporting period, Walker County had construction procurement underway for its street project. Negative balance for quarterly expenditure is a result of Clarification Form Adjustments.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2021-10-01 | 2022 Q1 | During the reporting period, Walker County had construction procurement underway for its Street Improvements project.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2022-01-01 | 2022 Q2 | During the reporting period, Walker County had construction activities underway for its street improvements project.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2022-04-01 | 2022 Q3 | During the reporting period, Walker County had construction activities underway for its street improvements project.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2022-07-01 | 2022 Q4 | During the reporting period, Walker County had construction activities underway for its street improvements project.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2022-10-01 | 2023 Q1 | During the reporting period, Walker County had construction underway for its street improvements project.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2023-04-01 | 2023 Q3 | During the reporting?period,?Walker County had 95% of construction?complete for its streets improvements project
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2023-10-01 | 2024 Q1 | During the quarter, an amendment to this contract was executed, that increased the total contract funding amount and was allocated to this activity, increasing the budget and obligation amount. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report. Activity previously contained HMID projects, which have been removed in addition to the previous MID expenditures. During the quarter, an amendment to this contract was executed, that increased the total contract funding amount and was allocated to this activity, increasing the budget and obligation amount.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2024-01-01 | 2024 Q2 | During the reporting period, Walker County completed construction and is pending submission of construction completion documentation for its street improvements project
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2024-10-01 | 2025 Q1 | During the reporting period, Walker County submitted grant closeout documents for its street improvements project.
INF_SMID_LMI_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2025-07-01 | 2025 Q4 | During the reporting period, Walker County had its grant closeout documents approved for its street improvements project.
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Palacios had environmental review and engineering design underway for its street improvements project.
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2020-10-01 | 2021 Q1
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Palacios had environmental complete for its street improvements project.
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Palacios had construction procurement underway for its Street Improvements project
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Palacios had construction underway for its Street Improvements project.
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Palacios had construction underway for its Street Improvements project.
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Palacios had construction underway for its Street Improvements project.
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Palacios had construction complete and the CoCC underway for its Street Improvements project.
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Palacios had grant closeout documents under review for its Street Improvements project.
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Palacios had grant closeout documents under review for its streets improvements project
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_LMI_20-065-108-C295_Palacios | Street Improvements | Construction/reconstruction of streets | Palacios | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
INF_SMID_LMI_20-065-111-C308_MilamCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Milam County | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-111-C308_MilamCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Milam County | 2020-10-01 | 2021 Q1 | During the reporting period, the Milam County had environmental review underway for its Drainage Infrastructure project.
INF_SMID_LMI_20-065-111-C308_MilamCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Milam County | 2021-07-01 | 2021 Q4 | During the reporting period, Milam County accepted applications for eligibility review for its infrastructure program. Negative balance for quarterly expenditure is a result of Clarification Form Adjustments.
INF_SMID_LMI_20-065-111-C308_MilamCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Milam County | 2021-10-01 | 2022 Q1 | During the reporting period, the Milam County completed environmental review for its flood and drainage project.
INF_SMID_LMI_20-065-111-C308_MilamCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Milam County | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-111-C308_MilamCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Milam County | 2023-07-01 | 2023 Q4 | During the reporting period, Milam County completed environmental review for its flood and drainage project.
INF_SMID_LMI_20-065-111-C308_MilamCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Milam County | 2024-04-01 | 2024 Q3 | During the reporting period, Milam County received the bid docs from the engineer and bid advertisements are running for its flood and drainage project.
INF_SMID_LMI_20-065-111-C308_MilamCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Milam County | 2025-01-01 | 2025 Q2 | During the reporting period, Milam County completed construction and submitted the COCC for its flood and drainage project.
INF_SMID_LMI_20-065-111-C308_MilamCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Milam County | 2025-04-01 | 2025 Q3 | Activity budget and obligation were reduced during the quarter as part of the closeout process.
INF_SMID_LMI_20-065-111-C308_MilamCounty | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Milam County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO received the final draw for Milam County&apos;s flood and drainage facilities project.
INF_SMID_LMI_20-065-112-C309_Waelder_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Waelder, City of | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-112-C309_Waelder_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Waelder, City of | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in End Date extended
INF_SMID_LMI_20-065-112-C309_Waelder_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Waelder, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Waelder has completed environmental review for its Flood and Drainage project
INF_SMID_LMI_20-065-112-C309_Waelder_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Waelder, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-112-C309_Waelder_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Waelder, City of | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-112-C309_Waelder_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Waelder, City of | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in End Date extended
INF_SMID_LMI_20-065-112-C309_Waelder_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Waelder, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Waelder has completed environmental review for its Sewer project
INF_SMID_LMI_20-065-112-C309_Waelder_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Waelder, City of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Matagorda County had environmental review underway for its flood and drainage project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Matagorda County had engineering design underway for its Flood and Drainage Facilities project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Matagorda County completed engineering design for its Flood and Drainage project
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Matagorda County had Environmental Review underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2022-04-01 | 2022 Q3 | During the reporting period, the County of Matagorda had completed environmental review for its Flood and Drainage projects.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2023-01-01 | 2023 Q2 | During the reporting period, the Matagorda County completed environmental review for its Flood & Drainage project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Matagorda County had construction underway for its Flood and Drainage Facilities (Van Vleck) project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Matagorda County had construction procurement underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Matagorda County had 50% of construction underway/complete for its Flood and Drainage project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2024-01-01 | 2024 Q2 | During the reporting?period,?the Matagorda County had 50% of construction?underway/complete for its Flood and Drainage projects.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2024-04-01 | 2024 Q3 | During the reporting?period,?the Matagorda County had 50% of construction?underway/complete for its Flood and Drainage project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2025-01-01 | 2025 Q2 | During the reporting period, Matagorda County had 50% of construction underway or completed for its Flood & Drainage projects, as work resumed following the execution of an amendment.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2025-07-01 | 2025 Q4 | During the reporting period, the Matagorda County had 92% of construction¿underway/complete for its Flood and Drainage project (#1 Van Vleck F&D - LMI).
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Matagorda, County of | 2025-10-01 | 2026 Q1 | During the reporting period, the Matagorda County had 92.89% of construction underway/complete for its Flood and drainage project (#1 Van Vleck F&D - LMI).
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Matagorda County had environmental review underway for its sewer facilities project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2021-01-01 | 2021 Q2 | During the reporting period, Matagorda County had design underway for its sewer facilities improvements project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Matagorda County had engineering design underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Matagorda County had preliminary engineering design underway for its Sewer Facilities project
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Matagorda County had Environmental Review underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2022-04-01 | 2022 Q3 | During the reporting period, the County of Matagorda had construction procurement underway for its Sewer Facilities projects.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2022-07-01 | 2022 Q4 | During the reporting period, the County of Matagorda had construction procurement underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Matagorda County had construction underway for part of its Sewer improvements project, with the remainder under construction procurement.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2023-01-01 | 2023 Q2 | During the reporting period, the Matagorda County did not have any activity that corresponds with this amount for its Sewer Facility project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Matagorda County had construction underway for its Sewer Facilities project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Matagorda County had construction underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2024-01-01 | 2024 Q2 | During the reporting?period,?the Matagorda County had 50% of construction?underway/complete for its Sewer Facilities projects.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2024-04-01 | 2024 Q3 | During the reporting period, the Matagorda County had 50% of construction underway/complete for its Sewer Facilities projects.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2025-01-01 | 2025 Q2 | During the reporting period, Matagorda County had 50% of construction underway or completed for its Sewer Facilities projects, as work resumed following the execution of an amendment.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2025-07-01 | 2025 Q4 | During the reporting period, the Matagorda County had construction complete and the COCC underway and the engineer prepped construction closeout documentation for its Sewer Facilities project (#11 Midfield Gen). During the reporting period, the Matagorda County completed construction and submitted the COCC for its Sewer Facilities project (#11 Midfield Gen).
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2020-04-01 | 2020 Q3
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Matagorda County had environmental review underway for its water facilities project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Matagorda County had engineering design underway for its Water Facilities project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Matagorda County had preliminary engineering design underway for its Water Facilities project
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Matagorda County had Environmental Review underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2022-04-01 | 2022 Q3 | During the reporting period, the County of Matagorda had construction procurement underway for its Water Facilities projects.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Matagorda County had construction procurement underway for part of its Water improvements project, with the remainder pending further coordination with USACE.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2023-01-01 | 2023 Q2 | During the reporting period, the Matagorda County completed environmental review for its Water Facility project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Matagorda County had construction procurement underway for its Water Facilities project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Matagorda County had construction procurement underway for its Water Facilities project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Matagorda County had construction procurement underway for its Water Facility project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2024-01-01 | 2024 Q2 | During the reporting?period,?the Matagorda County had 50% of construction?underway/complete for its Water Facilities projects.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2024-04-01 | 2024 Q3 | During the reporting period, the Matagorda County had 50% of construction underway/complete for its Water Facilities projects.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2025-01-01 | 2025 Q2 | During the reporting period, Matagorda County had 50% of construction underway or completed for its Water Facilities projects, as work resumed following the execution of an amendment. Additionally, Matagorda County had progress billing for completed engineering design for its Water Facilities project.
INF_SMID_LMI_20-065-123-C430_MatagordaCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2025-07-01 | 2025 Q4 | During the reporting?period,?the Matagorda County billed for administrative services related to construction closeout for its Water Facilities projects (Project #3 - Blessing Generators - WF - LMI -and- Project #4 - Matagorda WD & WSC Generators - WF - LMI).
INF_SMID_LMI_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2020-07-01 | 2020 Q4
INF_SMID_LMI_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2021-01-01 | 2021 Q2 | During the reporting period, Bastrop County had engineering design underway and environmental complete for its flood and drainage project.
INF_SMID_LMI_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2023-04-01 | 2023 Q3 | During the reporting period, Bastrop County had construction underway for its Flood and Drainage project.
INF_SMID_LMI_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2023-10-01 | 2024 Q1 | During the reporting period Bastrop County completed construction and is pending submission of construction completion documentation for its Flood and Drainage project.
INF_SMID_LMI_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2025-10-01 | 2026 Q1 | During the reporting period, Activity budget and obligation reduced according to closeout documentation.
INF_SMID_LMI_24-074-001-E284_Somerville_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Somerville | 2024-04-01 | 2024 Q3 | New activity created.
INF_SMID_LMI_24-074-001-E284_Somerville_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Somerville | 2025-07-01 | 2025 Q4 | During the reporting period, Somerville submitted Closeout Documentation.
INF_SMID_LMI_24-074-002-E285_GrimesCounty_SI | Street Improvements | Construction/reconstruction of streets | Grimes County | 2025-04-01 | 2025 Q3 | Activity created, budgeted and obligated during the quarter.
INF_SMID_LMI_24-074-003-E286_Anderson_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Anderson, City Of | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
INF_SMID_LMI_24-074-003-E286_Anderson_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Anderson, City Of | 2025-10-01 | 2026 Q1 | During this reporting period the Town of Anderson had environmental review underway for its flood and drainage facilities project.
INF_SMID_LMI_24-074-003-E286_Anderson_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Anderson, City Of | 2026-01-01 | 2026 Q2
INF_SMID_LMI_24-074-004-E287_Iola_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2025-01-01 | 2025 Q2 | The contract with the City of Iola was executed during the quarter and the DRGR activity was subsequently created.
INF_SMID_LMI_24-074-004-E287_Iola_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Iola, City Of | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Iola complete the start-up document phase and the commencement of engineering design.
INF_SMID_LMI_24-074-005-E288_Bedias_SI | Street Improvements | Construction/reconstruction of streets | Bedias, City of | 2025-01-01 | 2025 Q2 | The contract with the City of Bedias was executed during the quarter and the DRGR activity was subsequently created.
INF_SMID_LMI_24-074-005-E288_Bedias_SI | Street Improvements | Construction/reconstruction of streets | Bedias, City of | 2026-01-01 | 2026 Q2
INF_SMID_LMI_24-074-006-E289_ToddMission_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2025-04-01 | 2025 Q3 | Activity created, budgeted and obligated during the quarter.
INF_SMID_LMI_24-074-006-E289_ToddMission_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Todd Mission complete the start-up document phase and the commencement of engineering design.
INF_SMID_LMI_24-074-006-E289_ToddMission_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2025-10-01 | 2026 Q1 | During this reporting period the City of Todd Mission had environmental review underway for its flood and drainage project.
INF_SMID_LMI_24-074-006-E289_ToddMission_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Todd Mission, City of | 2026-01-01 | 2026 Q2
INF_SMID_LMI_24-074-009-F149_Edna_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Edna, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
INF_SMID_LMI_24-074-010-F150_JacksonCounty_SI | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
INF_SMID_LMI_24-074-011-F151_Goliad_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, City Of | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
INF_SMID_LMI_24-074-011-F151_Goliad_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, City Of | 2026-01-01 | 2026 Q2
INF_SMID_LMI_24-074-012-F152_GoliadCounty_WF | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Goliad, County of | 2025-07-01 | 2025 Q4 | During the reporting period, the contract was executed and the activity was created and budgeted in DRGR.
INF_SMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_SMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 46873.33 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 15049.36 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 19193.45 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 8530.46 - State costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 3917.9 - State costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 6597.64 - State costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID LMI Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_SMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_SMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 18599.78 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 7524.82 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 9596.72 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 3922.42 - State costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 1641.08 - State costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 4320.71 - State costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID LMI Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_SMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_SMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 38186.13 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 14477.04 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 18451.21 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 7683.2 - State costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 3287.09 - State costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 8307.37 - State costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID LMI Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_SMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_SMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 43929.74 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 16796.81 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 21770.15 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 9192.34 - State costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 3917.9 - State costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 9588.52 - State costs in support of activity delivery.
INF_SMID_LMI_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID LMI Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_SMID_NA_20-065-021-C076_SabineCounty | Infrastructure Planning Study | Planning | Sabine County | 2020-01-01 | 2020 Q2
INF_SMID_NA_20-065-021-C076_SabineCounty | Infrastructure Planning Study | Planning | Sabine County | 2020-04-01 | 2020 Q3 | During the reporting period, the Sabine County had environmental review and engineering design underway for its infrastructure project.
INF_SMID_NA_20-065-021-C076_SabineCounty | Infrastructure Planning Study | Planning | Sabine County | 2020-07-01 | 2020 Q4
INF_SMID_NA_20-065-021-C076_SabineCounty | Infrastructure Planning Study | Planning | Sabine County | 2020-10-01 | 2021 Q1 | During the reporting period, Sabine County completed it&apos;s planning study on it&apos;s planning study project.
INF_SMID_NA_20-065-021-C076_SabineCounty | Infrastructure Planning Study | Planning | Sabine County | 2021-01-01 | 2021 Q2 | During the reporting period, Sabine County had engineering design underway and environmental complete for its infrastructure planning study project.
INF_SMID_NA_20-065-021-C076_SabineCounty | Infrastructure Planning Study | Planning | Sabine County | 2022-07-01 | 2022 Q4 | During the reporting period, Sabine County had grant closeout documents under review for its infrastructure planning study project.
INF_SMID_NA_20-065-021-C076_SabineCounty | Infrastructure Planning Study | Planning | Sabine County | 2022-10-01 | 2023 Q1 | During the reporting period, Sabine County had grant closeout documents under review for its infrastructure planning project.
INF_SMID_NA_20-065-021-C076_SabineCounty | Infrastructure Planning Study | Planning | Sabine County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_SMID_NA_20-065-021-C076_SabineCounty | Infrastructure Planning Study | Planning | Sabine County | 2023-10-01 | 2024 Q1 | During the reporting period, Sabine County had grant closeout documents under review for its planning study project. Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_NA_20-065-139-C527_BastropCounty_PLAN | Planning Study | Planning | Bastrop County | 2020-07-01 | 2020 Q4
INF_SMID_NA_20-065-139-C527_BastropCounty_PLAN | Planning Study | Planning | Bastrop County | 2021-01-01 | 2021 Q2 | During the reporting period, Bastrop County had engineering design underway and environmental complete for its planning study project.
INF_SMID_NA_20-065-139-C527_BastropCounty_PLAN | Planning Study | Planning | Bastrop County | 2021-04-01 | 2021 Q3 | During the reporting period, Bastrop had completed its Planning Study project.
INF_SMID_NA_20-065-139-C527_BastropCounty_PLAN | Planning Study | Planning | Bastrop County | 2022-07-01 | 2022 Q4 | Contract amendment for related activities took effect during quarter and resulted in End Date extended
INF_SMID_NA_20-065-139-C527_BastropCounty_PLAN | Planning Study | Planning | Bastrop County | 2023-10-01 | 2024 Q1 | During the reporting period, Bastrop County completed planning study and is pending submission of completion documentation.
INF_SMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient SMID Planning Activities | Planning | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_SMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient SMID Planning Activities | Planning | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 2846.7 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient SMID Planning Activities | Planning | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 1159.78 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient SMID Planning Activities | Planning | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 1484.48 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient SMID Planning Activities | Planning | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 604.98 - State costs in support of activity delivery.
INF_SMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient SMID Planning Activities | Planning | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 251.34 - State costs in support of activity delivery.
INF_SMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient SMID Planning Activities | Planning | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 334.05 - State costs in support of activity delivery.
INF_SMID_NA_GranteeSupport[H5b]_PLAN | Infrastructure Grantee Support for Subrecipient SMID Planning Activities | Planning | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_SMID_UN_20-065-047-C139_Gonzales | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales County | 2020-01-01 | 2020 Q2
INF_SMID_UN_20-065-047-C139_Gonzales | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales County | 2020-10-01 | 2021 Q1 | During the reporting period, Gonzales County completed environmental review and had engineering design underway for its water facilities project.
INF_SMID_UN_20-065-047-C139_Gonzales | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales County | 2021-01-01 | 2021 Q2 | During the reporting period, Gonzales County had engineering design underway and environmental complete for its water facilities project.
INF_SMID_UN_20-065-047-C139_Gonzales | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales County | 2021-04-01 | 2021 Q3 | During the reporting period, Gonzales County had completed environmental and engineering design underway for its Water Facilities project.
INF_SMID_UN_20-065-047-C139_Gonzales | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales County | 2021-10-01 | 2022 Q1 | During the reporting period, Gonzales County had completed construction procurement for its Water Facilities project.
INF_SMID_UN_20-065-047-C139_Gonzales | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales County | 2022-01-01 | 2022 Q2 | During the reporting period, Gonzales County had construction procurement underway for its Public Facilities project.
INF_SMID_UN_20-065-047-C139_Gonzales | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales County | 2022-07-01 | 2022 Q4 | During the reporting period, Gonzales County had 50% complete for its Water Facilities project.
INF_SMID_UN_20-065-047-C139_Gonzales | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales County | 2022-10-01 | 2023 Q1 | During the reporting period, Gonzales County had construction complete and the COCC underway for its water facilities project.
INF_SMID_UN_20-065-047-C139_Gonzales | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales County | 2023-04-01 | 2023 Q3 | During the reporting period, Gonzales County completed construction and submitted the COCC for its Water Facilities project.
INF_SMID_UN_20-065-047-C139_Gonzales | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Gonzales County | 2024-01-01 | 2024 Q2 | During the reporting period, Gonzales County had grant closeout documents under review for its Water Facilities project.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2020-01-01 | 2020 Q2
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2020-10-01 | 2021 Q1 | During the reporting period, Austin County had engineering design underway for its street improvements project.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2021-04-01 | 2021 Q3 | During the reporting period, Austin County had engineering design underway for its Street Improvements project.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2021-10-01 | 2022 Q1 | During the reporting period, Austin County had preliminary engineering design underway for its street improvements project.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2022-04-01 | 2022 Q3 | During the reporting period, Austin County had construction procurement underway for its street improvement project.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2022-07-01 | 2022 Q4 | During the reporting period, Austin County had construction procurement underway for its street improvements project.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2023-04-01 | 2023 Q3 | During the reporting period, Austin County completed construction procurement for its street improvement project
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2024-01-01 | 2024 Q2 | During the reporting period, Austin County obtained materials to begin activities for Yellow Rose Road.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2024-04-01 | 2024 Q3 | During the reporting period, Austin County completed activities for Yellow Rose Road, and obtained materials for Svoboda.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2024-07-01 | 2024 Q4 | During the reporting?period,?Austin County had 50% of construction?sites completed for its Street Improvements project. ?
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2024-10-01 | 2025 Q1 | During the reporting period, Austin County had 75% of construction complete for its street improvements project.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2025-01-01 | 2025 Q2 | During the reporting period, Austin County had 85% of construction complete for its Street Improvements project.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2025-04-01 | 2025 Q3 | During the reporting period, Austin County had 90% of construction completed for its Street Improvements project.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2025-07-01 | 2025 Q4 | During the reporting period, Austin County had construction underway for its Street Improvements project.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2025-10-01 | 2026 Q1 | During the reporting period Austin County had construction underway and 75% complete for its street improvements project.
INF_SMID_UN_20-065-065-C184_AustinCounty | Street Improvements | Construction/reconstruction of streets | Austin County | 2026-01-01 | 2026 Q2
INF_SMID_UN_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2020-01-01 | 2020 Q2
INF_SMID_UN_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2020-07-01 | 2020 Q4 | During the reporting period, Jackson County had environmental review underway for its street improvements project.
INF_SMID_UN_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Jackson County had engineering design underway for its street improvements project.
INF_SMID_UN_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2021-01-01 | 2021 Q2 | During the reporting period, the County of Jackson County had engineering design underway and environmental complete for its street improvement project.
INF_SMID_UN_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Jackson had construction underway for its Street Improvements project.
INF_SMID_UN_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Jackson County completed engineering design for its street improvement project. Review of prior DRGR Vouchers resulted in revisions that lowered the total amount draw for this DRGR Activity.
INF_SMID_UN_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2022-01-01 | 2022 Q2 | No construction has started on this project. Jackson County submitted an amendment request to remove the UN projects from their contract due to high bids.
INF_SMID_UN_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2022-07-01 | 2022 Q4 | During the reporting period, the County completed construction and is pending submission of construction completion documentation for its street improvements project. Closeout is underway and documentation is forthcoming, once received actual accomplishments will be updated.
INF_SMID_UN_20-065-096-C267_JacksonCounty | Street Improvements | Construction/reconstruction of streets | Jackson, County of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_UN_20-065-099-C271_GoliadCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Goliad, County of | 2020-01-01 | 2020 Q2
INF_SMID_UN_20-065-099-C271_GoliadCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Goliad, County of | 2020-07-01 | 2020 Q4 | During the reporting period, Goliad County had environmental review and engineering design underway for its specially authorized public facilities project.
INF_SMID_UN_20-065-099-C271_GoliadCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Goliad, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Goliad County had environmental review and engineering design underway for its public facilities project.
INF_SMID_UN_20-065-099-C271_GoliadCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Goliad, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Goliad County had construction procurement underway for its public facilities project.
INF_SMID_UN_20-065-099-C271_GoliadCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Goliad, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Goliad County had construction underway for its Public Facilities project.
INF_SMID_UN_20-065-099-C271_GoliadCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Goliad, County of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_UN_20-065-099-C271_GoliadCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Goliad, County of | 2022-04-01 | 2022 Q3 | During the reporting period, Goliad County had construction underway for its public facilities project.
INF_SMID_UN_20-065-099-C271_GoliadCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Goliad, County of | 2022-07-01 | 2022 Q4 | During the reporting period, Goliad County completed construction and is pending submission of construction completion documents for its Public Facilities project.
INF_SMID_UN_20-065-099-C271_GoliadCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Goliad, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Goliad County had construction complete and the COCC underway for its Public Facilities project.
INF_SMID_UN_20-065-099-C271_GoliadCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Goliad, County of | 2023-01-01 | 2023 Q2 | During the reporting period, Goliad County has completed construction and submitted the COCC for its Public Facilities project.
INF_SMID_UN_20-065-099-C271_GoliadCounty_PF | Public Facilities | Rehabilitation/reconstruction of public facilities | Goliad, County of | 2023-10-01 | 2024 Q1 | Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
INF_SMID_UN_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2020-04-01 | 2020 Q3
INF_SMID_UN_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2020-10-01 | 2021 Q1 | During the reporting period, Walker County had its environmental review underway for its flood and drainage facilities project.
INF_SMID_UN_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2021-01-01 | 2021 Q2 | During the reporting period, Walker County had engineering design underway and environmental complete for its street improvements project.
INF_SMID_UN_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2021-04-01 | 2021 Q3 | During the reporting period, Walker County had environmental review underway for its Street Improvements project. It is anticipated that the AUGF will be issued in July 2021.
INF_SMID_UN_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2021-07-01 | 2021 Q4 | During the reporting period, Walker County accepted applications for eligibility review for its infrastructure program.
INF_SMID_UN_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2021-10-01 | 2022 Q1 | During the reporting period, Walker County had construction procurement underway for its Street Improvements project.
INF_SMID_UN_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2022-01-01 | 2022 Q2 | During the reporting period, Walker County had construction activities underway for its street improvements project.
INF_SMID_UN_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2022-07-01 | 2022 Q4 | During the reporting period, Walker County completed construction for its street improvements project. Closeout documentation pending submission.
INF_SMID_UN_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2023-04-01 | 2023 Q3 | During the reporting?period,?Walker County had 95% of construction?complete for its streets improvements project
INF_SMID_UN_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2024-10-01 | 2025 Q1 | During the reporting period, Walker County submitted grant closeout documents for its streets improvement project.
INF_SMID_UN_20-065-104-C279_WalkerCounty | Street Improvements | Construction/reconstruction of streets | Walker County | 2025-07-01 | 2025 Q4 | During the reporting period, Walker County had grant closeout documents under review for it&apos;s Street Improvements project.
INF_SMID_UN_20-065-104-C279_WalkerCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Walker County | 2020-04-01 | 2020 Q3
INF_SMID_UN_20-065-104-C279_WalkerCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Walker County | 2020-10-01 | 2021 Q1 | During the reporting period, the Walker County had environmental review underway for its Flood and Drainage project.
INF_SMID_UN_20-065-104-C279_WalkerCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Walker County | 2021-01-01 | 2021 Q2 | During the reporting period, Walker County had engineering design underway and environmental complete for its flood and drainage facilities project.
INF_SMID_UN_20-065-104-C279_WalkerCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Walker County | 2021-04-01 | 2021 Q3 | During the reporting period, Walker County had environmental review underway for its Flood and Drainage facilities project. It is anticipated that the AUGF will be issued in July 2021.
INF_SMID_UN_20-065-104-C279_WalkerCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Walker County | 2021-07-01 | 2021 Q4 | During the reporting period, Walker County had completed environmental review and engineering design for its flood and drainage project.
INF_SMID_UN_20-065-104-C279_WalkerCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Walker County | 2021-10-01 | 2022 Q1 | During the reporting period, Walker County had construction procurement underway for its Flood and Drainage project.
INF_SMID_UN_20-065-104-C279_WalkerCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Walker County | 2022-01-01 | 2022 Q2 | During the reporting period, Walker County had construction activities underway for its flood and drainage facilities project.
INF_SMID_UN_20-065-104-C279_WalkerCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Walker County | 2022-07-01 | 2022 Q4 | During the reporting period, Walker County completed construction for its flood and drainage project. Closeout documentation pending submission.
INF_SMID_UN_20-065-104-C279_WalkerCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Walker County | 2023-04-01 | 2023 Q3 | During the reporting?period,?Walker County had 95% of construction?complete for its flood and drainage facilities project
INF_SMID_UN_20-065-104-C279_WalkerCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Walker County | 2024-10-01 | 2025 Q1 | During the reporting period, Walker County submitted grant closeout documents for its streets improvement project.
INF_SMID_UN_20-065-104-C279_WalkerCounty_F&D | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Walker County | 2025-07-01 | 2025 Q4 | During the reporting period, Walker County had grant closeout documents under review for it&apos;s Flood and Drainage Improvements project.
INF_SMID_UN_20-065-111-C308_MilamCounty | Street Improvements | Construction/reconstruction of streets | Milam County | 2020-04-01 | 2020 Q3
INF_SMID_UN_20-065-111-C308_MilamCounty | Street Improvements | Construction/reconstruction of streets | Milam County | 2021-07-01 | 2021 Q4 | During the reporting period, Milam County accepted applications for eligibility review for its infrastructure program.
INF_SMID_UN_20-065-111-C308_MilamCounty | Street Improvements | Construction/reconstruction of streets | Milam County | 2022-07-01 | 2022 Q4 | During the reporting period, Milam County completed easement acquisitions.
INF_SMID_UN_20-065-111-C308_MilamCounty | Street Improvements | Construction/reconstruction of streets | Milam County | 2022-10-01 | 2023 Q1 | During the reporting period, the County completed required appraisals on two applications
INF_SMID_UN_20-065-111-C308_MilamCounty | Street Improvements | Construction/reconstruction of streets | Milam County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_SMID_UN_20-065-111-C308_MilamCounty | Street Improvements | Construction/reconstruction of streets | Milam County | 2023-07-01 | 2023 Q4 | During the reporting period, Milam County had construction underway for its street improvements project.
INF_SMID_UN_20-065-111-C308_MilamCounty | Street Improvements | Construction/reconstruction of streets | Milam County | 2023-10-01 | 2024 Q1 | During the reporting period Milam County had construction underway for its Street Improvement project.
INF_SMID_UN_20-065-111-C308_MilamCounty | Street Improvements | Construction/reconstruction of streets | Milam County | 2024-01-01 | 2024 Q2 | During the reporting period, Milam Co. completed construction for its Street Improvement project.
INF_SMID_UN_20-065-111-C308_MilamCounty | Street Improvements | Construction/reconstruction of streets | Milam County | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO received the final draw for Milam County&apos;s street improvement project.
INF_SMID_UN_20-065-116-C377_Anderson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Anderson, City Of | 2020-04-01 | 2020 Q3
INF_SMID_UN_20-065-116-C377_Anderson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Anderson, City Of | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Anderson had environmental review underway for its flood and drainage project.
INF_SMID_UN_20-065-116-C377_Anderson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Anderson, City Of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Anderson had Construction underway for it&apos;s flood and drainage facilities project.
INF_SMID_UN_20-065-116-C377_Anderson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Anderson, City Of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Anderson had 50% of construction complete for its Flood and Drainage project.
INF_SMID_UN_20-065-116-C377_Anderson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Anderson, City Of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_UN_20-065-116-C377_Anderson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Anderson, City Of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Anderson had grant closeout documents under review for its flood and drainage project.
INF_SMID_UN_20-065-116-C377_Anderson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Anderson, City Of | 2023-04-01 | 2023 Q3 | Area Benefit type corrected.
INF_SMID_UN_20-065-116-C377_Anderson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Anderson, City Of | 2025-04-01 | 2025 Q3 | During the reporting period the Town of Anderson had final payment processed and paid. Closeout underway for its flood and drainage facility project.
INF_SMID_UN_20-065-116-C377_Anderson | Flood and Drainage Facilities | Rehabilitation/reconstruction of a public improvement | Anderson, City Of | 2025-10-01 | 2026 Q1 | During the reporting period, performance measures were updated according to closeout documentation.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2020-04-01 | 2020 Q3
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Matagorda County had environmental review underway for its sewer facilities project.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2021-01-01 | 2021 Q2 | During the reporting period, Matagorda County had design underway for its sewer facilities improvements project. Funds moved to INF_SMID_LMI_20-065-123-C430_MatagordaCounty_SF in payment correction.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2021-04-01 | 2021 Q3 | During the reporting period, Matagorda County had engineering design underway for its Sewer Facilities project.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2022-01-01 | 2022 Q2 | During the reporting period, Matagorda County had Environmental Review underway for its Flood and Drainage project.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2022-04-01 | 2022 Q3 | During the reporting period, the County of Matagorda had construction procurement underway for its Sewer Facilities projects.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2022-07-01 | 2022 Q4 | During the reporting period, the County of Matagorda had construction procurement underway for its Sewer Facilities projects.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Matagorda County had construction procurement underway for its Sewer improvements project.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2023-01-01 | 2023 Q2 | During the reporting period, the Matagorda County completed environmental review for its Sewer Facilities project. During the reporting period, the Matagorda County had construction underway for its Sewer Facilities project.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Matagorda County had construction underway for its Sewer Facilities project.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Matagorda County had construction underway for its Sewer Facility project.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2024-04-01 | 2024 Q3 | During the reporting period, Matagorda County had construction underway for its Sewer Facility project.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2025-01-01 | 2025 Q2 | During the reporting?period,?Matagorda County had 50% of construction?underway/complete for its Sewer Facilities project.
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2025-07-01 | 2025 Q4 | During the reporting period, the Matagorda County had 90% of construction underway/complete for its Sewer Facilities project (#8 Van Vleck LS - UN).
INF_SMID_UN_20-065-123-C430_MatagordaCounty_SF | Sewer Facilities | Construction/reconstruction of water/sewer lines or systems | Matagorda, County of | 2025-10-01 | 2026 Q1 | During the reporting period, the Matagorda County had 95% of construction underway/complete for its Sewer Facilities project (#8 Van Vleck LS - UN).
INF_SMID_UN_20-065-124-C435_LeeCounty | Street Improvements | Construction/reconstruction of streets | Lee, County of | 2020-04-01 | 2020 Q3
INF_SMID_UN_20-065-124-C435_LeeCounty | Street Improvements | Construction/reconstruction of streets | Lee, County of | 2020-10-01 | 2021 Q1 | During the reporting period, the Lee County had environmental review underway for its street improvement project.
INF_SMID_UN_20-065-124-C435_LeeCounty | Street Improvements | Construction/reconstruction of streets | Lee, County of | 2021-07-01 | 2021 Q4 | ?During the reporting?period, Lee County had preliminary?engineering design underway for its street improvements project.
INF_SMID_UN_20-065-124-C435_LeeCounty | Street Improvements | Construction/reconstruction of streets | Lee, County of | 2022-10-01 | 2023 Q1 | During the reporting period, the Lee County had engineering design underway for its project.
INF_SMID_UN_20-065-124-C435_LeeCounty | Street Improvements | Construction/reconstruction of streets | Lee, County of | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
INF_SMID_UN_20-065-124-C435_LeeCounty | Street Improvements | Construction/reconstruction of streets | Lee, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Lee County completed engineering design for its flood and drainage project.
INF_SMID_UN_20-065-124-C435_LeeCounty | Street Improvements | Construction/reconstruction of streets | Lee, County of | 2023-10-01 | 2024 Q1 | During the reporting period Lee County completed engineering and environmental underway.
INF_SMID_UN_20-065-124-C435_LeeCounty | Street Improvements | Construction/reconstruction of streets | Lee, County of | 2024-01-01 | 2024 Q2 | During the reporting period Lee County had preliminary engineering design underway for its
INF_SMID_UN_20-065-124-C435_LeeCounty | Street Improvements | Construction/reconstruction of streets | Lee, County of | 2024-07-01 | 2024 Q4 | During the reporting period, the County had environmental review underway for its street improvement project.
INF_SMID_UN_20-065-124-C435_LeeCounty | Street Improvements | Construction/reconstruction of streets | Lee, County of | 2025-01-01 | 2025 Q2 | During the reporting?period,?Lee County had preliminary?engineering design underway for its street improvements project.
INF_SMID_UN_20-065-128-C439_Huntsville_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Huntsville | 2020-07-01 | 2020 Q4
INF_SMID_UN_20-065-128-C439_Huntsville_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Huntsville | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Huntsville completed environmental review and requested a NCTE for its flood and drainage project.
INF_SMID_UN_20-065-128-C439_Huntsville_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Huntsville | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Huntsville had bid advertisement underway for its Flood and Drainage project. The construction notice to proceed expected to be issued on 01/16/2023.
INF_SMID_UN_20-065-128-C439_Huntsville_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Huntsville | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Huntsville had construction underway for its flood and drainage project.
INF_SMID_UN_20-065-128-C439_Huntsville_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Huntsville | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
INF_SMID_UN_20-065-128-C439_Huntsville_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Huntsville | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Huntsville completed construction and is pending submission of construction completion documentation for its flood and drainage project
INF_SMID_UN_20-065-128-C439_Huntsville_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Huntsville | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Huntsville completed construction and submitted the COCC for its flood and drainage project
INF_SMID_UN_20-065-128-C439_Huntsville_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Huntsville | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Huntsville submitted the final construction and engineering invoices and submitted the Grant Completion Report for its Flood & Drainage facilities project
INF_SMID_UN_20-065-128-C439_Huntsville_SI | Street Improvements | Construction/reconstruction of streets | Huntsville | 2020-07-01 | 2020 Q4
INF_SMID_UN_20-065-128-C439_Huntsville_SI | Street Improvements | Construction/reconstruction of streets | Huntsville | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Huntsville completed environmental review and requested a NCTE for its street improvements project.
INF_SMID_UN_20-065-128-C439_Huntsville_SI | Street Improvements | Construction/reconstruction of streets | Huntsville | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Huntsville had bid advertisement underway for its Street Improvements project. The construction notice to proceed expected to be issued on 01/16/2023.
INF_SMID_UN_20-065-128-C439_Huntsville_SI | Street Improvements | Construction/reconstruction of streets | Huntsville | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Huntsville completed construction and is pending submission of construction completion documentation for its street improvements project
INF_SMID_UN_20-065-128-C439_Huntsville_SI | Street Improvements | Construction/reconstruction of streets | Huntsville | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Huntsville completed construction and submitted the COCC for its street improvements project
INF_SMID_UN_20-065-128-C439_Huntsville_SI | Street Improvements | Construction/reconstruction of streets | Huntsville | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Huntsville submitted the final construction and engineering invoices and submitted the Grant Completion Report for its Street Improvements project
INF_SMID_UN_20-065-132-C443_Sealy | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Sealy | 2020-07-01 | 2020 Q4
INF_SMID_UN_20-065-132-C443_Sealy | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Sealy | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Sealy had engineering design underway for its water facilities project.
INF_SMID_UN_20-065-132-C443_Sealy | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Sealy | 2021-01-01 | 2021 Q2 | During the reporting period, Sealy had engineering design underway and environmental complete for its water facilities project.
INF_SMID_UN_20-065-132-C443_Sealy | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Sealy | 2021-04-01 | 2021 Q3 | During the reporting period, Sealy had engineering design underway for its Water Facilities project.
INF_SMID_UN_20-065-132-C443_Sealy | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Sealy | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Sealy had construction underway for its water facilities project.
INF_SMID_UN_20-065-132-C443_Sealy | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Sealy | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
INF_SMID_UN_20-065-132-C443_Sealy | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Sealy | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Sealy County submitted grant closeout documents for its water facilities project.
INF_SMID_UN_20-065-132-C443_Sealy | Water Facilities | Construction/reconstruction of water/sewer lines or systems | Sealy | 2024-04-01 | 2024 Q3 | Activity budget and obligation reduced to drawn amounts and this contract has been administratively closed during the quarter. All payments have been completed and all accomplishments were entered. Activity status has been updated to Completed.
INF_SMID_UN_20-065-137-C503_Katy | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Katy, City of | 2020-07-01 | 2020 Q4
INF_SMID_UN_20-065-137-C503_Katy | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Katy, City of | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Katy had preliminary engineering design underway for its flood and drainage project.
INF_SMID_UN_20-065-137-C503_Katy | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Katy, City of | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Katy had preliminary engineering design underway for its flood and drainage facilities.
INF_SMID_UN_20-065-137-C503_Katy | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Katy, City of | 2022-10-01 | 2023 Q1 | During the reporting the City of Katy had engineering design underway for its flood and drainage project.
INF_SMID_UN_20-065-137-C503_Katy | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Katy, City of | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Katy has begun bid activities for its flood and drainage project.
INF_SMID_UN_20-065-137-C503_Katy | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Katy, City of | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Katy had construction underway for its Flood and Drainage project.
INF_SMID_UN_20-065-137-C503_Katy | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Katy, City of | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Katy had 50% of construction completed for its Flood and Drainage project.
INF_SMID_UN_20-065-137-C503_Katy | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Katy, City of | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Katy had construction underway for its Flood and Drainage project.
INF_SMID_UN_20-065-137-C503_Katy | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Katy, City of | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Katy submitted grant closeout documents for its Flood and drainage Facilities
INF_SMID_UN_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2020-07-01 | 2020 Q4
INF_SMID_UN_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2021-01-01 | 2021 Q2 | During the reporting period, Bastrop County had engineering design underway and environmental complete for its flood and drainage project.
INF_SMID_UN_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2021-07-01 | 2021 Q4 | During the reporting period, Bastrop County had preliminary engineering design underway for its flood and drainage facilities project.
INF_SMID_UN_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2021-10-01 | 2022 Q1 | During the reporting period, the Bastrop County had environmental review underway for its Flood and Drainage project.
INF_SMID_UN_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
INF_SMID_UN_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2022-04-01 | 2022 Q3 | During the reporting period, Bastrop County had construction underway for its flood and drainage project.
INF_SMID_UN_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2022-07-01 | 2022 Q4 | During the reporting period, Bastrop County had construction underway for its Flood and Drainage project.
INF_SMID_UN_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2022-10-01 | 2023 Q1 | During the reporting period, the Bastrop County had engineering design underway for its project.
INF_SMID_UN_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2023-01-01 | 2023 Q2 | During the reporting period, Bastrop County completed construction and is pending submission of construction completion documentation for its street improvements project.
INF_SMID_UN_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2023-04-01 | 2023 Q3 | During the reporting period, Bastrop County had construction underway for its Flood and Drainage project.
INF_SMID_UN_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
INF_SMID_UN_20-065-139-C527_BastropCounty_F&D | Flood and Drainage | Rehabilitation/reconstruction of a public improvement | Bastrop County | 2023-10-01 | 2024 Q1 | During the reporting period Bastrop County completed construction and is pending submission of construction completion documentation for its Flood and Drainage project.
INF_SMID_UN_20-065-139-C527_BastropCounty_SI | Street Improvements | Construction/reconstruction of streets | Bastrop County | 2020-07-01 | 2020 Q4
INF_SMID_UN_20-065-139-C527_BastropCounty_SI | Street Improvements | Construction/reconstruction of streets | Bastrop County | 2021-01-01 | 2021 Q2 | During the reporting period, Bastrop County had engineering design underway and environmental complete for its street improvements project.
INF_SMID_UN_20-065-139-C527_BastropCounty_SI | Street Improvements | Construction/reconstruction of streets | Bastrop County | 2023-04-01 | 2023 Q3 | During the reporting period, Bastrop County had construction underway for its Street improvement project.
INF_SMID_UN_20-065-139-C527_BastropCounty_SI | Street Improvements | Construction/reconstruction of streets | Bastrop County | 2023-10-01 | 2024 Q1 | During the reporting period Bastrop County completed construction and is pending submission of construction completion documentation for its Street Improvement project.
INF_SMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_SMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 18599.46 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 7524.29 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 9596.72 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 3922.42 - State costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 1641.08 - State costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 2658.24 - State costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_F&D | Infrastructure Grantee Support for Subrecipient SMID UN Reconstruction of a Public Improvement | Rehabilitation/reconstruction of a public improvement | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_SMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_SMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 1419.34 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 572.61 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 742.24 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 305.15 - State costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 128.13 - State costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 334.05 - State costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_PF | Infrastructure Grantee Support for Subrecipient SMID UN Public Facilities Activities | Rehabilitation/reconstruction of public facilities | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_SMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_SMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 18921.15 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 5205.27 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 6640.71 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 2718.43 - State costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 1138.41 - State costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 2658.24 - State costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_SI | Infrastructure Grantee Support for Subrecipient SMID UN Street Improvement Activities | Construction/reconstruction of streets | Texas General Land Office | 2026-01-01 | 2026 Q2
INF_SMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2024-04-01 | 2024 Q3 | Activity budgeted and obligated during the quarter.
INF_SMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 6946.47 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 2319.54 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 2956.01 - Quarterly expenditure for state costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 1342.18 - State costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 630.81 - State costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Infrastructure program. 1328.41 - State costs in support of activity delivery.
INF_SMID_UN_GranteeSupport[H5b]_WSF | Infrastructure Grantee Support for Subrecipient SMID UN Water or Sewer lines or systems Activities | Construction/reconstruction of water/sewer lines or systems | Texas General Land Office | 2026-01-01 | 2026 Q2
LBAP_HMID_LMA_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMA_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2024-10-01 | 2025 Q1 | During the reporting period, Montgomery County had applications under review and 19 underway for its buyout project.
LBAP_HMID_LMA_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2025-04-01 | 2025 Q3 | Amendment was executed during the quarter, that reallocated funding amongst activities resulting in an increase to the budget and obligation of this activity.
LBAP_HMID_LMA_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2025-07-01 | 2025 Q4 | During the reporting period, Montgomery County completed 9 buyout awards and 8 demos for its Local Buyout Acquisition Program.
LBAP_HMID_LMA_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2025-10-01 | 2026 Q1 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
LBAP_HMID_LMA_20-066-022-C166_RoseCity | Acquisition - general | Acquisition - general | Rose City | 2020-01-01 | 2020 Q2
LBAP_HMID_LMA_20-066-022-C166_RoseCity | Acquisition - general | Acquisition - general | Rose City | 2022-10-01 | 2023 Q1 | During the reporting period, eligibility determination was underway. No expenditures were reimbursed.
LBAP_HMID_LMA_20-066-022-C166_RoseCity | Acquisition - general | Acquisition - general | Rose City | 2023-01-01 | 2023 Q2 | During the reporting period, Rose City had closeout underway for its acquisition program.
LBAP_HMID_LMA_20-066-022-C166_RoseCity | Acquisition - general | Acquisition - general | Rose City | 2024-04-01 | 2024 Q3 | Due to unforeseen complications and through no fault of the subrecipient, this project has concluded early benefitting no individuals. All expenses are related to the release of funds for the subrecipient receiving approval of the Housing Guidelines for the program and environmental costs. The rest of the expected funds initally awarded have been reduced from the activities of this contract.
LBAP_HMID_LMA_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMA_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_LMA_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2024-07-01 | 2024 Q4 | Changes made to the activity in the Action Plan module in DRGR. No actual changes were made.
LBAP_HMID_LMA_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Vidor completed 1 buyout and 7 were underway in various stages.
LBAP_HMID_LMA_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2025-10-01 | 2026 Q1 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
LBAP_HMID_LMA_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2020-01-01 | 2020 Q2
LBAP_HMID_LMA_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Bridge City accepted applications for eligibility review for its acquisition program.
LBAP_HMID_LMA_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMA_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2022-10-01 | 2023 Q1 | During the reporting period, appraisals were performed on 3 properties and advance payments were requested to purchase 1 property.
LBAP_HMID_LMA_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2023-01-01 | 2023 Q2 | During the reporting period, Bridge City had acquisition underway for its buyout projects.
LBAP_HMID_LMA_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2023-04-01 | 2023 Q3 | During the reporting period, Bridge City had buyout activities underway for its Buyout/Acquisition program.
LBAP_HMID_LMA_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2023-07-01 | 2023 Q4 | During the reporting period, Bridge City had Buyout activities underway for its Acquisition and Buyout program.
LBAP_HMID_LMA_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2024-01-01 | 2024 Q2 | During the reporting period, Bridge City had buyout and acquisition activities underway.
LBAP_HMID_LMA_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2024-04-01 | 2024 Q3 | During the reporting period, Bridge City completed demolition for its buyout and acquisition activities.
LBAP_HMID_LMA_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Bridge City had its buyout acquisition project administratively closed.
LBAP_HMID_LMA_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2025-10-01 | 2026 Q1 | Activity was completed during the reporting period.
LBAP_HMID_LMA_20-066-029-C223_WestOrange | Acquisition - general | Acquisition - general | CITY OF WEST ORANGE | 2020-01-01 | 2020 Q2
LBAP_HMID_LMA_20-066-029-C223_WestOrange | Acquisition - general | Acquisition - general | CITY OF WEST ORANGE | 2020-07-01 | 2020 Q4 | During the reporting period, the City of West Orange program guidelines were approved and accepted applications for eligibility review for its acquisition project.
LBAP_HMID_LMA_20-066-029-C223_WestOrange | Acquisition - general | Acquisition - general | CITY OF WEST ORANGE | 2020-10-01 | 2021 Q1
LBAP_HMID_LMA_20-066-029-C223_WestOrange | Acquisition - general | Acquisition - general | CITY OF WEST ORANGE | 2022-04-01 | 2022 Q3 | During the reporting period, the City of West Orange had applications reviewed for its acquisition project.
LBAP_HMID_LMA_20-066-029-C223_WestOrange | Acquisition - general | Acquisition - general | CITY OF WEST ORANGE | 2022-07-01 | 2022 Q4 | Environmental Review cost budgted and obligated.
LBAP_HMID_LMA_20-066-029-C223_WestOrange | Acquisition - general | Acquisition - general | CITY OF WEST ORANGE | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMA_20-066-029-C223_WestOrange | Acquisition - general | Acquisition - general | CITY OF WEST ORANGE | 2023-07-01 | 2023 Q4 | During the reporting period, the City of West Orange had Buyout activities underway for its Acquisition and Buyout program.
LBAP_HMID_LMA_20-066-029-C223_WestOrange | Acquisition - general | Acquisition - general | CITY OF WEST ORANGE | 2024-07-01 | 2024 Q4 | During the reporting period, the City of West Orange completed 1 project demolition and submitted Post demolition compliance checklist.
LBAP_HMID_LMA_20-066-029-C223_WestOrange | Acquisition - general | Acquisition - general | CITY OF WEST ORANGE | 2024-10-01 | 2025 Q1 | During the reporting period, a review was performed and this activity was correctly recategorized as an area benefit activity, and projections were updated.
LBAP_HMID_LMA_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2020-01-01 | 2020 Q2
LBAP_HMID_LMA_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Ingleside accepted applications for eligibility review for its Acquisition project.
LBAP_HMID_LMA_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Ingleside had 1 acquisition appraisal cost draw for its Acquisition project.
LBAP_HMID_LMA_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_LMA_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2023-04-01 | 2023 Q3 | During the reporting period, City of Ingleside had buyout activities underway for its Buyout/Acquisition program.
LBAP_HMID_LMA_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2023-07-01 | 2023 Q4 | Amendment reallocated funds from related activities that were cancelled.
LBAP_HMID_LMA_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Ingleside completed 1 appraisal review and soft costs for LMA buyout of home.
LBAP_HMID_LMA_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2025-01-01 | 2025 Q2 | During the reporting period, the City decided to cancel the program and the money expended by the City is a refund from the community to the GLO.
LBAP_HMID_LMA_20-066-034-C232_PortArthur_ACQ | Acquisition Program | Acquisition - general | Port Arthur | 2020-10-01 | 2021 Q1
LBAP_HMID_LMA_20-066-034-C232_PortArthur_ACQ | Acquisition Program | Acquisition - general | Port Arthur | 2021-01-01 | 2021 Q2
LBAP_HMID_LMA_20-066-034-C232_PortArthur_ACQ | Acquisition Program | Acquisition - general | Port Arthur | 2021-07-01 | 2021 Q4 | Originally a Buyout program that was changed to an Acquisition program, and Urgent Need activities were removed adding the budgets to the LMI activities within the contract.
LBAP_HMID_LMA_20-066-034-C232_PortArthur_ACQ | Acquisition Program | Acquisition - general | Port Arthur | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Port Arthur had outreach underway for its for its acquisition project.
LBAP_HMID_LMA_20-066-034-C232_PortArthur_ACQ | Acquisition Program | Acquisition - general | Port Arthur | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Port Arthur had acquisition underway for its acquisition project.
LBAP_HMID_LMA_20-066-034-C232_PortArthur_ACQ | Acquisition Program | Acquisition - general | Port Arthur | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_LMA_20-066-034-C232_PortArthur_ACQ | Acquisition Program | Acquisition - general | Port Arthur | 2025-10-01 | 2026 Q1 | Activity was completed during the reporting period.
LBAP_HMID_LMB_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2019-10-01 | 2020 Q1
LBAP_HMID_LMB_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_HMID_LMB_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity.
LBAP_HMID_LMB_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2023-10-01 | 2024 Q1 | During the reporting period, Montgomery County accepted applications for eligibility review for its Buyout project
LBAP_HMID_LMB_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2024-10-01 | 2025 Q1 | During the reporting period, Montgomery County had applications under review and 9 underway for its buyout project.
LBAP_HMID_LMB_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2025-04-01 | 2025 Q3 | Amendment was executed during the quarter, that reallocated funding amongst activities resulting in a decrease to the budget and obligation of this activity.
LBAP_HMID_LMB_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2025-07-01 | 2025 Q4 | During the reporting period, Montgomery County completed 1 buyout awards and 1 demos for its Local Buyout Acquisition Program.
LBAP_HMID_LMB_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2025-10-01 | 2026 Q1 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
LBAP_HMID_LMB_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2019-10-01 | 2020 Q1
LBAP_HMID_LMB_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2020-10-01 | 2021 Q1 | During the reporting period, Victoria County accepted applications for eligibility review for its Buyout Program.
LBAP_HMID_LMB_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2021-10-01 | 2022 Q1 | During the reporting period, Victoria County accepted applications for eligibility review for its Local Buyout project.
LBAP_HMID_LMB_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMB_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2023-01-01 | 2023 Q2 | During the reporting period, Victoria County had 3 underway for its buyout program.
LBAP_HMID_LMB_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2023-04-01 | 2023 Q3 | During the reporting period, Victoria County had 3 projects underway for its Buyout program.
LBAP_HMID_LMB_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2023-07-01 | 2023 Q4 | During the reporting period, Victoria County had 1 project underway for its Buyout program.
LBAP_HMID_LMB_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2024-04-01 | 2024 Q3 | During the reporting period, Victoria County had no activity for LMB, closeout is underway. 1,875 in soft costs expenditures was submitted in this quarter.
LBAP_HMID_LMB_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2025-01-01 | 2025 Q2 | Activity budget and obligation reduced according to closeout documentation, this activity did not serve any beneficiaries despite active marketing and good faith efforts by the subrecipient.
LBAP_HMID_LMB_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2025-04-01 | 2025 Q3 | During the reporting period, Victoria County had no expenditures on the grant management side.
LBAP_HMID_LMB_20-066-005-C034_Wharton | Buyout Program | Acquisition - buyout of residential properties | Wharton | 2019-10-01 | 2020 Q1
LBAP_HMID_LMB_20-066-005-C034_Wharton | Buyout Program | Acquisition - buyout of residential properties | Wharton | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_HMID_LMB_20-066-005-C034_Wharton | Buyout Program | Acquisition - buyout of residential properties | Wharton | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Wharton continued negotiations with land owner for intended buyout site, however, no expenditures for professional services were reimbursed during Q4 2022
LBAP_HMID_LMB_20-066-005-C034_Wharton | Buyout Program | Acquisition - buyout of residential properties | Wharton | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_HMID_LMB_20-066-005-C034_Wharton | Buyout Program | Acquisition - buyout of residential properties | Wharton | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Wharton had eminent domain proceedings underway.
LBAP_HMID_LMB_20-066-005-C034_Wharton | Buyout Program | Acquisition - buyout of residential properties | Wharton | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Wharton had eminent domain proceedings underway.
LBAP_HMID_LMB_20-066-005-C034_Wharton | Buyout Program | Acquisition - buyout of residential properties | Wharton | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Wharton had grant closeout documents under review for its xx project
LBAP_HMID_LMB_20-066-005-C034_Wharton | Buyout Program | Acquisition - buyout of residential properties | Wharton | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Wharton submitted grant closeout documents for its buyout program.
LBAP_HMID_LMB_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2019-10-01 | 2020 Q1
LBAP_HMID_LMB_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Victoria accepted applications for eligibility review for its Buyout Program.
LBAP_HMID_LMB_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Victoria accepted applications for eligibility review for its Local Buyout project.
LBAP_HMID_LMB_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMB_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Victoria has 10 projects underway for its Buyout program.
LBAP_HMID_LMB_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Victoria completed 2 projects for its buyout program and 6 underway.
LBAP_HMID_LMB_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Victoria no new completed projects and had 5 underway for its Buyout program
LBAP_HMID_LMB_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Victoria had completed 3 projects and had 5 underway for it buyout program.
LBAP_HMID_LMB_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_LMB_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2024-04-01 | 2024 Q3 | During this reporting period, the City of Victoria had no activity for LMB. $67,728.00 in expenditures was submitted in this quarter for buyout, demolition and soft costs. Closeout is underway.
LBAP_HMID_LMB_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Victoria had one LMB demolition and one LMB Buyout expenditures.
LBAP_HMID_LMB_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Victoria had one LMB demolition and one LMB Buyout expenditures.
LBAP_HMID_LMB_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2019-10-01 | 2020 Q1
LBAP_HMID_LMB_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_HMID_LMB_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Texas City accepted applications for eligibility review for its Local Buyout project.
LBAP_HMID_LMB_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMB_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Texas City applications under review for its buyout program.
LBAP_HMID_LMB_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_HMID_LMB_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Texas City had grant closeout documents under review for its buyout program.
LBAP_HMID_LMB_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Texas City had grant closeout documents under review for its buyout program.
LBAP_HMID_LMB_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_LMB_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2025-01-01 | 2025 Q2 | Activity budget and obligation reduced according to closeout documentation, this activity did not serve any beneficiaries despite active marketing and good faith efforts by the subrecipient.
LBAP_HMID_LMB_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2025-04-01 | 2025 Q3 | This contract was closed on 12/18/2024. Activity budget and obligation reduced according to closeout documentation, this activity did not serve any beneficiaries despite active marketing and good faith efforts by the subrecipient.
LBAP_HMID_LMB_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2019-10-01 | 2020 Q1
LBAP_HMID_LMB_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_HMID_LMB_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2022-10-01 | 2023 Q1 | During the reporting period, appraisals were underway for approved applicants, however, no expenditures for professional services were reimbursed during Q4 2022
LBAP_HMID_LMB_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_HMID_LMB_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Wharton County had 6 projects underway for the buyout program.
LBAP_HMID_LMB_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Wharton County had appraisals ordered and offers underway for approved applicants.
LBAP_HMID_LMB_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2024-04-01 | 2024 Q3 | During the reporting period, the Wharton County had acquisition underway for its Buyout project.
LBAP_HMID_LMB_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2024-10-01 | 2025 Q1 | During the reporting period, Wharton County submitted grant closeout documents for its Buyout project.
LBAP_HMID_LMB_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2025-01-01 | 2025 Q2 | During the reporting period, Wharton County submitted grant closeout documents for its Buyout Project.
LBAP_HMID_LMB_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2025-07-01 | 2025 Q4 | During the reporting period, Wharton County submitted grant closeout documents for its Buyout project.
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2019-10-01 | 2020 Q1
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Fayette County accepted applications for eligibility review for its Buyout project.
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Fayette County accepted and approved applications for eligibility review for its Local Buyout project.
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2022-07-01 | 2022 Q4 | During the reporting period, Fayette County has 4 approved applications underway for its Buyout program.
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Fayette County completed 3 projects and has 1 underway for its Buyout program
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Fayette County had Buyout activities underway for its Acquisition and Buyout program.
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2023-10-01 | 2024 Q1 | During the reporting period Fayette County had Buyout Activities underway for it&apos;s Acquisition and Buyout Program. Negative expenditure caused from revising vouchers in which the payments for an Urgent Need beneficiary were paid from the LMI activity.
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2024-04-01 | 2024 Q3 | During the reporting period, the County worked to finish demolition of the final properties for its Buyout program.
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2024-07-01 | 2024 Q4 | During the reporting period, the final payment was processed and paid. Closeout underway for its Buyout program.
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO received a refund for overpayment of taxes for its Buyout program.
LBAP_HMID_LMB_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO received a refund for overpayment of taxes for its Buyout program.
LBAP_HMID_LMB_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2020-01-01 | 2020 Q2
LBAP_HMID_LMB_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2020-07-01 | 2020 Q4 | During the reporting period, Liberty County had outreach underway for its buyout program.
LBAP_HMID_LMB_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2020-10-01 | 2021 Q1
LBAP_HMID_LMB_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2021-10-01 | 2022 Q1 | During the reporting period, Liberty County accepted applications for eligibility review for its Local Buyout project.
LBAP_HMID_LMB_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMB_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2022-10-01 | 2023 Q1 | During the reporting period, Liberty County had twenty-six (26) applications underway for its Buyout project.
LBAP_HMID_LMB_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and increased funds.
LBAP_HMID_LMB_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2023-04-01 | 2023 Q3 | During the reporting period, Liberty County accepted applications for eligibility review for its Buyout project.
LBAP_HMID_LMB_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2023-07-01 | 2023 Q4 | During the reporting period, Liberty County had no new projects completed and 10 underway for it Buyout program.
LBAP_HMID_LMB_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2023-10-01 | 2024 Q1 | During the reporting period, Liberty County had buyout activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_LMB_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2024-01-01 | 2024 Q2 | During the reporting period, Liberty County had buyout activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_LMB_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2025-07-01 | 2025 Q4 | During the reporting period, Liberty County completed 4 buyout awards and 4 demos for its Local Buyout Acquisition Program.
LBAP_HMID_LMB_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2019-10-01 | 2020 Q1
LBAP_HMID_LMB_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2020-10-01 | 2021 Q1 | During the reporting period, Newton County continues to carry out administrative services for its Buyout project.
LBAP_HMID_LMB_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2024-04-01 | 2024 Q3 | Dur the reporting period, Newton County has been begin obtaining appraisal for 20 parcels for the buyout process.
LBAP_HMID_LMB_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2024-07-01 | 2024 Q4 | During the reporting period, Newton County completed 1 LMB Demo.
LBAP_HMID_LMB_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2024-10-01 | 2025 Q1 | During the reporting period, Newton County completed 5 LMB Buyouts and 2 Demos.
LBAP_HMID_LMB_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2025-01-01 | 2025 Q2 | During the reporting period, Newton had demolished 4 LMB homes and had 1 LMB buyout.
LBAP_HMID_LMB_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2025-04-01 | 2025 Q3 | During the reporting period, Newton County demolished 1 LMB BP home and submitted a LMB PD payment request for 100% funds drawn to date. An amendment was submitted to extend contract to 7/31/25, reduce the number of homes to be bought out and de-obligate $4.4 million.
LBAP_HMID_LMB_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2025-07-01 | 2025 Q4 | During the reporting period, a contract amendment was executed that deobligated total funds from the project that were unutilized. Several activities were also cancelled.
LBAP_HMID_LMB_20-066-017-C123_CorpusChristi | Buyout Program | Acquisition - buyout of residential properties | Corpus Christi, City Of | 2020-01-01 | 2020 Q2
LBAP_HMID_LMB_20-066-017-C123_CorpusChristi | Buyout Program | Acquisition - buyout of residential properties | Corpus Christi, City Of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Corpus Christi accepted applications for eligibility review for its buyout program.
LBAP_HMID_LMB_20-066-017-C123_CorpusChristi | Buyout Program | Acquisition - buyout of residential properties | Corpus Christi, City Of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMB_20-066-017-C123_CorpusChristi | Buyout Program | Acquisition - buyout of residential properties | Corpus Christi, City Of | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Corpus Christi accepted applications for eligibility review for its Buyout project.
LBAP_HMID_LMB_20-066-017-C123_CorpusChristi | Buyout Program | Acquisition - buyout of residential properties | Corpus Christi, City Of | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
LBAP_HMID_LMB_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2020-01-01 | 2020 Q2
LBAP_HMID_LMB_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2020-10-01 | 2021 Q1 | During the reporting period, Polk County accepted applications for eligibility review for its Buyout Project.
LBAP_HMID_LMB_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2021-10-01 | 2022 Q1 | During the reporting period, Polk County had applications under review for its Buyout Program.
LBAP_HMID_LMB_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMB_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2023-04-01 | 2023 Q3 | Amendment moved funds to related activity.
LBAP_HMID_LMB_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
LBAP_HMID_LMB_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2023-10-01 | 2024 Q1 | During the reporting period, Polk County had activity underway for four projects in the buyout program.
LBAP_HMID_LMB_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2024-04-01 | 2024 Q3 | During the reporting period, Polk County had buyout activities underway for its Local Buyout and Acquisition Program.
LBAP_HMID_LMB_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2024-07-01 | 2024 Q4 | During the reporting period, Polk County initiated the purchase of 3 homes under its Local Acquisition and Buyout Program.
LBAP_HMID_LMB_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2024-10-01 | 2025 Q1 | During the reporting period, a review was performed and this activity was correctly recategorized as an HMID activity. MID Expenditures were entered to equal the current expenditures.
LBAP_HMID_LMB_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2025-07-01 | 2025 Q4 | During the reporting period, Polk County completed demo on 8 properties.
LBAP_HMID_LMB_20-066-019-C134_Nome | Buyout Program | Acquisition - buyout of residential properties | Nome | 2020-01-01 | 2020 Q2
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2020-01-01 | 2020 Q2
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2020-10-01 | 2021 Q1 | During the reporting period, San Jacinto County accepted applications for eligibility review for its Buyout Project.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2021-10-01 | 2022 Q1 | During the reporting period, San Jacinto County had 37 applications under review for its Buyout Program.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2023-04-01 | 2023 Q3 | During the reporting period, San Jacinto County had buyout activities underway for its Buyout project.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2023-07-01 | 2023 Q4 | During the reporting period, San Jacinto County had Buyout activities underway for its Acquisition and Buyout program.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2023-10-01 | 2024 Q1 | During the reporting period, San Jacinto County had Buyout activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2024-01-01 | 2024 Q2 | During the reporting period, San Jacinto County had Buyout activities underway for its Local Buyout and Acquisition Program.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2024-04-01 | 2024 Q3 | During the reporting period, San Jacinto County had buyout activities underway for it Local Buyout and Acquisition Program.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2024-07-01 | 2024 Q4 | During the reporting period, San Jacinto County completed the purchase of 3 homes, initiated the purchase of 2 additional homes, and completed demo on 2 hones for its Local Acquisition and Buyout Program.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2025-01-01 | 2025 Q2 | During the reporting period, San Jacinto County completed a contract amendment which will allow them to complete purchases of the final properties and begin closeout activities.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2025-04-01 | 2025 Q3 | During the reporting period, San Jacinto County completed Buyout Awards for 2 properties, and demo for 9 properties.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2025-07-01 | 2025 Q4 | During the reporting period, San Jacinto County completed demo on 6 properties.
LBAP_HMID_LMB_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2025-10-01 | 2026 Q1 | During the reporting period San Jacinto County was completing GCR for its buyout program.
LBAP_HMID_LMB_20-066-021-C137_SourLake | Buyout Program | Acquisition - buyout of residential properties | Sour Lake | 2020-01-01 | 2020 Q2
LBAP_HMID_LMB_20-066-021-C137_SourLake | Buyout Program | Acquisition - buyout of residential properties | Sour Lake | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Sour Lake program guidelines were approved for its buyout project.
LBAP_HMID_LMB_20-066-021-C137_SourLake | Buyout Program | Acquisition - buyout of residential properties | Sour Lake | 2020-10-01 | 2021 Q1
LBAP_HMID_LMB_20-066-021-C137_SourLake | Buyout Program | Acquisition - buyout of residential properties | Sour Lake | 2022-07-01 | 2022 Q4 | The City of Sour Lake did not have any buyout applicants. Contract expired April 2022. Costs are being reallocated to UN activity.
LBAP_HMID_LMB_20-066-021-C137_SourLake | Buyout Program | Acquisition - buyout of residential properties | Sour Lake | 2024-10-01 | 2025 Q1 | During the reporting period, this contract was administratively closed in DRGR. All funds have been drawn, and accomplishment and beneficiaries were entered.
LBAP_HMID_LMB_20-066-021-C137_SourLake | Buyout Program | Acquisition - buyout of residential properties | Sour Lake | 2025-01-01 | 2025 Q2 | Activity budget and obligation reduced according to closeout documentation, this activity did not serve any beneficiaries despite active marketing and good faith efforts by the subrecipient.
LBAP_HMID_LMB_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2020-01-01 | 2020 Q2
LBAP_HMID_LMB_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Vidor program guidelines were approved for its Buyout project.
LBAP_HMID_LMB_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMB_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Vidor had Buyout activities underway for its Local Buyout and Acquisition Program.
LBAP_HMID_LMB_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Vidor completed the buyout process for 3 parcels and submitted 1 URA payment request. $205,865.75 expended in Q2.
LBAP_HMID_LMB_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Vidor submitted a advanced payment request for 1 LMB buyout.
LBAP_HMID_LMB_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Vidor continues to carry out administrative services for its buyout program.
LBAP_HMID_LMB_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Vidor completed demolition for 4 properties.
LBAP_HMID_LMB_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2025-10-01 | 2026 Q1 | During the reporting period the city of Vidor was completing purchase and demolition of the final 2 properties for its buyout program.
LBAP_HMID_LMB_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2020-01-01 | 2020 Q2
LBAP_HMID_LMB_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Silsbee program guidelines were approved for its buyout project.
LBAP_HMID_LMB_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2020-10-01 | 2021 Q1
LBAP_HMID_LMB_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Silsbee has two approved applications for its Buyout Program. Costs reallocated to UN activity.
LBAP_HMID_LMB_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Silsbee had two approved applications. One payment request is currently routing for buyout of one property.
LBAP_HMID_LMB_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Silsbee had acquisition underway for its buyout projects.
LBAP_HMID_LMB_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Silsbee had no new projects completed and 1 underway for its Buyout program.
LBAP_HMID_LMB_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Silsbee
LBAP_HMID_LMB_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
LBAP_HMID_LMB_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2025-10-01 | 2026 Q1 | Activity was completed during the reporting period.
LBAP_HMID_LMB_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMB_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2023-04-01 | 2023 Q3 | During the reporting period, Bridge City received advance payment to purchase 1 home under its Buyout program.
LBAP_HMID_LMB_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2023-07-01 | 2023 Q4 | During the reporting period, Bridge City had Buyout activities underway for its Acquisition and Buyout program.
LBAP_HMID_LMB_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2023-10-01 | 2024 Q1 | During the reporting period, Bridge City had buyout and demolition activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_LMB_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2024-01-01 | 2024 Q2 | During the reporting period, funds were removed from the budget and obligation, and other activities from this contract were deleted.
LBAP_HMID_LMB_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Bridge City had its buyout acquisition project administratively closed.
LBAP_HMID_LMB_20-066-025-C202_BridgeCity | Buyout Program - Acquisition | Acquisition - buyout of residential properties | Bridge City | 2025-10-01 | 2026 Q1 | Activity was completed during the reporting period.
LBAP_HMID_LMB_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2020-01-01 | 2020 Q2
LBAP_HMID_LMB_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Jasper had outreach underway for its Buyout project.
LBAP_HMID_LMB_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Jasper had applications under review for its buyout project.
LBAP_HMID_LMB_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMB_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Jasper had buyout underway for one home for its buyout program project.
LBAP_HMID_LMB_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Jasper had acquisition underway for its buyout project. *This project is on here twice - see below*.
LBAP_HMID_LMB_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2023-07-01 | 2023 Q4 | During the reporting period, Jasper had buyout activities underway for its underway for its buyout project.
LBAP_HMID_LMB_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2024-07-01 | 2024 Q4 | Time Extension approved for new contract end date: 12/31/2024. Subrecipient will provide a Buyout program for approximately three (3) residential dwellings affected by Hurricane Harvey, changing from three (3) to six(6) residential dwellings as indicated on Attachment A. The City believes that it may expend $1,000,000.00 of the total grant amount and requests no deobligation of funds at this time. This will be Amendment 6.
LBAP_HMID_LMB_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2025-04-01 | 2025 Q3 | During this reporting, the City of Jasper completed 1 demolition for 1 property, and walk bid walk thru for the other property
LBAP_HMID_LMB_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2025-07-01 | 2025 Q4 | During the reporting period, Jasper County completed demo on 1 property.
LBAP_HMID_LMB_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2025-10-01 | 2026 Q1 | During the reporting period the city of Jasper was completing demolition of the final properties for its buyout program.
LBAP_HMID_LMB_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2020-01-01 | 2020 Q2
LBAP_HMID_LMB_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2021-10-01 | 2022 Q1 | During the reporting period, Jefferson County accepted applications for eligibility review for its buyout project.
LBAP_HMID_LMB_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2022-10-01 | 2023 Q1 | During the reporting period, Jefferson County accepted applications for eligibility review for its 20 project.
LBAP_HMID_LMB_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_LMB_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Beaumont completed 1 (e.g. HAP projects, HBA projects, buyout program) and 8 were underway.
LBAP_HMID_LMB_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_LMB_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2024-10-01 | 2025 Q1 | During the reporting period, Jefferson County had 5 buyouts underway.
LBAP_HMID_LMB_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2025-07-01 | 2025 Q4 | During the reporting period, Jefferson County completed 6 additional projects.
LBAP_HMID_LMB_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2025-10-01 | 2026 Q1 | During the reporting period, Jefferson County submitted grant closeout documents for its buyout program.
LBAP_HMID_LMB_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2020-01-01 | 2020 Q2
LBAP_HMID_LMB_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Orange continues to carry out administrative services for its Acquisition project.
LBAP_HMID_LMB_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Orange accepted applications for eligibility review for its acquisition project.
LBAP_HMID_LMB_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMB_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2023-04-01 | 2023 Q3 | Amendment moved funds to related activity and decreased projected performance measures.
LBAP_HMID_LMB_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Orange accepted applications for eligibility review for its Acquisition and Buyout program.
LBAP_HMID_LMB_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments were made to the projected beneficiaries of this activity.
LBAP_HMID_LMB_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Orange had buyout activities underway for its Local Buyout and Acquisition Program.
LBAP_HMID_LMB_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Orange had closeout activities underway.
LBAP_HMID_LMB_20-066-040-C259_Dickinson | Buyout Program | Acquisition - buyout of residential properties | Dickinson | 2020-04-01 | 2020 Q3
LBAP_HMID_LMB_20-066-040-C259_Dickinson | Buyout Program | Acquisition - buyout of residential properties | Dickinson | 2021-01-01 | 2021 Q2 | During this reporting period, no new projects closed and there are 0 underway.
LBAP_HMID_LMB_20-066-040-C259_Dickinson | Buyout Program | Acquisition - buyout of residential properties | Dickinson | 2025-10-01 | 2026 Q1 | During the reporting period, Activity budget and obligation reduced according to closeout documentation.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2020-01-01 | 2020 Q2
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Hardin County of had outreach underway for its for its Acquisition project.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2021-04-01 | 2021 Q3 | During the reporting period, the Hardin County had acquisition underway.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2021-07-01 | 2021 Q4 | During the reporting period, Hardin County accepted applications for eligibility review for its acquisition project.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Hardin County accepted applications for eligibility review for its Acquisition project.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2022-07-01 | 2022 Q4 | During the reporting period, Hardin County had three of four approved applications to have appraisals completed.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Hardin County had four applications approved and offer letters signed by homeowners for its buyout project.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Hardin county received advanced payment to purchase two homes for its acquisition program.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2023-10-01 | 2024 Q1 | During this reporting period, Hardin County had demolition activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2024-01-01 | 2024 Q2 | During the reporting period, Hardin County completed all projects for the local buyout/acquisition program
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2024-04-01 | 2024 Q3 | During this reporting period Hardin County, payment request for soft cost, 3,750. Hardin County completed all projects for the local buyout and acquisition program. The buyout demolition-LMB is at 69.07 percent, buyout soft cost-LMB is at 80.02, buyout LMB-PD is at 88.98.
LBAP_HMID_LMB_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2024-07-01 | 2024 Q4 | There were no Draws submitted. No new projects closed and there are 0 underway.
LBAP_HMID_LMB_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2020-04-01 | 2020 Q3
LBAP_HMID_LMB_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2021-07-01 | 2021 Q4 | During the reporting period, Jasper County program guidelines were approved for its buyout project.
LBAP_HMID_LMB_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2022-10-01 | 2023 Q1 | During the reporting period, the County completed required appraisals on two applications
LBAP_HMID_LMB_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_LMB_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2023-07-01 | 2023 Q4 | During the reporting period, Jasper County had no new project completed and 5 underway for the buyout program.
LBAP_HMID_LMB_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2023-10-01 | 2024 Q1 | During this reporting period, Jasper County had 1 buy-out completed and 4 underway for the buyout program.
LBAP_HMID_LMB_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2024-07-01 | 2024 Q4 | Pending Approval of Time Extension for new contract end date of 02/28/2025. Jasper County needs the extension to finalize buyout activities such as draw processing draws, demolition and closeout.
LBAP_HMID_LMB_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2025-04-01 | 2025 Q3 | During the reporting period, Jasper County completed Buyout Awards for 2 properties.
LBAP_HMID_LMB_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2025-07-01 | 2025 Q4 | During the reporting period, Jasper County completed demo on 1 property.
LBAP_HMID_LMB_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2020-04-01 | 2020 Q3
LBAP_HMID_LMB_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Beaumont accepted applications for eligibility review for its buyout project.
LBAP_HMID_LMB_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Beaumont accepted applications for eligibility review for its buyout project.
LBAP_HMID_LMB_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_LMB_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Beaumont had buyout activities underway for its Local Buyout and Acquisition Program.
LBAP_HMID_LMB_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Beaumont completed 2 buyout program and 3 were underway.
LBAP_HMID_LMB_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Beaumont had 6 buyouts underway.
LBAP_HMID_LMB_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2025-04-01 | 2025 Q3 | Amendment was executed prior to this quarter, that reallocated funding amongst activities resulting in a decrease to the budget and obligation of this activity which was completed in this quarter
LBAP_HMID_LMB_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Beaumont completed 7 projects.
LBAP_HMID_LMB_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Beaumont submitted grant closeout documents for its buyout program.
LBAP_HMID_LMB_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2020-07-01 | 2020 Q4
LBAP_HMID_LMB_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2021-01-01 | 2021 Q2 | During the reporting period, the Orange County program guidelines were approved for its Buyout project.
LBAP_HMID_LMB_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2021-10-01 | 2022 Q1 | During the reporting period, Orange County accepted applications for eligibility review for its buyout project.
LBAP_HMID_LMB_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMB_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2022-10-01 | 2023 Q1 | During the reporting period, amendement 1 for this contract was executed. As a result of the amendment, funds were deobligated from the total contracted amount, new activites for housing incentive activity types were added, and projected performance measures and beneficaries were reduced.
LBAP_HMID_LMB_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2023-01-01 | 2023 Q2 | During the reporting period, Orange County accepted applications for eligibility review for its buyout project.
LBAP_HMID_LMB_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2023-10-01 | 2024 Q1 | During the reporting period, Orange County had buyout activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_LMB_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2024-01-01 | 2024 Q2 | Activity was unobligated by $0.01 and was corrected this quarter.
LBAP_HMID_LMB_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2024-04-01 | 2024 Q3 | During the reporting period, Orange County had buyout activities underway for its Local Buyout and Acquisition Program.
LBAP_HMID_LMB_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2024-07-01 | 2024 Q4 | During the reporting period, Orange County completed 1 buyout program demolition and 2 were underway.
LBAP_HMID_LMB_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2025-01-01 | 2025 Q2 | During the reporting period, Orange County had grant closeout documents under review for its buyout program.
LBAP_HMID_LMB_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2025-04-01 | 2025 Q3 | During the reporting period, Orange County had grant closeout documents under review for its Buyout Program.
LBAP_HMID_LMB_20-066-049-C772_LeagueCity_ACQ | Acquisition Program | Acquisition - buyout of residential properties | League City | 2021-01-01 | 2021 Q2
LBAP_HMID_LMB_20-066-049-C772_LeagueCity_ACQ | Acquisition Program | Acquisition - buyout of residential properties | League City | 2021-07-01 | 2021 Q4 | During the reporting period, the City of League City had program guidelines under review for its acquisition program.
LBAP_HMID_LMB_20-066-049-C772_LeagueCity_ACQ | Acquisition Program | Acquisition - buyout of residential properties | League City | 2023-01-01 | 2023 Q2 | During the reporting period, the City of League City had outreach underway for its Buyout project.
LBAP_HMID_LMB_20-066-049-C772_LeagueCity_ACQ | Acquisition Program | Acquisition - buyout of residential properties | League City | 2023-07-01 | 2023 Q4 | During the reporting period, the City of League City had applications under review for its Buyout project.
LBAP_HMID_LMB_20-066-049-C772_LeagueCity_ACQ | Acquisition Program | Acquisition - buyout of residential properties | League City | 2023-10-01 | 2024 Q1 | During the reporting period, League City had applications under review for its buyout project.
LBAP_HMID_LMB_20-066-049-C772_LeagueCity_ACQ | Acquisition Program | Acquisition - buyout of residential properties | League City | 2024-07-01 | 2024 Q4 | Performance measures decreased and budget decreased and reallocated to Urgent Need activity.
LBAP_HMID_LMH_20-066-001-B956_MontgomeryCounty_DPA | Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Montgomery County | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMH_20-066-001-B956_MontgomeryCounty_DPA | Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Montgomery County | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity.
LBAP_HMID_LMH_20-066-001-B956_MontgomeryCounty_DPA | Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Montgomery County | 2024-10-01 | 2025 Q1 | During the reporting period, Montgomery County had applications under review and 3 underway for its buyout project.
LBAP_HMID_LMH_20-066-001-B956_MontgomeryCounty_DPA | Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Montgomery County | 2025-04-01 | 2025 Q3 | Amendment was executed during the quarter, that reallocated funding amongst activities resulting in a decrease to the budget and obligation of this activity.
LBAP_HMID_LMH_20-066-001-B956_MontgomeryCounty_DPA | Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Montgomery County | 2025-07-01 | 2025 Q4 | During the reporting period, Montgomery County completed Down Payment Assistance for 2 projects.
LBAP_HMID_LMH_20-066-001-B956_MontgomeryCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Montgomery County | 2019-10-01 | 2020 Q1
LBAP_HMID_LMH_20-066-001-B956_MontgomeryCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Montgomery County | 2023-01-01 | 2023 Q2 | Amendment de-obligated funds. Responsible Organization corrected.
LBAP_HMID_LMH_20-066-001-B956_MontgomeryCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Montgomery County | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity.
LBAP_HMID_LMH_20-066-001-B956_MontgomeryCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Montgomery County | 2024-10-01 | 2025 Q1 | During the reporting period, Montgomery County had applications under review and 3 underway for its buyout project.
LBAP_HMID_LMH_20-066-001-B956_MontgomeryCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Montgomery County | 2025-04-01 | 2025 Q3 | Amendment was executed during the quarter, that reallocated funding amongst activities resulting in an increase to the budget and obligation of this activity.
LBAP_HMID_LMH_20-066-001-B956_MontgomeryCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Montgomery County | 2025-07-01 | 2025 Q4 | During the reporting period, Montgomery County completed relocation assistance for 3 properties.
LBAP_HMID_LMH_20-066-005-C034_Wharton_RA | Relocation Assistance | Relocation payments and assistance | Wharton | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMH_20-066-005-C034_Wharton_RA | Relocation Assistance | Relocation payments and assistance | Wharton | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Wharton had URA underway for its Buyout program.
LBAP_HMID_LMH_20-066-005-C034_Wharton_RA | Relocation Assistance | Relocation payments and assistance | Wharton | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Wharton submitted grant closeout documents for its buyout/RA program.
LBAP_HMID_LMH_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMH_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Victoria had on project completed for its Buyout Relocation Assistance project.
LBAP_HMID_LMH_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Victoria had one project completed and two underway for it Relocation Assistance activity.
LBAP_HMID_LMH_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_LMH_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2024-04-01 | 2024 Q3 | Contract amendment to extend end dates, revise budgets amongst activities and reduced all projected accomplishments.
LBAP_HMID_LMH_20-066-009-C052_WhartonCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Wharton, County of | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMH_20-066-009-C052_WhartonCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Wharton, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Wharton County had offers underway for approved applicants.
LBAP_HMID_LMH_20-066-009-C052_WhartonCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Wharton, County of | 2024-04-01 | 2024 Q3
LBAP_HMID_LMH_20-066-009-C052_WhartonCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Wharton, County of | 2024-10-01 | 2025 Q1 | During the reporting period, Wharton County had 2 underway for its buyout project.
LBAP_HMID_LMH_20-066-009-C052_WhartonCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Wharton, County of | 2025-07-01 | 2025 Q4 | During the reporting period, Wharton County submitted grant closeout documents for its Buyout project.
LBAP_HMID_LMH_20-066-010-C063_FayetteCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Fayette, County of | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMH_20-066-010-C063_FayetteCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Fayette, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Fayette County had Buyout activities underway for its Acquisition and Buyout program.
LBAP_HMID_LMH_20-066-010-C063_FayetteCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Fayette, County of | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_LMH_20-066-010-C063_FayetteCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Fayette, County of | 2024-07-01 | 2024 Q4 | During the reporting period, the final payment was processed and paid. Closeout underway for its Buyout program.
LBAP_HMID_LMH_20-066-013-C095_LibertyCounty_RA | Relocation Assistance | Relocation payments and assistance | Liberty County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMH_20-066-013-C095_LibertyCounty_RA | Relocation Assistance | Relocation payments and assistance | Liberty County | 2023-07-01 | 2023 Q4 | During the reporting period, Liberty County had no new projects completed and 10 underway for its Buyout Relocation Assistance program.
LBAP_HMID_LMH_20-066-013-C095_LibertyCounty_RA | Relocation Assistance | Relocation payments and assistance | Liberty County | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_LMH_20-066-013-C095_LibertyCounty_RA | Relocation Assistance | Relocation payments and assistance | Liberty County | 2025-07-01 | 2025 Q4 | During the reporting period, Liberty County completed 9 relocation assistance projects for its Local Buyout Acquisition Program.
LBAP_HMID_LMH_20-066-017-C123_CorpusChristi_RA | Buyout Program | Relocation payments and assistance | Corpus Christi, City Of | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMH_20-066-017-C123_CorpusChristi_RA | Buyout Program | Relocation payments and assistance | Corpus Christi, City Of | 2023-04-01 | 2023 Q3 | Activity created during previous quarter.
LBAP_HMID_LMH_20-066-018-C125_PolkCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Polk County | 2023-04-01 | 2023 Q3 | Activity created during quarter.
LBAP_HMID_LMH_20-066-018-C125_PolkCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Polk County | 2024-07-01 | 2024 Q4 | Budget reduced due to scope reduction.
LBAP_HMID_LMH_20-066-018-C125_PolkCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Polk County | 2025-07-01 | 2025 Q4 | During the reporting period, Polk County completed RA on 4 properties.
LBAP_HMID_LMH_20-066-020-C135_SanJacintoCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | San Jacinto County | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMH_20-066-020-C135_SanJacintoCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | San Jacinto County | 2023-10-01 | 2024 Q1 | During the reporting period, San Jacinto County had Relocation activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_LMH_20-066-020-C135_SanJacintoCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | San Jacinto County | 2024-01-01 | 2024 Q2 | During the reporting period, San Jacinto County had Relocation activities underway for its Local Buyout and Acquisition Program.
LBAP_HMID_LMH_20-066-020-C135_SanJacintoCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | San Jacinto County | 2025-01-01 | 2025 Q2 | During the reporting period, San Jacinto County completed a contract amendment which will allow them to complete relocation activities for the final properties and begin closeout activities.
LBAP_HMID_LMH_20-066-020-C135_SanJacintoCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | San Jacinto County | 2025-10-01 | 2026 Q1 | During the reporting period San Jacinto County was completing GCR for its buyout program.
LBAP_HMID_LMH_20-066-023-C168_Vidor_DPA | Buyout Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Vidor | 2020-01-01 | 2020 Q2
LBAP_HMID_LMH_20-066-023-C168_Vidor_DPA | Buyout Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Vidor | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_LMH_20-066-023-C168_Vidor_DPA | Buyout Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Vidor | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Vidor provided down payment assistance to one property owner.
LBAP_HMID_LMH_20-066-023-C168_Vidor_DPA | Buyout Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Vidor | 2025-10-01 | 2026 Q1 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
LBAP_HMID_LMH_20-066-023-C168_Vidor_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Vidor | 2020-01-01 | 2020 Q2
LBAP_HMID_LMH_20-066-023-C168_Vidor_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Vidor | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_LMH_20-066-023-C168_Vidor_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Vidor | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Vidor had 1 LMH RA activity payment submitted.
LBAP_HMID_LMH_20-066-023-C168_Vidor_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Vidor | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Vidor provided relocation assistance to a residential dwelling.
LBAP_HMID_LMH_20-066-023-C168_Vidor_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Vidor | 2025-10-01 | 2026 Q1 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
LBAP_HMID_LMH_20-066-024-C178_Silsbee | Buyout Program - Relocation Assistance | Relocation payments and assistance | Silsbee | 2020-01-01 | 2020 Q2
LBAP_HMID_LMH_20-066-024-C178_Silsbee | Buyout Program - Relocation Assistance | Relocation payments and assistance | Silsbee | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMH_20-066-024-C178_Silsbee | Buyout Program - Relocation Assistance | Relocation payments and assistance | Silsbee | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Silsbee had 1 project completed and 15 underway for Buyout Housing Incentive program.
LBAP_HMID_LMH_20-066-024-C178_Silsbee | Buyout Program - Relocation Assistance | Relocation payments and assistance | Silsbee | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
LBAP_HMID_LMH_20-066-024-C178_Silsbee | Buyout Program - Relocation Assistance | Relocation payments and assistance | Silsbee | 2025-10-01 | 2026 Q1 | During the reporting period, Activity budget and obligation reduced according to closeout documentation.
LBAP_HMID_LMH_20-066-025-C202_BridgeCity_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bridge City | 2020-01-01 | 2020 Q2
LBAP_HMID_LMH_20-066-025-C202_BridgeCity_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bridge City | 2020-07-01 | 2020 Q4 | During the reporting period, the City of Bridge City program guidelines were approved and accepted applications for eligibility review for its acquisition project.
LBAP_HMID_LMH_20-066-025-C202_BridgeCity_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bridge City | 2020-10-01 | 2021 Q1
LBAP_HMID_LMH_20-066-025-C202_BridgeCity_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bridge City | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Bridge City accepted applications for eligibility review for its acquisition program.
LBAP_HMID_LMH_20-066-025-C202_BridgeCity_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bridge City | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMH_20-066-025-C202_BridgeCity_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bridge City | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMH_20-066-025-C202_BridgeCity_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bridge City | 2023-04-01 | 2023 Q3 | During the reporting period, Bridge City received payment for moving expenses for 1 household for its Acquisition program.
LBAP_HMID_LMH_20-066-025-C202_BridgeCity_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bridge City | 2024-04-01 | 2024 Q3 | During the reporting period, Bridge City completed demolition for its buyout and acquisition activities. DRGR RA was corrected.
LBAP_HMID_LMH_20-066-025-C202_BridgeCity_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bridge City | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
LBAP_HMID_LMH_20-066-029-C223_WestOrange_HA | Acquisition Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | CITY OF WEST ORANGE | 2020-01-01 | 2020 Q2
LBAP_HMID_LMH_20-066-029-C223_WestOrange_HA | Acquisition Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | CITY OF WEST ORANGE | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMH_20-066-029-C223_WestOrange_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | CITY OF WEST ORANGE | 2020-01-01 | 2020 Q2
LBAP_HMID_LMH_20-066-029-C223_WestOrange_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | CITY OF WEST ORANGE | 2020-07-01 | 2020 Q4
LBAP_HMID_LMH_20-066-029-C223_WestOrange_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | CITY OF WEST ORANGE | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMH_20-066-031-C225_Jasper_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jasper | 2020-01-01 | 2020 Q2
LBAP_HMID_LMH_20-066-031-C225_Jasper_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jasper | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Jasper had applications under review for its buyout project.
LBAP_HMID_LMH_20-066-031-C225_Jasper_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jasper | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMH_20-066-031-C225_Jasper_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jasper | 2023-07-01 | 2023 Q4 | Activity created.
LBAP_HMID_LMH_20-066-031-C225_Jasper_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jasper | 2024-01-01 | 2024 Q2 | Budgets were corrected based on an amendment from the previous quarter.
LBAP_HMID_LMH_20-066-031-C225_Jasper_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jasper | 2025-04-01 | 2025 Q3 | During this reporting, the City of Jasper completed 1 demolition for 1 property, and walk bid walk thru for the other property
LBAP_HMID_LMH_20-066-031-C225_Jasper_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jasper | 2025-07-01 | 2025 Q4 | During the reporting period, City of Jasper demolition complete on 1 property
LBAP_HMID_LMH_20-066-036-C242_JeffersonCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jefferson County | 2020-01-01 | 2020 Q2
LBAP_HMID_LMH_20-066-036-C242_JeffersonCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jefferson County | 2025-07-01 | 2025 Q4 | During the reporting period, the subrecipient requested a budget adjustment to reallocate funding, primarily from the Low/Mod Buyout activity, to the various housing incentive activities.
LBAP_HMID_LMH_20-066-039-C258_Orange_DPA | Acquisition Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Orange | 2020-01-01 | 2020 Q2
LBAP_HMID_LMH_20-066-039-C258_Orange_DPA | Acquisition Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Orange | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Orange accepted applications for eligibility review for its acquisition project.
LBAP_HMID_LMH_20-066-039-C258_Orange_DPA | Acquisition Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Orange | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMH_20-066-039-C258_Orange_DPA | Acquisition Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Orange | 2023-04-01 | 2023 Q3 | Amendment moved funds to related activity.
LBAP_HMID_LMH_20-066-039-C258_Orange_DPA | Acquisition Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Orange | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Orange accepted applications for eligibility review for its Acquisition and Buyout program.
LBAP_HMID_LMH_20-066-039-C258_Orange_RA | Acquisition Program - Relocation Payments | Relocation payments and assistance | Orange | 2020-04-01 | 2020 Q3
LBAP_HMID_LMH_20-066-039-C258_Orange_RA | Acquisition Program - Relocation Payments | Relocation payments and assistance | Orange | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Orange accepted applications for eligibility review for its acquisition project.
LBAP_HMID_LMH_20-066-039-C258_Orange_RA | Acquisition Program - Relocation Payments | Relocation payments and assistance | Orange | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMH_20-066-039-C258_Orange_RA | Acquisition Program - Relocation Payments | Relocation payments and assistance | Orange | 2023-04-01 | 2023 Q3 | Amendment moved funds to related activity and decreased projected performance measures.
LBAP_HMID_LMH_20-066-039-C258_Orange_RA | Acquisition Program - Relocation Payments | Relocation payments and assistance | Orange | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Orange accepted applications for eligibility review for its Acquisition and Buyout program.
LBAP_HMID_LMH_20-066-041-C266_HardinCounty_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | Hardin, County of | 2020-01-01 | 2020 Q2
LBAP_HMID_LMH_20-066-041-C266_HardinCounty_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | Hardin, County of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMH_20-066-043-C300_JasperCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jasper County | 2023-07-01 | 2023 Q4 | Activity created.
LBAP_HMID_LMH_20-066-043-C300_JasperCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jasper County | 2024-07-01 | 2024 Q4 | Budget reduced due to scope reduction.
LBAP_HMID_LMH_20-066-043-C300_JasperCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jasper County | 2025-07-01 | 2025 Q4 | During the reporting period, Jasper County completed RA on 2 properties.
LBAP_HMID_LMH_20-066-044-C314_Beaumont_RA | Relocation Assistance | Relocation payments and assistance | Beaumont | 2025-04-01 | 2025 Q3 | Activity created, budgeted and obligated during the quarter.
LBAP_HMID_LMH_20-066-044-C314_Beaumont_RA | Relocation Assistance | Relocation payments and assistance | Beaumont | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Beaumont completed 5 projects.
LBAP_HMID_LMH_20-066-045-C444_Friendswood_RA | Relocation Assistance | Relocation payments and assistance | City of Friendswood | 2023-07-01 | 2023 Q4 | Activity created.
LBAP_HMID_LMH_20-066-045-C444_Friendswood_RA | Relocation Assistance | Relocation payments and assistance | City of Friendswood | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Friendswood completed the demolition of all 16 acquired homes.
LBAP_HMID_LMH_20-066-045-C444_Friendswood_RA | Relocation Assistance | Relocation payments and assistance | City of Friendswood | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Friendswood completed the demolition of all 16 acquired homes.
LBAP_HMID_LMH_20-066-045-C444_Friendswood_RA | Relocation Assistance | Relocation payments and assistance | City of Friendswood | 2025-10-01 | 2026 Q1 | During the reporting period, Activity budget and obligation were reduced.
LBAP_HMID_LMH_20-066-046-C455_GalvestonCounty_RA | Relocation Assistance | Relocation payments and assistance | Galveston County | 2024-01-01 | 2024 Q2 | During the reporting period, a contract amendment was executed that reduced budgets for existing UN activities to create 3 new LMI activities and an additional UN activity, and reduced projected measures.
LBAP_HMID_LMH_20-066-046-C455_GalvestonCounty_RA | Relocation Assistance | Relocation payments and assistance | Galveston County | 2024-07-01 | 2024 Q4 | During this period, the county submitted draw #5 & #6 for its relocation assistance program.
LBAP_HMID_LMH_20-066-048-C526_OrangeCounty_DPA | Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Orange County | 2022-10-01 | 2023 Q1 | During the reporting period, amendement 1 for this contract was executed. As a result of the amendment, funds were deobligated from the total contracted amount, new activites for housing incentive activity types were added, and projected performance measures and beneficaries were reduced.
LBAP_HMID_LMH_20-066-048-C526_OrangeCounty_DPA | Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Orange County | 2023-10-01 | 2024 Q1 | During the quarter, an amendment to this contract was executed, reducing the budget, obligation and projected measures.
LBAP_HMID_LMH_20-066-048-C526_OrangeCounty_DPA | Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Orange County | 2025-01-01 | 2025 Q2 | Reduced the activity budget and obligation and the funding was reallocated to other activities within this contract.
LBAP_HMID_LMH_20-066-048-C526_OrangeCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Orange County | 2020-07-01 | 2020 Q4
LBAP_HMID_LMH_20-066-048-C526_OrangeCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Orange County | 2021-10-01 | 2022 Q1 | During the reporting period, Orange County accepted applications for eligibility review for its buyout project.
LBAP_HMID_LMH_20-066-048-C526_OrangeCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Orange County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMH_20-066-048-C526_OrangeCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Orange County | 2022-10-01 | 2023 Q1 | During the reporting period, amendement 1 for this contract was executed. As a result of the amendment, funds were deobligated from the total contracted amount, new activites for housing incentive activity types were added, and projected performance measures and beneficaries were reduced.
LBAP_HMID_LMH_20-066-048-C526_OrangeCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Orange County | 2023-10-01 | 2024 Q1 | During the quarter, an amendment to this contract was executed, reducing the budget, obligation and projected measures.
LBAP_HMID_LMH_20-066-048-C526_OrangeCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Orange County | 2024-07-01 | 2024 Q4 | During the reporting period, Orange County completed 1 buyout program and 2 were underway.
LBAP_HMID_LMHI_20-066-001-B956_MontgomeryCounty_HI | Housing Incentives | Housing incentives to encourage resettlement | Montgomery County | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMHI_20-066-001-B956_MontgomeryCounty_HI | Housing Incentives | Housing incentives to encourage resettlement | Montgomery County | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity.
LBAP_HMID_LMHI_20-066-001-B956_MontgomeryCounty_HI | Housing Incentives | Housing incentives to encourage resettlement | Montgomery County | 2024-10-01 | 2025 Q1 | During the reporting period, Montgomery County had applications under review and 12 underway for its buyout project.
LBAP_HMID_LMHI_20-066-001-B956_MontgomeryCounty_HI | Housing Incentives | Housing incentives to encourage resettlement | Montgomery County | 2025-04-01 | 2025 Q3 | Amendment was executed during the quarter, that reallocated funding amongst activities resulting in an increase to the budget and obligation of this activity.
LBAP_HMID_LMHI_20-066-001-B956_MontgomeryCounty_HI | Housing Incentives | Housing incentives to encourage resettlement | Montgomery County | 2025-07-01 | 2025 Q4 | During the reporting period, Montgomery County completed Housing Incentives assistance for 4 projects.
LBAP_HMID_LMHI_20-066-007-C041_Victoria | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Victoria, City of (INC) | 2019-10-01 | 2020 Q1
LBAP_HMID_LMHI_20-066-007-C041_Victoria | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Victoria, City of (INC) | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Victoria accepted applications for eligibility review for its Local Buyout project.
LBAP_HMID_LMHI_20-066-007-C041_Victoria | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Victoria, City of (INC) | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMHI_20-066-007-C041_Victoria | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Victoria, City of (INC) | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMHI_20-066-007-C041_Victoria | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Victoria, City of (INC) | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Victoria had no new projects completed for its Housing Incentive program
LBAP_HMID_LMHI_20-066-007-C041_Victoria | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Victoria, City of (INC) | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Victoria completed one project for its Buyout Incentive project.
LBAP_HMID_LMHI_20-066-007-C041_Victoria | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Victoria, City of (INC) | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_LMHI_20-066-007-C041_Victoria | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Victoria, City of (INC) | 2024-04-01 | 2024 Q3 | Contract amendment to extend end dates, revise budgets amongst activities and reduced all projected accomplishments.
LBAP_HMID_LMHI_20-066-009-C052_WhartonCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Wharton, County of | 2019-10-01 | 2020 Q1
LBAP_HMID_LMHI_20-066-010-C063_FayetteCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2019-10-01 | 2020 Q1
LBAP_HMID_LMHI_20-066-010-C063_FayetteCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Fayette County accepted and approved applications for eligibility review for its Local Buyout project.
LBAP_HMID_LMHI_20-066-010-C063_FayetteCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMHI_20-066-010-C063_FayetteCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_HMID_LMHI_20-066-010-C063_FayetteCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Fayette County had Buyout activities underway for its Acquisition and Buyout program.
LBAP_HMID_LMHI_20-066-010-C063_FayetteCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_LMHI_20-066-010-C063_FayetteCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2024-04-01 | 2024 Q3 | During the reporting period, the County worked to finish demolition of the final properties for its Buyout program.
LBAP_HMID_LMHI_20-066-013-C095_LibertyCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Liberty County | 2020-01-01 | 2020 Q2
LBAP_HMID_LMHI_20-066-013-C095_LibertyCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Liberty County | 2021-10-01 | 2022 Q1 | During the reporting period, Liberty County accepted applications for eligibility review for its Local Buyout project.
LBAP_HMID_LMHI_20-066-013-C095_LibertyCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Liberty County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMHI_20-066-013-C095_LibertyCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Liberty County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_HMID_LMHI_20-066-013-C095_LibertyCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Liberty County | 2023-07-01 | 2023 Q4 | During the reporting period, Liberty County had no new projects completed and 10 underway for its Buyout Housing Incentive program.
LBAP_HMID_LMHI_20-066-013-C095_LibertyCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Liberty County | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_LMHI_20-066-017-C123_CorpusChristi | Buyout Program | Housing incentives to encourage resettlement | Corpus Christi, City Of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMHI_20-066-017-C123_CorpusChristi | Buyout Program | Housing incentives to encourage resettlement | Corpus Christi, City Of | 2023-04-01 | 2023 Q3 | Activity created during previous quarter.
LBAP_HMID_LMHI_20-066-018-C125_PolkCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Polk County | 2023-04-01 | 2023 Q3 | Activity created during quarter.
LBAP_HMID_LMHI_20-066-018-C125_PolkCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Polk County | 2024-01-01 | 2024 Q2 | During the reporting period, a contract amendment was executed that extended the End Date, reduction to projected households, and UN RA activity created.
LBAP_HMID_LMHI_20-066-018-C125_PolkCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Polk County | 2025-07-01 | 2025 Q4 | During the reporting period, Polk County completed HI on 5 properties.
LBAP_HMID_LMHI_20-066-020-C135_SanJacintoCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | San Jacinto County | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_LMHI_20-066-023-C168_Vidor_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Vidor | 2020-01-01 | 2020 Q2
LBAP_HMID_LMHI_20-066-023-C168_Vidor_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Vidor | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_LMHI_20-066-023-C168_Vidor_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Vidor | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Vidor provided housing incentives to a residential dwelling.
LBAP_HMID_LMHI_20-066-023-C168_Vidor_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Vidor | 2025-10-01 | 2026 Q1 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
LBAP_HMID_LMHI_20-066-029-C223_WestOrange | Acquisition Program - Housing Incentives | Housing incentives to encourage resettlement | CITY OF WEST ORANGE | 2020-01-01 | 2020 Q2
LBAP_HMID_LMHI_20-066-029-C223_WestOrange | Acquisition Program - Housing Incentives | Housing incentives to encourage resettlement | CITY OF WEST ORANGE | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMHI_20-066-031-C225_Jasper | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Jasper | 2020-01-01 | 2020 Q2
LBAP_HMID_LMHI_20-066-031-C225_Jasper | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Jasper | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Jasper had applications under review for its buyout project.
LBAP_HMID_LMHI_20-066-031-C225_Jasper | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Jasper | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMHI_20-066-031-C225_Jasper | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Jasper | 2023-07-01 | 2023 Q4 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMHI_20-066-031-C225_Jasper | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Jasper | 2025-10-01 | 2026 Q1 | During the reporting period the city of Jasper was completing demolition of the final properties for its buyout program.
LBAP_HMID_LMHI_20-066-036-C242_JeffersonCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Jefferson County | 2020-01-01 | 2020 Q2
LBAP_HMID_LMHI_20-066-036-C242_JeffersonCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Jefferson County | 2025-07-01 | 2025 Q4 | During the reporting period, the subrecipient requested a budget adjustment to reallocate funding, primarily from the Low/Mod Buyout activity, to the various housing incentive activities.
LBAP_HMID_LMHI_20-066-043-C300_JasperCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Jasper County | 2020-04-01 | 2020 Q3
LBAP_HMID_LMHI_20-066-043-C300_JasperCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Jasper County | 2023-07-01 | 2023 Q4 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_LMHI_20-066-043-C300_JasperCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Jasper County | 2024-07-01 | 2024 Q4 | Budget reduced due to scope reduction.
LBAP_HMID_LMHI_20-066-044-C314_Beaumont | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2020-04-01 | 2020 Q3
LBAP_HMID_LMHI_20-066-044-C314_Beaumont | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Beaumont accepted applications for eligibility review for its buyout project.
LBAP_HMID_LMHI_20-066-044-C314_Beaumont | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_LMHI_20-066-044-C314_Beaumont | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_LMHI_20-066-044-C314_Beaumont | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Beaumont completed 2 buyout program and 4 were underway.
LBAP_HMID_LMHI_20-066-044-C314_Beaumont | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2025-04-01 | 2025 Q3 | Amendment was executed prior to this quarter, that reallocated funding amongst activities resulting in a decrease to the budget and obligation of this activity which was completed in this quarter
LBAP_HMID_LMHI_20-066-044-C314_Beaumont | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Beaumont completed 7 projects.
LBAP_HMID_LMHI_20-066-046-C455_GalvestonCounty_HI | Housing Incentives | Housing incentives to encourage resettlement | Galveston County | 2024-01-01 | 2024 Q2 | During the reporting period, a contract amendment was executed that reduced budgets for existing UN activities to create 3 new LMI activities and an additional UN activity, and reduced projected measures.
LBAP_HMID_LMHI_20-066-048-C526_OrangeCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Orange County | 2020-07-01 | 2020 Q4
LBAP_HMID_LMHI_20-066-048-C526_OrangeCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Orange County | 2021-10-01 | 2022 Q1 | During the reporting period, Orange County accepted applications for eligibility review for its buyout project.
LBAP_HMID_LMHI_20-066-048-C526_OrangeCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Orange County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMHI_20-066-048-C526_OrangeCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Orange County | 2022-10-01 | 2023 Q1 | During the reporting period, amendement 1 for this contract was executed. As a result of the amendment, funds were deobligated from the total contracted amount, new activites for housing incentive activity types were added, and projected performance measures and beneficaries were reduced.
LBAP_HMID_LMHI_20-066-048-C526_OrangeCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Orange County | 2023-10-01 | 2024 Q1 | During the quarter, an amendment to this contract was executed, reducing the budget, obligation and projected measures.
LBAP_HMID_LMHI_20-066-048-C526_OrangeCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Orange County | 2025-04-01 | 2025 Q3 | During the reporting period, Orange County had grant closeout documents under review for its Buyout Program.
LBAP_HMID_LMI_20-066-035-C237_PineForest | Acquisition - general | Acquisition - general | Pine Forest | 2020-01-01 | 2020 Q2
LBAP_HMID_LMI_20-066-035-C237_PineForest | Acquisition - general | Acquisition - general | Pine Forest | 2021-04-01 | 2021 Q3 | During the reporting period, the City of Pine Forest program guidelines were approved for its Acquisition project.
LBAP_HMID_LMI_20-066-035-C237_PineForest | Acquisition - general | Acquisition - general | Pine Forest | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Pine Forest completed its Broad Review.
LBAP_HMID_LMI_20-066-035-C237_PineForest | Acquisition - general | Acquisition - general | Pine Forest | 2023-07-01 | 2023 Q4 | Unused funds de-obligated pending project completion.
LBAP_HMID_LMI_20-066-035-C237_PineForest | Acquisition - general | Acquisition - general | Pine Forest | 2024-04-01 | 2024 Q3 | Due to unforeseen complications and through no fault of the subrecipient, this project has concluded early benefitting no individuals. All expenses are related to the release of funds for the subrecipient receiving approval of the Housing Guidelines for the program. The rest of the expected funds initally awarded have been reduced from the activities of this contract.
LBAP_HMID_LMI_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2020-04-01 | 2020 Q3
LBAP_HMID_LMI_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the City Rose Hill Acres of had outreach underway for its for its Acquisition project.
LBAP_HMID_LMI_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_HMID_LMI_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2021-07-01 | 2021 Q4 | During the reporting period, City of Rose Hill Acres accepted applications for eligibility review for its acquisition project.
LBAP_HMID_LMI_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Rose Hill Acres accepted applications for eligibility review for its acquisition project.
LBAP_HMID_LMI_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_LMI_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Rose Hill Acres had applications reviewed and approved for its buyout project.
LBAP_HMID_LMI_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Rose Hill Acres had five applications approved and four voluntary offers accepted for its buyout project.
LBAP_HMID_LMI_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and increased funds.
LBAP_HMID_LMI_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Rose Hill Acres had 2 projects completed and 1 underway for its Buyout program.
LBAP_HMID_LMI_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2024-01-01 | 2024 Q2 | During the reporting period, Rose Hill Acres had 2 project completed for its Buyout program. Close-out is underway.
LBAP_HMID_LMI_20-066-040-C259_Dickinson | Acquisition - general | Acquisition - general | Dickinson | 2020-04-01 | 2020 Q3
LBAP_HMID_LMI_20-066-040-C259_Dickinson | Acquisition - general | Acquisition - general | Dickinson | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_HMID_LMI_20-066-040-C259_Dickinson | Acquisition - general | Acquisition - general | Dickinson | 2025-10-01 | 2026 Q1 | During the reporting period, Activity budget and obligation reduced according to closeout documentation.
LBAP_HMID_LMI_20-066-046-C455_GalvestonCounty_ACQ | Acquisition - Buyout | Acquisition - buyout of residential properties | Galveston County | 2024-01-01 | 2024 Q2 | During the reporting period, a contract amendment was executed that reduced budgets for existing UN activities to create 3 new LMI activities and an additional UN activity, and reduced projected measures.
LBAP_HMID_LMI_20-066-046-C455_GalvestonCounty_ACQ | Acquisition - Buyout | Acquisition - buyout of residential properties | Galveston County | 2024-07-01 | 2024 Q4 | There were no further draws submitted for the county&apos;s acquisition program, and the program is ongoing.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID LMI Acquisition - General | Acquisition - general | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID LMI Acquisition - General | Acquisition - general | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 2288.83 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID LMI Acquisition - General | Acquisition - general | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 614.14 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID LMI Acquisition - General | Acquisition - general | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 591 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID LMI Acquisition - General | Acquisition - general | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 296.87 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID LMI Acquisition - General | Acquisition - general | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 160.58 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID LMI Acquisition - General | Acquisition - general | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 332.52 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 58571.21 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 18240.32 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 17087.77 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 8802.27 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 4861.13 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 10164.93 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2026-01-01 | 2026 Q2
LBAP_HMID_LMI_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID LMI Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_HMID_LMI_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID LMI Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 7254.74 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID LMI Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 368.15 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID LMI Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 354.09 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID LMI Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 240.76 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID LMI Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 160.58 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID LMI Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 332.52 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID LMI Homeownership Assistance | Homeownership Assistance to low- and moderate-income | Texas General Land Office | 2026-01-01 | 2026 Q2
LBAP_HMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_HMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 8551.88 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 2388.92 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 2603.44 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 1334.59 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 735.66 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 1661.29 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_HMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 7900.15 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 3290.61 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 3937.59 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 2377.95 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 1375.25 - State costs in support of activity delivery.
LBAP_HMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 3422.59 - State costs in support of activity delivery.
LBAP_HMID_UN_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2023-01-01 | 2023 Q2 | Amendment de-obligated funds. Responsible Organization corrected.
LBAP_HMID_UN_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2023-04-01 | 2023 Q3 | During the reporting period, Montgomery County had 1 Buyout activities underway for its Buyout project.
LBAP_HMID_UN_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2023-10-01 | 2024 Q1 | During the reporting period, Montgomery County accepted applications for eligibility review for its Buyout project. Negative expenditures were caused from misallocating costs to the Urgent Need activity rather than the Low to Moderate Buyout activity within this contract.
LBAP_HMID_UN_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2025-04-01 | 2025 Q3 | Amendment was executed during the quarter, that reallocated funding amongst activities resulting in a decrease to the budget and obligation of this activity.
LBAP_HMID_UN_20-066-001-B956_MontgomeryCounty | Buyout Program | Acquisition - buyout of residential properties | Montgomery County | 2025-10-01 | 2026 Q1 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
LBAP_HMID_UN_20-066-001-B956_MontgomeryCounty_HI | Housing Incentives | Housing incentives to encourage resettlement | Montgomery County | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_UN_20-066-001-B956_MontgomeryCounty_HI | Housing Incentives | Housing incentives to encourage resettlement | Montgomery County | 2023-04-01 | 2023 Q3 | Amendment moved funds to related activity.
LBAP_HMID_UN_20-066-001-B956_MontgomeryCounty_HI | Housing Incentives | Housing incentives to encourage resettlement | Montgomery County | 2025-04-01 | 2025 Q3 | Amendment was executed during the quarter, that reallocated funding amongst activities resulting in a decrease to the budget and obligation of this activity.
LBAP_HMID_UN_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2020-10-01 | 2021 Q1 | During the reporting period, Victoria County accepted applications for eligibility review for its Buyout Program.
LBAP_HMID_UN_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2021-10-01 | 2022 Q1 | During the reporting period, Victoria County accepted applications for eligibility review for its Local Buyout project.
LBAP_HMID_UN_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_HMID_UN_20-066-004-C033_VictoriaCounty | Buyout Program | Acquisition - buyout of residential properties | Victoria County | 2025-01-01 | 2025 Q2 | Activity budget and obligation reduced according to closeout documentation, this activity did not serve any beneficiaries despite active marketing and good faith efforts by the subrecipient.
LBAP_HMID_UN_20-066-005-C034_Wharton | Buyout Program | Acquisition - buyout of residential properties | Wharton | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-005-C034_Wharton | Buyout Program | Acquisition - buyout of residential properties | Wharton | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_HMID_UN_20-066-005-C034_Wharton | Buyout Program | Acquisition - buyout of residential properties | Wharton | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Wharton continued negotiations with land owner for intended buyout site, however, no expenditures for professional services were reimbursed during Q4 2022
LBAP_HMID_UN_20-066-005-C034_Wharton | Buyout Program | Acquisition - buyout of residential properties | Wharton | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_HMID_UN_20-066-006-C038_FortBendCounty | Buyout Program | Acquisition - buyout of residential properties | Fort Bend County | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-006-C038_FortBendCounty | Buyout Program | Acquisition - buyout of residential properties | Fort Bend County | 2022-10-01 | 2023 Q1 | During the reporting period, amendement 2 for this contract was executed. As a result of the amendment, funds were deobligated from the total contracted amount due to reduced applicants for the project than originally anticipated. Several activities had budget reductions, reductions in projection performance measures and four activities were cancelled and deleted.
LBAP_HMID_UN_20-066-006-C038_FortBendCounty | Buyout Program | Acquisition - buyout of residential properties | Fort Bend County | 2025-07-01 | 2025 Q4 | During the reporting period, Fort Bend County, had 1 underway for its buyout project.
LBAP_HMID_UN_20-066-006-C038_FortBendCounty_DPA | Buyout Program - Down-Payment Assistance | Homeownership Assistance (with waiver only) | Fort Bend County | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-006-C038_FortBendCounty_DPA | Buyout Program - Down-Payment Assistance | Homeownership Assistance (with waiver only) | Fort Bend County | 2022-10-01 | 2023 Q1 | During the reporting period, amendement 2 for this contract was executed. As a result of the amendment, funds were deobligated from the total contracted amount due to reduced applicants for the project than originally anticipated. Several activities had budget reductions, reductions in projection performance measures and four activities were cancelled and deleted.
LBAP_HMID_UN_20-066-006-C038_FortBendCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fort Bend County | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-006-C038_FortBendCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fort Bend County | 2022-10-01 | 2023 Q1 | During the reporting period, amendement 2 for this contract was executed. As a result of the amendment, funds were deobligated from the total contracted amount due to reduced applicants for the project than originally anticipated. Several activities had budget reductions, reductions in projection performance measures and four activities were cancelled and deleted.
LBAP_HMID_UN_20-066-006-C038_FortBendCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Fort Bend County | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-006-C038_FortBendCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Fort Bend County | 2022-10-01 | 2023 Q1 | During the reporting period, amendement 2 for this contract was executed. As a result of the amendment, funds were deobligated from the total contracted amount due to reduced applicants for the project than originally anticipated. Several activities had budget reductions, reductions in projection performance measures and four activities were cancelled and deleted.
LBAP_HMID_UN_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Victoria accepted applications for eligibility review for its Buyout Program.
LBAP_HMID_UN_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Victoria accepted applications for eligibility review for its Local Buyout project.
LBAP_HMID_UN_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Victoria had 1 projects completed and 1 underway for its buyout program.
LBAP_HMID_UN_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Victoria had no new completed projects and 3 underway for its Buyout program.
LBAP_HMID_UN_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Victoria had one completed project for Buyouts program.
LBAP_HMID_UN_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Victoria had 2 projects underway for its Urgent Need Buyout program
LBAP_HMID_UN_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_UN_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2024-04-01 | 2024 Q3 | During this reporting period, the City of Victoria had no buyout activity. There was an expenditure of $78,083.49 for buyout, demolition and soft costs. Closeout is underway.
LBAP_HMID_UN_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Victoria had Project Delivery and Soft Cost UN expenditures.
LBAP_HMID_UN_20-066-007-C041_Victoria | Buyout Program | Acquisition - buyout of residential properties | Victoria, City of (INC) | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Victoria had Project Delivery and Soft Cost UN expenditures.
LBAP_HMID_UN_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Victoria accepted applications for eligibility review for its Local Buyout project.
LBAP_HMID_UN_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_UN_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Victoria completed one project for its Buyout Relocation Assistance program.
LBAP_HMID_UN_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Victoria had one project completed and two underway for it Relocation Assistance activity.
LBAP_HMID_UN_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_UN_20-066-007-C041_Victoria_RA | Relocation Assistance | Relocation payments and assistance | Victoria, City of (INC) | 2024-04-01 | 2024 Q3 | During this reporting period, the City of Victoria had no Relocation Assistance activity. There was an expenditure of $2,340 for moving expenses. Closeout is underway.
LBAP_HMID_UN_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_HMID_UN_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Texas City accepted applications for eligibility review for its Local Buyout project.
LBAP_HMID_UN_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2023-01-01 | 2023 Q2 | Amendment reduced scope and increased funds.
LBAP_HMID_UN_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2023-04-01 | 2023 Q3 | During the reporting period, the City of Texas City had grant closeout documents under review for its buyout program.
LBAP_HMID_UN_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Texas City had grant closeout documents under review for its buyout program.
LBAP_HMID_UN_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_UN_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2025-01-01 | 2025 Q2 | Activity budget and obligation reduced according to closeout documentation, this activity did not serve any beneficiaries despite active marketing and good faith efforts by the subrecipient.
LBAP_HMID_UN_20-066-008-C043_TexasCity | Buyout Program | Acquisition - buyout of residential properties | Texas City | 2025-04-01 | 2025 Q3 | This contract was closed on 12/18/2024. Activity budget and obligation reduced according to closeout documentation, this activity did not serve any beneficiaries despite active marketing and good faith efforts by the subrecipient.
LBAP_HMID_UN_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_HMID_UN_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2022-10-01 | 2023 Q1 | During the reporting period, appraisals were underway for approved applicants, however, no expenditures for professional services were reimbursed during Q4 2022
LBAP_HMID_UN_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and increased funds.
LBAP_HMID_UN_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2023-07-01 | 2023 Q4 | During the reporting period, the County of Wharton has 6 projects underway for its Buyout program.
LBAP_HMID_UN_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2023-10-01 | 2024 Q1 | During the reporting period, Wharton County had appraisals ordered and offers underway for approved applicants.
LBAP_HMID_UN_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2024-04-01 | 2024 Q3 | During the reporting period, the Wharton County had acquisition underway for its Buyout project.
LBAP_HMID_UN_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2024-10-01 | 2025 Q1 | During the reporting period, Wharton County submitted grant closeout documents for its Buyout project.
LBAP_HMID_UN_20-066-009-C052_WhartonCounty | Buyout Program | Acquisition - buyout of residential properties | Wharton, County of | 2025-01-01 | 2025 Q2 | During the reporting period, Wharton County submitted grant closeout documents for its Buyout project.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Fayette County accepted applications for eligibility review for its Buyout project.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Fayette County accepted and approved applications for eligibility review for its Local Buyout project.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2022-07-01 | 2022 Q4 | During the reporting period, Fayette County has 7 approved applications underway for its Buyout program.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2022-10-01 | 2023 Q1 | During the reporting period, Fayette County completed 2 projects with 5 underway for its Buyout program
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2023-01-01 | 2023 Q2 | During the reporting period, the Fayette County program guidelines were approved for its buyout program project.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Fayette County had buyout activities underway for its Buyout project.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Fayette County had Buyout activities underway for its Acquisition and Buyout program.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2023-10-01 | 2024 Q1 | During the reporting period Fayette County had Buyout Activities underway for it&apos;s Acquisition and Buyout Program.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2024-04-01 | 2024 Q3 | During the reporting period, the County worked to finish demolition of the final properties for its Buyout program.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2024-07-01 | 2024 Q4 | During the reporting period, the final payment was processed and paid. Closeout underway for its Buyout program.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2025-04-01 | 2025 Q3 | During the reporting period, the GLO received a refund for overpayment of taxes for its Buyout program.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty | Buyout Program | Acquisition - buyout of residential properties | Fayette, County of | 2025-07-01 | 2025 Q4 | During the reporting period, the GLO received a refund for overpayment of taxes for its Buyout program.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty_HI-11022023163938 | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-010-C063_FayetteCounty_HI-11022023163938 | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Fayette County accepted and approved applications for eligibility review for its Local Buyout project.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty_HI-11022023163938 | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty_HI-11022023163938 | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty_HI-11022023163938 | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2023-07-01 | 2023 Q4
LBAP_HMID_UN_20-066-010-C063_FayetteCounty_HI-11022023163938 | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Fayette, County of | 2023-10-01 | 2024 Q1 | Activity was previously deleted but had to be reopened in order to remove previous expenditures. This activity will be permanently deleted after the not synced expenditure values are corrected through a data push.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Fayette, County of | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Fayette, County of | 2023-07-01 | 2023 Q4 | During the reporting period, Fayette County had Buyout activities underway for its Acquisition and Buyout program.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Fayette, County of | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_UN_20-066-010-C063_FayetteCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Fayette, County of | 2024-04-01 | 2024 Q3 | During the reporting period, the County worked to finish demolition of the final properties for its Buyout program.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2020-07-01 | 2020 Q4 | During the reporting period, Liberty County had outreach underway for its buyout program.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2020-10-01 | 2021 Q1
LBAP_HMID_UN_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2021-10-01 | 2022 Q1 | During the reporting period, Liberty County accepted applications for eligibility review for its Local Buyout project.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and increased funds.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2023-04-01 | 2023 Q3 | During the reporting period, Liberty County had acquisition activities underway.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2023-07-01 | 2023 Q4 | During the reporting period, Liberty County, had no new projects underway and 15 projects underway for its Buyout program.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2023-10-01 | 2024 Q1 | During the period Liberty County had buyout activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2024-01-01 | 2024 Q2 | During the reporting period, Liberty County had buyout activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty | Buyout Program | Acquisition - buyout of residential properties | Liberty County | 2025-07-01 | 2025 Q4 | During the reporting period, Liberty County completed 3 buyout awards and 4 demos for its Local Buyout Acquisition Program.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Liberty County | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-013-C095_LibertyCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Liberty County | 2021-10-01 | 2022 Q1 | During the reporting period, Liberty County accepted applications for eligibility review for its Local Buyout project.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Liberty County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Liberty County | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Liberty County | 2023-07-01 | 2023 Q4 | During the reporting period, Liberty County had no new projects completed and 15 underway for its Buyout Relocation assistance program.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Liberty County | 2024-01-01 | 2024 Q2 | During the reporting period, adjustments to the split for environmental costs for activities in this contract were made, resulting in changes to the budgets and obligations.
LBAP_HMID_UN_20-066-013-C095_LibertyCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Liberty County | 2025-07-01 | 2025 Q4 | During the reporting period, Liberty County completed 4 relocation assistance projects for its Local Buyout Acquisition Program.
LBAP_HMID_UN_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2019-10-01 | 2020 Q1
LBAP_HMID_UN_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2020-10-01 | 2021 Q1 | During the reporting period, Newton County continues to carry out administrative services for its Buyout project.
LBAP_HMID_UN_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2024-04-01 | 2024 Q3 | During the reporting period, Newton County has obtained 3 appraisals for the buyout process. And is currently working obtaining appraisals for the remainder 20 applicants. Time extension to 1/31/25 was approved during this quarter.
LBAP_HMID_UN_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2024-07-01 | 2024 Q4 | During the reporting period, Newton County completed 1 UN demo.
LBAP_HMID_UN_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2024-10-01 | 2025 Q1 | During the reporting period, Newton County completed 3 UN buyouts and 5 UN demos.
LBAP_HMID_UN_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2025-01-01 | 2025 Q2 | During the reporting period, Newton County demolished 2 UN homes and had 1 UN buyout.
LBAP_HMID_UN_20-066-015-C108_NewtonCounty | Buyout Program | Acquisition - buyout of residential properties | Newton County | 2025-04-01 | 2025 Q3 | During the reporting period, Newton County demolished 1UN BP home and submitted a UN PD payment request for 100% funds drawn to date. An amendment was submitted to extend contract to 7/31/25, reduce the number of homes to be bought out and de-obligate $4.4 million.
LBAP_HMID_UN_20-066-017-C123_CorpusChristi | Pending Cancellation | Acquisition - buyout of residential properties | Corpus Christi, City Of | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-017-C123_CorpusChristi | Pending Cancellation | Acquisition - buyout of residential properties | Corpus Christi, City Of | 2021-07-01 | 2021 Q4 | During the reporting period, the City of Corpus Christi accepted applications for eligibility review for its buyout program.
LBAP_HMID_UN_20-066-017-C123_CorpusChristi | Pending Cancellation | Acquisition - buyout of residential properties | Corpus Christi, City Of | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2020-10-01 | 2021 Q1 | During the reporting period, Polk County accepted applications for eligibility review for its Buyout Project.
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2021-10-01 | 2022 Q1 | During the reporting period, Polk County had applications under review for its Buyout Program.
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2022-10-01 | 2023 Q1 | During the reporting period, Polk County had four (4) applications underway for its Buyout project.
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2023-04-01 | 2023 Q3 | Amendment moved funds to related activity.
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2023-10-01 | 2024 Q1 | During the reporting period, Polk County had activity underway for two projects in the buyout program.
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2024-04-01 | 2024 Q3 | During the reporting period, Polk County had buyout activities underway for its Local Buyout and Acquisition Program.
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2024-07-01 | 2024 Q4 | During the reporting period, Polk County initiated the purchase of 3 homes under it&apos;s Local Acquisition and Buyout Program.
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2024-10-01 | 2025 Q1 | During the reporting period, a review was performed and this activity was correctly recategorized as an HMID activity. MID Expenditures were entered to equal the current expenditures.
LBAP_HMID_UN_20-066-018-C125_PolkCounty | Buyout Program | Acquisition - buyout of residential properties | Polk County | 2025-07-01 | 2025 Q4 | DUring the reporting period, Polk County completed 1 purchase under UN.
LBAP_HMID_UN_20-066-018-C125_PolkCounty_RA | Relocation Assistance | Relocation payments and assistance | Polk County | 2024-01-01 | 2024 Q2 | During the reporting period, a contract amendment was executed that extended the End Date, reduction to projected households, and UN RA activity created.
LBAP_HMID_UN_20-066-018-C125_PolkCounty_RA | Relocation Assistance | Relocation payments and assistance | Polk County | 2025-07-01 | 2025 Q4 | DUring the reporting period, Polk County completed 1 RA under UN.
LBAP_HMID_UN_20-066-019-C134_Nome | Buyout Program | Acquisition - buyout of residential properties | Nome | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2020-10-01 | 2021 Q1 | During the reporting period, San Jacinto County accepted applications for eligibility review for its Buyout Project.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2021-10-01 | 2022 Q1 | During the reporting period, San Jacinto County had 37 applications under review for its Buyout Program.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2022-10-01 | 2023 Q1 | During the reporting period, eligibility determination was underway. No expenditures were reimbursed.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and de-obligated funds.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2023-04-01 | 2023 Q3 | During the reporting period, San Jacinto County had buyout activities underway for its Buyout project.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2023-07-01 | 2023 Q4 | During the reporting period, San Jacinto County had Buyout activities underway for its Acquisition and Buyout program.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2023-10-01 | 2024 Q1 | During the reporting period, San Jacinto County had Buyout activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2024-01-01 | 2024 Q2 | During the reporting period, San Jacinto County had Buyout activities underway for its Local Buyout and Acquisition Program.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2024-04-01 | 2024 Q3 | During the reporting period, San Jacinto County had buyout activities underway for it Local Buyout and Acquisition Program.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2024-07-01 | 2024 Q4 | During the reporting period, San Jacinto County completed the purchase of 3 homes, initiated the purchase of 2 additional homes, and completed demo on 2 hones for its Local Acquisition and Buyout Program.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2025-01-01 | 2025 Q2 | During the reporting period, San Jacinto County completed a contract amendment which will allow them to complete purchase activities for the final properties and begin closeout activities.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2025-04-01 | 2025 Q3 | During the reporting period, San Jacinto County completed buyouts on 2 properties and demo on 8 properties.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2025-07-01 | 2025 Q4 | During the reporting period, San Jacinto County completed 1 purchase under UN.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty | Buyout Program | Acquisition - buyout of residential properties | San Jacinto County | 2025-10-01 | 2026 Q1 | During the reporting period San Jacinto County was completing GCR for its buyout program.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | San Jacinto County | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | San Jacinto County | 2023-10-01 | 2024 Q1 | During the reporting period, San Jacinto County had Relocation activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_UN_20-066-020-C135_SanJacintoCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | San Jacinto County | 2025-01-01 | 2025 Q2 | During the reporting period, San Jacinto County completed a contract amendment which will allow them to complete relocation activities for the final properties and begin closeout activities.
LBAP_HMID_UN_20-066-021-C137_SourLake | Buyout Program | Acquisition - buyout of residential properties | Sour Lake | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-021-C137_SourLake | Buyout Program | Acquisition - buyout of residential properties | Sour Lake | 2022-07-01 | 2022 Q4 | The City of Sour Lake did not have any buyout applicants. Contract expired April 2022.
LBAP_HMID_UN_20-066-021-C137_SourLake | Buyout Program | Acquisition - buyout of residential properties | Sour Lake | 2024-10-01 | 2025 Q1 | During the reporting period, this contract was administratively closed in DRGR. All funds have been drawn, and accomplishment and beneficiaries were entered.
LBAP_HMID_UN_20-066-021-C137_SourLake | Buyout Program | Acquisition - buyout of residential properties | Sour Lake | 2025-01-01 | 2025 Q2 | Activity budget and obligation reduced according to closeout documentation, this activity did not serve any beneficiaries despite active marketing and good faith efforts by the subrecipient.
LBAP_HMID_UN_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2021-01-01 | 2021 Q2 | During the reporting period, the City of Vidor program guidelines were approved for its Buyout project.
LBAP_HMID_UN_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_UN_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Vidor submitted a advanced payment request for 1 UN buyout.
LBAP_HMID_UN_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Vidor continues to carry out administrative services for its buyout program.
LBAP_HMID_UN_20-066-023-C168_Vidor | Buyout Program | Acquisition - buyout of residential properties | Vidor | 2025-10-01 | 2026 Q1 | During the reporting period the city of Vidor was completing purchase and demolition of the final 2 properties for its buyout program.
LBAP_HMID_UN_20-066-023-C168_Vidor_DPA | Buyout Program - Down- Payment Assistance | Homeownership Assistance (with waiver only) | Vidor | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-023-C168_Vidor_DPA | Buyout Program - Down- Payment Assistance | Homeownership Assistance (with waiver only) | Vidor | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_UN_20-066-023-C168_Vidor_DPA | Buyout Program - Down- Payment Assistance | Homeownership Assistance (with waiver only) | Vidor | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Vidor completed 4 additional projects, 2 project(s) were canceled and 7 projects were underway
LBAP_HMID_UN_20-066-023-C168_Vidor_DPA | Buyout Program - Down- Payment Assistance | Homeownership Assistance (with waiver only) | Vidor | 2025-10-01 | 2026 Q1 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
LBAP_HMID_UN_20-066-023-C168_Vidor_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Vidor | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-023-C168_Vidor_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Vidor | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_UN_20-066-023-C168_Vidor_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Vidor | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Vidor completed 4 additional projects, 2 project(s) were canceled and 7 projects were underway
LBAP_HMID_UN_20-066-023-C168_Vidor_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Vidor | 2025-10-01 | 2026 Q1 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
LBAP_HMID_UN_20-066-023-C168_Vidor_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Vidor | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-023-C168_Vidor_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Vidor | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_UN_20-066-023-C168_Vidor_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Vidor | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Vidor completed 4 additional projects, 2 project(s) were canceled and 7 projects were underway
LBAP_HMID_UN_20-066-023-C168_Vidor_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Vidor | 2025-10-01 | 2026 Q1 | During the reporting period, a contract amendment was executed in which changes to the activity budgets within the contract were reallocated.
LBAP_HMID_UN_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Silsbee has two approved applications for its Buyout Program.
LBAP_HMID_UN_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Silsbee had two approved applications. One payment request is currently routing for buyout of one property.
LBAP_HMID_UN_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity.
LBAP_HMID_UN_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Silsbee completed 1 project and demolition is underway
LBAP_HMID_UN_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Silsbee had no buyout activity and the program is ongoing.
LBAP_HMID_UN_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Silsbee had no new projects completed and no projects underway.
LBAP_HMID_UN_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Silsbee had grant closeout documents under review for its buyout program project.
LBAP_HMID_UN_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
LBAP_HMID_UN_20-066-024-C178_Silsbee | Buyout Program | Acquisition - buyout of residential properties | Silsbee | 2025-10-01 | 2026 Q1 | During the reporting period, Activity budget and obligation reduced according to closeout documentation.
LBAP_HMID_UN_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Ingleside accepted applications for eligibility review for its Acquisition project.
LBAP_HMID_UN_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Ingleside had 1 acquisition appraisal cost draw for its Acquisition project.
LBAP_HMID_UN_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_UN_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2023-04-01 | 2023 Q3 | During the reporting period, City of Ingleside had buyout activities underway for its Buyout/Acquisition program.
LBAP_HMID_UN_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2023-07-01 | 2023 Q4 | Amendment reallocated funds from related activities that were cancelled.
LBAP_HMID_UN_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Ingleside completed 1 UN buyout and soft costs for buyout of home.
LBAP_HMID_UN_20-066-030-C224_Ingleside | Acquisition - general | Acquisition - general | Ingleside | 2025-01-01 | 2025 Q2 | During the reporting period, the City decided to cancel the program and the money expended by the City is a refund from the community to the GLO.
LBAP_HMID_UN_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2020-10-01 | 2021 Q1 | During the reporting period, the City of Jasper had outreach underway for its Buyout project.
LBAP_HMID_UN_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Jasper had applications under review for its buyout project.
LBAP_HMID_UN_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Jasper had revised program guidelines approved for its buyout program project.
LBAP_HMID_UN_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2024-01-01 | 2024 Q2 | Budgets were corrected based on an amendment from the previous quarter.
LBAP_HMID_UN_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2024-07-01 | 2024 Q4 | Time Extension approved for new contract end date: 12/31/2024. Subrecipient will provide a Buyout program for approximately three (3) residential dwellings affected by Hurricane Harvey, changing from three(3) to six(6) residential dwellings as indicated on Attachment A. The City believes that it may expend $1,000,000.00 of the total grant amount and requests no deobligation of funds at this time. This will be Amendment 6.
LBAP_HMID_UN_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2025-04-01 | 2025 Q3 | During the reporting period, the City of Jasper completed 3 buyout and 1 were underway.
LBAP_HMID_UN_20-066-031-C225_Jasper | Buyout Program | Acquisition - buyout of residential properties | Jasper | 2025-07-01 | 2025 Q4 | During the reporting period, City of Jasper demolition complete on 1 property
LBAP_HMID_UN_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2021-10-01 | 2022 Q1 | During the reporting period, Jefferson County accepted applications for eligibility review for its Buyout project.
LBAP_HMID_UN_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2022-10-01 | 2023 Q1 | During the reporting period, Jefferson County accepted applications for eligibility review for its 20 project.
LBAP_HMID_UN_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_UN_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_UN_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2025-07-01 | 2025 Q4 | During the reporting period, Jefferson County completed 7 projects.
LBAP_HMID_UN_20-066-036-C242_JeffersonCounty | Buyout Program | Acquisition - buyout of residential properties | Jefferson County | 2025-10-01 | 2026 Q1 | During the reporting period, Jefferson County submitted grant closeout documents for its buyout program.
LBAP_HMID_UN_20-066-036-C242_JeffersonCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Jefferson County | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-036-C242_JeffersonCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Jefferson County | 2025-07-01 | 2025 Q4 | During the reporting period, the subrecipient requested a budget adjustment to reallocate funding, primarily from the Low/Mod Buyout activity, to the various housing incentive activities.
LBAP_HMID_UN_20-066-036-C242_JeffersonCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jefferson County | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-036-C242_JeffersonCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Jefferson County | 2025-07-01 | 2025 Q4 | During the reporting period, Jefferson County completed 5 projects
LBAP_HMID_UN_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2020-04-01 | 2020 Q3
LBAP_HMID_UN_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2020-10-01 | 2021 Q1 | During the reporting period, the City Rose Hill Acres of had outreach underway for its for its Acquisition project.
LBAP_HMID_UN_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_HMID_UN_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2021-07-01 | 2021 Q4 | During the reporting period, City of Rose Hill Acres accepted applications for eligibility review for its acquisition project.
LBAP_HMID_UN_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Rose Hill Acres accepted applications for eligibility review for its Acquisition project.
LBAP_HMID_UN_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Rose Hill Acres had applications reviewed and approved for its buyout project.
LBAP_HMID_UN_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Rose Hill Acres had five applications approved and four voluntary offers accepted for its buyout project.
LBAP_HMID_UN_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2023-07-01 | 2023 Q4 | During the reporting period, Rose Hill Acres had 1 project completed and 2 underway for its Buyout program.
LBAP_HMID_UN_20-066-038-C251_RoseHill | Acquisition - general | Acquisition - general | Rose Hill Acres, City of | 2024-01-01 | 2024 Q2 | During the reporting period, Rose Hill Acres had 2 project completed for its Buyout program. Close-out is underway.
LBAP_HMID_UN_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Orange accepted applications for eligibility review for its acquisition project.
LBAP_HMID_UN_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity and decreased projected performance measures.
LBAP_HMID_UN_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Orange accepted applications for eligibility review for its Acquisition and Buyout program.
LBAP_HMID_UN_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Orange had Buyout activities underway for its Local Buyout and Acquisition Program.
LBAP_HMID_UN_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2024-04-01 | 2024 Q3 | During the reporting period, the City of Orange had buyout activities underway for its Local Buyout and Acquisition Program.
LBAP_HMID_UN_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2024-10-01 | 2025 Q1 | During the reporting period, the City of Orange completed demo activities for the 2 remaining homes in its Local Buyout and Acquisition Project.
LBAP_HMID_UN_20-066-039-C258_Orange | Acquisition - Buyout | Acquisition - buyout of residential properties | Orange | 2025-01-01 | 2025 Q2 | During the reporting period, the City of Orange had closeout activities underway.
LBAP_HMID_UN_20-066-039-C258_Orange_DPA | Acquisition Program - Down-Payment Assistance | Homeownership Assistance (with waiver only) | Orange | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-039-C258_Orange_DPA | Acquisition Program - Down-Payment Assistance | Homeownership Assistance (with waiver only) | Orange | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Orange accepted applications for eligibility review for its acquisition project.
LBAP_HMID_UN_20-066-039-C258_Orange_DPA | Acquisition Program - Down-Payment Assistance | Homeownership Assistance (with waiver only) | Orange | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-039-C258_Orange_DPA | Acquisition Program - Down-Payment Assistance | Homeownership Assistance (with waiver only) | Orange | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity and decreased projected performance measures.
LBAP_HMID_UN_20-066-039-C258_Orange_DPA | Acquisition Program - Down-Payment Assistance | Homeownership Assistance (with waiver only) | Orange | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Orange accepted applications for eligibility review for its Acquisition and Buyout program.
LBAP_HMID_UN_20-066-039-C258_Orange_RA | Acquisition Program - Relocation Payments | Relocation payments and assistance | Orange | 2020-01-01 | 2020 Q2
LBAP_HMID_UN_20-066-039-C258_Orange_RA | Acquisition Program - Relocation Payments | Relocation payments and assistance | Orange | 2021-10-01 | 2022 Q1 | During the reporting period, the City of Orange accepted applications for eligibility review for its acquisition project.
LBAP_HMID_UN_20-066-039-C258_Orange_RA | Acquisition Program - Relocation Payments | Relocation payments and assistance | Orange | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-039-C258_Orange_RA | Acquisition Program - Relocation Payments | Relocation payments and assistance | Orange | 2023-04-01 | 2023 Q3 | Amendment added funds from related activity and decreased projected performance measures.
LBAP_HMID_UN_20-066-039-C258_Orange_RA | Acquisition Program - Relocation Payments | Relocation payments and assistance | Orange | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Orange accepted applications for eligibility review for its Acquisition and Buyout program.
LBAP_HMID_UN_20-066-040-C259_Dickinson | Buyout Program | Acquisition - buyout of residential properties | Dickinson | 2020-04-01 | 2020 Q3
LBAP_HMID_UN_20-066-040-C259_Dickinson | Buyout Program | Acquisition - buyout of residential properties | Dickinson | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_HMID_UN_20-066-040-C259_Dickinson | Buyout Program | Acquisition - buyout of residential properties | Dickinson | 2025-10-01 | 2026 Q1 | During the reporting period, Activity budget and obligation reduced according to closeout documentation.
LBAP_HMID_UN_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_HMID_UN_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2023-04-01 | 2023 Q3 | During the reporting period, Hardin county received advanced payment to purchase two homes for its buyout program.
LBAP_HMID_UN_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2023-10-01 | 2024 Q1 | During this reporting period, Hardin County had buyout activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_UN_20-066-041-C266_HardinCounty | Buyout Program | Acquisition - buyout of residential properties | Hardin, County of | 2024-01-01 | 2024 Q2 | During the reporting period, Hardin County completed all projects for the local buyout/acquisition program
LBAP_HMID_UN_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2020-04-01 | 2020 Q3
LBAP_HMID_UN_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2021-07-01 | 2021 Q4 | During the reporting period, Jasper County program guidelines were approved for its buyout project.
LBAP_HMID_UN_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2022-10-01 | 2023 Q1 | During the reporting period, the County completed required appraisals on two applications
LBAP_HMID_UN_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_UN_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2023-07-01 | 2023 Q4 | During the reporting period, Jasper county had no new project completed and 2 underway for the buyout program.
LBAP_HMID_UN_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2024-07-01 | 2024 Q4 | Budget reduced due to scope reduction.
LBAP_HMID_UN_20-066-043-C300_JasperCounty | Buyout Program | Acquisition - buyout of residential properties | Jasper County | 2025-04-01 | 2025 Q3 | During the reporting period, Jasper County completed buyout of 2 UN properties.
LBAP_HMID_UN_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2020-04-01 | 2020 Q3
LBAP_HMID_UN_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Beaumont accepted applications for eligibility review for its buyout project.
LBAP_HMID_UN_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_UN_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2023-07-01 | 2023 Q4 | Increased obligation by $0.09 to match budget.
LBAP_HMID_UN_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_UN_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2025-04-01 | 2025 Q3 | Amendment was executed prior to this quarter, that reallocated funding amongst activities resulting in an increase to the budget and obligation of this activity which was completed in this quarter
LBAP_HMID_UN_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2025-07-01 | 2025 Q4 | During the reporting period, the City of Beaumont completed 5 projects.
LBAP_HMID_UN_20-066-044-C314_Beaumont | Buyout Program | Acquisition - buyout of residential properties | Beaumont | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Beaumont submitted grant closeout documents for its buyout program.
LBAP_HMID_UN_20-066-044-C314_Beaumont_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2020-04-01 | 2020 Q3
LBAP_HMID_UN_20-066-044-C314_Beaumont_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2022-04-01 | 2022 Q3 | During the reporting period, the City of Beaumont accepted applications for eligibility review for its buyout project.
LBAP_HMID_UN_20-066-044-C314_Beaumont_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Beaumont accepted applications for eligibility review for its buyout project.
LBAP_HMID_UN_20-066-044-C314_Beaumont_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_UN_20-066-044-C314_Beaumont_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2024-04-01 | 2024 Q3 | Contract amendment was executed to extend the end date, revise budgets amongst activities, and reduce projected measures.
LBAP_HMID_UN_20-066-044-C314_Beaumont_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Beaumont | 2025-04-01 | 2025 Q3 | Amendment was executed prior to this quarter, that reallocated funding amongst activities resulting in a decrease to the budget and obligation of this activity which was completed in this quarter
LBAP_HMID_UN_20-066-044-C314_Beaumont_RA | Relocation Assistance | Relocation payments and assistance | Beaumont | 2025-04-01 | 2025 Q3 | Activity created, budgeted and obligated during the quarter.
LBAP_HMID_UN_20-066-045-C444_Friendswood | Acquisition - general | Acquisition - general | City of Friendswood | 2020-04-01 | 2020 Q3
LBAP_HMID_UN_20-066-045-C444_Friendswood | Acquisition - general | Acquisition - general | City of Friendswood | 2022-01-01 | 2022 Q2 | During the reporting period, the City of Friendswood had applications under review and 0 underway for its acquisition project.
LBAP_HMID_UN_20-066-045-C444_Friendswood | Acquisition - general | Acquisition - general | City of Friendswood | 2022-07-01 | 2022 Q4 | During the reporting period, the City of Friendswood had 8 acquisitions underway for its Acquisition program.
LBAP_HMID_UN_20-066-045-C444_Friendswood | Acquisition - general | Acquisition - general | City of Friendswood | 2022-10-01 | 2023 Q1 | During the reporting period, the City of Friendswood completed 8 acquisitions for its acquisition program.
LBAP_HMID_UN_20-066-045-C444_Friendswood | Acquisition - general | Acquisition - general | City of Friendswood | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Friendswood completed the acquisition of 8 homes with the acquisition of 12 properties underway.
LBAP_HMID_UN_20-066-045-C444_Friendswood | Acquisition - general | Acquisition - general | City of Friendswood | 2023-07-01 | 2023 Q4 | During the reporting period, the City of Friendswood completed the acquisition of 8 homes with the acquisition of 12 properties underway.
LBAP_HMID_UN_20-066-045-C444_Friendswood | Acquisition - general | Acquisition - general | City of Friendswood | 2023-10-01 | 2024 Q1 | During the quarter, an amendment to this contract was executed, upon which a change was needed in reducing the budget and obligation amounts.
LBAP_HMID_UN_20-066-045-C444_Friendswood | Acquisition - general | Acquisition - general | City of Friendswood | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Friendswood completed the demolition of all 16 acquired homes.
LBAP_HMID_UN_20-066-045-C444_Friendswood | Acquisition - general | Acquisition - general | City of Friendswood | 2024-04-01 | 2024 Q3 | During the reporting period the City of Friendswood submitted a PR for its demolition of 8 properties on Deepwood Dr.
LBAP_HMID_UN_20-066-045-C444_Friendswood | Acquisition - general | Acquisition - general | City of Friendswood | 2025-01-01 | 2025 Q2 | Activity budget and obligation increased due to a pending revision from another activity in this contract.
LBAP_HMID_UN_20-066-045-C444_Friendswood | Acquisition - general | Acquisition - general | City of Friendswood | 2025-10-01 | 2026 Q1 | During the reporting period, the City of Friendswood had grant closeout documents under review for its acquisition project.
LBAP_HMID_UN_20-066-045-C444_Friendswood_HI | Housing Incentives | Housing incentives to encourage resettlement | City of Friendswood | 2023-07-01 | 2023 Q4 | Activity created.
LBAP_HMID_UN_20-066-045-C444_Friendswood_HI | Housing Incentives | Housing incentives to encourage resettlement | City of Friendswood | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Friendswood completed the demolition of all 16 acquired homes.
LBAP_HMID_UN_20-066-045-C444_Friendswood_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | City of Friendswood | 2020-04-01 | 2020 Q3
LBAP_HMID_UN_20-066-045-C444_Friendswood_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | City of Friendswood | 2022-10-01 | 2023 Q1 | During the reporting period, the City completed relocation assistance to 7 property owners for its relocation assistance program.
LBAP_HMID_UN_20-066-045-C444_Friendswood_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | City of Friendswood | 2023-01-01 | 2023 Q2 | During the reporting period, the City of Friendswood completed 7 relocation assistance payments and 3 relocation assistance underway.
LBAP_HMID_UN_20-066-045-C444_Friendswood_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | City of Friendswood | 2023-07-01 | 2023 Q4 | Activity budget and obligation reduced.
LBAP_HMID_UN_20-066-045-C444_Friendswood_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | City of Friendswood | 2023-10-01 | 2024 Q1 | During the reporting period, the City of Friendswood completed the demolition of all 16 acquired homes. Negative expenditure due to voucher adjustments from the contract originally only expecting to be provide relocation assistance to Urgent Need beneficiaries, and since then interest in relocation assistance for Low to Moderate income beneficiaries has occurred. Costs for two LMI households were reallocated from this activity to the LMI activity.
LBAP_HMID_UN_20-066-045-C444_Friendswood_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | City of Friendswood | 2024-01-01 | 2024 Q2 | During the reporting period, the City of Friendswood completed the demolition of all 16 acquired homes.
LBAP_HMID_UN_20-066-045-C444_Friendswood_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | City of Friendswood | 2025-10-01 | 2026 Q1 | During the reporting period, Activity budget and obligation were reduced.
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_ACQ | Acquisition - general | Acquisition - buyout of residential properties | Galveston County | 2020-07-01 | 2020 Q4
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_ACQ | Acquisition - general | Acquisition - buyout of residential properties | Galveston County | 2020-10-01 | 2021 Q1 | During the reporting period, Galveston County had Housing Guidelines underway for its acquisition program.
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_ACQ | Acquisition - general | Acquisition - buyout of residential properties | Galveston County | 2021-07-01 | 2021 Q4 | During the reporting period, Galveston County had environmental and applicant review underway for its voluntary acquisition program.
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_ACQ | Acquisition - general | Acquisition - buyout of residential properties | Galveston County | 2022-01-01 | 2022 Q2 | During the reporting period, Galveston County had the individual application phase and appraisals underway for its acquisition activities.
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_ACQ | Acquisition - general | Acquisition - buyout of residential properties | Galveston County | 2022-07-01 | 2022 Q4 | Activity created during the quarter.
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_ACQ | Acquisition - general | Acquisition - buyout of residential properties | Galveston County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_ACQ | Acquisition - general | Acquisition - buyout of residential properties | Galveston County | 2024-01-01 | 2024 Q2 | Reduced budgets for existing UN activities to create 3 new LMI activities and an additional UN activity, reduced projected measures
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_ACQ | Acquisition - general | Acquisition - buyout of residential properties | Galveston County | 2024-07-01 | 2024 Q4 | There were no draws submitted for the county&apos;s acquisition program and the program is ongoing.
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_HI | Housing Incentives | Housing incentives to encourage resettlement | Galveston County | 2024-01-01 | 2024 Q2 | During the reporting period, a contract amendment was executed that reduced budgets for existing UN activities to create 3 new LMI activities and an additional UN activity, and reduced projected measures.
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | Galveston County | 2020-07-01 | 2020 Q4
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | Galveston County | 2022-07-01 | 2022 Q4 | Activity created during the quarter.
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | Galveston County | 2024-01-01 | 2024 Q2 | Reduced budgets for existing UN activities to create 3 new LMI activities and an additional UN activity, reduced projected measures
LBAP_HMID_UN_20-066-046-C455_GalvestonCounty_RA | Acquisition Program - Relocation Assistance | Relocation payments and assistance | Galveston County | 2024-07-01 | 2024 Q4 | During this period, the county submitted draw #5 & #6 for its relocation assistance program.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2020-07-01 | 2020 Q4
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2021-01-01 | 2021 Q2 | During the reporting period, the Orange County program guidelines were approved for its Buyout project.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2021-10-01 | 2022 Q1 | During the reporting period, Orange County accepted applications for eligibility review for its buyout project.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2022-10-01 | 2023 Q1 | During the reporting period, amendement 1 for this contract was executed. As a result of the amendment, funds were deobligated from the total contracted amount, new activites for housing incentive activity types were added, and projected performance measures and beneficaries were reduced.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2023-07-01 | 2023 Q4 | During the reporting period, the Orange County completed 2 buyouts and 5 were underway.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2023-10-01 | 2024 Q1 | During the reporting period, Orange County had buyout activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2024-01-01 | 2024 Q2 | During the reporting period, Orange County had buyout activities underway for its Local Buyout Acquisition Program.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2024-04-01 | 2024 Q3 | During the reporting period, Orange County had buyout activities underway for its Local Buyout and Acquisition Program.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2024-07-01 | 2024 Q4 | During the reporting period, the City of Beaumont completed 1 buyout program Demolition and 2 were underway.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2024-10-01 | 2025 Q1 | During the reporting period, Orange County completed 2 demolitions.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2025-01-01 | 2025 Q2 | During the reporting period, Orange County had grant closeout documents under review for its buyout program.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty | Buyout Program | Acquisition - buyout of residential properties | Orange County | 2025-04-01 | 2025 Q3 | During the reporting period, Orange County had grant closeout documents under review for its Buyout Program.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Orange County | 2020-07-01 | 2020 Q4
LBAP_HMID_UN_20-066-048-C526_OrangeCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Orange County | 2021-10-01 | 2022 Q1 | During the reporting period, Orange County accepted applications for eligibility review for its buyout project.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Orange County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Orange County | 2023-10-01 | 2024 Q1 | During the quarter, an amendment to this contract was executed, reducing the budget, obligation and projected measures.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Orange County | 2025-01-01 | 2025 Q2 | Reduced the activity budget and obligation and the funding was reallocated to other activities within this contract.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty_HI | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Orange County | 2025-04-01 | 2025 Q3 | During the reporting period, Orange County had grant closeout documents under review for its Buyout Program.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Orange County | 2020-07-01 | 2020 Q4
LBAP_HMID_UN_20-066-048-C526_OrangeCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Orange County | 2021-10-01 | 2022 Q1 | During the reporting period, Orange County accepted applications for eligibility review for its buyout project.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Orange County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Orange County | 2023-10-01 | 2024 Q1 | During the quarter, an amendment to this contract was executed, reducing the budget, obligation and projected measures.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Orange County | 2024-07-01 | 2024 Q4 | During the reporting period, Orange County completed 1 buyout program incentive and 0 were underway.
LBAP_HMID_UN_20-066-048-C526_OrangeCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Orange County | 2024-10-01 | 2025 Q1 | During the reporting period, Orange County completed 1 buyout program incentive.
LBAP_HMID_UN_20-066-049-C772_LeagueCity | Buyout Program | Acquisition - buyout of residential properties | League City | 2021-01-01 | 2021 Q2
LBAP_HMID_UN_20-066-049-C772_LeagueCity | Buyout Program | Acquisition - buyout of residential properties | League City | 2024-07-01 | 2024 Q4 | National Objective and Activity Type changed from LMA Housing Assistance to UN Buyout.
LBAP_HMID_UN_20-066-049-C772_LeagueCity | Buyout Program | Acquisition - buyout of residential properties | League City | 2025-01-01 | 2025 Q2 | During the reporting period, the City of League City had an applications under review underway for its buyout program.
LBAP_HMID_UN_20-066-049-C772_LeagueCity | Buyout Program | Acquisition - buyout of residential properties | League City | 2025-04-01 | 2025 Q3 | During the reporting period, the City of League City submitted grant closeout documents for its buyout project.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID UN Acquisition - General | Acquisition - general | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID UN Acquisition - General | Acquisition - general | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 11819.52 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID UN Acquisition - General | Acquisition - general | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 3519.78 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID UN Acquisition - General | Acquisition - general | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 2603.44 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID UN Acquisition - General | Acquisition - general | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 1303.8 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID UN Acquisition - General | Acquisition - general | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 704.1 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ | Grantee Support for Subrecipient HMID UN Acquisition - General | Acquisition - general | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 1462.89 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 38373.05 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 12693.13 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 12126.2 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 6260.15 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 3487.54 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient HMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 7343.13 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID UN Homeownership Assistance | Homeownership Assistance (with waiver only) | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_HMID_UN_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID UN Homeownership Assistance | Homeownership Assistance (with waiver only) | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 502.41 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID UN Homeownership Assistance | Homeownership Assistance (with waiver only) | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 55.91 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID UN Homeownership Assistance | Homeownership Assistance (with waiver only) | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 90.96 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID UN Homeownership Assistance | Homeownership Assistance (with waiver only) | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 64.51 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_HA | Grantee Support for Subrecipient HMID UN Homeownership Assistance | Homeownership Assistance (with waiver only) | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 132.71 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID UN Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_HMID_UN_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID UN Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 2898.8 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID UN Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 863.51 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID UN Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 827.91 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID UN Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 508.24 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID UN Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 319.79 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient HMID UN Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 663.63 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_HMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 6182.14 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 2587.19 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 2651.45 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 1484.39 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 831.74 - State costs in support of activity delivery.
LBAP_HMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient HMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 1926.71 - State costs in support of activity delivery.
LBAP_SMID_LMA_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2020-01-01 | 2020 Q2
LBAP_SMID_LMA_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_SMID_LMA_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2021-10-01 | 2022 Q1 | During the reporting period, Gonzales County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_LMA_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMA_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2024-04-01 | 2024 Q3 | Contract was cancelled, funds are being deobligated in order to delete these activities.
LBAP_SMID_LMA_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2024-07-01 | 2024 Q4 | Number of Persons performance metric added.
LBAP_SMID_LMA_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2025-04-01 | 2025 Q3 | This contract was closed 8/11/2024. Due to the activity being cancelled, funds were condensed into a single activity in this contract.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2019-10-01 | 2020 Q1
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2020-07-01 | 2020 Q4 | During the reporting period, Austin County accepted applications for eligibility review for its buyout project.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2020-10-01 | 2021 Q1
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2021-10-01 | 2022 Q1 | During the reporting period, Austin County accepted applications for eligibility review for its buyout project.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2022-10-01 | 2023 Q1 | During the reporting period, Austin County had 5 underway for its buyout program.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2023-04-01 | 2023 Q3 | During the reporting period, Austin County had 9 underway for its buyout project.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2023-07-01 | 2023 Q4 | During the reporting period, Austin County had 2 projects underway for its buyout project.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2023-10-01 | 2024 Q1 | During the reporting period, Austin County had 1 buyout project for this period.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2024-01-01 | 2024 Q2 | During the reporting period, Austin County completed purchase of Mixville Road property.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2024-04-01 | 2024 Q3 | Contract was cancelled, funds are being deobligated in order to delete these activities.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2024-07-01 | 2024 Q4 | During the reporting period, Austin County had two underway for its Buyout program.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2025-01-01 | 2025 Q2 | During the reporting period, Austin County submitted grant closeout documents for its Buyout project.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2025-04-01 | 2025 Q3 | During the reporting period, Austin County had grant closeout documents under review for its Buyout project.
LBAP_SMID_LMB_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2025-10-01 | 2026 Q1 | During the reporting period, Austin County had its Buyout Program administratively closed.
LBAP_SMID_LMB_20-066-003-B966_GrimesCounty | Buyout Program | Acquisition - buyout of residential properties | Grimes County | 2019-10-01 | 2020 Q1
LBAP_SMID_LMB_20-066-003-B966_GrimesCounty | Buyout Program | Acquisition - buyout of residential properties | Grimes County | 2020-10-01 | 2021 Q1 | During the reporting period, Grimes County accepted applications for eligibility review for it&apos;s Buyout project.
LBAP_SMID_LMB_20-066-003-B966_GrimesCounty | Buyout Program | Acquisition - buyout of residential properties | Grimes County | 2021-10-01 | 2022 Q1 | During the reporting period, Grimes County accepted applications for eligibility review for its buyout project.
LBAP_SMID_LMB_20-066-003-B966_GrimesCounty | Buyout Program | Acquisition - buyout of residential properties | Grimes County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMB_20-066-003-B966_GrimesCounty | Buyout Program | Acquisition - buyout of residential properties | Grimes County | 2022-10-01 | 2023 Q1 | During the reporting period, Grimes County had 6 underway for its buyout program.
LBAP_SMID_LMB_20-066-003-B966_GrimesCounty | Buyout Program | Acquisition - buyout of residential properties | Grimes County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and increased funds.
LBAP_SMID_LMB_20-066-003-B966_GrimesCounty | Buyout Program | Acquisition - buyout of residential properties | Grimes County | 2023-07-01 | 2023 Q4 | During this reporting period, Grimes County request a 6 month extension. Packet was submitted to extend contract out to new end date of 4/30/2024.
LBAP_SMID_LMB_20-066-003-B966_GrimesCounty | Buyout Program | Acquisition - buyout of residential properties | Grimes County | 2024-07-01 | 2024 Q4 | During the reporting period, Grimes County had no activity. Closeout underway.
LBAP_SMID_LMB_20-066-003-B966_GrimesCounty | Buyout Program | Acquisition - buyout of residential properties | Grimes County | 2024-10-01 | 2025 Q1 | During the reporting period, Grimes County had no activity and closeout underway.
LBAP_SMID_LMB_20-066-003-B966_GrimesCounty | Buyout Program | Acquisition - buyout of residential properties | Grimes County | 2025-07-01 | 2025 Q4 | During the reporting period, the Grimes County submitted their final PD payment request. Closeout is in the final closeout stages.
LBAP_SMID_LMB_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2019-10-01 | 2020 Q1
LBAP_SMID_LMB_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2021-01-01 | 2021 Q2 | During this reporting period, no new projects closed and there are 0 underway.
LBAP_SMID_LMB_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2021-10-01 | 2022 Q1 | During the reporting period, Waller County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_LMB_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMB_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2022-10-01 | 2023 Q1 | During the reporting period, Waller County had 3 underway for its buyout program.
LBAP_SMID_LMB_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2023-01-01 | 2023 Q2 | During the reporting period, Waller County had 2 projects underway for its buyout program.
LBAP_SMID_LMB_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
LBAP_SMID_LMB_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2024-01-01 | 2024 Q2 | During the reporting period,Waller County had a draw reconciliation completed. Draw 1 needed to be reconciled to allow draw 8 to be submitted.
LBAP_SMID_LMB_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2024-04-01 | 2024 Q3 | During the reporting period, Waller County completed demolition activities for two properties.
LBAP_SMID_LMB_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2024-07-01 | 2024 Q4 | During the reporting period, Waller County submitted grant closeout documents for its Buyout program.
LBAP_SMID_LMB_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2025-01-01 | 2025 Q2 | During the reporting period, Waller County had grant closeout documents under review for its Buyout project.
LBAP_SMID_LMB_20-066-012-C094_CaldwellCounty | Buyout Program | Acquisition - buyout of residential properties | Caldwell, County of | 2019-10-01 | 2020 Q1
LBAP_SMID_LMB_20-066-012-C094_CaldwellCounty | Buyout Program | Acquisition - buyout of residential properties | Caldwell, County of | 2020-10-01 | 2021 Q1 | During the reporting period, the Caldwell County program guidelines were approved for its buyout project.
LBAP_SMID_LMB_20-066-012-C094_CaldwellCounty | Buyout Program | Acquisition - buyout of residential properties | Caldwell, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Caldwell County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_LMB_20-066-012-C094_CaldwellCounty | Buyout Program | Acquisition - buyout of residential properties | Caldwell, County of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMB_20-066-012-C094_CaldwellCounty | Buyout Program | Acquisition - buyout of residential properties | Caldwell, County of | 2024-04-01 | 2024 Q3 | Contract was cancelled, funds are being deobligated in order to delete these activities.
LBAP_SMID_LMB_20-066-012-C094_CaldwellCounty | Buyout Program | Acquisition - buyout of residential properties | Caldwell, County of | 2025-04-01 | 2025 Q3 | Contract was cancelled, funds are being deobligated in order to delete these activities.
LBAP_SMID_LMB_20-066-012-C094_CaldwellCounty | Buyout Program | Acquisition - buyout of residential properties | Caldwell, County of | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
LBAP_SMID_LMB_20-066-012-C094_CaldwellCounty | Buyout Program | Acquisition - buyout of residential properties | Caldwell, County of | 2025-10-01 | 2026 Q1 | Activity was completed during the reporting period.
LBAP_SMID_LMB_20-066-014-C106_LeeCounty | Buyout Program | Acquisition - buyout of residential properties | Lee, County of | 2020-01-01 | 2020 Q2
LBAP_SMID_LMB_20-066-014-C106_LeeCounty | Buyout Program | Acquisition - buyout of residential properties | Lee, County of | 2020-10-01 | 2021 Q1 | During the reporting period, the Lee County program guidelines were approved for its buyout project.
LBAP_SMID_LMB_20-066-014-C106_LeeCounty | Buyout Program | Acquisition - buyout of residential properties | Lee, County of | 2024-04-01 | 2024 Q3 | Due to unforeseen complications and through no fault of the subrecipient, this project has concluded early benefitting no individuals. All expenses are related to the release of funds for the subrecipient receiving approval of the Housing Guidelines for the program. The rest of the expected funds initally awarded have been reduced from the activities of this contract.
LBAP_SMID_LMB_20-066-016-C112_TylerCounty | Buyout Program | Acquisition - buyout of residential properties | Tyler County | 2019-10-01 | 2020 Q1
LBAP_SMID_LMB_20-066-016-C112_TylerCounty | Buyout Program | Acquisition - buyout of residential properties | Tyler County | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_SMID_LMB_20-066-016-C112_TylerCounty | Buyout Program | Acquisition - buyout of residential properties | Tyler County | 2021-10-01 | 2022 Q1 | During the reporting period, Tyler County had 5 applications under review for its Buyout Program.
LBAP_SMID_LMB_20-066-016-C112_TylerCounty | Buyout Program | Acquisition - buyout of residential properties | Tyler County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMB_20-066-016-C112_TylerCounty | Buyout Program | Acquisition - buyout of residential properties | Tyler County | 2022-10-01 | 2023 Q1 | During the reporting period, appraisals were underway for approved applicants, however, no expenditures for professional services were reimbursed.
LBAP_SMID_LMB_20-066-016-C112_TylerCounty | Buyout Program | Acquisition - buyout of residential properties | Tyler County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds. Environmental Review cost budgeted and obligated.
LBAP_SMID_LMB_20-066-016-C112_TylerCounty | Buyout Program | Acquisition - buyout of residential properties | Tyler County | 2023-07-01 | 2023 Q4 | Amendment reduced scope and de-obligated funds.
LBAP_SMID_LMB_20-066-016-C112_TylerCounty | Buyout Program | Acquisition - buyout of residential properties | Tyler County | 2024-01-01 | 2024 Q2 | During the reporting period, Tyler County had grant closeout documents under review for its Buyout Program.
LBAP_SMID_LMB_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2020-01-01 | 2020 Q2
LBAP_SMID_LMB_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2022-07-01 | 2022 Q4 | During the reporting period, Milam County completed their Housing Guidelines reimbursement.
LBAP_SMID_LMB_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2022-10-01 | 2023 Q1 | During the reporting period, the County completed required appraisals on two applications
LBAP_SMID_LMB_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_SMID_LMB_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2023-07-01 | 2023 Q4 | Amendment reduced scope and de-obligated funds.
LBAP_SMID_LMB_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2024-07-01 | 2024 Q4 | Changes made in preparation of activity closeout.
LBAP_SMID_LMB_20-066-027-C220_GoliadCounty | Buyout Program | Acquisition - buyout of residential properties | Goliad, County of | 2020-01-01 | 2020 Q2
LBAP_SMID_LMB_20-066-027-C220_GoliadCounty | Buyout Program | Acquisition - buyout of residential properties | Goliad, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Goliad County program guidelines were approved for its Buyout Program.
LBAP_SMID_LMB_20-066-027-C220_GoliadCounty | Buyout Program | Acquisition - buyout of residential properties | Goliad, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Goliad County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_LMB_20-066-027-C220_GoliadCounty | Buyout Program | Acquisition - buyout of residential properties | Goliad, County of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMB_20-066-027-C220_GoliadCounty | Buyout Program | Acquisition - buyout of residential properties | Goliad, County of | 2024-04-01 | 2024 Q3 | Contract was cancelled, funds are being deobligated in order to delete these activities.
LBAP_SMID_LMB_20-066-027-C220_GoliadCounty | Buyout Program | Acquisition - buyout of residential properties | Goliad, County of | 2025-04-01 | 2025 Q3 | During the reporting period, Victoria County had no expenditures on the grant management side.
LBAP_SMID_LMB_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2020-01-01 | 2020 Q2
LBAP_SMID_LMB_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2021-01-01 | 2021 Q2 | During the reporting period, Bastrop County&apos;s program guidelines were approved for its Buyout program.
LBAP_SMID_LMB_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2021-10-01 | 2022 Q1 | During the reporting period, Bastrop County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_LMB_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMB_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2022-10-01 | 2023 Q1 | During the reporting period, Bastrop County had appraisals underway for its buyout project.
LBAP_SMID_LMB_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2023-04-01 | 2023 Q3 | During the reporting period, Bastrop County had grant closeout documents under review for its buyout program.
LBAP_SMID_LMB_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2023-07-01 | 2023 Q4 | During the reporting period, Bastrop County had grant closeout documents under review for its buyout program.
LBAP_SMID_LMB_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2023-10-01 | 2024 Q1 | During the quarter, the budgets of the activities within this contract were adjusted due to environmental costs incurred so that it accurately reflects for which projects these funds were spent.
LBAP_SMID_LMB_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2024-01-01 | 2024 Q2 | During the reporting period, Bastrop Co had grant closeout documents under review for its buyout program.
LBAP_SMID_LMB_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2024-04-01 | 2024 Q3
LBAP_SMID_LMB_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
LBAP_SMID_LMB_20-066-032-C226_KarnesCounty | Buyout Program | Acquisition - buyout of residential properties | Karnes, County of | 2020-01-01 | 2020 Q2
LBAP_SMID_LMB_20-066-032-C226_KarnesCounty | Buyout Program | Acquisition - buyout of residential properties | Karnes, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Karnes County program guidelines were approved for its Buyout program.
LBAP_SMID_LMB_20-066-032-C226_KarnesCounty | Buyout Program | Acquisition - buyout of residential properties | Karnes, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Karnes County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_LMB_20-066-032-C226_KarnesCounty | Buyout Program | Acquisition - buyout of residential properties | Karnes, County of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMB_20-066-032-C226_KarnesCounty | Buyout Program | Acquisition - buyout of residential properties | Karnes, County of | 2024-04-01 | 2024 Q3 | Contract was cancelled, funds are being deobligated in order to delete these activities.
LBAP_SMID_LMB_20-066-032-C226_KarnesCounty | Buyout Program | Acquisition - buyout of residential properties | Karnes, County of | 2025-04-01 | 2025 Q3 | This contract was closed effective 4/3/2024. Due to the activity being cancelled, funds were condensed into a single activity in this contract.
LBAP_SMID_LMH_20-066-002-B957_AustinCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Austin County | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_SMID_LMH_20-066-002-B957_AustinCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Austin County | 2023-07-01 | 2023 Q4 | During the reporting period, Austin County had 2 projects underway for its housing incentive project.
LBAP_SMID_LMH_20-066-002-B957_AustinCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Austin County | 2023-10-01 | 2024 Q1 | During the reporting period, Austin County had 1 buyout project for this period.
LBAP_SMID_LMH_20-066-002-B957_AustinCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Austin County | 2024-04-01 | 2024 Q3 | Contract was cancelled, funds are being deobligated in order to delete these activities.
LBAP_SMID_LMH_20-066-002-B957_AustinCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Austin County | 2024-07-01 | 2024 Q4 | During the reporting period, Austin County had two underway for its Buyout program.
LBAP_SMID_LMH_20-066-003-B966_GrimesCounty_DPA | Buyout Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Grimes County | 2019-10-01 | 2020 Q1
LBAP_SMID_LMH_20-066-003-B966_GrimesCounty_DPA | Buyout Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Grimes County | 2021-10-01 | 2022 Q1 | During the reporting period, Grimes County accepted applications for eligibility review for its buyout project.
LBAP_SMID_LMH_20-066-003-B966_GrimesCounty_DPA | Buyout Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Grimes County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMH_20-066-003-B966_GrimesCounty_DPA | Buyout Program - Down-Payment Assistance | Homeownership Assistance to low- and moderate-income | Grimes County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_SMID_LMH_20-066-003-B966_GrimesCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Grimes County | 2019-10-01 | 2020 Q1
LBAP_SMID_LMH_20-066-003-B966_GrimesCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Grimes County | 2021-10-01 | 2022 Q1 | During the reporting period, Grimes County accepted applications for eligibility review for its buyout project.
LBAP_SMID_LMH_20-066-003-B966_GrimesCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Grimes County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMH_20-066-003-B966_GrimesCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Grimes County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and increased funds.
LBAP_SMID_LMH_20-066-003-B966_GrimesCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Grimes County | 2023-10-01 | 2024 Q1 | During the reporting period, Grimes County had activity underway for one project in the buyout program.
LBAP_SMID_LMH_20-066-003-B966_GrimesCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Grimes County | 2024-07-01 | 2024 Q4 | During the reporting period, Grimes County had no activity. Closeout underway.
LBAP_SMID_LMH_20-066-011-C074_WallerCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Waller County | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_SMID_LMH_20-066-011-C074_WallerCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Waller County | 2023-10-01 | 2024 Q1 | During the reporting period, Waller County is in the final stages of buyouts.
LBAP_SMID_LMH_20-066-011-C074_WallerCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Waller County | 2024-04-01 | 2024 Q3
LBAP_SMID_LMH_20-066-016-C112_TylerCounty_DPA | Buyout Program - Downpayment Assistance | Homeownership Assistance to low- and moderate-income | Tyler County | 2023-07-01 | 2023 Q4 | Activity created.
LBAP_SMID_LMH_20-066-016-C112_TylerCounty_RA | Relocation Assistance | Relocation payments and assistance | Tyler County | 2023-07-01 | 2023 Q4 | Activity created.
LBAP_SMID_LMH_20-066-016-C112_TylerCounty_RA | Relocation Assistance | Relocation payments and assistance | Tyler County | 2024-01-01 | 2024 Q2 | During the reporting period, Tyler County had grant closeout documents under review for its Buyout Program.
LBAP_SMID_LMH_20-066-028-C222_BastropCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bastrop County | 2020-01-01 | 2020 Q2
LBAP_SMID_LMH_20-066-028-C222_BastropCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bastrop County | 2021-10-01 | 2022 Q1 | During the reporting period, Bastrop County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_LMH_20-066-028-C222_BastropCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bastrop County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMH_20-066-028-C222_BastropCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bastrop County | 2023-04-01 | 2023 Q3 | During the reporting period, Bastrop County had grant closeout documents under review for its buyout program.
LBAP_SMID_LMH_20-066-028-C222_BastropCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bastrop County | 2023-07-01 | 2023 Q4 | During the reporting period, Bastrop County had grant closeout documents under review for its buyout program.
LBAP_SMID_LMH_20-066-028-C222_BastropCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bastrop County | 2023-10-01 | 2024 Q1 | During the quarter, the budgets of the activities within this contract were adjusted due to environmental costs incurred so that it accurately reflects for which projects these funds were spent.
LBAP_SMID_LMH_20-066-028-C222_BastropCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bastrop County | 2024-04-01 | 2024 Q3
LBAP_SMID_LMH_20-066-028-C222_BastropCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Bastrop County | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
LBAP_SMID_LMHI_20-066-011-C074_WallerCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Waller County | 2019-10-01 | 2020 Q1
LBAP_SMID_LMHI_20-066-011-C074_WallerCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Waller County | 2021-10-01 | 2022 Q1 | During the reporting period, Waller County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_LMHI_20-066-011-C074_WallerCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Waller County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_LMHI_20-066-011-C074_WallerCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Waller County | 2023-01-01 | 2023 Q2 | Amendment moved funds from related activity
LBAP_SMID_LMHI_20-066-011-C074_WallerCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Waller County | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
LBAP_SMID_LMHI_20-066-016-C112_TylerCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Tyler County | 2023-07-01 | 2023 Q4 | Activity created.
LBAP_SMID_LMHI_20-066-016-C112_TylerCounty | Buyout Program - Housing Incentives | Housing incentives to encourage resettlement | Tyler County | 2024-01-01 | 2024 Q2 | During the reporting period, Tyler County had grant closeout documents under review for its Buyout Program.
LBAP_SMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_SMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 21575.39 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 3037.37 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 2728.52 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 1022.71 - State costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 415.87 - State costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID LMI Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 731.1 - State costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient SMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_SMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient SMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 555.09 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient SMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 122.14 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient SMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 117.17 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient SMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 58.84 - State costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient SMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 31.57 - State costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_HI | Grantee Support for Subrecipient SMID LMI Housing Incentives | Housing incentives to encourage resettlement | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 67.1 - State costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_SMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 3574.99 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 1274.99 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 1245.81 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 592.39 - State costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 319.79 - State costs in support of activity delivery.
LBAP_SMID_LMI_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID LMI Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 598.03 - State costs in support of activity delivery.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2019-10-01 | 2020 Q1
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2020-07-01 | 2020 Q4 | During the reporting period, Austin County accepted applications for eligibility review for its buyout project.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2020-10-01 | 2021 Q1
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2021-10-01 | 2022 Q1 | During the reporting period, Austin County accepted applications for eligibility review for its buyout project.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2023-01-01 | 2023 Q2 | Amendment reduced scope and decreased funds.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2023-04-01 | 2023 Q3 | During the reporting period, Austin County had 9 underway for its buyout project.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2023-07-01 | 2023 Q4 | During the reporting period, Austin County had 2 projects underway for its buyout project.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2023-10-01 | 2024 Q1 | During the reporting period, Austin County had 1 buyout project for this period.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2024-01-01 | 2024 Q2 | During the reporting period, Austin County completed activities for purchase of fourth and final property.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2024-04-01 | 2024 Q3 | Contract was cancelled, funds are being deobligated in order to delete these activities.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2024-07-01 | 2024 Q4 | During the reporting period, Austin County had two underway for its Buyout program.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2025-01-01 | 2025 Q2 | During the reporting period, Austin County submitted grant closeout documents for its Buyout project.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2025-04-01 | 2025 Q3 | During the reporting period, Austin County had grant closeout documents under review for its Buyout project.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2025-07-01 | 2025 Q4 | During the reporting period, a budget adjustment occurred, increasing this activity&apos;s budget, that was due from a prior pending adjustment.
LBAP_SMID_UN_20-066-002-B957_AustinCounty | Buyout Program | Acquisition - buyout of residential properties | Austin County | 2025-10-01 | 2026 Q1 | During the reporting period, Austin County had its Buyout Program admininstratively closed.
LBAP_SMID_UN_20-066-002-B957_AustinCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Austin County | 2023-01-01 | 2023 Q2 | Activity created during quarter.
LBAP_SMID_UN_20-066-002-B957_AustinCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Austin County | 2023-07-01 | 2023 Q4 | During the reporting period, Austin County had 1 project underway for its buyout project.
LBAP_SMID_UN_20-066-002-B957_AustinCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Austin County | 2023-10-01 | 2024 Q1 | During the reporting period, Austin County had 1 buyout project for this period.
LBAP_SMID_UN_20-066-002-B957_AustinCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Austin County | 2024-07-01 | 2024 Q4 | During the reporting period, Austin County had two underway for its Buyout program.
LBAP_SMID_UN_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2019-10-01 | 2020 Q1
LBAP_SMID_UN_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2021-01-01 | 2021 Q2 | During this reporting period, no new projects closed and there are 0 underway.
LBAP_SMID_UN_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2021-10-01 | 2022 Q1 | During the reporting period, Waller County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_UN_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_UN_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2022-10-01 | 2023 Q1 | During the reporting period, Waller County had 3 underway for its buyout program.
LBAP_SMID_UN_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2023-01-01 | 2023 Q2 | During the reporting period, Waller County had 1 project completed and 1 underway for its buyout program.
LBAP_SMID_UN_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
LBAP_SMID_UN_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2023-10-01 | 2024 Q1 | During the reporting period, Waller County is in the final stages of buyouts.
LBAP_SMID_UN_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2024-01-01 | 2024 Q2 | During the reporting period,Waller County had a draw reconciliation completed. Draw 1 needed to be reconciled to allow draw 8 to be submitted.
LBAP_SMID_UN_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2024-04-01 | 2024 Q3 | During the reporting period, Waller County completed project delivery activities.
LBAP_SMID_UN_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2024-07-01 | 2024 Q4 | During the reporting period, Waller County submitted grant closeout documents for its Buyout program.
LBAP_SMID_UN_20-066-011-C074_WallerCounty | Buyout Program | Acquisition - buyout of residential properties | Waller County | 2025-01-01 | 2025 Q2 | During the reporting period, Waller County had grant closeout documents under review for its Buyout project.
LBAP_SMID_UN_20-066-011-C074_WallerCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Waller County | 2019-10-01 | 2020 Q1
LBAP_SMID_UN_20-066-011-C074_WallerCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Waller County | 2021-10-01 | 2022 Q1 | During the reporting period, Waller County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_UN_20-066-011-C074_WallerCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Waller County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_UN_20-066-011-C074_WallerCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Waller County | 2023-01-01 | 2023 Q2 | Amendment moved funds to related activity.
LBAP_SMID_UN_20-066-011-C074_WallerCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Waller County | 2023-07-01 | 2023 Q4 | Environmental Review cost budgeted and obligated.
LBAP_SMID_UN_20-066-011-C074_WallerCounty_RA | Buyout Program - Relocation Assistance | Relocation payments and assistance | Waller County | 2024-07-01 | 2024 Q4 | During the reporting period, Waller County submitted grant closeout documents for its Buyout program.
LBAP_SMID_UN_20-066-016-C112_TylerCounty | Buyout Program | Acquisition - buyout of residential properties | Tyler County | 2019-10-01 | 2020 Q1
LBAP_SMID_UN_20-066-016-C112_TylerCounty | Buyout Program | Acquisition - buyout of residential properties | Tyler County | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_SMID_UN_20-066-016-C112_TylerCounty | Buyout Program | Acquisition - buyout of residential properties | Tyler County | 2023-07-01 | 2023 Q4 | Budget and obligation funds removed pending cancellation.
LBAP_SMID_UN_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2020-01-01 | 2020 Q2
LBAP_SMID_UN_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2022-07-01 | 2022 Q4 | During the reporting period, Milam County completed their Housing Guidelines reimbursement.
LBAP_SMID_UN_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2022-10-01 | 2023 Q1 | During the reporting period, the County completed required appraisals on two applications
LBAP_SMID_UN_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2023-01-01 | 2023 Q2 | Environmental Review cost budgeted and obligated.
LBAP_SMID_UN_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2023-07-01 | 2023 Q4 | Amendment reduced scope and de-obligated funds.
LBAP_SMID_UN_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2024-01-01 | 2024 Q2 | During the reporting period, Milam Co. submitted grant closeout documents for its buyout program.
LBAP_SMID_UN_20-066-026-C215_MilamCounty | Buyout Program | Acquisition - buyout of residential properties | Milam County | 2024-07-01 | 2024 Q4 | Changes made in preparation of activity closeout.
LBAP_SMID_UN_20-066-027-C220_GoliadCounty | Buyout Program | Acquisition - buyout of residential properties | Goliad, County of | 2020-01-01 | 2020 Q2
LBAP_SMID_UN_20-066-027-C220_GoliadCounty | Buyout Program | Acquisition - buyout of residential properties | Goliad, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Goliad County program guidelines were approved for its Buyout Program.
LBAP_SMID_UN_20-066-027-C220_GoliadCounty | Buyout Program | Acquisition - buyout of residential properties | Goliad, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Goliad County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_UN_20-066-027-C220_GoliadCounty | Buyout Program | Acquisition - buyout of residential properties | Goliad, County of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_UN_20-066-027-C220_GoliadCounty | Buyout Program | Acquisition - buyout of residential properties | Goliad, County of | 2024-04-01 | 2024 Q3 | Contract was cancelled, funds are being deobligated in order to delete these activities.
LBAP_SMID_UN_20-066-027-C220_GoliadCounty | Buyout Program | Acquisition - buyout of residential properties | Goliad, County of | 2025-04-01 | 2025 Q3 | During the reporting period, Victoria County had no expenditures on the grant management side.
LBAP_SMID_UN_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2020-01-01 | 2020 Q2
LBAP_SMID_UN_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2021-01-01 | 2021 Q2 | During the reporting period, Bastrop County&apos;s program guidelines were approved for its Buyout program.
LBAP_SMID_UN_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2021-10-01 | 2022 Q1 | During the reporting period, Bastrop County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_UN_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_UN_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2023-04-01 | 2023 Q3 | Amendment reduced scope and de-obligated funds.
LBAP_SMID_UN_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2023-07-01 | 2023 Q4 | During the reporting period, Bastrop County had grant closeout documents under review for its buyout program.
LBAP_SMID_UN_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2023-10-01 | 2024 Q1 | During the quarter, the budgets of the activities within this contract were adjusted due to environmental costs incurred so that it accurately reflects for which projects these funds were spent.
LBAP_SMID_UN_20-066-028-C222_BastropCounty | Buyout Program | Acquisition - buyout of residential properties | Bastrop County | 2025-07-01 | 2025 Q4 | During the reporting period, all construction has been completed, funds drawn and accomplishment and beneficiary data reported. This contract has been administratively closed.
LBAP_SMID_UN_20-066-032-C226_KarnesCounty | Buyout Program | Acquisition - buyout of residential properties | Karnes, County of | 2020-01-01 | 2020 Q2
LBAP_SMID_UN_20-066-032-C226_KarnesCounty | Buyout Program | Acquisition - buyout of residential properties | Karnes, County of | 2020-10-01 | 2021 Q1 | During the reporting period, Karnes County program guidelines were approved for its Buyout program.
LBAP_SMID_UN_20-066-032-C226_KarnesCounty | Buyout Program | Acquisition - buyout of residential properties | Karnes, County of | 2021-10-01 | 2022 Q1 | During the reporting period, Karnes County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_UN_20-066-032-C226_KarnesCounty | Buyout Program | Acquisition - buyout of residential properties | Karnes, County of | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_UN_20-066-032-C226_KarnesCounty | Buyout Program | Acquisition - buyout of residential properties | Karnes, County of | 2024-04-01 | 2024 Q3 | Contract was cancelled, funds are being deobligated in order to delete these activities.
LBAP_SMID_UN_20-066-032-C226_KarnesCounty | Buyout Program | Acquisition - buyout of residential properties | Karnes, County of | 2025-04-01 | 2025 Q3 | This contract was closed effective 4/3/2024. Due to the activity being cancelled, funds were condensed into a single activity in this contract.
LBAP_SMID_UN_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2020-01-01 | 2020 Q2
LBAP_SMID_UN_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2021-01-01 | 2021 Q2 | During the reporting period, no new projects closed and there are 0 underway.
LBAP_SMID_UN_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2021-10-01 | 2022 Q1 | During the reporting period, Gonzales County accepted applications for eligibility review for its Local Buyout project.
LBAP_SMID_UN_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2022-01-01 | 2022 Q2 | Increased DRGR activity budget and obligation to include environmental costs charged to-date that are additionally added on top of the subrecipient contracted amount.
LBAP_SMID_UN_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2024-04-01 | 2024 Q3 | Contract was cancelled, funds are being deobligated in order to delete these activities.
LBAP_SMID_UN_20-066-033-C229_GonzalesCounty | Buyout Program | Acquisition - buyout of residential properties | Gonzales County | 2025-04-01 | 2025 Q3 | This contract was closed 8/11/2024. Due to the activity being cancelled, funds were condensed into a single activity in this contract.
LBAP_SMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_SMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 7783.75 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 1601.41 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 1538.63 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 521.28 - State costs in support of activity delivery.
LBAP_SMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 160.58 - State costs in support of activity delivery.
LBAP_SMID_UN_GranteeSupport[H5b]_ACQ_B | Grantee Support for Subrecipient SMID UN Acquisition - Buyout | Acquisition - buyout of residential properties | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 269.14 - State costs in support of activity delivery.
LBAP_SMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2024-04-01 | 2024 Q3 | During the quarter, state costs in support of activity delivery were proportional drawn and expended.
LBAP_SMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2024-07-01 | 2024 Q4 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 1125.92 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2024-10-01 | 2025 Q1 | Activity draws are for costs related to grant administration services and state costs for activity delivery. 287.61 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-01-01 | 2025 Q2 | During the reporting period, previous expenditures within the Administration project were appropriately revised to activities for state costs in support of activity delivery. 354.09 - Quarterly expenditure for state costs in support of activity delivery.
LBAP_SMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-04-01 | 2025 Q3 | During the reporting period, costs were expensed in support of the Subrecipient Local Acquisition and Buyout program. 177.85 - State costs in support of activity delivery.
LBAP_SMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-07-01 | 2025 Q4 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 96.08 - State costs in support of activity delivery.
LBAP_SMID_UN_GranteeSupport[H5b]_RA | Grantee Support for Subrecipient SMID UN Relocation Assistance | Relocation payments and assistance | Texas General Land Office | 2025-10-01 | 2026 Q1 | During the reporting period, costs were expensed in support of the Subrecipient Buyout and Acquisition program. 67.1 - State costs in support of activity delivery.
PLANNING | State Planning | Planning | Texas General Land Office | 2018-07-01 | 2018 Q4 | During the reporting period the GLO continued planning services.
PLANNING | State Planning | Planning | Texas General Land Office | 2018-10-01 | 2019 Q1
PLANNING | State Planning | Planning | Texas General Land Office | 2019-01-01 | 2019 Q2 | During the reporting period the GLO continued planning services.
PLANNING | State Planning | Planning | Texas General Land Office | 2019-04-01 | 2019 Q3 | During the reporting period the GLO continued planning services.
PLANNING | State Planning | Planning | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period the GLO continued planning services.
PLANNING | State Planning | Planning | Texas General Land Office | 2019-10-01 | 2020 Q1 | Planning operations are ongoing.
PLANNING | State Planning | Planning | Texas General Land Office | 2020-01-01 | 2020 Q2 | During the reporting period the GLO continued planning services for the Harvey 5B grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2020-04-01 | 2020 Q3 | During the reporting period the GLO continued planning services for the Harvey 5B grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2020-07-01 | 2020 Q4 | During the reporting period the GLO continued planning services for the Harvey 5B grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2020-10-01 | 2021 Q1 | During the reporting period the GLO continued planning services for the Harvey 5B grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2021-01-01 | 2021 Q2 | During the reporting period, the GLO continued planning services for the Harvey5B grant. Adjustments were made to move Houston/Harris County costs to their respective DRGR activities.
PLANNING | State Planning | Planning | Texas General Land Office | 2021-04-01 | 2021 Q3 | During the reporting period the GLO continued planning services for the Harvey5B grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2021-07-01 | 2021 Q4 | During the reporting period, the GLO continued planning services for the Harvey 5B grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2021-10-01 | 2022 Q1 | During the reporting period the GLO continued planning services for the Harvey5B grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2022-01-01 | 2022 Q2 | During the reporting period the GLO continued planning services for the Harvey5B grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2022-04-01 | 2022 Q3 | During the reporting period the GLO continued planning services for the Harvey5B grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2022-07-01 | 2022 Q4 | During the reporting period the Texas General Land Office continued planning services for the Harvey5B grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2022-10-01 | 2023 Q1 | During the reporting period the GLO continued planning services for the Harvey5B grant. There were 11 open contracts for this allocation. No major changes for any of the contracts during the last quarter. Major studies that are ongoing include Regional Basin Flood Study (RBFS), Community Health and Resource Management (CHARM), TDIS, and USACE-support for the RBFS.
PLANNING | State Planning | Planning | Texas General Land Office | 2023-01-01 | 2023 Q2 | There are 12 open contracts for this allocation. Major studies that are ongoing include Regional Basin Flood Study (RBFS), Community Health and Resources Management (CHARM), Texas Disaster Information System (TDIS), and USACE-support for the RBFS. USACE is currently on hold and pending cancellation. One pending Request for Proposal, for Alternative Housing Testing and Implementation is currently with Procurement. During the reporting period the GLO continued planning services for the Harvey5B grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2023-04-01 | 2023 Q3 | There are 11 open contracts for this allocation. Major studies that are ongoing include Regional Basin Flood Study, Community Health and Resources Management, and Texas Disaster Information System. USACE is currently pending cancellation. One pending request for qualifications, for Alternative Housing Testing and Implementation is actively posted for procurement.
PLANNING | State Planning | Planning | Texas General Land Office | 2023-07-01 | 2023 Q4 | There are still 11 open contracts for this allocation. Major studies that are ongoing include Regional Basin Flood Study, Community Health and Resources Management, and Texas Disaster Information System.
PLANNING | State Planning | Planning | Texas General Land Office | 2023-10-01 | 2024 Q1 | There are 5 open contracts for this allocation, including the Lower Rio Grande Valley (LRGV) region of the River Basin Flood Study (RBFS) and the Technical Flood Model Reviewer. An additional 6 studies utilizing this funding are in the early phases of scope development. Expenditure and MID Expenditure amount entered differs from the quarterly disbursed amount calculated in the QPR due to DRGR errors previously doubling expenditures. Quarterly Expenditure and MID Expenditure amount entered brings the to-date expended amount to equal to-date disbursed as supported by the F45 Voucher Report.
PLANNING | State Planning | Planning | Texas General Land Office | 2024-01-01 | 2024 Q2 | There are currently 11 open contracts for this funding source, including the River Basin Flood Studies. One additional contract is pending execution.
PLANNING | State Planning | Planning | Texas General Land Office | 2024-04-01 | 2024 Q3 | There are currently 10 open contracts for this funding source, including the River Basin Flood Studies. Two additional contracts are pending execution.
PLANNING | State Planning | Planning | Texas General Land Office | 2024-07-01 | 2024 Q4 | There are 10 additional active planning contracts currently underway, including Texas Disaster Information System & Regional Basin Flood Study.
PLANNING | State Planning | Planning | Texas General Land Office | 2024-10-01 | 2025 Q1 | There are 10 additional active planning contracts currently underway, including Texas Disaster Information System & Regional Basin Flood Study. One study was concluded from the previous quarter, and a new contract has been executed.
PLANNING | State Planning | Planning | Texas General Land Office | 2025-01-01 | 2025 Q2 | There are 10 additional active planning contracts currently underway, including Texas Disaster Information System & Regional Basin Flood Study.
PLANNING | State Planning | Planning | Texas General Land Office | 2025-04-01 | 2025 Q3 | There are 5 additional active planning contracts currently underway, including Texas Disaster Information System & Regional Basin Flood Study.
PLANNING | State Planning | Planning | Texas General Land Office | 2025-07-01 | 2025 Q4 | There are 7 additional active contracts underway, including River Basin Flood Study and Texas Integrated Flood Framework (TIFF). TIFF also splits costs with the 2015 Floods grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2025-10-01 | 2026 Q1 | There are 7 additional active contracts underway, including River Basin Flood Study and Texas Integrated Flood Framework (TIFF). TIFF also splits costs with the 2015 Floods grant.
PLANNING | State Planning | Planning | Texas General Land Office | 2026-01-01 | 2026 Q2
Planning[H5b]_20-152-000-C177_TexasA&MUniversity | Planning | Planning | TEXAS A&M AGRILIFE EXTENSION SERVICE | 2024-07-01 | 2024 Q4 | This is an active planning contract for the Community Health and Resource Management system with Texas A&M to assist with technological improvements and increase the availability of the program across impacted areas.
Planning[H5b]_20-152-000-C177_TexasA&MUniversity | Planning | Planning | TEXAS A&M AGRILIFE EXTENSION SERVICE | 2025-04-01 | 2025 Q3 | This is an active planning contract for the Community Health and Resource Management system with Texas A&M to assist with technological improvements and increase the availability of the program across impacted areas.
Planning[H5b]_20-152-000-C177_TexasA&MUniversity | Planning | Planning | TEXAS A&M AGRILIFE EXTENSION SERVICE | 2025-07-01 | 2025 Q4 | This is an active planning contract for the Community Health and Resource Management system with Texas A&M to assist with technological improvements and increase the availability of the program across impacted areas.
Planning[H5b]_20-165-000-C238_TexasA&MUniversity | Planning | Planning | THE TEXAS A&M UNIVERSITY SYSTEM | 2024-07-01 | 2024 Q4 | Activity was created previously but budgeted and obligated this quarter.
Planning[H5b]_20-165-000-C238_TexasA&MUniversity | Planning | Planning | THE TEXAS A&M UNIVERSITY SYSTEM | 2025-04-01 | 2025 Q3 | Planning study is ongoing.
Planning[H5b]_21-127-000-C778_TWDB | Planning | Planning | TEXAS WATER DEVELOPMENT BOARD | 2025-10-01 | 2026 Q1 | During the reporting period, activity was created.
Planning[H5b]_21-127-000-C778_TWDB | Planning | Planning | TEXAS WATER DEVELOPMENT BOARD | 2026-01-01 | 2026 Q2
Planning[H5b]_21-245-000-D081_TexasA&MUniversity | Planning | Planning | TEXAS A & M UNIVERSITY AT GALVESTON | 2024-07-01 | 2024 Q4 | Activity was created previously but budgeted and obligated this quarter.
Planning[H5b]_21-245-000-D081_TexasA&MUniversity | Planning | Planning | TEXAS A & M UNIVERSITY AT GALVESTON | 2025-04-01 | 2025 Q3 | Planning study is ongoing.
Planning[H5b]_21-245-000-D082_TexasA&MUniversity | Planning | Planning | TEXAS A & M UNIVERSITY AT GALVESTON | 2025-01-01 | 2025 Q2 | Activity was created and fully budgeted and obligated during the quarter.
Planning[H5b]_21-245-000-D082_TexasA&MUniversity | Planning | Planning | TEXAS A & M UNIVERSITY AT GALVESTON | 2025-07-01 | 2025 Q4 | This is an active planning contract for the Texas Disaster Information System (TDIS) through Texas A&M that is funded by the Mitigation grant.
Planning[H5b]_22-093-000-D262_TexasA&MUniversity | Planning | Planning | TEXAS A&M AGRILIFE EXTENSION SERVICE | 2024-07-01 | 2024 Q4 | This is an active planning contract for the Standardization of Green Infrastructure in Texas to assist Coastal Resources on a green infrastructure project.
Planning[H5b]_22-093-000-D262_TexasA&MUniversity | Planning | Planning | TEXAS A&M AGRILIFE EXTENSION SERVICE | 2025-04-01 | 2025 Q3 | This is an active planning contract for the Standardization of Green Infrastructure in Texas to assist Coastal Resources on a green infrastructure project.
Planning[H5b]_22-093-000-D262_TexasA&MUniversity | Planning | Planning | TEXAS A&M AGRILIFE EXTENSION SERVICE | 2026-01-01 | 2026 Q2
PREPS_HMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-01-01 | 2019 Q2 | During the reporting period the GLO captured the cost share of the PREPS Program.
PREPS_HMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
PREPS_HMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period the GLO captured the cost share of the PREPS Program.
PREPS_HMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | The program is complete and the draws have been made.
PREPS_HMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | CDR program team determined that more work was done on HUD MI so disbursements were moved from activity PREPS_SMID_UN.
PREPS_HMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3
PREPS_HMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | Expenditure adjustment, funds came from "PREPS_SMID_UN"
PREPS_HMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1
PREPS_HMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | Beneficiary addresses added.
PREPS_HMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Estimates of beneficiary demographic characteristics added.
PREPS_SMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-01-01 | 2019 Q2 | During the reporting period the GLO captured the cost share of the PREPS Program.
PREPS_SMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-04-01 | 2019 Q3
PREPS_SMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-07-01 | 2019 Q4 | During the reporting period the GLO captured the cost share of the PREPS Program.
PREPS_SMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2019-10-01 | 2020 Q1 | The program is complete and the draws have been made.
PREPS_SMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-01-01 | 2020 Q2 | CDR program team determined that more work was done on HUD MI so disbursements were moved to activity PREPS_HMID_UN.
PREPS_SMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-04-01 | 2020 Q3
PREPS_SMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-07-01 | 2020 Q4 | Expenditure adjustment, moved funds to "PREPS_HMID_UN"
PREPS_SMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2020-10-01 | 2021 Q1
PREPS_SMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-01-01 | 2023 Q2 | Beneficiary addresses added.
PREPS_SMID_UN | PREPS Program | Rehabilitation/reconstruction of residential structures | Texas General Land Office | 2023-07-01 | 2023 Q4 | Estimates of beneficiary demographic characteristics added.